## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | 12 | Navi4x configuration changes | Dennis | GFX |  |  | P1 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
1 | 12.001 | Separate color blend opt bits out of CB_COLORn_INFO | Steven/David | PP |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
2 | 12.001999999999999 | Change SPI_VS_OUT_CONFIG and SPI_PS_IN_CONTROL from context to persistent state regs | Xiaojing | SIO |  |  | P1 | spi20.0,spi20.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
3 | 12.002999999999998 | Separate PS_ITER_SAMPLE out of PA_SC_MODE_CNTL_1 | Steven/David | PP |  |  | P1 | std4.34 | TServer |  | 1 | 1 | New | 1 |  | 0.9 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
4 | 12.003999999999998 | Separate SAMPLE_RATE out of DB_COUNT_CONTROL | David/Faez | PP |  |  | P1 | PPI39 PPI100.65.1-2 | TServer |  | 1 | 2 | New | 1 | 1 | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
5 | 12.005999999999997 | GE_CNTL and VGT_LS_HS_CONFIG changes | Yu Xuan | GEO |  |  | P1 | ge1.0, ge1.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | ./tserverlite -test=ge1.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; ./tserverlite -test=ge1.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
6 | 12.006999999999996 | PA_SC_AA_CONFIG changes | David/Steven | PP |  |  | P1 | PPI101.5 | TServer |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
7 | 12.007999999999996 | PA_SC_CONSERVATIVE_RASTERIZATION_CNTL changes | David/Steven | PP |  |  | P1 | PPI100.141 | TServer |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
8 | 12.008999999999995 | Eliminate PA_SU_SC_MODE_CNTL.KEEP_TOGETHER_ENABLE | David/Steven | PP |  |  | P1 | STD1.6 -tglEnableSCBinning=0 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
9 | 12.009999999999994 | Separate AUTO_RESET_CNTL from PA_SC_LINE_STIPPLE | David/Steven | PP |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
10 | 12.010999999999994 | Implicit viewport scissoring | David/Steven | PP |  |  | P1 | sc42.2 sc42.3 sc26.9 sc26.10 sc26.11 sc26.12 | TServer |  | 1 | 7 | New | 1 | 6 | 0.85714 | C-Model | 6 | 2 | 2 |  |  |  | 0.33333 |  | 0 |  |  |  |  | 0 |  | WK4
11 | 12.011999999999993 | Simplify workaround for DEGGIGXX0-4644 | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | Delta | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Feature dropped | 0 |  |  |  |  | 1
12 | 12.012999999999993 | Separate event enable bits out of SPI_CONFIG_CNTL | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 2 | New | 1 | 1 | 0.5 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
13 | 12.013999999999992 | Split DB_RENDER_OVERRIDE | David/Steven | PP |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
14 | 12.014999999999992 | DB_STENCILREFMASK refactor | David/Steven | PP |  |  | P1 |  | TServer |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
15 | 12.015999999999991 | Per target control for CB BIG_PAGE/L2_BYPASS | Steven/David | PP |  |  | P1 |  | TServer |  | 1 | 5 | New | 1 |  | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
16 | 12.01699999999999 | MSAA shader write support for D/S images | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Covered by 12.164 hybrid_depth_comp | 0 |  |  |  |  | 1
17 | 12.01899999999999 | Broadcast stores | Faez/Frank | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 1 | 1 |  |  |  | 0.5 |  | 0 |  |  |  |  | 0 |  | WK5
18 | 12.019999999999989 | out of order per-wave vmem returns | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 6 | New | 1 | 6 | 1 | Gopher | 6 | 6 | 6 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
19 | 12.026999999999985 | Configuration agnostic memory scope and policy control (dup of 12.041) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 5 | New | 1 | 5 | 1 | C-Model | 5 | 5 | 5 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
20 | 12.029999999999983 | Add support for image atomics fp32 add (makes fp32 add orthogonal). Make fp behaviour among lds/cmm/df identical | Botao | SH |  |  | P1 | gfx.inst_perf/atomic_denorm gfx.inst_perf/buffer_atomic_cond_sub_u32 gfx.inst_perf/buffer_atomic_pk_add_bf16 gfx.inst_perf/buffer_atomic_pk_add_f16 gfx.inst_perf/buffer_atomic_sub_clamp_u32 gfx.inst_perf/ds_cond_sub_u32 gfx.inst_perf/ds_pk_add_bf16 gfx.inst_perf/ds_pk_add_f16 gfx.inst_perf/ds_sub_clamp_u32 gfx.inst_perf/global_atomic_cond_sub_u32 gfx.inst_perf/global_atomic_pk_add_bf16 gfx.inst_perf/global_atomic_pk_add_f16 gfx.inst_perf/global_atomic_sub_clamp_u32 gfx.image_op/image_atomic_add_flt gfx.image_op/image_atomic_min_flt gfx.image_op/image_atomic_max_flt gfx.image_op/image_atomic_pk_add_f16 gfx.image_op/image_atomic_pk_add_bf16.1-18 | TNG |  | 1 | 18 | New | 1 | 18 | 1 | C-Model | 18 | 18 | 18 |  |  |  | 1 | gfx_inst/atomic_denorm can only run in GopherPlus env. Verify if single variation pass on gopher+ good enough | 0 |  |  |  |  | 0 |  | WK5
21 | 12.030999999999983 | Support greater than 16k x 16k x 8k textures (64k x 64k x 16k, inc. 16 mip levels to support 64k). Reduce/simplify swizzle modes. | Steven/David | PP |  |  | P1 | ppi302.3,ppi302.5 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
22 | 12.032999999999982 | Unclamped image load/store support | Frank | TEX |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK9
23 | 12.033999999999981 | Move PRT++ atomic ops out of TCP tags | Frank | TEX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not an implemented feature in Navi4x | 0 |  |  |  |  | 1
24 | 12.03599999999998 | Double Ray Tracing Intersect Engine | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
25 | 12.037 | RT instance node transform | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
26 | 12.039999999999978 | 64B RT node | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
27 | 12.041 | New GL2 policies (same/child of 12.027) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 18 | New | 1 | 18 | 1 | Gopher | 18 | 18 | 18 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
28 | 12.041999999999977 | Unify GLC->EA request interface | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
29 | 12.043999999999976 | GLC guarantee of same address order for any op or scope (dep. On 12.042) | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
30 | 12.045999999999975 | GLC Cascading Read-Mod-Write Atomic Ops (includes retaining gfx11 atomic ops) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
31 | 12.047999999999973 | GLC Full CL sized write support | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
32 | 12.048999999999973 | GLC Up to 256B Write Support to EA | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
33 | 12.051 | cache last_use policy (child of 12.041/12.027) | Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
34 | 12.05299999999997 | Distributed compression architecture in CMM and client impacts (w/ physical meta-data) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
35 | 12.054 | SQG Ring Bus conversion for multi-chip | Botao | SH |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to software and diags | 0 |  |  |  |  | 1
36 | 12.05499999999997 | Split workgroup barrier | Botao | SH |  |  | P1 | gci1301.0 | TServer | -ace_aql=0 | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
37 | 12.055999999999969 | Shader Instruction Data Prefetch (viola item) | Botao | SH |  |  | P1 | gci1304.0 | TServer | -pv_proxy=true -counter=SQC_PERF_SEL_ICACHE_PREFETCH_REQ_CACHELINES,SQC_PERF_SEL_ICACHE_PREFETCH_MISSES -countertemp=counterfile | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
38 | 12.057 | Shader software data dependency control | Botao | SH |  |  | P2 | gfx.inst_perf/sched_mode_dep_mode1 gfx.inst_perf/sched_mode_dep_mode2.1-2 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
39 | 12.058999999999967 | Shader SALU Float support (in M1/M2/gfx11.5) | Botao | SH |  |  | P1 | gfx.inst_perf/s_.*_f32$ gfx.inst_perf/s_.*_f16$ gfx.inst_perf/s_cvt_f32_i32 gfx.inst_perf/s_cvt_f32_u32.1-62 | TNG |  | 1 | 62 | New | 1 | 62 | 1 | C-Model | 62 | 62 | 62 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
40 | 12.059999999999967 | VGPR DMA for Function Calls (uniform mask only) | Botao | SH |  |  | P1 | gfx.inst_perf/global_load_block gfx.inst_perf/global_store_block gfx.inst_perf/scratch_load_block gfx.inst_perf/scratch_store_block.1-4 | TNG |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
41 | 12.061999999999966 | Shader Debugger Enablement | Botao | SH |  |  | P1 | gci1305.0 gci1305.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
42 | 12.062999999999965 | Shader Illegal Instruction Detection | Botao | SH |  |  | P2 | gci1305.2 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
43 | 12.063999999999965 | Support PERMUTE/BPERMUTE for wave64 | Botao | SH |  |  | P2 | gfx.inst_perf/ds_permute_b32_w64 gfx.inst_perf/ds_bpermute_b32_w64.1-2 | TNG |  | 1 | 2 | Delta | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
44 | 12.064999999999964 | Shader VALU Improvements | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_permlanex16_var_b32 gfx.inst_perf/v_permlane16_var_b32.1-2 | TNG |  | 1 | 2 | Delta | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8400 | 0 |  |  |  |  | 0 |  | WK2
45 | 12.065999999999963 | Shader Scalar Improvements | Botao | SH |  |  | P2 | gfx.inst_perf/s_sleep_var gfx.inst_perf/s_sleep gfx.inst_perf/s_add_nc_u64 gfx.inst_perf/s_sub_nc_u64 gfx.inst_perf/s_mul_u64 gfx.inst_perf/s_mul_i32.1-6 | TNG |  | 1 | 6 | Delta | 1 | 6 | 1 | C-Model | 6 | 6 | 6 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
46 | 12.066999999999963 | Fix SQG GRBM design | Botao | SH |  |  | P1 | gci1303.0 | TServer | -tt_enable=true -tt_config=tt.ini | 1 | 1 | Delta | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | Indirect coverage: Can be covered by any test with thread trace enabled | 0 |  |  |  |  | 0 |  | WK5
47 | 12.067999999999962 | SQC Latency reduction (inherit approach from mi300) | Botao | SH |  |  | P1 |  |  |  | 1 | 0 | Legacy | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to software and diags | 0 |  |  |  |  | 1
48 | 12.068999999999962 | WGP-takeover mode | Botao | SH |  |  | P1 | gci1303.0 gci1303.1 gci1303.2 | TServer | -ace_aql=0 | 1 | 3 | New | 1 | 3 | 1 | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
49 | 12.07099999999996 | Shader Instruction Store convert to Cache (likely in M2/gfx11.5) | Botao | SH |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to software and diags | 0 |  |  |  |  | 1
50 | 12.07299999999996 | Shader signed memory offsets | Botao | SH |  |  | P2 | gfx.inst_perf/vglobal_signed_offset | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
51 | 12.077999999999957 | Move SQG outside of SPI | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Hardware feature change, no software visibility. | 0 |  |  |  |  | 1
52 | 12.078999999999956 | Dynamic VGPR allocation | Shuhui | SH |  |  | P1 | gci1302.0 / gci1302.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
53 | 12.083999999999953 | Prep for Navi + MIx00 shader merge | Botao | SH |  |  | P2 | gfx.inst_perf/v_add_f64 gfx.inst_perf/v_mul_f64 gfx.inst_perf/v_lshlrev_b64.1-3 | TNG |  | 1 | 3 | New | 1 | 3 | 1 | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
54 | 12.092 | Documentation - UTCL* MAS | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not a feature, the MAS to be delivered by the DE team | 0 |  |  |  |  | 1
55 | 12.096 | UTCL1: check page_size using the stored frag_size | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived by UTCL1 design | 0 |  |  |  |  | 1
56 | 12.098 | Remove unused client shootdown interface | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
57 | 12.104 | GPUVM PTE bits | Steven | UTCL2 |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived from gfx coverage by IPSE | 0 |  |  |  |  | 1
58 | 12.111 | Deprecate metadata probe and client shootdown in UTCL0 | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
59 | 12.112 | GCR single cycle UTC request interface | Steven | CMM |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 | 0.5 | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
60 | 12.113 | RLC dont disable CGCG while thread trace is active | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this | 0 |  |  |  |  | 1
61 | 12.114 | CP ucode use dispatch index for TTMP init | Meiru | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a rejected feature | 0 |  |  |  |  | 1
62 | 12.115 | Single Pass Wave64 Trans Issue (in M2) | Botao | SH |  |  | P1 | gfx.inst_perf/v_exp_f32_w64 gfx.inst_perf/v_log_f32_w64 gfx.inst_perf/v_rcp_f32_w64 gfx.inst_perf/v_rsq_f32_w64 gfx.inst_perf/v_sqrt_f32_w64 gfx.inst_perf/v_sin_f32_w64 gfx.inst_perf/v_cos_f32_w64 gfx.inst_perf/v_exp_f16_w64 gfx.inst_perf/v_log_f16_w64 gfx.inst_perf/v_rcp_f16_w64 gfx.inst_perf/v_rsq_f16_w64 gfx.inst_perf/v_sqrt_f16_w64 gfx.inst_perf/v_sin_f16_w64 gfx.inst_perf/v_cos_f16_w64.1-14 | TNG |  | 1 | 14 | New | 1 | 14 | 1 | C-Model | 14 | 14 | 14 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
63 | 12.118 | PH Memory Queues | Yu Xuan | GEO |  |  | P1 | ge2.0, ge2.1, std1.6 | TServer |  | 1 | 3 | New | 1 | 3 | 1 | Gopher | 3 | 3 | 2 |  | 1 |  | 0.66667 | ./tserverlite -test=ge2.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; ./tserverlite -test=ge2.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
64 | 12.119 | Harvesting enabled by default | Xiaojing | GC |  |  | P1 |  | TNG |  | 1 | 0 | New | 1 |  | 1 |  | 1 | 0 |  |  |  |  | 0 | Confirmed with arch, because this feature is RLC ROM to program the harvesting setting during fuse distribution stage, and there's no needed to test from diag side. | 0 |  |  |  |  | 1 |  | WK5
65 | 12.12 | WGP&RB GRBM Index Remapping (possible gfx11.5) | Xiaojing | CTL |  |  | P1 | gci1300.0,gci1300.1,gci1300.2,gci1300.3 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
66 | 12.124 | CSC Group Launch guarantee | Xiaojing | SIO |  |  | P2 | spi124.0,spi124.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
67 | 12.125 | GFX Pipe Group Launch Guarantee | Xiaojing | SIO |  |  | P2 | spi125 | TServer |  | 1 | 1 | New | 1 | 0.75 | 0.75 | C-Model | 1 | 0 |  |  |  |  | 0 | Issues in gfx_pm4_packets | 0 |  |  |  |  | 0 |  | WK6
68 | 12.128 | Packet Hardening for Microsoft Telemetry | Pierce | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
69 | 12.13 | add TCP out of order response support | Steven | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
70 | 12.132 | CP/RLC/SDMA 40-bit Register Addressing to GRBM<>RSMU | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
71 | 12.133 | Removal of Clear State Context 0 and reclamation for rendering | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
72 | 12.134 | MES Handling Doorbell Misses | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
73 | 12.139 | Simplify software debugger register change process | Xiaojing | SIO |  |  | P1 | spi1390.1-2,spi1391.1-2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
74 | 12.142 | Double shader DOT Int4 and Int8 rates | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_dot4_i32_iu8 gfx.inst_perf/v_dot4_u32_u8 gfx.inst_perf/v_dot8_i32_iu4 gfx.inst_perf/v_dot8_u32_u4 gfx.inst_perf/v_wmma_i32_16x16x16_iu4 gfx.inst_perf/v_wmma_i32_16x16x32_iu4 gfx.inst_perf/v_wmma_i32_16x16x16_iu8.1-7 | TNG |  | 1 | 7 | Delta | 1 | 7 | 1 | Gopher | 7 | 7 | 7 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7782 | 0 |  |  |  |  | 0 |  | WK1
75 | 12.143 | Remove SA Affinity for Pixel Shaders | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Driver team will verify this | 0 |  |  |  |  | 1
76 | 12.146 | RS64 L0 Instr Cache | Yu Xuan | CTL |  |  | P1 | std1.1, gci30.4 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 |  |  | 2 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
77 | 12.148 | RS64 L0 Data Cache | Yu Xuan | CTL |  |  | P1 | std1.1, gci30.4 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 |  |  | 2 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
78 | 12.15 | RS64 Bit Manip Instructions | Yu Xuan | CTL |  |  | P1 | gci3.12 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=gci3.12 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
79 | 12.152 | RS64 Dynamic TMR Loading | Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this | 0 |  |  |  |  | 1
80 | 12.157 | Shader pseudo-scalar trans ops (M2 item) | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_s_.*.1-10 | TNG |  | 1 | 10 | New | 1 | 10 | 1 | C-Model | 10 | 10 | 10 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8507 | 0 |  |  |  |  | 0 |  | WK8
81 | 12.159 | Shader reduce VGPR writes (M2 item, evaluate for gaming) | Shuhui | SH |  |  | P1 | shci2038.0-3,104.1-5 | TServer |  | 1 | 5 | New | 1 | 5 | 1 | Gopher | 5 | 5 | 5 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
82 | 12.16 | Shader double wave64 VINTERP rate (por gfx11.5, evaluate gaming) | Shuhui | SH |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
83 | 12.162 | Shader Performance Profiler Enablement | Shuhui | SH |  |  | P1 | std1.1 std3.1 std4.1 rt1.300 rt1.320 gci1304 gci1305 gci1308 shci2033 shci2036 gssi212.10 | TServer | "-tt_enable=1 -tt_config=exclude_nondetail_wavestart_ext=1,exclude_nondetail_alloc=1,wavestart_mode=wg_id,tracese=0,wavetype=65,ctrlmode=on,stall_all_simds=1 -thread_trace_config=exclude_nondetail_wavestart_ext=1,exclude_nondetail_alloc=1,wavestart_mode=wg_id,tracese=0,wavetype=65,ctrlmode=on,stall_all_simds=1" | 1 | 14 | Delta | 1 | 14 | 1 | Gopher | 14 | 11 | 11 |  |  |  | 0.78571 | Thread trace related can only be verified in gopher and using thread trace viewer. There are a few perf counters that are not tested but the test is avaliable. SQ_PERF_SEL_INSTS_LOCK SQ_PERF_SEL_INST_CYCLES_VALU_WMMA SQ_PERF_SEL_INSTS_VEC32_VALU_WMMA SQ_PERF_SEL_INSTS_WMMA_LOAD SQ_PERF_SEL_INSTS_TEX_BLOCK_LOAD SQ_PERF_SEL_INSTS_TEX_BLOCK_STORE | 0 |  |  |  |  | 0 |  | WK5
84 | 12.163 | Architected SGPR Values | Xiaojing | SIO |  |  | P2 | sh1630.1-2 | TServer |  | 1 | 2 | New | 1 | 1 | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 | may need write in TNG | 0 |  |  |  |  | 0 |  | WK6
85 | 12.164 | Hybrid Depth Compression | David/Faez | PP |  |  | P1 | PPI406.1-8 PPI406.11-18 PPI406.21-28 PPI406.31-38 PPI406.41-48 | TServer |  | 1 | 54 | New | 1 | 54 | 1 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
86 | 12.165 | HiZ/S in SC | Steven/David | PP |  |  | P1 | std5.9 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | run with -tZTileBuffer=0 and 1 | 0 |  |  |  |  | 0 |  | WK2
87 | 12.167 | CB codec removal/simplifications | David/Steven | PP |  |  | P1 | Same to 12.164 | TServer |  | 1 | 2 | New | 1 | 1 | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
88 | 12.168 | VRS fragment compression | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Descoped, can drop | 0 |  |  |  |  | 1
89 | 12.174 | RS64 64bit Stream Input | Yu Xuan | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
90 | 12.175 | RS64 Atomic ISA Ext | Yu Xuan | CTL |  |  | P1 | gci30.3 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
91 | 12.184 | GLx bus widths and configuration | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 8 | New | 1 | 8 | 1 | Gopher | 8 | 8 | 8 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
92 | 12.185 | CH 256B read/write support | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
93 | 12.186 | Add SP support for float8 (fp8/bf8) dot products (ieee and/or non-ieee) | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_wmma.* gfx.inst_perf/v_cvt.* gfx.inst_perf/v_dot4_f32.*.1-15 | TNG |  | 1 | 15 | New | 1 | 15 | 1 | C-Model | 15 | 15 | 15 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8491 | 0 |  |  |  |  | 0 |  | WK3
94 | 12.188 | Make shader round-robin arb in workgroup usable by driver | Shuhui | SH |  |  | P1 | gci1306.0-2, gssi212.11 | TServer |  | 1 | 3 | New | 1 | 3 | 1 | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
95 | 12.191 | Capture shader memviol source to speed up bringup debug | Shuhui | SH |  |  | P1 | gci1305.0,3.1-5,4.1-5,5.1-5,6.1-5 | TServer | For gci1305.3 only, "-vm -tc_ulVidmemFragmentSize=0" | 1 | 5 | New | 1 | 5 | 1 | C-Model | 5 | 5 | 5 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
96 | 12.192 | UTCL2 UTCL1 Dummy INV interface removal | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
97 | 12.193 | Additional SAx client to UTCL1 (from 12. | Steven/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
98 | 12.197 | Ping-Pong walking for dispatches | Xiaojing | SIO |  |  | P2 | spi197 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
99 | 12.201 | Compute Grid Programmable Walk Order (cs_grid_walk_order). If not doing morton'ish (ex. 2x2) then improving launch rate for existing typewriter (ex 4x1) is P1) | Xiaojing | SIO |  |  | P1 | spi2010.1-2,spi2011.1-2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
100 | 12.202 | Compute Thread Walk Order (cs_thread_walk_order) | Xiaojing | SIO |  |  | P1 | spi2020.1-2,spi2021.1-2 | TServer |  | 1 | 2 | New | 1 | 1.5 | 0.75 | C-Model | 1 | 0 |  |  |  |  | 0 | Issues in gfx_pm4_packets | 0 |  |  |  |  | 0 |  | WK4
101 | 12.206 | DC->SPI wire reduction |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indirect | 0 |  |  |  |  | 1
102 | 12.208 | wave64 FMAF32 power reduction (M2 item) -> large area | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_sad.* gfx.inst_perf/v_swap.* gfx.inst_perf/v_perm.* gfx.inst_perf/v_sat_pk_u8_i16 gfx.inst_perf/v_max.* gfx.inst_perf/v_sub_co_ci_u32.* gfx.inst_perf/v_med.* gfx.inst_perf/v_min.* gfx.inst_perf/v_qsad.* gfx.inst_perf/v_mqsad.* gfx.inst_perf/v_mad.* gfx.inst_perf/v_lerp.* gfx.inst_perf/v_and.* gfx.inst_perf/v_cndmask_b16.1-64 | TNG |  | 1 | 64 | New | 1 | 32 | 0.5 | C-Model | 64 | 32 | 32 |  |  |  | 0.5 | https://ontrack-internal.amd.com/browse/TNG-8760 | 0 |  |  |  |  | 0 |  | WK8
103 | 12.209 | Add Structured Sparsity Support | Claire/Meiru | SH |  |  | P1 |  | TServer |  | 1 | 22 | New | 1 | 11 | 0.5 | C-Model | 22 | 2 | 2 |  |  |  | 0.090909 |  | 0 |  |  |  |  | 0 |  | WK3
104 | 12.21 | Fully connect capability to use high and normal MALL reuse hint (child of 12.027/12.041) | Steven | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 0.5 | 0.5 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
105 | 12.211 | UTCL1_identity_mode (SED Crest) | Steven | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | For chiplet SED Crest, not applicable for NV4m | 0 |  |  |  |  | 1
106 | 12.213 | deprecate HPG | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Deprecated, not visible to diags | 0 |  |  |  |  | 1
107 | 12.214 | reduce GE_DIST to GE_SE wire count | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | We expect indirect coverage for this feature from many Graphics workloads including Geometry shader. There is no need to plan for direct/dedicated test case for this one. | 0 |  |  |  |  | 1
108 | 12.216 | All debug bus buffers to 4K size | Daniel G | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
109 | 12.219 | ge_se in sed. Sub item under basic configuration | Xiaojing | GEO |  |  | P1 | gfx.red_triangle_draw_composite | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
110 | 12.22 | register cleanup | Xiaojing | GEO |  |  | P1 | navi48.gfx.ge.register_access | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
111 | 12.221 | Add support to the SDMA to dequeue similar to the way the CP does | Yu Xuan | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
112 | 12.223 | Update PA/SC support for 1 to 9SE and updated pix distribution algorithm | David/Steven | PP |  |  | P1 | STD1.6 GCI30.3 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
113 | 12.224 | Drop the FSR support from SC PBB implementation | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | No direct coverage required | 0 |  |  |  |  | 1
114 | 12.225 | DB design simplificaitons while updating for hybrid depth compression | David/Steven | PP |  |  | P1 | Same to 12.164 | TServer |  | 1 | 2 | New | 1 | 1 | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
115 | 12.233 | add DRAM logging support for RLC | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this, with RLC FW team support | 0 |  |  |  |  | 1
116 | 12.235 | Add RLC SRM as an RLC_CH client | Pierce | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE coverage | 0 |  |  |  |  | 1
117 | 12.236 | change RLC LX7 config used for power management | Pierce | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Navi4x no longer has SED N/A | 0 |  |  |  |  | 1
118 | 12.239 | increase adaptive stretch response of GDFLL | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indirect covered by regular clock stretch, not directly covered by diag | 0 |  |  |  |  | 1
119 | 12.247 | Register remap to match M1 | Xiaojing | GEO |  |  | P1 | food_store.1-3,mountain_range.1-3,navi48.gfx.ge.register_access.1-3 | TNG |  | 1 | 3 | New | 1 | 3 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
120 | 12.253 | GFX12 IMU - Remove CPAXI and send doorbells directly to CP/RLC/SDMA | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
121 | 12.255 | GFX12 IMU - Modify doorbell interface from Syshub to IMU | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
122 | 12.263 | GFX12 IMU - Add Resets and idle sidebands | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
123 | 12.266 | GFX12 Firewall update for 40 bit address | David | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
124 | 12.27 | Work Graph Scheduler | David | CTL |  |  | P1 | wgs.6 :: wgs_dispatch_sanity_pm4_01 wgs.8 :: wgs_dispatch_two_pipes_pm4_01 wgs.1 :: wgs_ace_cwsr_pm4_01 wgs.100 :: wgs_dispatch_sanity_tacl_01 wgs.12 :: wgs_gl1_ret_xnack_pm4_01 linpack_wgs wgs_interrrupt_tacl | TServer |  | 1 | 7 | New | 1 | 7 | 1 | Gopher | 6 | 6 | 6 |  |  |  | 1 | TSERVER tests | 0 |  |  |  |  | 0 |  | WK5
125 | 12.276 | Remove the data duplication for MLOPS | Claire/Meiru | SH |  |  | P1 |  | TServer |  | 1 | 14 | New | 1 | 0 | 0 | C-Model | 14 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
126 | 12.277 | Add Conditional-subtract memory atomic for locks | Shuhui | SH |  |  | P2 | gfx.inst_perf/flat_atomic_cond_sub_u32_global gfx.inst_perf/flat_atomic_sub_clamp_u32_global gfx.inst_perf/ds_cond_sub_rtn_u32 gfx.inst_perf/ds_sub_clamp_rtn_u32 gci1307.0-3.1-8 | TNG |  | 1 | 8 | New | 1 | 8 | 1 | C-Model | 8 | 8 | 8 |  |  |  | 1 | Partially covered by 12.030 and in tserver gci1307 test. https://ontrack-internal.amd.com/browse/TNG-8541 | 0 |  |  |  |  | 0 |  | WK8
127 | 12.278 | DCC sector size to increase to 128B | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | Will be covered by any DCC tests | 0 |  |  |  |  | 0 |  | WK5
128 | 12.28 | DCC auto-CT detection | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
129 | 12.281 | Sector-separated DCC compressed data layout | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
130 | 12.282 | rename GE BIA containers | Xiaojing | GEO |  |  | P1 | navi48.gfx.ge.register_access | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
131 | 12.284 | Data return for clamped PRT is "0" only (no longer needs to be programable) | Frank | TEX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
132 | 12.285 | Remove BIG_PAGE control for UTC probing | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
133 | 12.286 | Remove passthru_en/esgs_ring_itemsize/old gs fastlaunch | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
134 | 12.287 | VRS removal in DCC | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
135 | 12.291 | Remove F32 from CPG and CPC; No BC support in PM4 parsers |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
136 | 12.292 | move offchip lds manager to GE | Yu Xuan | GEO |  |  | P1 | ge3.0, std4.34 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 1 |  | 1 |  | 0.5 | ./tserverlite -test=ge3.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
137 | 12.294 | Improve SPI work limiting controls (spi_work_limit_ctrl) | Xiaojing | SIO |  |  | P1 | spi2940.1-2, spi2941.1-2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
138 | 12.299 | [Navi4x] Move RTAVFS/DLDO/DFLL initialization to after CP is running workloads | David | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indirect coverage with front door loading | 0 |  |  |  |  | 1
139 | 12.3 | [Navi4x] SDMA ucode caching | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
140 | 12.301 | [Navi4x] CP ucode firmware execution speed-up via cache priming | Daniel G | CTL |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
141 | 12.302 | [Navi4x] Remove SDMA load/run commands or disallow DRAM access allowed for load/run commands |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
142 | 12.308 | RS64 Debug Enablement | Daniel G | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
143 | 12.31 | SED client to 256B reads | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
144 | 12.311 | Shader VALU min/max IEEE compliant | Shuhui | SH |  |  | P1 | gfx.ieee_min_max | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7987 | 0 |  |  |  |  | 0 |  | WK1
145 | 12.312 | Convert PAL implementation of streamout to sw solution enables GDS removal | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
146 | 12.318 | SED<>AID and AID<>AID interfaces must support arbitrary clk deviation, so protocols like valid-only need to be converted. | David/Steven | GC |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Invisible to diags, workload cross the original die interface will cover | 0 |  |  |  |  | 1
147 | 12.319 | GCRD->GCR response interface to credit/debit | Steven | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 0.9 | 0.9 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
148 | 12.32 | GCRD_SE SAX client | Steven/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
149 | 12.321 | Limit wires SED<->AID for PMM Ips | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
150 | 12.322 | GFX12 UTLC2 - Add idle sidebands | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived by design/FET lead | 0 |  |  |  |  | 1
151 | 12.328 | GFX12 SDMA - Add sidebands to control Idle request | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
152 | 12.329 | remove GCR dummy UTCL2 invalidation interface | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
153 | 12.332 | GFX12 EA - Add idle sidebands | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
154 | 12.333 | Swap PRIM_CONFIG register to SA_UNIT_DISABLE register | David | GC |  |  | P2 | STD1.6 GCI30.3 | TNG |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
155 | 12.334 | GTS support in GFX12 | David | CTL |  |  | P1 |  | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
156 | 12.336 | Remove harvesting connectivity/RTL mux in SP | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
157 | 12.339 | GFX12 IH Gasket update for chiplet design | Sid | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
158 | 12.342 | GFX12 IMU - Add FIFO for blocked RSMU writes and keep read outstanding | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
159 | 12.343 | SPM sample sync across AID and GFX to DF | Yu Xuan | CTL |  |  | P1 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
160 | 12.344 | Faulting illegal ops to PCIE | Steven/JJ/Anthony | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
161 | 12.349 | Perfmon: GFX - Convert all counter modules to SPM-only mode | Yu Xuan | GC |  |  | P2 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
162 | 12.356 | Perfmon: GFX - GFX SPM sampling window to be driven by REFCLK | Yu Xuan | GC |  |  | P1 | rlc1.0 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=rlc1.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
163 | 12.357 | Perfmon: GFX - SQ counters to support shader type filters per individual counter | Dennis | GC |  |  | P1 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
164 | 12.358 | Perfmon: GFX - Custom data injection from CP into SPM with delta counters | Yu Xuan | GC |  |  | P2 | rlc1.0, rlc1.1 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=rlc1.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK8
165 | 12.36 | WMMA wave level matrix load Instruction | Shuhui | SH |  |  | P2 | gfx.inst_perf/global_load_tr.*.1-2 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8759 | 0 |  |  |  |  | 0 |  | WK6
166 | 12.361 | Perfmon: GFX - VMID Specific Profiling/Debugging | Shuhui | SH |  |  | P2 | shci2039.4 | TServer | "-tt_enable=1" | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | Requires thread trace viewer | 0 |  |  |  |  | 0 |  | WK8
167 | 12.366 | NV4x: Perfmon: Review and refinement of available perf counter events for GC and DF | Dennis | GC |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | GFX IPSE will cover the Perfmon related features | 0 |  |  |  |  | 1
168 | 12.37 | Fix VOPD dual V_MOV | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_dual_mov_b32 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8273 | 0 |  |  |  |  | 0 |  | WK6
169 | 12.373 | Modification of GS throttle (due to 12.118 ph_memory_queues) | Xiaojing | GEO |  |  | P1 | std1.1-4,2.1-4,3.1-4,4.1-4 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
170 | 12.374 | MEM_PWR_CTRL Bus increase to support FGCG | Pierce | GC |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE coverage | 0 |  |  |  |  | 1
171 | 12.382 | [Strix] pbb_tile_order_rev -- from BRP:11.5.017 | Steven/David | PP |  |  | P2 |  |  |  | 1 | 0 | Legacy | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Driver team will verify this | 0 |  |  |  |  | 1
172 | 12.387 | Block Initiatives |  | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not a feature | 0 |  |  |  |  | 1
173 | 12.389 | GFX EDC Controller using XVmin/Mafdd |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
174 | 12.392 | NV4x: GFX Cac Events selection enhancement |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
175 | 12.393 | GFX PCC latency optimization |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
176 | 12.396 | Airtight FIFO Design Robustness | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | The change is a quality initiative, and transparent to software. | 0 |  |  |  |  | 1
177 | 12.397 | Benchmark Stimulus Replay at Block | Xiaojing | GFX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1
178 | 12.398 | Adoption of RDL2RTL | Xiaojing | GFX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1
179 | 12.399 | Remove Coverage into Render Targets | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Design confirmed feature is fully dropped | 0 |  |  |  |  | 1
180 | 12.4 | SRAM Bit/byte write enable | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pure H/W change which impacts the SRAM access. This would be covered implicitly by running various 3D/Compute workload. There is no need to develop a target test case for this feature. | 0 |  |  |  |  | 1
181 | 12.401 | Improving MBFF ratio (Octa/Hexa Flops) | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not applicable to our scope and waived | 0 |  |  |  |  | 1
182 | 12.402 | Repeater Clock Gating (Clock Gating Efficiency focus) | Pierce | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Device level change, no in-out verification, indirect coverage through GFXOFF setting ClockGatingGfxRepeaterFgcg=1, PMM coverage through CGCG/PG features | 0 |  |  |  |  | 1
183 | 12.403 | MGCG partitioning (Goal is to reduce gating residency of MGCG domains. Power saved is function of reduction in MGCG domain clock residency, and physical partitioning of domain (size of domain, clones, ICG placement, pre MGCG power). | Pierce | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Device level change, no in-out verification, indirect coverage through GFXOFF setting ClockGatingGfxMgcg=1, PMM coverage through CGCG/PG features | 0 |  |  |  |  | 1
184 | 12.406 | With GPO enabled, perfmon clock and flops connected to it are currently not gated. Proposal is to improve clock gating of “event” flops and counters used in performance monitor logic | Pierce | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Deferred GFX13, GFXIPARCH-785 | 0 |  |  |  |  | 1
185 | 12.41 | User Data Scatter Engine (RS64) | Pierce | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removed, DEGFX12-10852 | 0 |  |  |  |  | 1
186 | 12.411 | Replace SDMA F32 with RS64 | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
187 | 12.412 | Enable GPA in UTCL0 of SAx GL1C | David/Steven | CMM |  |  | P1 | cs16.0 wgs_gpa3_disable_dispatch_pm4_01 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | WGS dependent | 0 |  |  |  |  | 0 |  | WK5
188 | 12.413 | Switch GFX to Memgen-based SRAM FGCG | Pierce | GC |  |  | P1 | PMM coverage through CGCG/PG features |  |  | 1 | 0 | New | 1 |  | 1 | C-Model | 1 | 0 |  |  |  |  | 0 | Indirect coverage through FGCG | 0 |  |  |  |  | 1 |  | WK5
189 | 12.414 | Add an L1 TLB into the SDMA front-end | Steven | UTCL2 |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | OSS diag will provide coverage | 0 |  |  |  |  | 1
190 | 12.417 | GFX12 IMU - Add light sleep and deep sleep to SRAMs | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not POR for NV48/44 | 0 |  |  |  |  | 1
191 | 12.418 | GFX12 IMU - Add deep sleep support and sideband for IMUCLK | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not POR for NV48/44 | 0 |  |  |  |  | 1
192 | 12.42 | Increase max scratch allocation | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
193 | 12.421 | TOC updates for RLC FW | David | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indrect coverage with front door loading | 0 |  |  |  |  | 1
194 | 12.422 | Navi4c (chiplet) GFXIP STA Targets | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | The feature is not applicable to Navi44/48. Please remove this from your feature list. | 0 |  |  |  |  | 1
195 | 12.425 | GE WD_QOS.DRAW_STALL behavior | Xiaojing | GEO |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Feature removal, no software visibility. | 0 |  |  |  |  | 1
196 | 12.429 | HP64 child reuse | Frank | TEX |  |  | P1 |  | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | de-featured | 0 |  |  |  |  | 0 |  | WK5
197 | 12.43 | Ray Tracing Tri Pair optimization | Faez | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
198 | 12.438 | Remove Soft Lock feature | Xiaojing | SIO |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a removal, and no direct coverage is required. Makhan/Wanshou to check with Arch and waive from PostSi coverage. | 0 |  |  |  |  | 1
199 | 12.439 | Improve register based invalidation | Steven/Glenn | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
200 | 12.44 | Make SE CAC Counters accessible over Debug Bus |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
201 | 12.441 | reduce VGPRs for LS and ES stages | Xiaojing | SIO |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Feature removal inside hardware, no software visibility. | 0 |  |  |  |  | 1
202 | 12.442 | EA and GL2CC move from GRBM to GRBMH | Steven/Glenn | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE confirmed chiplet only | 0 |  |  |  |  | 1
203 | 12.444 | Expand V# const_stride from 14 to 17 bit width | Frank | TEX |  |  | P2 |  | TServer |  | 1 | 4 | New | 1 | 3 | 0.75 | Gopher | 4 | 3 | 3 |  |  |  | 0.75 |  | 0 |  |  |  |  | 0 |  | WK8
204 | 12.445 | Improve Thread Trace ExecPopCount bandwidth | Shuhui | SH |  |  | P2 | shci2039.0-3 | TServer | "-tt_enable -vm" | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 | Requires thread trace viewer | 0 |  |  |  |  | 0 |  | WK8
205 | 12.446 | Load_reserved/store_conditional support in SE$ | David/Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | WGS related, covered by gaming exerciser with test firmware | 0 |  |  |  |  | 1
206 | 12.447 | Load_reserved/store_conditional support in DF | David/Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | WGS related, covered by gaming exerciser with test firmware | 0 |  |  |  |  | 1
207 | 12.448 | Change flags encoded in barycentrics to simplify detection of procedural nodes | Faez | TEX |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
208 | 12.449 | Remove culling with skip_triangles in TA | Faez | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
209 | 12.45 | Add AtomicAdd packed math for F16 | Shuhui | SH |  |  | P2 | gci1307.4-7 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 | Tested on gopher+ Partially addresses by 12.030 | 0 |  |  |  |  | 0 |  | WK7
210 | 12.451 | Extend compression control support in Texture | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 | 1 | 0.5 | Gopher | 2 | 1 | 1 |  |  |  | 0.5 |  | 0 |  |  |  |  | 0 |  | WK6
211 | 12.452 | Breaking SE reuse in Navi48 | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | No direct coverage required | 0 |  |  |  |  | 1
212 | 12.453 | Add HS and GS Stages to event collection for PS_DONE and PS_PARTIAL_FLUSH | Xiaojing | SIO |  |  | P2 | spi453 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
213 | 12.454 | Proper Handling of the Force Decompression and Comp Key Read Command on compression-bypassed resources | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
214 | 12.455 | Decrease CS max grid size support to X,Y,Z = 32b,16b,16b | Xiaojing | SIO |  |  | P2 | gfx.linpack_gfx_compute | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
215 | 12.457 | Decrompress BLTs via SDMA | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
216 | 12.458 | Descope VRS Compression feature | Steven/David | PP |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
217 | 12.459 | Remove support for Shared VGPRs and Subvector Execution | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
218 | 12.46 | BVH Footprint Improvement | Frank | TEX |  |  | P2 |  | TServer |  | 1 | 4 | New | 1 | 3 | 0.75 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
219 | 12.461 | RT support for OBB and Instance Node Intersection | Frank | TEX |  |  | P2 |  | TServer |  | 1 | 8 | New | 1 | 2 | 0.25 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
220 | 12.462 | Descope Verification of 16xaa for VRS Coarse Rates (1x2, 2x2, 2x1) | Steven/David | PP |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
221 | 12.463 | GFXCLK Deep Sleep trigger based on XVMIN | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | PPA team will enable this, IPSE team will verify | 0 |  |  |  |  | 1
222 | 12.464 | SP Throttling and the first DIDT droop | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
223 | 12.465 | SP src operand invalidated by td/lds return | Shuhui | SH |  |  | P2 | gci1310 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
224 | 12.466 | Distributed DIDT controller | Pierce | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 | C-Model | 1 | 0 |  |  |  |  | 0 | Leverage SMU coverage through feature enablement | 0 |  |  |  |  | 1 |  | WK8
225 | 12.467 | GRBM/H SYNC registers | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
226 | 12.468 | RS64: Adding performance features for both Navi4x and MI400 | Daniel G | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Risc-V features, will be tested by IPSE team | 0 |  |  |  |  | 1
227 | 12.469 | F8 1.4.3 IEEE mode behavior change (match with NV) | Shuhui | SH |  |  | P2 | gci1309.0-3 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
228 | 12.47 | RS64: No support for OOO IO read and write memory transactions | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Emulator | 1 | 0 |  |  |  |  | 0 | Will use MHUB team's ATHUB RAW check and Single VC for GFX IO test's CPWD variation as coverage | 0 |  |  |  |  | 0 |  | WK5
229 | 12.471 | Save and Restore of perfcounter and ttrace enable for GFXOFF/SRIOV | Xiaojing | SIO |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
230 | 12.473 | GL2 shared across all SEs for Navi44/48 | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
231 | 12.474 | 2x MLOPs performance | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_wmma_f32_16x16x.* gfx.inst_perf/v_wmma_i32_16x16x32_iu4 gci39.1-6.1-11 | TNG |  | 1 | 11 | New | 1 | 11 | 1 | Gopher | 11 | 11 | 11 |  |  |  | 1 | Partially covered by 12.209. Checked cycles by using thread trace WMMA8/WMMA16 tokens | 0 |  |  |  |  | 0 |  | WK6
232 | 12.475 | IO traffic can potentially block DRAM traffic | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Confirmed ownership has been passed to SDMA team for perf verfication | 0 |  |  |  |  | 1
233 | 12.476 | Descope 8xaa for VRS coarse rates (1x2, 2x2, 2x1) | Steven/David | PP |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon DV effort that does not apply to post-silicon | 0 |  |  |  |  | 1
234 | 12.477 | Hook up AVFS debug bus to debug bus chains in 4 gc_2gl2c_1_tiles | Daniel G | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
235 | 12.479 | Add Ordered-Add memory atomic for faster SW Streamout (global_atomic_ordered_add_b64) | Glenn/Javad/JJ/Anthony | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
236 | 12.48 | Move GFX PSMs to faster clock for faster DIDT controller response | Dennis | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived. PMM Diags, Tools team, and PPA team should cover this. | 0 |  |  |  |  | 1
237 | 12.483 | Processor controllable performance counters for CP Bottleneck profiling | Daniel G | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
238 | 12.484 | decoding of op ATOMIC_UMAX_8_NO_RTN from EA to SDP is not expected | Steven/Frank | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
239 | 12.485 | Navi4 GFXIMU Interrupt Capability | David | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
240 | 12.486 | Allow GFX doorbells through IMU doorbell fence | Pierce | CTL |  |  | P1 | gfx.stress3d.gfxoff/food_store |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this, in diag this is an indirect coverage through GFXOFF | 0 |  |  |  |  | 1
241 | 12.487 | Increase DB Z cache size for performance | Steven/David | PP |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | No need for diag to do performance check | 0 |  |  |  |  | 1
242 | 12.488 | Reduce PBB maximum batch size from 1024 to 512 and constrain the minimum bin size in the PBB to 128 pixels | David/Steven | PP |  |  | P3 | STD1.6 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
243 | 12.489 | Deprioritize NOT_EOP=1 mode | Xiaojing | GEO |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1
244 | 12.49 | GFXCLK has risk to achieve 3.46GHz due to AR change | Dennis | PD |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived. PMM Diags and PPA team should cover this. | 0 |  |  |  |  | 1
245 | 12.493 | Add new jump table for SET_SH_REG and SET_SH_REG_PAIRS when packet count=1 and state is clean | Dennis | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indirect coverage with updated/correct CP FW | 0 |  |  |  |  | 1
246 | 12.494 | [Navi4m] GRBM Queue to optimize CP processor performance | Daniel G | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, not programmable | 0 |  |  |  |  | 1
247 | 12.495 | [RS64] Add Load-IO Custom instruction w/16 CSRs | Daniel G | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Risc-V feature, will be tested by IPSE team | 0 |  |  |  |  | 1
248 | 12.497 | load_reserved store_conditional unitID aliasing requires a change in GFX client unitID values | David/Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | WGS related, covered by gaming exerciser with test firmware | 0 |  |  |  |  | 1
249 | 12.498 | Increase in DB FIFOs for Write-Only Performance | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | No need for diag to do performance check | 0 |  |  |  |  | 1
250 | 12.499 | CB/DB compress to clear/single before sending to GLx | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
251 | 12.5 | 2ch_cant_saturate_pcie_rdBW | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Confirmed ownership has been passed to SDMA team for perf verfication | 0 |  |  |  |  | 1