## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | EX-FEAT-001 | Check RAS (It is software function, not a HW feature | Charlie Song | SOC RAS |  | check ras | P1 | ras6.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 |  | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | AB+5WK
1 | EX-FEAT-002 | Disable Fatal Error Event ( It is software function, not HW feature) | Charlie Song | SOC RAS |  | disable fatal error event | P2 | ras6.5 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 |  | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | AB+9WK
2 | EX-FEAT-001 | Check RAS (It is software function, not a HW feature | Charlie Song | SOC RAS |  | check ras | P1 | soc.ras/checkras | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 |  | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | AB+5WK
3 | EX-FEAT-002 | Disable Fatal Error Event ( It is software function, not HW feature) | Charlie Song | SOC RAS |  | disable fatal error event | P2 | soc.ras/disable_fatal_error_event | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 |  | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | AB+9WK