## Sheet1
| Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id | test_list_id
0 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 3 | 4 | MALL20.1-2,MALL20.11-12 | 1
1 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 2 | 4 | MALL20.1-2,MALL20.11-12 | 1
2 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.11 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 1 | 4 | MALL20.1-2,MALL20.11-12 | 1
3 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.12 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 0 | 4 | MALL20.1-2,MALL20.11-12 | 1
4 | 1 | DF-HWPRS-062 | Harvesting of DF components |  | MALL |  | Fill (Full FB) | p2 | mall.fill.1 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 | waiting on downconfig board to test | WK06 |  | 0 | 1 | mall.fill.1 | 2
5 | 2 | DF-HWPRS-020 | Distributed Compression Logic support in DF |  | MALL |  | Decompression tests | p1 | mall.dcc.1 | TNG |  | 1 | 1 | New | 1 | 1 | 0.5 | Emulator | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK07 |  | 1 | 2 | mall.dcc.1-2 | 3
6 | 2 | DF-HWPRS-020 | Distributed Compression Logic support in DF |  | MALL |  | Decompression tests | p1 | mall.dcc.2 | TNG |  | 1 | 1 | New | 1 | 0 | 0.5 | Emulator | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK07 |  | 0 | 2 | mall.dcc.1-2 | 3
7 | 3 | DF-HWPRS-023 | MALL Next Victim Forecast [Existing] |  | MALL |  | Fill (Full FB) | p2 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 4
8 | 4 | DF-HWPRS-028 | Replace NoAlloc Request attribute with 2 bit Cache Hints (temporal hints). |  | MALL |  | NoAlloc 2bit test | p1 | mall.noalloc.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK02 |  | 0 | 1 | mall.noalloc.2 | 5
9 | 5 | DF-HWPRS-050 | Configurable Dedicated Meta Cache for DCN |  | DCN |  | DCN DCC Test | p1 | MALL_DCHB064 | TServer |  | 1 | 1 | New | 1 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | DCN Diags Coverage | 0 | 1 | MALL_DCHB064 | 6
10 | 6 | DF-HWPRS-049 | SDP Command - DCN Prefetch to MALL with OKAY_NODATA response |  | DCN |  | DCN CAB Test | p1 | MALL_DCHB023 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK07 | DCN Diags Coverage | 0 | 1 | MALL_DCHB023 | 7
11 | 7 | DF-HWPRS-040 | LRU Based Way Selection for Periodic/Async MALL Rinsing |  | MALL |  | ORT test | p1 | mall.lru_periodic_rinse | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK04 |  | 0 | 1 | mall.lru_periodic_rinse | 8
12 | 8 | DF-HWPRS-066 | [DfV: MALL RAS] Poison/parity error injection on write path from MALL to UMC. |  | RAS |  | RAS test | p2 | mall.ras_dfv_poison_parity_test | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK05 | RAS Diags Coverage | 0 | 1 | mall.ras_dfv_poison_parity_test | 9
13 | 9 | DF-HWPRS-021 | Cache as Buffer Mode |  | DCN |  | DCN CAB Test | p1 | MALL_DCHB023 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK07 | DCN Diags Coverage | 0 | 1 | MALL_DCHB023 | 10
14 | 10 | DF-HWPRS-051 | [Cache as buffer mode] Uncompressed DCN Data in MALL on a Prefetch |  | DCN |  | DCN CAB Test (new variant?) | p1 | MALL_DCHB064 | TServer |  | 1 | 1 | New | 1 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | DCN Diags Coverage | 0 | 1 | MALL_DCHB064 | 11
15 | 11 | DF-HWPRS-056 | MALL Statistics |  | MALL |  | Fill (Full FB) | p2 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 12
16 | 12 | DEDFRTL-7231 | Increase configurability for ORR and OWT in MALL |  | MALL |  | NoAlloc 2bit test | p2 | mall.noalloc.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK02 |  | 0 | 1 | mall.noalloc.2 | 13
17 | 13 | DEDFRTL-7498 | MALL: Support 8 TAG/LRU/DAT Banks per macro |  | MALL |  | Fill (Full FB) | p1 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 14
18 | 14 | DEDFRTL-7501 | MALL: Flush cache and disable allocation |  | MALL |  | MALL Flush Test | p1 | mall.flush.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.flush.1 | 15
19 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 3 | 4 | MALL20.1-2,MALL20.11-12 | 16
20 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 2 | 4 | MALL20.1-2,MALL20.11-12 | 16
21 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.11 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 1 | 4 | MALL20.1-2,MALL20.11-12 | 16
22 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.12 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 |  | 0 | 1 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK08 |  | 0 | 4 | MALL20.1-2,MALL20.11-12 | 16
23 | 16 | DEDFRTL-7505 | MALL: Support NV3x Hash |  | MALL |  | Fill (Full FB) | P3 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 17
24 | 17 | DEDFRTL-7559 | MALL: Add separate queue for Victims |  | MALL |  | Victim Queue Stress | p2 | mall.throughput.1x4/victim | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK04 |  | 0 | 1 | mall.throughput.1x4/victim | 18
25 | 18 | DEDFRTL-7800 | MALL: flip FlushComplete to FlushInProg so SW can do a bcst poll for flush completion |  | MALL |  | MALL Flush Test | p1 | mall.flush.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.flush.1 | 19
26 | 19 | DENV31-956 | New PState with MALL (sub-frame MALL retrieve) |  | DCN |  | DCN Sub-Viewport test | p2 | MALL_DCHB017 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK07 |  | 0 | 1 | MALL_DCHB017 | 20
27 | 20 | NV4X-MALL-01 | System level testing + high power draw |  | MALL |  | MALL Throughput | p2 | mall.throughput.1x4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK04 |  | 0 | 1 | mall.throughput.1x4 | 21
28 | 21 | NV4X-MALL-02 | Performance and BW validation |  | MALL |  | MALL Throughput | p2 | mall.throughput.1x4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK04 |  | 0 | 1 | mall.throughput.1x4 | 22
29 | 22 | NV4X-MALL-03 | MALL fill test |  | MALL |  | Fill (Full FB) | p1 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 23