## Sheet1
| Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id | test_list_id | Tcyclename | Tcycleid | Tsuitename | Tsuiteid | Tcasename | Tcaseid | Pre_Trelid | Pre_Trelname | Pre_Trun | Pre_Logid | Pre_Log_status | Pre_Exec_Start_Time | Pre_Exec_End_Time | Post_Trelid | Post_Trelname | Post_Trun | Post_Logid | Post_Log_status | Post_Exec_Start_Time | Post_Exec_End_Time
0 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 3 | 4 | MALL20.1-2,MALL20.11-12 | 1
1 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 2 | 4 | MALL20.1-2,MALL20.11-12 | 1
2 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.11 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 1 | 4 | MALL20.1-2,MALL20.11-12 | 1 | MALL | 4915971 | MALL | 7336314 | MALL20.11 | 89096882 | 880253 | Pre-Silicon NV48 | 206347690 | 425236425 | blocked | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583256 | 425236433 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
3 | 0 | DF-HWPRS-061 | TMZ (Trusted Memory Zone) HW Protection |  | MALL |  | MALL TMZ Tests | p2 | MALL20.12 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 0 | 4 | MALL20.1-2,MALL20.11-12 | 1 | MALL | 4915971 | MALL | 7336314 | MALL20.12 | 89096883 | 880253 | Pre-Silicon NV48 | 206347694 | 425236435 | blocked | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583259 | 425236438 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
4 | 1 | DF-HWPRS-062 | Harvesting of DF components |  | MALL |  | Fill (Full FB) | p2 | mall.fill.1 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | waiting on downconfig board to test | WK06 |  | 0 | 1 | mall.fill.1 | 2 | MALL | 4915971 | MALL | 7336314 | mall.fill.1 | 89096884 | 880253 | Pre-Silicon NV48 | 206347697 | 425236442 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583264 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
5 | 2 | DF-HWPRS-020 | Distributed Compression Logic support in DF |  | MALL |  | Decompression tests | p1 | mall.dcc.1 | TNG |  | 1 | 1 | New | 1 | 1 | 0.5 | Emulator | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK07 |  | 1 | 2 | mall.dcc.1-2 | 3 | MALL | 4915971 | MALL | 7336314 | mall.dcc.1 | 89096887 | 880253 | Pre-Silicon NV48 | 206347698 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583268 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
6 | 2 | DF-HWPRS-020 | Distributed Compression Logic support in DF |  | MALL |  | Decompression tests | p1 | mall.dcc.2 | TNG |  | 1 | 1 | New | 1 | 0 | 0.5 | Emulator | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK07 |  | 0 | 2 | mall.dcc.1-2 | 3 | MALL | 4915971 | MALL | 7336314 | mall.dcc.2 | 89096888 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 204583310 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
7 | 3 | DF-HWPRS-023 | MALL Next Victim Forecast [Existing] |  | MALL |  | Fill (Full FB) | p2 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 4 | MALL | 4915971 | MALL | 7336314 | mall.fill.1 | 89096884 | 880253 | Pre-Silicon NV48 | 206347700 | 425236447 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583314 | 425236453 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
8 | 4 | DF-HWPRS-028 | Replace NoAlloc Request attribute with 2 bit Cache Hints (temporal hints). |  | MALL |  | NoAlloc 2bit test | p1 | mall.noalloc.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK02 |  | 0 | 1 | mall.noalloc.2 | 5 | MALL | 4915971 | MALL | 7336314 | mall.noalloc.2 | 89096893 | 880253 | Pre-Silicon NV48 | 206347704 | 425236457 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583326 | 425236467 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
9 | 5 | DF-HWPRS-050 | Configurable Dedicated Meta Cache for DCN |  | DCN |  | DCN DCC Test | p1 | MALL_DCHB064 | TServer |  | 1 | 1 | New | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | DCN Diags Coverage | 0 | 1 | MALL_DCHB064 | 6 | MALL | 4915971 | DCN | 7336317 | MALL_DCHB064 | 89096894 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 204583346 |  | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
10 | 6 | DF-HWPRS-049 | SDP Command - DCN Prefetch to MALL with OKAY_NODATA response |  | DCN |  | DCN CAB Test | p1 | MALL_DCHB023 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK07 | DCN Diags Coverage | 0 | 1 | MALL_DCHB023 | 7 | MALL | 4915971 | DCN | 7336317 | MALL_DCHB023 | 89096897 | 880253 | Pre-Silicon NV48 | 206347706 | 425236488 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583354 | 425236494 | pass | 2024-06-26T00:00:00-0400 | 2024-06-26T00:00:00-0400
11 | 7 | DF-HWPRS-040 | LRU Based Way Selection for Periodic/Async MALL Rinsing |  | MALL |  | ORT test | p1 | mall.lru_periodic_rinse | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK04 |  | 0 | 1 | mall.lru_periodic_rinse | 8 | MALL | 4915971 | MALL | 7336314 | mall.lru_periodic_rinse | 89096898 | 880253 | Pre-Silicon NV48 | 206347710 |  | pass | 2024-06-26T00:00:00-0400 | 2024-06-26T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583359 | 425236503 | pass | 2024-06-05T00:00:00-0400 | 2024-06-05T00:00:00-0400
12 | 8 | DF-HWPRS-066 | [DfV: MALL RAS] Poison/parity error injection on write path from MALL to UMC. |  | RAS |  | RAS test | p2 | mall.ras_dfv_poison_parity_test | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 1 | 1 | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK05 | RAS Diags Coverage | 0 | 1 | mall.ras_dfv_poison_parity_test | 9 | MALL | 4915971 | RAS | 7336322 | mall.ras_dfv_poison_parity_test | 89096900 | 880253 | Pre-Silicon NV48 | 206347711 | 425236516 | incomplete | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583364 |  | incomplete | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
13 | 9 | DF-HWPRS-021 | Cache as Buffer Mode |  | DCN |  | DCN CAB Test | p1 | MALL_DCHB023 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK07 | DCN Diags Coverage | 0 | 1 | MALL_DCHB023 | 10 | MALL | 4915971 | DCN | 7336317 | MALL_DCHB023 | 89096897 | 880253 | Pre-Silicon NV48 | 206347712 | 425236523 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583367 | 425236652 | pass | 2024-06-26T00:00:00-0400 | 2024-06-26T00:00:00-0400
14 | 10 | DF-HWPRS-051 | [Cache as buffer mode] Uncompressed DCN Data in MALL on a Prefetch |  | DCN |  | DCN CAB Test (new variant?) | p1 | MALL_DCHB064 | TServer |  | 1 | 1 | New | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | DCN Diags Coverage | 0 | 1 | MALL_DCHB064 | 11 | MALL | 4915971 | DCN | 7336317 | MALL_DCHB064 | 89096894 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 204583372 |  | pass | 2024-06-26T00:00:00-0400 | 2024-06-26T00:00:00-0400
15 | 11 | DF-HWPRS-056 | MALL Statistics |  | MALL |  | Fill (Full FB) | p2 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 12 | MALL | 4915971 | MALL | 7336314 | mall.fill.1 | 89096884 | 880253 | Pre-Silicon NV48 | 206347715 | 425236657 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583376 | 425236665 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
16 | 12 | DEDFRTL-7231 | Increase configurability for ORR and OWT in MALL |  | MALL |  | NoAlloc 2bit test | p2 | mall.noalloc.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK02 |  | 0 | 1 | mall.noalloc.2 | 13 | MALL | 4915971 | MALL | 7336314 | mall.noalloc.2 | 89096893 | 880253 | Pre-Silicon NV48 | 206347717 | 425236670 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583390 | 425236674 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
17 | 13 | DEDFRTL-7498 | MALL: Support 8 TAG/LRU/DAT Banks per macro |  | MALL |  | Fill (Full FB) | p1 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 14 | MALL | 4915971 | MALL | 7336314 | mall.fill.1 | 89096884 | 880253 | Pre-Silicon NV48 | 206347723 | 425236677 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583398 | 425236685 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
18 | 14 | DEDFRTL-7501 | MALL: Flush cache and disable allocation |  | MALL |  | MALL Flush Test | p1 | mall.flush.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.flush.1 | 15 | MALL | 4915971 | MALL | 7336314 | mall.flush.1 | 89096902 | 880253 | Pre-Silicon NV48 | 206347725 | 425236711 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583409 | 425236718 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
19 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 3 | 4 | MALL20.1-2,MALL20.11-12 | 16 | MALL | 4915971 | MALL | 7336314 | MALL20.1 | 89096880 | 880253 | Pre-Silicon NV48 | 206347727 | 425236725 | blocked | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583414 | 425236731 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
20 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 2 | 4 | MALL20.1-2,MALL20.11-12 | 16 | MALL | 4915971 | MALL | 7336314 | MALL20.2 | 89096881 | 880253 | Pre-Silicon NV48 | 206347732 | 425236738 | blocked | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583421 | 425236741 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
21 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.11 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 1 | 4 | MALL20.1-2,MALL20.11-12 | 16 | MALL | 4915971 | MALL | 7336314 | MALL20.11 | 89096882 | 880253 | Pre-Silicon NV48 | 206347735 | 425236745 | blocked | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583428 | 425236788 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
22 | 15 | DEDFRTL-7502 | MALL: Allow TMZ=1 requests to allocate in cache |  | MALL |  | MALL TMZ Tests | p1 | MALL20.12 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK08 |  | 0 | 4 | MALL20.1-2,MALL20.11-12 | 16 | MALL | 4915971 | MALL | 7336314 | MALL20.12 | 89096883 | 880253 | Pre-Silicon NV48 | 206347738 | 425236798 | blocked | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583444 | 425236806 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
23 | 16 | DEDFRTL-7505 | MALL: Support NV3x Hash |  | MALL |  | Fill (Full FB) | P3 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 17 | MALL | 4915971 | MALL | 7336314 | mall.fill.1 | 89096884 | 880253 | Pre-Silicon NV48 | 206347746 | 425236810 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583464 | 425236814 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
24 | 17 | DEDFRTL-7559 | MALL: Add separate queue for Victims |  | MALL |  | Victim Queue Stress | p2 | mall.throughput.1x4/victim | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 |  | WK04 |  | 0 | 1 | mall.throughput.1x4/victim | 18 | MALL | 4915971 | MALL | 7336314 | mall.throughput.1x4/victim | 89096913 | 880253 | Pre-Silicon NV48 | 206347749 | 425236821 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583467 | 425236826 | pass | 2024-06-05T00:00:00-0400 | 2024-06-05T00:00:00-0400
25 | 18 | DEDFRTL-7800 | MALL: flip FlushComplete to FlushInProg so SW can do a bcst poll for flush completion |  | MALL |  | MALL Flush Test | p1 | mall.flush.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.flush.1 | 19 | MALL | 4915971 | MALL | 7336314 | mall.flush.1 | 89096902 | 880253 | Pre-Silicon NV48 | 206347755 | 425236837 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583471 | 425236846 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
26 | 19 | DENV31-956 | New PState with MALL (sub-frame MALL retrieve) |  | DCN |  | DCN Sub-Viewport test | p2 | MALL_DCHB017 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK07 |  | 0 | 1 | MALL_DCHB017 | 20 | MALL | 4915971 | DCN | 7336317 | MALL_DCHB017 | 89096914 | 880253 | Pre-Silicon NV48 | 206347757 | 425236849 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583624 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
27 | 20 | NV4X-MALL-01 | System level testing + high power draw |  | MALL |  | MALL Throughput | p2 | mall.throughput.1x4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK04 |  | 0 | 1 | mall.throughput.1x4 | 21 | MALL | 4915971 | MALL | 7336314 | mall.throughput.1x4 | 89096916 | 880253 | Pre-Silicon NV48 | 206347759 | 425236851 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583709 | 425236858 | pass | 2024-06-05T00:00:00-0400 | 2024-06-05T00:00:00-0400
28 | 21 | NV4X-MALL-02 | Performance and BW validation |  | MALL |  | MALL Throughput | p2 | mall.throughput.1x4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK04 |  | 0 | 1 | mall.throughput.1x4 | 22 | MALL | 4915971 | MALL | 7336314 | mall.throughput.1x4 | 89096916 | 880253 | Pre-Silicon NV48 | 206347763 | 425236867 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583773 | 425236881 | pass | 2024-06-05T00:00:00-0400 | 2024-06-05T00:00:00-0400
29 | 22 | NV4X-MALL-03 | MALL fill test |  | MALL |  | Fill (Full FB) | p1 | mall.fill.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | pass on BRP004 MALL enabled IFWI | WK02 |  | 0 | 1 | mall.fill.1 | 23 | MALL | 4915971 | MALL | 7336314 | mall.fill.1 | 89096884 | 880253 | Pre-Silicon NV48 | 206347764 | 425236883 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204583828 | 425236885 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400