## Sheet1
| Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id | test_list_id | Tcyclename | Tcycleid | Tsuitename | Tsuiteid | Tcasename | Pre_Trelid | Pre_Trelname | Pre_Trun | Pre_Logid | Pre_Log_status | Pre_Exec_Start_Time | Pre_Exec_End_Time | Post_Trelid | Post_Trelname | Post_Trun | Post_Logid | Post_Log_status | Post_Exec_Start_Time | Post_Exec_End_Time
0 | 0 | NV48-DF-001 | Byte Enable Writes | sbalabat | DF |  | HDP,CPDMA Byte Enable Write | P3 | FEAT_1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 1 | FEAT_1 | 1 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
1 | 1 | NV48-DF-002 | Coherency | sbalabat | DF |  | DF Coherency Test | P1 | FEAT_2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_2 | 2 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
2 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 11 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
3 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 10 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
4 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 9 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
5 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 8 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
6 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 7 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
7 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 6 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
8 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 5 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
9 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 4 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
10 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 3 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
11 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 2 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
12 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 1 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
13 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.12 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
14 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 5 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
15 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 4 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
16 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.3 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 3 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
17 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 2 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
18 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 1 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
19 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.6 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
20 | 4 | NV48-DF-004 | DF Pstate with Memory Traffic | sbalabat | DF |  | DF Pstate Test | P2 | FEAT_5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK10 |  | 0 | 1 | FEAT_5 | 5 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
21 | 5 | NV48-DF-005 | DF Cstate | sbalabat | DF |  | DF Cstate Test | P1 | FEAT_6 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK8 |  | 0 | 1 | FEAT_6 | 6 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
22 | 6 | NV48-DF-006 | Display and Stutter Mode | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT_7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_7 | 7 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
23 | 7 | NV48-DF-006 | ULV during display stutter | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT_8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_8 | 8 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
24 | 8 | NV48-DF-007 | 128B Gfx Large Reads to Mall | sbalabat | DF |  | DF large read test | P1 | FEAT_9 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_9 | 9 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
25 | 9 | NV48-DF-008 | Performance Monitors | sbalabat | DF |  | DF large read test | P1 | FEAT_10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_10 | 10 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
26 | 10 | NV48-DF-009 | Power Gate During DF C-State | sbalabat | DF |  | DF Cstate Stutter Test | P2 | FEAT_11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_11 | 11 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
27 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 6 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
28 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 5 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
29 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.3 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 4 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
30 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.4 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 3 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
31 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.5 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 2 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
32 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.6 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 1 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
33 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.7 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 0 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
34 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 15 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
35 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 14 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
36 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 13 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
37 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 12 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
38 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 11 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
39 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 10 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
40 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 9 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
41 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 8 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
42 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 7 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
43 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 6 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
44 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 5 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
45 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.12 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 4 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
46 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.13 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 3 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
47 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.14 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 2 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
48 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.15 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 1 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
49 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.16 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
50 | 13 | NV48-DF-012 | MALL NoAlloc override for HDP | sbalabat | DF |  | DF NCM No-Alloc Mall diag | P2 | FEAT_14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 1 | 2 | FEAT_14.1-2 | 14 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
51 | 13 | NV48-DF-012 | MALL NoAlloc override for HDP | sbalabat | DF |  | DF NCM No-Alloc Mall diag | P2 | FEAT_14.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 2 | FEAT_14.1-2 | 14 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
52 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 3 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
53 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 2 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
54 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.3 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 1 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
55 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.4 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 0 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
56 | 15 | NV48-DF-014 | Mall Hashing Support in NV4x | sbalabat | DF |  | DF EL3 diag | P2 | FEAT_16.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK11 |  | 1 | 2 | FEAT_16.1-2 | 16 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
57 | 15 | NV48-DF-014 | Mall Hashing Support in NV4x | sbalabat | DF |  | DF EL3 diag | P2 | FEAT_16.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK11 |  | 0 | 2 | FEAT_16.1-2 | 16 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
58 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 3 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
59 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 2 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
60 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.3 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 1 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
61 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.4 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 0 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
62 | 17 | NV48-DF-016 | Dual Edge Synchronous Buses (Double Pumping) | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT_18 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK4 |  | 0 | 1 | FEAT_18 | 18 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
63 | 18 | NV48-DF-016 | DBI support for double pumping | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT_19 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Partial coverage is done, low risk. Aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_19 | 19 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
64 | 19 | NV48-DF-017 | GCM/NCM Large Write | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_21 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | wk-6 |  | 0 | 1 | FEAT_21 | 20 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
65 | 20 | NV48-DF-017 | Single VC for GFX IO | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_22 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_22 | 21 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
66 | 21 | NV48-DF-017 | QOS throttle changes | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_23 | Tserver |  | 1 | 1 | New | 1 | 0 | 0.5 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_23 | 22 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
67 | 22 | NV48-DF-019 | NCM Subtype for CPWD | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT_25 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK5 |  | 0 | 1 | FEAT_25 | 23 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
68 | 23 | NV48-DF-020 | 2 PG Domain | sbalabat | DF |  |  | P1 | FEAT_26 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_26 | 24 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
69 | 24 | NV48-DF-021 | TCDX traffic Stress case | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT_26 | Tserver |  | 1 | 1 | New | 1 | 1 | 0.8 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK4 |  | 0 | 1 | FEAT_26 | 25 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
70 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 9 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
71 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 8 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
72 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 7 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
73 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 6 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
74 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 5 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
75 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 4 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
76 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 3 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
77 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 2 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
78 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 1 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
79 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
80 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 9 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
81 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 8 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
82 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.3 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 7 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
83 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.4 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 6 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
84 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.5 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 5 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
85 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.6 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 4 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
86 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.7 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 3 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
87 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.8 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 2 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | 880253 | Pre-Silicon NV48 | [5 empty] | 884319 | Post Silicon NV48 AFE A0
88 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.9 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK3 |  | 1 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0
89 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.10 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | Not Found | [7 empty] | 884319 | Post Silicon NV48 AFE A0