## Sheet1
| Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id | test_list_id | Tcyclename | Tcycleid | Tsuitename | Tsuiteid | Tcasename | Tcaseid | Pre_Trelid | Pre_Trelname | Pre_Trun | Pre_Logid | Pre_Log_status | Pre_Exec_Start_Time | Pre_Exec_End_Time | Post_Trelid | Post_Trelname | Post_Trun | Post_Logid | Post_Log_status | Post_Exec_Start_Time | Post_Exec_End_Time
0 | 0 | NV48-DF-001 | Byte Enable Writes | sbalabat | DF |  | HDP,CPDMA Byte Enable Write | P3 | FEAT_1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 1 | FEAT_1.1 | 1
1 | 1 | NV48-DF-002 | Coherency | sbalabat | DF |  | DF Coherency Test | P1 | FEAT_2.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_2.1 | 2
2 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 11 | 12 | FEAT_3.1-12 | 3
3 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 10 | 12 | FEAT_3.1-12 | 3
4 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 9 | 12 | FEAT_3.1-12 | 3
5 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 8 | 12 | FEAT_3.1-12 | 3
6 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 7 | 12 | FEAT_3.1-12 | 3
7 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 6 | 12 | FEAT_3.1-12 | 3
8 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 5 | 12 | FEAT_3.1-12 | 3
9 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 4 | 12 | FEAT_3.1-12 | 3
10 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 3 | 12 | FEAT_3.1-12 | 3
11 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 2 | 12 | FEAT_3.1-12 | 3
12 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 1 | 12 | FEAT_3.1-12 | 3
13 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.12 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 12 | FEAT_3.1-12 | 3
14 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 5 | 6 | FEAT_3.1-6 | 4
15 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 4 | 6 | FEAT_3.1-6 | 4
16 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.3 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 3 | 6 | FEAT_3.1-6 | 4
17 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 2 | 6 | FEAT_3.1-6 | 4
18 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 1 | 6 | FEAT_3.1-6 | 4
19 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.6 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 6 | FEAT_3.1-6 | 4
20 | 4 | NV48-DF-004 | DF Pstate with Memory Traffic | sbalabat | DF |  | DF Pstate Test | P2 | FEAT_5.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK10 |  | 0 | 1 | FEAT_5.1 | 5
21 | 5 | NV48-DF-005 | DF Cstate | sbalabat | DF |  | DF Cstate Test | P1 | FEAT_6.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK8 |  | 0 | 1 | FEAT_6.1 | 6 | DF | 4912733 | DF | 7332084 | FEAT_6.1 | 89078236 | 880253 | Pre-Silicon NV48 | 204460042 | 424776138 | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204460048 | 424776141 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
22 | 6 | NV48-DF-006 | Display and Stutter Mode | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT_7.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_7.1 | 7 | DF | 4912733 | DF | 7332084 | FEAT_7.1 | 89078237 | 880253 | Pre-Silicon NV48 | 204460055 | 424776142 | pass | 2024-04-21T00:00:00-0400 | 2024-04-21T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189329 |  | pass | 2024-04-21T00:00:00-0400 | 2024-04-21T00:00:00-0400
23 | 7 | NV48-DF-006 | ULV during display stutter | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT_8.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_8.1 | 8 | DF | 4912733 | DF | 7332084 | FEAT_8.1 | 89078238 | 880253 | Pre-Silicon NV48 | 204460061 | 424776145 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189331 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
24 | 8 | NV48-DF-007 | 128B Gfx Large Reads to Mall | sbalabat | DF |  | DF large read test | P1 | FEAT_9.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_9.1 | 9 | DF | 4912733 | DF | 7332084 | FEAT_9.1 | 89078239 | 880253 | Pre-Silicon NV48 | 204460065 | 424776146 | pass | 2024-03-03T00:00:00-0400 | 2024-03-03T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204460067 | 424776148 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
25 | 9 | NV48-DF-008 | Performance Monitors | sbalabat | DF |  | DF large read test | P1 | FEAT_10.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_10.1 | 10 | DF | 4912733 | DF | 7332084 | FEAT_10.1 | 89078243 | 880253 | Pre-Silicon NV48 | 204460069 | 424776150 | pass | 2024-03-03T00:00:00-0400 | 2024-03-03T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 204460071 | 424776151 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
26 | 10 | NV48-DF-009 | Power Gate During DF C-State | sbalabat | DF |  | DF Cstate Stutter Test | P2 | FEAT_11.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_11.1 | 11 | DF | 4912733 | DF | 7332084 | FEAT_11.1 | 89078244 | 880253 | Pre-Silicon NV48 | 204460073 | 424776152 | pass | 2024-04-21T00:00:00-0400 | 2024-04-21T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189336 |  | pass | 2024-04-21T00:00:00-0400 | 2024-04-21T00:00:00-0400
27 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 6 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | FEAT_12.1 | 89078245 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 204460080 | 424776154 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
28 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 5 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | FEAT_12.2 | 89078246 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 204460084 | 424776155 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
29 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.3 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 4 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | FEAT_12.3 | 89078247 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 204460087 | 424776158 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
30 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.4 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 3 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | FEAT_12.4 | 89078249 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 204460090 | 424776160 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
31 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.5 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 2 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [8 empty] | 884319 | Post Silicon NV48 AFE A0 |  |  | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
32 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.6 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 1 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [8 empty] | 884319 | Post Silicon NV48 AFE A0 |  |  | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
33 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.7 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 0 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7332084 | Not Found | [8 empty] | 884319 | Post Silicon NV48 AFE A0 |  |  | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
34 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 15 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.1 | 89078250 | 880253 | Pre-Silicon NV48 | 206189338 | 424776164 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189341 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
35 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 14 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.2 | 89078251 | 880253 | Pre-Silicon NV48 | 206189343 | 424776166 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189345 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
36 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 13 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.3 | 89078253 | 880253 | Pre-Silicon NV48 | 206189346 | 424776169 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189347 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
37 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 12 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.4 | 89078254 | 880253 | Pre-Silicon NV48 | 206189349 | 424776171 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189350 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
38 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 11 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.5 | 89078256 | 880253 | Pre-Silicon NV48 | 206189351 | 424776173 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189353 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
39 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 10 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.6 | 89078257 | 880253 | Pre-Silicon NV48 | 206189355 | 424776174 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189357 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
40 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 9 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.7 | 89078258 | 880253 | Pre-Silicon NV48 | 206189358 | 424776175 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189359 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
41 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 8 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.8 | 89078259 | 880253 | Pre-Silicon NV48 | 206189361 | 424776178 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189363 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
42 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 7 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.9 | 89078260 | 880253 | Pre-Silicon NV48 | 206189365 | 424776180 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189368 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
43 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 6 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.10 | 89078261 | 880253 | Pre-Silicon NV48 | 206189369 | 424776187 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189370 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
44 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 5 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.11 | 89078262 | 880253 | Pre-Silicon NV48 | 206189371 | 424776192 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189373 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
45 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.12 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 4 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.12 | 89078263 | 880253 | Pre-Silicon NV48 | 206189374 | 424776194 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189377 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
46 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.13 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 3 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.13 | 89078264 | 880253 | Pre-Silicon NV48 | 206189378 | 424776201 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189382 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
47 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.14 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 2 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.14 | 89078265 | 880253 | Pre-Silicon NV48 | 206189385 | 424776211 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189387 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
48 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.15 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 1 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.15 | 89078266 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189388 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
49 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.16 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7332084 | FEAT_13.16 | 89078267 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189391 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
50 | 13 | NV48-DF-012 | MALL NoAlloc override for HDP | sbalabat | DF |  | DF NCM No-Alloc Mall diag | P2 | FEAT_14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 1 | 2 | FEAT_14.1-2 | 14 | DF | 4912733 | DF | 7332084 | FEAT_14.1 | 89078268 | 880253 | Pre-Silicon NV48 | 206189393 | 424776287 | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189451 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
51 | 13 | NV48-DF-012 | MALL NoAlloc override for HDP | sbalabat | DF |  | DF NCM No-Alloc Mall diag | P2 | FEAT_14.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 2 | FEAT_14.1-2 | 14 | DF | 4912733 | DF | 7332084 | FEAT_14.2 | 89078269 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189453 |  | pass | 2024-03-24T00:00:00-0400 | 2024-03-24T00:00:00-0400
52 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 3 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | FEAT_15.1 | 89078275 | 880253 | Pre-Silicon NV48 | 206189454 | 424776293 | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189455 |  | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400
53 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 2 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | FEAT_15.2 | 89078276 | 880253 | Pre-Silicon NV48 | 206189456 | 424776298 | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189459 |  | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400
54 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.3 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 1 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | FEAT_15.3 | 89078277 | 880253 | Pre-Silicon NV48 | 206189461 | 424776306 | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189464 |  | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400
55 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.4 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 0 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7332084 | FEAT_15.4 | 89078279 | 880253 | Pre-Silicon NV48 | 206189465 | 424776311 | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189466 |  | pass | 2024-04-07T00:00:00-0400 | 2024-04-07T00:00:00-0400
56 | 15 | NV48-DF-014 | Mall Hashing Support in NV4x | sbalabat | DF |  | DF EL3 diag | P2 | FEAT_16.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK11 |  | 1 | 2 | FEAT_16.1-2 | 16 | DF | 4912733 | DF | 7332084 | FEAT_16.1 | 89078280 | 880253 | Pre-Silicon NV48 | 206189467 | 424776314 | pass | 2024-05-05T00:00:00-0400 | 2024-05-05T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189468 |  | pass | 2024-05-05T00:00:00-0400 | 2024-05-05T00:00:00-0400
57 | 15 | NV48-DF-014 | Mall Hashing Support in NV4x | sbalabat | DF |  | DF EL3 diag | P2 | FEAT_16.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK11 |  | 0 | 2 | FEAT_16.1-2 | 16 | DF | 4912733 | DF | 7332084 | FEAT_16.2 | 89078281 | 880253 | Pre-Silicon NV48 | 206189469 | 424776318 | pass | 2024-05-05T00:00:00-0400 | 2024-05-05T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189470 |  | pass | 2024-05-05T00:00:00-0400 | 2024-05-05T00:00:00-0400
58 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 3 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | FEAT_17.1 | 89078282 | 880253 | Pre-Silicon NV48 | 206189472 | 424776325 | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189475 |  | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400
59 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 2 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | FEAT_17.2 | 89078283 | 880253 | Pre-Silicon NV48 | 206189476 | 424776330 | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189478 |  | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400
60 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.3 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 1 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | FEAT_17.3 | 89078284 | 880253 | Pre-Silicon NV48 | 206189480 | 424776333 | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189485 |  | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400
61 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.4 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 0 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7332084 | FEAT_17.4 | 89078285 | 880253 | Pre-Silicon NV48 | 206189487 | 424776338 | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189489 |  | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400
62 | 17 | NV48-DF-016 | Dual Edge Synchronous Buses (Double Pumping) | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT_18.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK4 |  | 0 | 1 | FEAT_18.1 | 18 | DF | 4912733 | DF | 7332084 | FEAT_18.1 | 89078286 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189490 |  | pass | 2024-04-14T00:00:00-0400 | 2024-04-14T00:00:00-0400
63 | 18 | NV48-DF-016 | DBI support for double pumping | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT_19.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Partial coverage is done, low risk. Aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_19.1 | 19 | DF | 4912733 | DF | 7332084 | FEAT_19.1 | 89078288 | 880253 | Pre-Silicon NV48 | 206189492 | 424776341 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189495 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
64 | 19 | NV48-DF-017 | GCM/NCM Large Write | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_21.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | wk-6 |  | 0 | 1 | FEAT_21.1 | 20 | DF | 4912733 | DF | 7332084 | FEAT_21.1 | 89078289 | 880253 | Pre-Silicon NV48 | 206189497 | 424776343 | pass | 2024-01-07T00:00:00-0400 | 2024-01-07T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189498 | 424776345 | pass | 2024-03-27T00:00:00-0400 | 2024-03-27T00:00:00-0400
65 | 20 | NV48-DF-017 | Single VC for GFX IO | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_22.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_22.1 | 21 | DF | 4912733 | DF | 7332084 | FEAT_22.1 | 89078291 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189499 |  | pass | 2024-03-27T00:00:00-0400 | 2024-03-27T00:00:00-0400
66 | 21 | NV48-DF-017 | QOS throttle changes | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_23.1 | Tserver |  | 1 | 1 | New | 1 | 0 | 0.5 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_23.1 | 22 | DF | 4912733 | DF | 7332084 | FEAT_23.1 | 89078293 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189500 |  | pass | 2024-03-27T00:00:00-0400 | 2024-03-27T00:00:00-0400
67 | 22 | NV48-DF-019 | NCM Subtype for CPWD | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT_25.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK5 |  | 0 | 1 | FEAT_25.1 | 23 | DF | 4912733 | DF | 7332084 | FEAT_25.1 | 89078294 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189501 | 424776347 | pass | 2024-06-12T00:00:00-0400 | 2024-06-12T00:00:00-0400
68 | 23 | NV48-DF-020 | 2 PG Domain | sbalabat | DF |  |  | P1 | FEAT_26.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_26.1 | 24 | DF | 4912733 | DF | 7332084 | FEAT_26.1 | 89078295 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189503 |  | pass | 2024-06-12T00:00:00-0400 | 2024-06-12T00:00:00-0400
69 | 24 | NV48-DF-021 | TCDX traffic Stress case | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT_26.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 0.8 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK4 |  | 0 | 1 | FEAT_26.1 | 25 | DF | 4912733 | DF | 7332084 | FEAT_26.1 | 89078295 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189504 | 424776354 | pass | 2024-06-05T00:00:00-0400 | 2024-06-05T00:00:00-0400
70 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 9 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.1 | 89078297 | 880253 | Pre-Silicon NV48 | 206189506 | 424776358 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189508 | 424776359 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
71 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 8 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.2 | 89078305 | 880253 | Pre-Silicon NV48 | 206189509 | 424776362 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189512 | 424776365 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
72 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 7 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.3 | 89078320 | 880253 | Pre-Silicon NV48 | 206189513 | 424776368 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189516 | 424776370 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
73 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 6 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.4 | 89078329 | 880253 | Pre-Silicon NV48 | 206189518 | 424776374 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189520 | 424776376 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
74 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 5 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.5 | 89078330 | 880253 | Pre-Silicon NV48 | 206189521 | 424776377 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189522 | 424776378 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
75 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 4 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.6 | 89078331 | 880253 | Pre-Silicon NV48 | 206189523 | 424776380 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189528 | 424776384 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
76 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 3 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.7 | 89078332 | 880253 | Pre-Silicon NV48 | 206189530 | 424776386 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189531 | 424776389 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
77 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 2 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.8 | 89078333 | 880253 | Pre-Silicon NV48 | 206189534 | 424776390 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189536 | 424776392 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
78 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 1 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.9 | 89078334 | 880253 | Pre-Silicon NV48 | 206189538 | 424776393 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189539 | 424776395 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
79 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7332084 | FEAT_27.10 | 89078335 | 880253 | Pre-Silicon NV48 | 206189540 | 424776398 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189543 | 424776399 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
80 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 9 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.1 | 89078336 | 880253 | Pre-Silicon NV48 | 206189544 | 424776400 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189547 | 424776403 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
81 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 8 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.2 | 89078337 | 880253 | Pre-Silicon NV48 | 206189548 | 424776404 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189549 | 424776405 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
82 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.3 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 7 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.3 | 89078338 | 880253 | Pre-Silicon NV48 | 206189550 | 424776408 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189552 | 424776409 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
83 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.4 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 6 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.4 | 89078339 | 880253 | Pre-Silicon NV48 | 206189553 | 424776410 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189554 | 424776412 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
84 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.5 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 5 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.5 | 89078340 | 880253 | Pre-Silicon NV48 | 206189559 | 424776414 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189560 | 424776416 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
85 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.6 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 4 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.6 | 89078341 | 880253 | Pre-Silicon NV48 | 206189561 | 424776419 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189562 | 424776421 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
86 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.7 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 3 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.7 | 89078342 | 880253 | Pre-Silicon NV48 | 206189564 | 424776430 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189566 | 424776431 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
87 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.8 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 2 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.8 | 89078343 | 880253 | Pre-Silicon NV48 | 206189567 | 424776432 | pass | 2024-03-10T00:00:00-0400 | 2024-03-10T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206189569 | 424776449 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
88 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.9 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK3 |  | 1 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.9 | 89078344 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189570 |  | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
89 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.10 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7332084 | FEAT_28.10 | 89078345 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206189572 |  | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400