## Sheet1
| Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id | test_list_id | Tcyclename | Tcycleid | Tsuitename | Tsuiteid | Tcasename | Tcaseid | Pre_Trelid | Pre_Trelname | Pre_Trun | Pre_Logid | Pre_Log_status | Pre_Exec_Start_Time | Pre_Exec_End_Time | Post_Trelid | Post_Trelname | Post_Trun | Post_Logid | Post_Log_status | Post_Exec_Start_Time | Post_Exec_End_Time
0 | 0 | NV48-DF-001 | Byte Enable Writes | sbalabat | DF |  | HDP,CPDMA Byte Enable Write | P3 | FEAT_1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 1 | FEAT_1.1 | 1 | DF | 4912733 | DF | 7382400 | FEAT_1.1 | 89078220 | 880253 | Pre-Silicon NV48 | 206306304 | 425089573 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306306 | 425089579 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
1 | 1 | NV48-DF-002 | Coherency | sbalabat | DF |  | DF Coherency Test | P1 | FEAT_2.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_2.1 | 2 | DF | 4912733 | DF | 7382400 | FEAT_2.1 | 89078221 | 880253 | Pre-Silicon NV48 | 206306307 | 425089586 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306308 | 425089596 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
2 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 11 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.1 | 89078222 | 880253 | Pre-Silicon NV48 | 206306309 | 425089603 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306311 | 425089607 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
3 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 10 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.2 | 89078223 | 880253 | Pre-Silicon NV48 | 206306313 | 425089616 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306315 | 425089626 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
4 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 9 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.3 | 89078224 | 880253 | Pre-Silicon NV48 | 206306316 | 425089634 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306319 | 425089641 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
5 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 8 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.4 | 89078225 | 880253 | Pre-Silicon NV48 | 206306321 | 425089651 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306323 | 425089660 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
6 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 7 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.5 | 89078226 | 880253 | Pre-Silicon NV48 | 206306324 | 425089666 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306325 | 425089681 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
7 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 6 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.6 | 89078227 | 880253 | Pre-Silicon NV48 | 206306328 | 425089690 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306329 | 425089697 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
8 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 5 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.7 | 89078228 | 880253 | Pre-Silicon NV48 | 206306331 | 425089700 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306336 | 425089707 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
9 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 4 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.8 | 89078229 | 880253 | Pre-Silicon NV48 | 206306340 | 425089727 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306341 | 425089735 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
10 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 3 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.9 | 89078230 | 880253 | Pre-Silicon NV48 | 206306345 | 425089744 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306347 | 425089749 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
11 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 2 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.10 | 89078231 | 880253 | Pre-Silicon NV48 | 206306348 | 425089756 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306350 | 425089767 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
12 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 1 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.11 | 89078232 | 880253 | Pre-Silicon NV48 | 206306352 | 425089772 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306354 | 425089775 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
13 | 2 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.12 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 12 | FEAT_3.1-12 | 3 | DF | 4912733 | DF | 7382400 | FEAT_3.12 | 89078233 | 880253 | Pre-Silicon NV48 | 206306356 | 425089784 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306357 | 425089789 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
14 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 5 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7382400 | FEAT_3.1 | 89078222 | 880253 | Pre-Silicon NV48 | 206306358 | 425089801 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306361 | 425089809 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
15 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 4 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7382400 | FEAT_3.2 | 89078223 | 880253 | Pre-Silicon NV48 | 206306366 | 425089822 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306383 | 425089830 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
16 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.3 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 3 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7382400 | FEAT_3.3 | 89078224 | 880253 | Pre-Silicon NV48 | 206306398 | 425089860 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306418 | 425089879 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
17 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 2 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7382400 | FEAT_3.4 | 89078225 | 880253 | Pre-Silicon NV48 | 206306421 | 425089885 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306429 | 425089909 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
18 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 1 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7382400 | FEAT_3.5 | 89078226 | 880253 | Pre-Silicon NV48 | 206306439 | 425089918 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306451 | 425089927 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
19 | 3 | NV48-DF-003 | I/O and Graphics Atomic , CS and ATHUB needs to support Atomic commands | sbalabat | DF |  | DF Atomic Test | P1 | FEAT_3.6 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 6 | FEAT_3.1-6 | 4 | DF | 4912733 | DF | 7382400 | FEAT_3.6 | 89078227 | 880253 | Pre-Silicon NV48 | 206306464 | 425089939 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306470 | 425089949 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
20 | 4 | NV48-DF-004 | DF Pstate with Memory Traffic | sbalabat | DF |  | DF Pstate Test | P2 | FEAT_5.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK10 |  | 0 | 1 | FEAT_5.1 | 5 | DF | 4912733 | DF | 7382400 | FEAT_5.1 | 89078235 | 880253 | Pre-Silicon NV48 | 206306475 | 425089964 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306477 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
21 | 5 | NV48-DF-005 | DF Cstate | sbalabat | DF |  | DF Cstate Test | P1 | FEAT_6.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK8 |  | 0 | 1 | FEAT_6.1 | 6 | DF | 4912733 | DF | 7382400 | FEAT_6.1 | 89078236 | 880253 | Pre-Silicon NV48 | 206306482 | 425089984 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306485 | 425090010 | pass | 2024-07-03T00:00:00-0400 | 2024-07-03T00:00:00-0400
22 | 6 | NV48-DF-006 | Display and Stutter Mode | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT_7.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_7.1 | 7 | DF | 4912733 | DF | 7382400 | FEAT_7.1 | 89078237 | 880253 | Pre-Silicon NV48 | 206306493 | 425090030 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306500 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
23 | 7 | NV48-DF-006 | ULV during display stutter | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT_8.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_8.1 | 8 | DF | 4912733 | DF | 7382400 | FEAT_8.1 | 89078238 | 880253 | Pre-Silicon NV48 | 206306505 | 425090043 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306518 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
24 | 8 | NV48-DF-007 | 128B Gfx Large Reads to Mall | sbalabat | DF |  | DF large read test | P1 | FEAT_9.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_9.1 | 9 | DF | 4912733 | DF | 7382400 | FEAT_9.1 | 89078239 | 880253 | Pre-Silicon NV48 | 206306525 | 425090054 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306541 | 425090064 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
25 | 9 | NV48-DF-008 | Performance Monitors | sbalabat | DF |  | DF large read test | P1 | FEAT_10.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK2 |  | 0 | 1 | FEAT_10.1 | 10 | DF | 4912733 | DF | 7382400 | FEAT_10.1 | 89078243 | 880253 | Pre-Silicon NV48 | 206306563 | 425090100 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306597 | 425090136 | pass | 2024-05-22T00:00:00-0400 | 2024-05-22T00:00:00-0400
26 | 10 | NV48-DF-009 | Power Gate During DF C-State | sbalabat | DF |  | DF Cstate Stutter Test | P2 | FEAT_11.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_11.1 | 11 | DF | 4912733 | DF | 7382400 | FEAT_11.1 | 89078244 | 880253 | Pre-Silicon NV48 | 206306614 | 425090171 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306625 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
27 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 6 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7382400 | FEAT_12.1 | 89078245 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306628 | 425090190 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
28 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 5 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7382400 | FEAT_12.2 | 89078246 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306632 | 425090233 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
29 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.3 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 4 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7382400 | FEAT_12.3 | 89078247 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306637 | 425090241 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
30 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.4 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK6 |  | 3 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7382400 | FEAT_12.4 | 89078249 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306644 | 425090252 | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
31 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.5 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 2 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7382400 | FEAT_12.5 | 89342442 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306655 |  | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
32 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.6 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 1 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7382400 | FEAT_12.6 | 89342462 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306672 |  | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
33 | 11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT_12.7 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK6 |  | 0 | 7 | FEAT_12.1-7 | 12 | DF | 4912733 | DF | 7382400 | FEAT_12.7 | 89342473 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306678 |  | pass | 2024-06-19T00:00:00-0400 | 2024-06-19T00:00:00-0400
34 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 15 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.1 | 89078250 | 880253 | Pre-Silicon NV48 | 206306681 | 425090302 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306686 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
35 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 14 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.2 | 89078251 | 880253 | Pre-Silicon NV48 | 206306688 | 425090310 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306695 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
36 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 13 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.3 | 89078253 | 880253 | Pre-Silicon NV48 | 206306698 | 425090329 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306703 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
37 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 12 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.4 | 89078254 | 880253 | Pre-Silicon NV48 | 206306707 | 425090350 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306712 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
38 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 11 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.5 | 89078256 | 880253 | Pre-Silicon NV48 | 206306713 | 425090363 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306720 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
39 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 10 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.6 | 89078257 | 880253 | Pre-Silicon NV48 | 206306722 | 425090368 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306729 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
40 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 9 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.7 | 89078258 | 880253 | Pre-Silicon NV48 | 206306731 | 425090383 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306733 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
41 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 8 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.8 | 89078259 | 880253 | Pre-Silicon NV48 | 206306734 | 425090394 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306742 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
42 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 7 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.9 | 89078260 | 880253 | Pre-Silicon NV48 | 206306752 | 425090409 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306754 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
43 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 6 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.10 | 89078261 | 880253 | Pre-Silicon NV48 | 206306759 | 425090422 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306761 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
44 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 5 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.11 | 89078262 | 880253 | Pre-Silicon NV48 | 206306762 | 425090434 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306768 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
45 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.12 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 4 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.12 | 89078263 | 880253 | Pre-Silicon NV48 | 206306773 | 425090453 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306774 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
46 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.13 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 3 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.13 | 89078264 | 880253 | Pre-Silicon NV48 | 206306776 | 425090464 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306778 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
47 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.14 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 2 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.14 | 89078265 | 880253 | Pre-Silicon NV48 | 206306779 | 425090473 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306780 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
48 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.15 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 1 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.15 | 89078266 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306781 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
49 | 12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT_13.16 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 16 | FEAT_13.1-16 | 13 | DF | 4912733 | DF | 7382400 | FEAT_13.16 | 89078267 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306784 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
50 | 13 | NV48-DF-012 | MALL NoAlloc override for HDP | sbalabat | DF |  | DF NCM No-Alloc Mall diag | P2 | FEAT_14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 1 | 2 | FEAT_14.1-2 | 14 | DF | 4912733 | DF | 7382400 | FEAT_14.1 | 89078268 | 880253 | Pre-Silicon NV48 | 206306785 | 425090489 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306788 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
51 | 13 | NV48-DF-012 | MALL NoAlloc override for HDP | sbalabat | DF |  | DF NCM No-Alloc Mall diag | P2 | FEAT_14.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 2 | FEAT_14.1-2 | 14 | DF | 4912733 | DF | 7382400 | FEAT_14.2 | 89078269 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306792 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
52 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 3 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7382400 | FEAT_15.1 | 89078275 | 880253 | Pre-Silicon NV48 | 206306794 | 425090502 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306797 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
53 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 2 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7382400 | FEAT_15.2 | 89078276 | 880253 | Pre-Silicon NV48 | 206306802 | 425090514 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306809 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
54 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.3 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 1 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7382400 | FEAT_15.3 | 89078277 | 880253 | Pre-Silicon NV48 | 206306812 | 425090531 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306814 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
55 | 14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT_15.4 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 | 0 |  | 0 | 0 | 0 |  | WK7 |  | 0 | 4 | FEAT_15.1-4 | 15 | DF | 4912733 | DF | 7382400 | FEAT_15.4 | 89078279 | 880253 | Pre-Silicon NV48 | 206306817 | 425090543 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306824 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
56 | 15 | NV48-DF-014 | Mall Hashing Support in NV4x | sbalabat | DF |  | DF EL3 diag | P2 | FEAT_16.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK11 |  | 1 | 2 | FEAT_16.1-2 | 16 | DF | 4912733 | DF | 7382400 | FEAT_16.1 | 89078280 | 880253 | Pre-Silicon NV48 | 206306826 | 425090560 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306832 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
57 | 15 | NV48-DF-014 | Mall Hashing Support in NV4x | sbalabat | DF |  | DF EL3 diag | P2 | FEAT_16.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK11 |  | 0 | 2 | FEAT_16.1-2 | 16 | DF | 4912733 | DF | 7382400 | FEAT_16.2 | 89078281 | 880253 | Pre-Silicon NV48 | 206306834 | 425090575 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306841 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
58 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 3 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7382400 | FEAT_17.1 | 89078282 | 880253 | Pre-Silicon NV48 | 206306843 | 425090589 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306845 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
59 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.2 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 2 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7382400 | FEAT_17.2 | 89078283 | 880253 | Pre-Silicon NV48 | 206306848 | 425090604 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306849 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
60 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.3 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 1 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7382400 | FEAT_17.3 | 89078284 | 880253 | Pre-Silicon NV48 | 206306851 | 425090613 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306853 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
61 | 16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT_17.4 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK8 |  | 0 | 4 | FEAT_17.1-4 | 17 | DF | 4912733 | DF | 7382400 | FEAT_17.4 | 89078285 | 880253 | Pre-Silicon NV48 | 206306855 | 425090635 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306860 |  | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400
62 | 17 | NV48-DF-016 | Dual Edge Synchronous Buses (Double Pumping) | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT_18.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK4 |  | 0 | 1 | FEAT_18.1 | 18 | DF | 4912733 | DF | 7382400 | FEAT_18.1 | 89078286 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306861 | 425090648 | pass | 2024-06-05T00:00:00-0400 | 2024-06-05T00:00:00-0400
63 | 18 | NV48-DF-016 | DBI support for double pumping | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT_19.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 | Partial coverage is done, low risk. Aligned with IPSE | 1 | 1 |  | 0 | 0 | 1 |  |  |  | 0 | 1 | FEAT_19.1 | 19 | DF | 4912733 | DF | 7382400 | FEAT_19.1 | 89078288 | 880253 | Pre-Silicon NV48 | 206306865 | 425090659 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306867 | 425090663 | pass | 2024-05-08T00:00:00-0400 | 2024-05-08T00:00:00-0400
64 | 19 | NV48-DF-017 | GCM/NCM Large Write | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_21.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | wk-6 |  | 0 | 1 | FEAT_21.1 | 20 | DF | 4912733 | DF | 7382400 | FEAT_21.1 | 89078289 | 880253 | Pre-Silicon NV48 | 206306872 | 425090669 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306877 | 425090678 | pass | 2024-03-27T00:00:00-0400 | 2024-03-27T00:00:00-0400
65 | 20 | NV48-DF-017 | Single VC for GFX IO | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_22.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  |  |  | 0 | 1 | FEAT_22.1 | 21 | DF | 4912733 | DF | 7382400 | FEAT_22.1 | 89078291 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306884 | 425090687 | pass | 2024-05-08T00:00:00-0400 | 2024-05-08T00:00:00-0400
66 | 21 | NV48-DF-017 | QOS throttle changes | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT_23.1 | Tserver |  | 1 | 1 | New | 1 | 0 | 0.5 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | FEAT_23.1 | 22 | DF | 4912733 | DF | 7382400 | FEAT_23.1 | 89078293 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306892 |  | pass | 2024-05-08T00:00:00-0400 | 2024-05-08T00:00:00-0400
67 | 22 | NV48-DF-019 | NCM Subtype for CPWD | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT_25.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK5 |  | 0 | 1 | FEAT_25.1 | 23 | DF | 4912733 | DF | 7382400 | FEAT_25.1 | 89078294 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306895 | 425090692 | pass | 2024-06-12T00:00:00-0400 | 2024-06-12T00:00:00-0400
68 | 23 | NV48-DF-020 | 2 PG Domain | sbalabat | DF |  |  | P1 | FEAT_26.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK9 |  | 0 | 1 | FEAT_26.1 | 24 | DF | 4912733 | DF | 7382400 | FEAT_26.1 | 89078295 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306898 |  | pass | 2024-06-12T00:00:00-0400 | 2024-06-12T00:00:00-0400
69 | 24 | NV48-DF-021 | TCDX traffic Stress case | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT_26.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 0.8 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK4 |  | 0 | 1 | FEAT_26.1 | 25 | DF | 4912733 | DF | 7382400 | FEAT_26.1 | 89078295 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206306903 | 425090705 | pass | 2024-06-05T00:00:00-0400 | 2024-06-05T00:00:00-0400
70 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 9 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.1 | 89078297 | 880253 | Pre-Silicon NV48 | 206306906 | 425090709 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306908 | 425090718 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
71 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 8 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.2 | 89078305 | 880253 | Pre-Silicon NV48 | 206306910 | 425090723 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306912 | 425090732 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
72 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 7 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.3 | 89078320 | 880253 | Pre-Silicon NV48 | 206306914 | 425090740 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306915 | 425090747 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
73 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.4 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 6 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.4 | 89078329 | 880253 | Pre-Silicon NV48 | 206306919 | 425090761 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306923 | 425090767 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
74 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 5 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.5 | 89078330 | 880253 | Pre-Silicon NV48 | 206306926 | 425090776 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306929 | 425090780 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
75 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 4 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.6 | 89078331 | 880253 | Pre-Silicon NV48 | 206306934 | 425090794 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306939 | 425090806 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
76 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 3 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.7 | 89078332 | 880253 | Pre-Silicon NV48 | 206306943 | 425090824 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306947 | 425090833 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
77 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 2 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.8 | 89078333 | 880253 | Pre-Silicon NV48 | 206306953 | 425090838 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306959 | 425090852 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
78 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.9 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 1 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.9 | 89078334 | 880253 | Pre-Silicon NV48 | 206306963 | 425090863 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306968 | 425090879 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
79 | 25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT_27.10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 10 | FEAT_27.1-10 | 26 | DF | 4912733 | DF | 7382400 | FEAT_27.10 | 89078335 | 880253 | Pre-Silicon NV48 | 206306972 | 425090889 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306978 | 425090897 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
80 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 9 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.1 | 89078336 | 880253 | Pre-Silicon NV48 | 206306985 | 425090905 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306987 | 425090912 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
81 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 8 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.2 | 89078337 | 880253 | Pre-Silicon NV48 | 206306988 | 425090927 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306990 | 425090932 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
82 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.3 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 7 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.3 | 89078338 | 880253 | Pre-Silicon NV48 | 206306994 | 425090939 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206306995 | 425090947 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
83 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.4 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 6 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.4 | 89078339 | 880253 | Pre-Silicon NV48 | 206307000 | 425090966 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206307004 | 425090969 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
84 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.5 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 5 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.5 | 89078340 | 880253 | Pre-Silicon NV48 | 206307006 | 425090984 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206307007 | 425090994 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
85 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.6 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 4 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.6 | 89078341 | 880253 | Pre-Silicon NV48 | 206307008 | 425090996 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206307013 | 425091013 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
86 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.7 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 3 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.7 | 89078342 | 880253 | Pre-Silicon NV48 | 206307017 | 425091025 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206307020 | 425091036 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
87 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.8 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 2 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.8 | 89078343 | 880253 | Pre-Silicon NV48 | 206307022 | 425091044 | pass | 2024-02-18T00:00:00-0400 | 2024-02-18T00:00:00-0400 | 884319 | Post Silicon NV48 AFE A0 | 206307023 | 425091053 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
88 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.9 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 1 | 1 |  | 0 | 0 | 1 |  | WK3 |  | 1 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.9 | 89078344 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206307024 | 425091064 | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400
89 | 26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT_28.10 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 1 |  | WK3 |  | 0 | 10 | FEAT_28.1-10 | 27 | DF | 4912733 | DF | 7382400 | FEAT_28.10 | 89078345 | [7 empty] | 884319 | Post Silicon NV48 AFE A0 | 206307026 |  | pass | 2024-05-29T00:00:00-0400 | 2024-05-29T00:00:00-0400