## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | variation | Remainder Variations | PreTotal | PostTotal | input variations | org test case id | test_list_id
0 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.1 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 2 | 18 | {'Pass': 4.0, 'Waived': 11.0, 'Fail': 0, 'Skip': 0, 'Total Run': 15.0} | {'Pass.1': 15.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 15.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
1 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.2 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 3 | 17 | {'Pass': 4.0, 'Waived': 11.0, 'Fail': 0, 'Skip': 0, 'Total Run': 15.0} | {'Pass.1': 15.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 15.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
2 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.3 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 4 | 16 | {'Pass': 4.0, 'Waived': 11.0, 'Fail': 0, 'Skip': 0, 'Total Run': 15.0} | {'Pass.1': 15.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 15.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
3 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.4 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 5 | 15 | {'Pass': 4.0, 'Waived': 11.0, 'Fail': 0, 'Skip': 0, 'Total Run': 15.0} | {'Pass.1': 15.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 15.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
4 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.10 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 6 | 14 | {'Pass': 4.0, 'Waived': 10.0, 'Fail': 0, 'Skip': 0, 'Total Run': 14.0} | {'Pass.1': 14.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 14.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
5 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.12 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 7 | 13 | {'Pass': 4.0, 'Waived': 9.0, 'Fail': 0, 'Skip': 0, 'Total Run': 13.0} | {'Pass.1': 13.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 13.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
6 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.20 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 8 | 12 | {'Pass': 4.0, 'Waived': 8.0, 'Fail': 0, 'Skip': 0, 'Total Run': 12.0} | {'Pass.1': 12.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 12.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
7 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.30 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 9 | 11 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
8 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.31 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 10 | 10 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
9 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.32 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 11 | 9 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
10 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.33 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 12 | 8 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
11 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.34 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 13 | 7 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
12 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.35 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 14 | 6 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
13 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.36 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 15 | 5 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
14 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.37 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 16 | 4 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
15 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.38 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 17 | 3 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
16 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.39 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 18 | 2 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
17 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.40 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 19 | 1 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231
18 | NV48-HUBS-1070 | MMHUB:Security - Trusted Memory Zone (TMZ) | Radhika | MMHUB |  | MMHUB TMZ System Level Testing | P1 | mhub150.41 | Tserver | -vm -SkipMhubDfInit | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 1 | BRP018 | 7wk | • Refer to TP section 4.3.3.5 MARC and 4.3.3.6 MMEA Removal • MMEA registers to be replaced with DAGB ones | 20 | 0 | {'Pass': 4.0, 'Waived': 5.0, 'Fail': 0, 'Skip': 0, 'Total Run': 9.0} | {'Pass.1': 9.0, 'Waived.1': 0, 'Fail.1': 0, 'Skip.1': 0, 'Total Run.1': 9.0} | 19 | mhub150.1-4,mhub150.10,mhub150.12,mhub150.20,mhub150.30-41 | 231