## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | DCN-020 | 4 level Host VM |  | DCHB |  | DCC Decompression Test | P2 | DCHB002.1-63 | TNG |  | 1 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
1 | DCN-019 | 1 level GPUVM |  | DCHB |  | DCC Decompression Test | P2 | DCHB002.1-63 | TNG |  | 1 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
2 | DCN-009 | DCC |  | DCHB |  | DCC Decompression Test | P2 | DCHB002.1-63 | TNG |  | 1 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
3 | DCN-015 | DCHUBBUB watermark change (SR enter/exit, DRAM CLK change, Urgency) |  | DCHB |  | Rotation & Mirroring Test | P2 | DCHB004.1-12 | TNG |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 24 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
4 | DCN-021 | HW rotation and mirroring |  | DCHB |  | Rotation & Mirroring Test | P2 | DCHB004.1-12 | TNG |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 24 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
5 | DCN-105 | Interrupts |  | DCHB |  | Rotation & Mirroring Test | P2 | DCHB004.1-12 | TNG |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 24 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
6 | DCN-020 | 4 level Host VM |  | DCHB |  | Basic Flip Test | P2 | DCHB005.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
7 | DCN-019 | 1 level GPUVM |  | DCHB |  | Basic Flip Test | P2 | DCHB005.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
8 | DCN-028 | 3D Stereo Display |  | DCHB |  | Basic Flip Test | P2 | DCHB005.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
9 | DCN-022 | V-flip and I-flip type surface flip |  | DCHB |  | Basic Flip Test | P2 | DCHB005.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
10 | DCN-028 | 3D Stereo Display |  | DCHB |  | Stereoscopic Flip Test | P2 | DCHB006.1-10 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
11 | DCN-022 | V-flip and I-flip type surface flip |  | DCHB |  | Stereoscopic Flip Test | P2 | DCHB006.1-10 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
12 | DCN-024 | Global Flip Control Support |  | DCHB |  | Viewport Panning Test | P2 | DCHB007.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
13 | DCN-021 | HW rotation and mirroring |  | DCHB |  | Viewport Panning Test | P2 | DCHB007.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
14 | DCN-022 | V-flip and I-flip type surface flip |  | DCHB |  | Immediate Flip Stress Test | P2 | DCHB008.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
15 | DCN-i024 | [DCHUB]V-flip and I-flip type surface flip, [DCHUB]I-Flip latency [DCHUB]I-Flip testing with YUV420 and VM |  | DCHB |  | Immediate Flip Stress Test |  | DCHB008.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
16 | DCN-023 | I-Flip testing with YUV420 and VM |  | DCHB |  | Immediate Flip Stress Test | P2 | DCHB008.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
17 | DCN-024 | Global Flip Control Support |  | DCHB |  | Global Flip Control Test | P2 | DCHB010 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
18 | DCN-029 | Reader Line Position Support |  | DCHB |  | Reader Line Position Test | P2 | DCHB011.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
19 | DCN-009 | DCC |  | DCHB |  | DCC Zero-Sized Request Test | P2 | DCHB012.1-9 | TServer |  | 1 | 9 | Legacy | 1 | 9 | 1 | N-1 | 9 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-1
20 | DCN-009 | DCC |  | DCHB |  | DCC Dynamic Decompression Test | P2 | DCHB013.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-1
21 | DCN-026 | Surface Format: GFX11 tiling library |  | DCHB |  | GFX10 Tiling/Swizzle Modes Test | P2 | DCHB014.1-231 | TServer |  | 1 | 231 | Legacy | 1 | 231 | 1 | N-1 | 231 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
22 | DCN-025 | Surface Address support linear and 2D tiled |  | DCHB |  | GFX10 Tiling/Swizzle Modes Test | P2 | DCHB014.1-231 | TServer |  | 1 | 231 | Legacy | 1 | 231 | 1 | N-1 | 231 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
23 | DCN-020 | 4 level Host VM |  | DCHB |  | Advanced Flip Test | P2 | DCHB021.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
24 | DCN-019 | 1 level GPUVM |  | DCHB |  | Advanced Flip Test | P2 | DCHB021.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
25 | DCN-028 | 3D Stereo Display |  | DCHB |  | Advanced Flip Test | P2 | DCHB021.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
26 | DCN-022 | V-flip and I-flip type surface flip |  | DCHB |  | Advanced Flip Test | P2 | DCHB021.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
27 | DCN-027 | TMZ |  | DCHB |  | Display Surface TMZ Test | P2 | DCHB030.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-4
28 | DCN-024 | Global Flip Control Support |  | DCHB |  | Colour Component Crossbar Test | P2 | DCHB033 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
29 | DCN-019 | 1 level GPUVM |  | DCHB |  | Basic Virtual Memory(GPUVM) Testing | P2 | DCHB022.1-24 | TServer |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 24 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
30 | DCN-020 | 4 level Host VM |  | DCHB |  | DCHUB HOST VM & Invalidation Test | P2 | DCHB040 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
31 | DCN-027 | TMZ |  | DCHB |  | DCHUBBUB TMR Support Test | P2 | DCHB050 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-4
32 | DCN-020 | 4 level Host VM |  | DCHB |  | DCHUB RIOMMU Event Logging Test | P2 | DCHB060 | TServer |  | 8 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
33 | DCN-112 | Zstate Z9 and Z10) |  | DCHB |  | DCHUB RIOMMU Event Logging Test | P2 | DCHB060 | TServer |  | 8 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
34 | DCN-020 | 4 level Host VM |  | DCHB |  | DCHUB RIOMMU Z-state (Z10) Invalidation Test | P2 | DCHB061 | TServer |  | 8 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
35 | DCN-112 | Zstate Z9 and Z10) |  | DCHB |  | DCHUB RIOMMU Z-state (Z10) Invalidation Test | P2 | DCHB061 | TServer |  | 8 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
36 | DCN-030 | Format Conversion |  | DPP |  | CNVC Dynamic Pixel Expansion Test | P2 | DPP002.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-1
37 | DCN-031 | Cursor Composition |  | DPP |  | Stereoscopic Cursor Test | P2 | DPP005.1-2 | TNG |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
38 | DCN-043 | Scaling: Auto Calculation Mode |  | DPP |  | Scaler Bypass Mode Test | P2 | DPP006.1-14 | TServer |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-4
39 | DCN-043 | Scaling: Auto Calculation Mode |  | DPP |  | Scaler Hardcoded 2-Tap Scaling Test | P2 | DPP007.1-28 | TServer |  | 1 | 28 | Legacy | 1 | 28 | 1 | N-1 | 28 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-4
40 | DCN-042 | Scaling: Sharpening Support |  | DPP |  | Scaler Hardcoded 2-Tap Sharpening Test | P2 | DPP008.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
41 | DCN-044 | Scaling: Underscan/Overscan |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009.1-52 | TNG |  | 1 | 52 | Legacy | 1 | 52 | 1 | N-1 | 52 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
42 | DCN-046 | Scaling: Scaler Boundary Condition Support |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009.1-52 | TNG |  | 1 | 52 | Legacy | 1 | 52 | 1 | N-1 | 52 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
43 | DCN-039 | Scaling: Downscaling |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009.1-52 | TNG |  | 1 | 52 | Legacy | 1 | 52 | 1 | N-1 | 52 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
44 | DCN-038 | Scaling: Pre-Scaling Linearization |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009.1-52 | TNG |  | 1 | 52 | Legacy | 1 | 52 | 1 | N-1 | 52 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
45 | DCN-047 | Line buffer dynamic memory allocation and partitioning |  | DPP |  | Line Buffer Memory Size Test | P2 | DPP010.1-35 | TServer |  | 1 | 35 | Legacy | 1 | 35 | 1 | N-1 | 35 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
46 | DCN-036 | Color Processing: Gamut Remap after blend |  | DPP |  | Gamut Remap Test | P2 | DPP016.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
47 | DCN-035 | Color Processing: HDR Multiplier coefficients |  | DPP |  | HDR Multiplier Test | P2 | DPP020.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-4
48 | DCN-033 | Color Processing: Input Color Space Conversion |  | DPP |  | Color Keyer Alpha Generation Test | P2 | DPP024 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
49 | DCN-033 | Color Processing: Input Color Space Conversion |  | DPP |  | Basic Pixel Unpacking Test | P2 | DPP029.1-62 | TServer |  | 1 | 62 | Legacy | 1 | 62 | 1 | N-1 | 62 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
50 | DCN-020 | 4 level Host VM |  | DPP |  | Basic Pixel Unpacking Test | P2 | DPP029.1-62 | TServer |  | 1 | 62 | Legacy | 1 | 62 | 1 | N-1 | 62 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
51 | DCN-019 | 1 level GPUVM |  | DPP |  | Basic Pixel Unpacking Test | P2 | DPP029.1-62 | TServer |  | 1 | 62 | Legacy | 1 | 62 | 1 | N-1 | 62 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
52 | DCN-030 | Format Conversion |  | DPP |  | Format Converter Bias & Scale Test | P2 | DPP030.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-1
53 | DCN-030 | Format Conversion |  | DPP |  | Alpha Expansion LUT Test | P2 | DPP031 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-1
54 | DCN-036 | Color Processing: Gamut Remap after blend |  | DPP |  | Scaler Scenario Test | P2 | DPP034.1-13 | TServer |  | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
55 | DCN-039 | Scaling: Downscaling |  | DPP |  | Scaler Scenario Test | P2 | DPP034.1-13 | TServer |  | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
56 | DCN-046 | Scaling: Scaler Boundary Condition Support |  | DPP |  | Scaler Scenario Test | P2 | DPP034.1-13 | TServer |  | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
57 | DCN-041 | Scaling: Alpha Scaling |  | DPP |  | Scaler Scenario Test | P2 | DPP034.1-13 | TServer |  | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
58 | DCN-040 | Scaling: Upscaling |  | DPP |  | Scaler Scenario Test | P2 | DPP034.1-13 | TServer |  | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
59 | DCN-044 | Scaling: Underscan/Overscan |  | DPP |  | Scaler Scenario Test | P2 | DPP034.1-13 | TServer |  | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
60 | DCN-045 | Scaling: Stereo scaling |  | DPP |  | Stereoscopic Scaling Test | P2 | DPP036.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
61 | DCN-032 | Color Processing: De-alpha & Bias |  | DPP |  | De-alpha and Bias Test | P2 | DPP037 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-3
62 | DCN-036 | Color Processing: Gamut Remap after blend |  | DPP |  | Gamut Reamp S3.12 Coefficient Format Test | P2 | DPP039.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
63 | DCN-030 | Format Conversion |  | DPP |  | FCNV Clamp to Positive Test | P2 | DPP042.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-1
64 | DCN-031 | Cursor Composition |  | DPP |  | Basic Cursor Test | P2 | DPP043.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
65 | DCN-031 | Cursor Composition |  | DPP |  | Cursor Combo Test | P2 | DPP044.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
66 | DCN-031 | Cursor Composition |  | DPP |  | Cursor Blending Stereoscopic Test | P2 | DPP045.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
67 | DCN-127 | Color Processing: Pre-DeAlpha |  | DPP |  | CNVC Pre-DeAlpha Test | P2 | DPP046 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
68 | DCN-033 | Color Processing: Input Color Space Conversion |  | DPP |  | CNVC PreCSC S2.13 Coefcient Format Test | P2 | DPP047.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
69 | DCN-033 | Color Processing: Input Color Space Conversion |  | DPP |  | CNVC PreCSC S3.12 Coefficient Format Test | P2 | DPP048.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
70 | DCN-128 | Color Processing: Post-scaler CSC |  | DPP |  | CM PostCSC S2.13 Coefcient Format Test | P2 | DPP049.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
71 | DCN-128 | Color Processing: Post-scaler CSC |  | DPP |  | CM PostCSC S3.12 Coefficient Format Test | P2 | DPP050.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
72 | DCN-034 | Color Processing: Degamma |  | DPP |  | CNVC Pre-DeGamma Test | P2 | DPP051.1-7 | TServer |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-3
73 | DCN-032 | Color Processing: De-alpha & Bias |  | DPP |  | Pre-ReAlpha and De-Alpha Test | P2 | DPP052.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
74 | DCN-129 | Color Processing: Pre-ReAlpha Support |  | DPP |  | Pre-ReAlpha and De-Alpha Test | P2 | DPP052.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
75 | DCN-130 | Color Processing: Gamma Correction |  | DPP |  | CM Gamma Correction Test | P2 | DPP053.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
76 | DCN-049 | Top-layer Pass-through Mode Support |  | MPC |  | MPCC Mode Test | P2 | MPC003.1-5 | TNG |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
77 | DCN-050 | Pre-Pixel Alpha Blending with Gain Support |  | MPC |  | MPCC Mode Test | P2 | MPC003.1-5 | TNG |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
78 | DCN-051 | Global Alpha Blending with Gain Support |  | MPC |  | MPCC Mode Test | P2 | MPC003.1-5 | TNG |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
79 | DCN-052 | Stereo Format Blending Support |  | MPC |  | MPCC Stereo Mixing Test | P2 | MPC005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
80 | DCN-050 | Pre-Pixel Alpha Blending with Gain Support |  | MPC |  | Alpha Blending Per-Layer Gain Test | P2 | MPC007.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
81 | DCN-051 | Global Alpha Blending with Gain Support |  | MPC |  | Alpha Blending Per-Layer Gain Test | P2 | MPC007.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
82 | DCN-054 | Output Color Space Conversion |  | MPC |  | MPC Output CSC Test | P2 | MPC009.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-3
83 | DCN-055 | De-normalization, Rounding and Clamping Support |  | MPC |  | MPC Denormalization and Clamping Test | P2 | MPC010.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
84 | DCN-125 | MPCC 3D LUT Support |  | MPC |  | MPC 3D LUT Test | P2 | MPC017.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
85 | DCN-126 | MPCC Gamut Remap Support |  | MPC |  | MPC Gamut Remap Test | P2 | MPC012 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
86 | DCN-126 | MPCC Gamut Remap Support |  | MPC |  | MPC Gamut Remap S3.12 Coefficient Format Test | P2 | MPC013 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
87 | DCN-060 | Formatter: 4:2:2 and 4:2:0 Sub-sampling Support |  | MPC |  | MPCC Extend Output Gamma Test | P2 | MPC015.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
88 | DCN-053 | Output Gamma |  | MPC |  | MPCC Extend Output Gamma Test | P2 | MPC015.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
89 | DCN-010 | ABM |  | ABM |  | ABM Histogram | P2 | ABM066.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
90 | DCN-010 | ABM |  | ABM |  | ABM Luma Statistics | P2 | ABM067 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
91 | DCN-058 | Formatter: Truncation or rounding |  | FMT |  | FMT Truncation Test | P2 | FMT001.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
92 | DCN-058 | Formatter: Truncation or rounding |  | FMT |  | FMT Basic Spatial Dither Test | P2 | FMT002.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
93 | DCN-058 | Formatter: Truncation or rounding |  | FMT |  | FMT Spatial Dither Mode Test | P2 | FMT003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
94 | DCN-058 | Formatter: Truncation or rounding |  | FMT |  | FMT Frame Random Spatial Dither Test | P2 | FMT004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
95 | DCN-058 | Formatter: Truncation or rounding |  | FMT |  | FMT Spatial Dither Frame Counter Test | P2 | FMT005.1-10 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
96 | DCN-058 | Formatter: Truncation or rounding |  | FMT |  | FMT Temporal Dither Test | P2 | FMT006.1-52 | TServer |  | 1 | 52 | Legacy | 1 | 52 | 1 | N-1 | 52 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
97 | DCN-059 | Formatter: Legal Color Space Clamping Support |  | FMT |  | FMT Clamping Test | P2 | FMT007.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
98 | DCN-058 | Formatter: Truncation or rounding |  | FMT |  | FMT Random Dither with Stereo Test | P2 | FMT008.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-2
99 | DCN-060 | Formatter: 4:2:2 and 4:2:0 Sub-sampling Support |  | FMT |  | FMT 4:2:2 Subsampling Test | P2 | FMT009.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
100 | DCN-060 | Formatter: 4:2:2 and 4:2:0 Sub-sampling Support |  | FMT |  | FMT 4:2:0 Basic Subsampling Test | P2 | FMT010.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
101 | DCN-060 | Formatter: 4:2:2 and 4:2:0 Sub-sampling Support |  | FMT |  | FMT 4:2:0 Stereoscopic (Side-by-Side Half) Subsampling Test | P2 | FMT011 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
102 | DCN-061 | Formatter: Dynamic & Zero expansion |  | FMT |  | FMT Dynamic Expansion Test | P2 | FMT012.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-7
103 | DCN-060 | Formatter: 4:2:2 and 4:2:0 Sub-sampling Support |  | FMT |  | FMT 4:2:2 Subsampling with ODM Combine Test | P2 | FMT014.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
104 | DCN-060 | Formatter: 4:2:2 and 4:2:0 Sub-sampling Support |  | FMT |  | Basic Subsampling with ODM Combine Test | P2 | FMT015.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
105 | DCN-065 | DSC for DP |  | DSC |  | Multi-Stream DSC Test | P2 | DSC004.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
106 | DCN-066 | DSC for HDMI FRL |  | DSC |  | Multi-Stream DSC Test | P2 | DSC004.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
107 | DCN-064 | DPG |  | DSC |  | Multi-Stream DSC Test | P2 | DSC004.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
108 | DCN-xxx | [DSC] DSC for DP, [DSC] DSC for HDMI2.1, [DIO]DP FEC support, [OPP]DSC Resource Manager Support |  | DSC |  | Multi-Stream DSC Test |  | DSC004.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
109 | DCN-068 | ODM: Combine mode for 2: 1 and 4:1 for w/o DSC and with DSC |  | ODM |  | ODM Combine Mode Basic Test | P2 | ODM001.1-20 | TServer |  | 1 | 20 | Legacy | 1 | 20 | 1 | N-1 | 20 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
110 | DCN-068 | ODM: Combine mode for 2: 1 and 4:1 for w/o DSC and with DSC |  | ODM |  | ODM Combine Mode DSC Test | P2 | ODM003.1-18 | TServer |  | 1 | 18 | Legacy | 1 | 18 | 1 | N-1 | 18 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
111 | DCN-068 | ODM: Combine mode for 2: 1 and 4:1 for w/o DSC and with DSC |  | ODM |  | ODM Combine Mode (4:1) with DSC Test (For HPO FRL or DP2.0) | P2 | ODM004.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 18 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
112 | DCN-068 | ODM: Combine mode for 2: 1 and 4:1 for w/o DSC and with DSC |  | ODM |  | ODM Combine Mode with HBR3 Test | P2 | ODM005 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
113 | DCN-141 | [ODM] Dynamic switch of ODM |  | ODM |  | Dynamic Switch Of ODM Test |  | ODM007.1-12 | TServer |  | 2 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
114 | DCN-062 | Formatter: Pixel Repetition Support |  | OTG |  | OTG Pixel Repetition Test | P2 | OTG005.1-10 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
115 | DCN-073 | Horizontal pixel repetition |  | OTG |  | OTG Pixel Repetition Test | P2 | OTG005.1-10 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
116 | DCN-075 | Forced Vsync Support |  | OTG |  | OTG Force VSYNC Next Line Test | P2 | OTG007.1-215 | TServer |  | 1 | 215 | Legacy | 1 | 215 | 1 | N-1 | 215 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-7
117 | DCN-076 | H, V and Frame Count Snapshot Support |  | OTG |  | OTG Snapshot Test | P2 | OTG008.1-215 | TServer |  | 1 | 215 | Legacy | 1 | 215 | 1 | N-1 | 215 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
118 | DCN-070 | Stereo 3D Timing Support |  | OTG |  | OTG Frame-Sequential Stereoscopic Test | P2 | OTG009.1-215 | TServer |  | 1 | 215 | Legacy | 1 | 215 | 1 | N-1 | 215 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
119 | DCN-074 | OTG Trigger Support |  | OTG |  | OTG Trigger Detection Test | P2 | OTG011 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
120 | DCN-077 | Forced H and V Counter Support |  | OTG |  | OTG Force Count Test | P2 | OTG013 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
121 | DCN-081 | DRR |  | OTG |  | OTG Dynamic Refresh Rate Test | P2 | OTG014.1-199 | TServer |  | 1 | 199 | Legacy | 1 | 199 | 1 | N-1 | 199 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
122 | DCN-080 | GSL |  | OTG |  | OTG Pixel Repetition Test | P2 | OTG017.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
123 | DCN-069 | SLS Mode Timing Sync Support |  | OTG |  | OTG Pixel Repetition Test | P2 | OTG017.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
124 | DCN-072 | Underflow Detection and Recovery |  | OTG |  | Underflow Recovery Test | P2 | OTG025.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
125 | DCN-079 | Static Screen Support |  | OTG |  | OTG Static Screen Event Test | P2 | OTG026.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
126 | DCN-057 | Video Blanking Generation Support |  | OTG |  | Display Pattern Generator Test | P2 | OTG027.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
127 | DCN-064 | DPG |  | OTG |  | Display Pattern Generator Test | P2 | OTG027.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
128 | DCN-057 | Video Blanking Generation Support |  | OTG |  | OTG Dynamic V-active Support Test | P2 | OTG032.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
129 | DCN-074 | OTG Trigger Support |  | OTG |  | OTG Stream Synchronization Support | P2 | OTG033 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
130 | DCN-078 | Vstartup, Vupdate and Vready Interrupt Support |  | OTG |  | OTG VUPDATE Interrupt Test | P2 | OTG800.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
131 | DCN-106 | Fine Grain Security Gasket Support |  | OTG |  | OTG VUPDATE Interrupt Test | P2 | OTG800.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
132 | DCN-078 | Vstartup, Vupdate and Vready Interrupt Support |  | OTG |  | OTG Snapshot Interrupt Test | P2 | OTG801 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
133 | DCN-076 | H, V and Frame Count Snapshot Support |  | OTG |  | OTG Snapshot Interrupt Test | P2 | OTG801 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
134 | DCN-106 | Fine Grain Security Gasket Support |  | OTG |  | OTG TRIGA Interrupt Test | P2 | OTG804 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
135 | DCN-074 | OTG Trigger Support |  | OTG |  | OTG TRIGA Interrupt Test | P2 | OTG804 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
136 | DCN-106 | Fine Grain Security Gasket Support |  | OTG |  | OTG TRIGB Interrupt Test | P2 | OTG805 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
137 | DCN-074 | OTG Trigger Support |  | OTG |  | OTG TRIGB Interrupt Test | P2 | OTG805 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
138 | DCN-078 | Vstartup, Vupdate and Vready Interrupt Support |  | OTG |  | OTG VSTARTUP Interrupt Test | P2 | OTG809.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
139 | DCN-078 | Vstartup, Vupdate and Vready Interrupt Support |  | OTG |  | OTG VREADY Interrupt Test | P2 | OTG810 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
140 | DCN-090 | Aux/I2C |  | DIO |  | EDID Read Tests | P2 | DIO002.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-7
141 | DCN-090 | Aux/I2C |  | DIO |  | Aux Channel DPCD Read/Write Tests | P2 | DIO003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-7
142 | 2 | [DIO]AUX/I2C |  | DIO |  | EDID Variable Length Read |  | DIO011.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
143 | DCN-070 | Stereo 3D Timing Support |  | DIO |  | HDMI 1.4 Frame Packing 3D Test | P2 | DIO220.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
144 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI 1.4 Frame Packing 3D Test | P2 | DIO220.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
145 | DCN-063 | Stereo Dummy Data Insertion Support |  | DIO |  | HDMI 1.4 Frame Packing 3D Test | P2 | DIO220.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
146 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI 2.0 Scrambler Test | P2 | DIO221.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
147 | DCN-084 | HDMI Dolby Vision Support |  | DIO |  | HDMI 2.0 Dynamic Metadata Test | P2 | DIO222.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
148 | DCN-088 | DP Dynamic Metadata |  | DIO |  | HDMI 2.0 Dynamic Metadata Test | P2 | DIO222.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
149 | DCN-020 | 4 level Host VM |  | DIO |  | HDMI 2.0 Dynamic Metadata Test | P2 | DIO222.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
150 | DCN-019 | 1 level GPUVM |  | DIO |  | HDMI 2.0 Dynamic Metadata Test | P2 | DIO222.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
151 | DCN-085 | HDMI and DP SPDIF Control Bits Support |  | DIO |  | HDMI SPDIF Control Bits Test | P2 | DIO223.1-9 | TServer |  | 1 | 9 | Legacy | 1 | 9 | 1 | N-1 | 9 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-7
152 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Basic Output Test on PHYA | P2 | DIO217.1-95 | TServer |  | 1 | 95 | Legacy | 1 | 95 | 1 | N-1 | 95 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
153 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Random Audio Test | P2 | DIO224.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
154 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Ramp Audio Test | P2 | DIO225.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
155 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia Basic Audio Sine Wave Test | P2 | DIO226.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
156 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia Basic Audio Test | P2 | DIO227.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
157 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia 2.0 Channel HD Audio Test | P2 | DIO228.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
158 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia 4.0 Channel HD Audio Test | P2 | DIO229.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
159 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia 5.1 Channel HD Audio Test | P2 | DIO230.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
160 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia 6.1 Channel HD Audio Test | P2 | DIO231.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
161 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia 7.1 Channel HD Audio Test | P2 | DIO232.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
162 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia HBR Audio Test | P2 | DIO233.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
163 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Multi-Channel Single Stream DMA Out | P2 | DIO234.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
164 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Keep-alive Enable Azalia Audio Test | P2 | DIO235 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
165 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Deep Color Azalia 2.0 Channel HD Audio Test | P2 | DIO236.1-28 | TServer |  | 1 | 28 | Legacy | 1 | 28 | 1 | N-1 | 28 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
166 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Deep Color Azalia 7.1 Channel HD Audio Test | P2 | DIO237.1-28 | TServer |  | 1 | 28 | Legacy | 1 | 28 | 1 | N-1 | 28 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
167 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Deep Color Azalia HBR Audio Test | P2 | DIO238.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
168 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI 1.4 Frame Packing 3D Test with Azalia Audio | P2 | DIO240.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
169 | DCN-99 | [AZ]Audio Content Protection/Management Support |  | DIO |  | HDMI Audio Content Management Packet Test |  | DIO241.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
170 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI2.0 Packet Generation test | P2 | DIO242 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
171 | DCN-082 | HDMI 2.0 |  | DIO |  | HDMI Azalia Audio Test | P2 | DIO253.1-24 | TNG |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 24 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
172 | DCN-086 | DP 1.4 support |  | DIO |  | Multi-Stream HD Audio Test | P2 | DIO270 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
173 | DCN-018 | HDR support |  | DIO |  | DisplayPort Dynamic Metadata Test | P2 | DIO359 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
174 | DCN-070 | Stereo 3D Timing Support |  | DIO |  | DP Frame Packing 3D Test | P2 | DIO365.1-7 | TServer |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
175 | DCN-070 | Stereo 3D Timing Support |  | DIO |  | DP Frame Packing 3D Test with Scaling | P2 | DIO366.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
176 | DCN-071 | Ranged timing |  | DIO |  | DisplayPort Ranged Timing H/V TOTAL Change Test | P2 | DIO367 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
177 | DCN-071 | Ranged timing |  | DIO |  | DisplayPort Ranged Timing Pixel Rate Change Test | P2 | DIO368 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-5
178 | DCN-086 | DP 1.4 support |  | DIO |  | DP 1.62GHz 1 Lane Test | P2 | DIO369.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
179 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 1.62GHz 1 Lane Test | P2 | DIO369.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
180 | DCN-086 | DP 1.4 support |  | DIO |  | DP 1.62GHz 2 Lane Test | P2 | DIO370.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
181 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 1.62GHz 2 Lane Test | P2 | DIO370.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
182 | DCN-086 | DP 1.4 support |  | DIO |  | DP 1.62GHz 4 Lane Test | P2 | DIO371.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
183 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 1.62GHz 4 Lane Test | P2 | DIO371.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
184 | DCN-086 | DP 1.4 support |  | DIO |  | DP 2.70GHz 1 Lane Test | P2 | DIO372.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
185 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 2.70GHz 1 Lane Test | P2 | DIO372.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
186 | DCN-086 | DP 1.4 support |  | DIO |  | DP 2.70GHz 2 Lane Test | P2 | DIO373.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
187 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 2.70GHz 2 Lane Test | P2 | DIO373.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
188 | DCN-086 | DP 1.4 support |  | DIO |  | DP 2.70GHz 4 Lane Test | P2 | DIO374.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
189 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 2.70GHz 4 Lane Test | P2 | DIO374.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
190 | DCN-086 | DP 1.4 support |  | DIO |  | DP 5.40GHz 1 Lane Test | P2 | DIO375.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
191 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 5.40GHz 1 Lane Test | P2 | DIO375.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
192 | DCN-086 | DP 1.4 support |  | DIO |  | DP 5.40GHz 2 Lane Test | P2 | DIO376.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
193 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 5.40GHz 2 Lane Test | P2 | DIO376.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
194 | DCN-086 | DP 1.4 support |  | DIO |  | DP 5.40GHz 4 Lane Test | P2 | DIO377.1-4 | TNG |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
195 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 5.40GHz 4 Lane Test | P2 | DIO377.1-4 | TNG |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
196 | DCN-086 | DP 1.4 support |  | DIO |  | DP 8.10GHz 1 Lane Test | P2 | DIO378.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
197 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 8.10GHz 1 Lane Test | P2 | DIO378.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
198 | DCN-086 | DP 1.4 support |  | DIO |  | DP 8.10GHz 2 Lane Test | P2 | DIO379.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
199 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 8.10GHz 2 Lane Test | P2 | DIO379.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
200 | DCN-086 | DP 1.4 support |  | DIO |  | DP 8.10GHz 4 Lane Test | P2 | DIO380.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
201 | DCN-092 | USB-C Alt Mode |  | DIO |  | DP 8.10GHz 4 Lane Test | P2 | DIO380.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
202 | DCN-087 | DP 1.4 MST support |  | DIO |  | DP MST Source Test | P2 | DIO322.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
203 | DCN-087 | DP 1.4 MST support |  | DIO |  | DP MST Combo Test: UNIPHYB | P2 | DIO324.1-15 | TServer |  | 1 | 15 | Legacy | 1 | 15 | 1 | N-1 | 15 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
204 | DCN-087 | DP 1.4 MST support |  | DIO |  | DP MST Combo Test: UNIPHYC | P2 | DIO325.1-15 | TServer |  | 1 | 15 | Legacy | 1 | 15 | 1 | N-1 | 15 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
205 | DCN-086 | DP 1.4 support |  | DIO |  | DisplayPort 4:2:0 Subsampling Test | P2 | DIO381.1-15 | TServer |  | 1 | 15 | Legacy | 1 | 15 | 1 | N-1 | 15 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
206 | DCN-056 | DP Link Layer Compliance Pattern Support |  | DIO |  | DisplayPort Link Layer Compliance Pattern Test | P2 | DIO328.1-63 | TServer |  | 1 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-4
207 | DCN-99 | [AZ]Audio Content Protection/Management Support |  | DIO |  | DisplayPort Audio Content Management Packet Test |  | DIO382 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
208 | DCN-086 | DP 1.4 support |  | DIO |  | DisplayPort 1.4 basic output Test on PHYA | P2 | DIO335.1-12 | TNG |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 169 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
209 | DCN-086 | DP 1.4 support |  | DIO |  | DisplayPort Basic Output Test on PHYA/B | P2 | DIO337.1-130 | TServer |  | 1 | 130 | Legacy | 1 | 130 | 1 | N-1 | 130 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
210 | DCN-086 | DP 1.4 support |  | DIO |  | DP Random Audio Test | P2 | DIO383.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
211 | DCN-086 | DP 1.4 support |  | DIO |  | DP Ramp Audio Test | P2 | DIO384.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
212 | DCN-086 | DP 1.4 support |  | DIO |  | DP Azalia Audio Test | P2 | DIO385.1-34 | TServer |  | 1 | 34 | Legacy | 1 | 34 | 1 | N-1 | 34 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
213 | DCN-097 | Hardware Silent Stream Support |  | DIO |  | DisplayPort Keep-alive Enable Azalia Audio Test | P2 | DIO386.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
214 | DCN-088 | DP Dynamic Metadata |  | DIO |  | DisplayPort Dynamic Metadata Test | P2 | DIO359 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
215 | DCN-020 | 4 level Host VM |  | DIO |  | DisplayPort Dynamic Metadata Test | P2 | DIO359 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
216 | DCN-019 | 1 level GPUVM |  | DIO |  | DisplayPort Dynamic Metadata Test | P2 | DIO359 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
217 | DCN-086 | DP 1.4 support |  | DIO |  | DisplayPort Tx-Rx CRC Test | P2 | DIO389.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
218 | DCN-115 | HDMI2.1 FRL up to 12G |  | DIO |  | HPO Video Ouput test on PHYx | P2 | DIO620.1-63 | TServer |  | 63 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
219 | DCN-083 | HDMI 2.1 support VRR, FVA, QMS for TMDS operation |  | DIO |  | HPO Video Ouput test on PHYx | P2 | DIO620.1-63 | TServer |  | 63 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
220 | DCN-121 | HDMI 2.1 Audio Support |  | DIO |  | HDMI2.1 Azalia 2.0 Channel HD Audio test | P2 | DIO602.1-7 | TServer |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
221 | DCN-121 | HDMI 2.1 Audio Support |  | DIO |  | HDMI2.1 Azalia 7.1 Channel HD Audio test | P2 | DIO603.1-7 | TServer |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
222 | DCN-121 | HDMI 2.1 Audio Support |  | DIO |  | HDMI2.1 Azalia HBR Audio test | P2 | DIO604 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
223 | DCN-122 | HDMI2.1 Stereo 3D Timing Support |  | DIO |  | HPO Stereo test on PHYA | P2 | DIO605 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
224 | DCN-123 | HDMI 2.1 Frame Accurate metadata Support |  | DIO |  | HDMI2.1 Frame Accurate Metadata test | P2 | DIO606.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
225 | DCN-123 | HDMI 2.1 Frame Accurate metadata Support |  | DIO |  | HDMI2.1 EM Data Non-interleave Transmission test | P2 | DIO607 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
226 | DCN-124 | HDMI 2.1 Packet Generation Support |  | DIO |  | HDMI2.1 Packet Generation test | P2 | DIO608 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W8
227 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 10GHz 1 Lane Test | P2 | DIO650.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W10
228 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 10GHz 2 Lane Test | P2 | DIO651.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W10
229 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 10GHz 4 Lane Test | P2 | DIO652.1-100 | TNG |  | 1 | 100 | Legacy | 1 | 100 | 1 | N-1 | 6 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W10
230 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO653.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
231 | DCN-142 | DP2.0 [DIO] C20 combo PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test |  | DIO653.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
232 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO654.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
233 | DCN-142 | DP2.0 [DIO] C20 combo PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test |  | DIO654.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
234 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO655.1-100 | TServer |  | 1 | 100 | Legacy | 1 | 100 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
235 | DCN-142 | DP2.0 [DIO] C20 combo PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test |  | DIO655.1-100 | TServer |  | 1 | 100 | Legacy | 1 | 100 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
236 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO656.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
237 | DCN-142 | DP2.0 [DIO] C20 combo PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test |  | DIO656.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
238 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO657.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
239 | DCN-142 | DP2.0 [DIO] C20 combo PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test |  | DIO657.1-31 | TServer |  | 1 | 31 | Legacy | 1 | 31 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
240 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO658.1-100 | TServer |  | 1 | 100 | Legacy | 1 | 100 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
241 | DCN-142 | DP2.0 [DIO] C20 combo PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test |  | DIO658.1-100 | TServer |  | 1 | 100 | Legacy | 1 | 100 | 1 | N-1 | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
242 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 Audio Content Management Packet Test | P2 | DIO659 | TServer |  | 0 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W10
243 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 Random Audio Test | P2 | DIO660.1-7 | TServer |  | 0 | 7 | Legacy | 1 | 7 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W10
244 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 Ramp Audio Test | P2 | DIO661.1-7 | TServer |  | 0 | 7 | Legacy | 1 | 7 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W10
245 | DCN-113 | DP2.0: UHBR10 for native DP and USBC-DP ALT mode |  | DIO |  | DP2.0 Azalia Audio Test | P2 | DIO662 | TServer |  | 0 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | W10
246 | DCN-102 | DWB support 444 in 32bpp, 1080P60 |  | DWB |  | Stereo | P2 | DWB002.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
247 | DCN-102 | DWB support 444 in 32bpp, 1080P60 |  | DWB |  | DWB Bypass Mode Test | P2 | DWB018.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
248 | DCN-015 | DCHUBBUB watermark change (SR enter/exit, DRAM CLK change, Urgency) |  | DWB |  | DWB Bypass Mode Test | P2 | DWB018.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
249 | DCN-093 | HDCP1.4 |  | EB |  | HDCP Check Keys | P2 | EB001.1-19 | TServer |  | 1 | 19 | Delta | 1 | 19 | 1 | FPGA | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
250 | DCN-093 | HDCP1.4 |  | EB |  | HDCP 1.x HDMI with Azalia Audio Test: PHYA | P2 | EB200.1-5 | TServer |  | 1 | 5 | Delta | 1 | 5 | 1 | FPGA | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
251 | DCN-093 | HDCP1.4 |  | EB |  | HDCP 1.x HDMI 1.4 Frame Packing 3D with 7.1 LPCM Audio Test: PHYA | P2 | EB213.1-4 | TServer |  | 1 | 4 | Delta | 1 | 4 | 1 | FPGA | 3 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
252 | DCN-093 | HDCP1.4 |  | EB |  | HDCP 1.x DisplayPort Test | P2 | EB300.1-6 | TServer |  | 1 | 6 | Delta | 1 | 6 | 1 | FPGA | 8 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
253 | DCN-99 | [AZ]Audio HDCP Support |  | EB |  | DisplayPort with Audio HDCP Test |  | EB302.1-42 | TServer |  | 1 | 42 | Delta | 1 | 42 | 1 | FPGA | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
254 | DCN-094 | HDCP2.3 |  | EB |  | HDCP 2.2 DisplayPort Cipher Test | P2 | EB303.1-31 | TServer |  | 1 | 31 | Delta | 1 | 31 | 1 | FPGA | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-6
255 | DCN-096 | Jack Presence Support |  | CE |  | Auto payload in unsolicited response | P2 | CE005.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
256 | DCN-100 | Audio Controller Clock Gating and Deep Sleep Support |  | CE |  | Azalia Controller Clock Gating Test | P2 | CE012 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | wk-8
257 | DCN-101 | External Event and Unsolicited Response Support |  | CE |  | Azalia Unsolicited Response Holding Test | P2 | CE013.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 4 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
258 | DCN-119 | Unallocated space access |  | DMU |  | Unallocated Register Access Test | P2 | DMU001.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
259 | DCN-104 | DMCU: Secure Firmware Load Support |  | DMU |  | Unallocated Register Access Test | P2 | DMU001.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
260 | DCN-107 | Double Buffered Register Update Support |  | DMU |  | Fine-Grained Security Gasket Test | P2 | DMU002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
261 | DCN-104 | DMCU: Secure Firmware Load Support |  | DMU |  | Register Access Timeout Test | P2 | DMU003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
262 | DCN-118 | Register access and timeout Support |  | DMU |  | Register Access Timeout Test | P2 | DMU003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
263 | DCN-110 | Digital Bypass |  | DISP |  | Direct Digital Bypass Mode Test | P2 | DISP001.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
264 | DCN-048 | Blender Bypass Mode Support |  | DISP |  | Direct Digital Bypass Mode Test | P2 | DISP001.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
265 | DCN-108 | Triple Buffered Register Update Support |  | DISP |  | Display Register Double-Buffering Test | P2 | DISP002.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
266 | DCN-109 | Register Update Pending and Update Taken Support |  | DISP |  | Triple Buffered Register Update Test | P2 | DISP007.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
267 | DCN-98 | [AZ]Audio Latency Hiding Support |  | DISP |  | Display High Bandwidth Usage Test |  | DISP005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
268 | DCN-014 | P-State/DRAM Clock Switching |  | DISP |  | Memory P-State Switching at High Refresh Rate | P2 | DISP014 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
269 | DCN-016 | DRAM Self-Refresh ,C-State and stutter efficency |  | DISP |  | Memory P-State Switching at High Refresh Rate | P2 | DISP014 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
270 | DCN-001 | Optimize power gating for long vblank video |  | DLPC |  | IPS Transition Test | P2 | DLPC001.1-2 | TNG |  | 80 | 2 | New | 1 | 2 | 1 | FPGA |  | 0 | [6 empty] | 0 |  |  |  |  | 0
271 | DCN-002 | Hierarchical power gating(IPx DLDO) |  | DLPC |  | IPS Transition Test | P2 | DLPC001.1-2 | TNG |  | 80 | 2 | New | 1 | 2 | 1 | FPGA |  | 0 | [6 empty] | 0 |  |  |  |  | 0
272 | DCN-005 | SRAM retention in DPP & MPC to reduce restore time |  | DLPC |  | IPS SRAM / 0 pin flop retention test | P2 | DLPC002 DLPC003.1-2 | TNG |  | 40 | 2 | New | 1 | 2 | 1 | FPGA |  | 0 | [6 empty] | 0 |  |  |  |  | 0
273 | DCN-006 | 0pin retention/Security group 2 retention |  | DLPC |  | IPS SRAM / 0 pin flop retention test | P2 | DLPC002 DLPC003.1-2 | TNG |  | 40 | 2 | New | 1 | 2 | 1 | FPGA |  | 0 | [6 empty] | 0 |  |  |  |  | 0
274 | DCN-xxx | SLT test suite |  | DISP |  | Display Non-Stream Test |  | DISP016 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0