## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | EX-FEAT-002 | GFXCLK DFLL support |  | SB-01 | CLK-DPM | auto_dpm_tog=sclk | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
1 | EX-FEAT-009 | FW DPM Tester |  | SB-01 | CLK-DPM | auto_dpm_tog=sclk | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
2 | EX-FEAT-075 | Clock Management and Control |  | SB-01 | CLK-DPM | auto_dpm_tog=sclk | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
3 | EX-FEAT-077 | Voltage Controller |  | SB-01 | CLK-DPM | auto_dpm_tog=sclk | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
4 | EX-FEAT-102 | GFX AVFS |  | SB-01 | CLK-DPM | auto_dpm_tog=sclk | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
5 | EX-FEAT-073 | DPM Controller/HUB |  | SB-01 | CLK-DPM | auto_dpm_tog=sclk | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
6 | EX-FEAT-108 | GFXCLK DPM |  | SB-01 | CLK-DPM | auto_dpm_tog=sclk | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
7 | EX-FEAT-002 | GFXCLK DFLL support |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
8 | EX-FEAT-009 | FW DPM Tester |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
9 | EX-FEAT-075 | Clock Management and Control |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
10 | EX-FEAT-077 | Voltage Controller |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
11 | EX-FEAT-102 | GFX AVFS |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
12 | EX-FEAT-073 | DPM Controller/HUB |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
13 | EX-FEAT-108 | GFXCLK DPM |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
14 | EX-FEAT-090 | GFX IMU Interaction |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
15 | EX-FEAT-008 | DRAM Temperature reading |  | SB-01 | Data-Logging | Monitor_perf=thermal_metrics | P1 | PM80.12 | TNG |  | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
16 | EX-FEAT-005 | Tmon/Tsense Configurability and Reading |  | SB-01 | Data-Logging | Monitor_perf=thermal_metrics | P1 | PM80.12 | TNG |  | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
17 | EX-FEAT-042 | DRAM Temperature Controlling using UMC BW Throttling |  | SB-01 | Data-Logging | Monitor_perf=thermal_metrics | P1 | PM80.12 | TNG |  | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
18 | EX-FEAT-072 | FW Telemetry Reading |  | SB-01 | Data-Logging | Monitor_perf=thermal_metrics | P1 | PM80.12 | TNG |  | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
19 | EX-FEAT-004 | Power Configurability |  | SB-01 | Throttling | monitor_perf=ppt_limit | P2 | PM80.12 | Tserver | PPT_limit | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
20 | EX-FEAT-088 | PPT control |  | SB-01 | Throttling | monitor_perf=ppt_limit | P1 | PM80.12 | Tserver | PPT_limit | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
21 | EX-FEAT-006 | SVI3 VR Telemetry |  | SB-01 | SVI3 | force VID | P1 | PMxx.xx | Tserver |  | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | [5 empty] | 0 |  | 0 |  |  |  |  | 0 |  | 0
22 | EX-FEAT-010 | FW Logger |  | SB-01 | Data-Logging | agmlog | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
23 | EX-FEAT-068 | DMA |  | SB-01 | Data-Logging | agmlog | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
24 | EX-FEAT-003 | Data Controller |  | SB-01 | Data-Logging | agmlog | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
25 | EX-FEAT-072 | FW Telemetry Reading |  | SB-01 | Data-Logging | agmlog | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
26 | EX-FEAT-011 | FCLK DPM |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
27 | EX-FEAT-009 | FW DPM Tester |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
28 | EX-FEAT-011 | FCLK DPM |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
29 | EX-FEAT-009 | FW DPM Tester |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
30 | EX-FEAT-075 | Clock Management and Control |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
31 | EX-FEAT-009 | FW DPM Tester |  | SB-01 | P-state | force dpm | P1 | PM23.1 | Tserver |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
32 | EX-FEAT-077 | Voltage Controller |  | SB-01 | P-state | force dpm | P1 | PM23.1 | Tserver |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
33 | EX-FEAT-012 | UCLK DPM |  | SB-01 | P-state | sweep dpm | P1 | PM80.12 | TNG | autodpmtog=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
34 | EX-FEAT-009 | FW DPM Tester |  | SB-01 | P-state | sweep dpm | P1 | PM80.12 | TNG | autodpmtog=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
35 | EX-FEAT-077 | Voltage Controller |  | SB-01 | P-state | sweep dpm | P1 | PM80.12 | TNG | autodpmtog=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
36 | EX-FEAT-012 | UCLK DPM |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG | nature=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
37 | EX-FEAT-073 | DPM Controller/HUB |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG | nature=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
38 | EX-FEAT-100 | VDDCI DVS |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG | nature=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
39 | EX-FEAT-075 | Clock Management and Control |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG | nature=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
40 | EX-FEAT-009 | FW DPM Tester |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG | nature=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
41 | EX-FEAT-098 | Psedo-AVFS on non-GFX Clocks(SOCCLK,MMCLK,DCN,VCN,UCLK) |  | SB-01 | CLK-DPM | naturedpm | P1 | PM80.12 | TNG | nature=mclk | 1 | 1 | New | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
42 | EX-FEAT-014 | SOCCLK DPM |  | SB-01 | CLK-DPM | force dpm | P1 | PM20.1 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
43 | EX-FEAT-077 | Voltage Controller |  | SB-01 | CLK-DPM | force dpm | P1 | PM20.1 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
44 | EX-FEAT-014 | SOCCLK DPM |  | SB-01 | CLK-DPM | sweep dpm | P1 | PM80.12 | TNG | autodpmtog=socclk | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
45 | EX-FEAT-077 | Voltage Controller |  | SB-01 | CLK-DPM | sweep dpm | P1 | PM80.12 | TNG | autodpmtog=socclk | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
46 | EX-FEAT-014 | SOCCLK DPM |  | SB-01 | CLK-DPM | nature dpm | P1 | PM80.13 | Tserver | nature=socclk | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
47 | EX-FEAT-075 | Clock Management and Control |  | SB-01 | CLK-DPM | nature dpm | P1 | PM80.13 | Tserver | nature=socclk | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
48 | EX-FEAT-073 | DPM Controller/HUB |  | SB-01 | CLK-DPM | nature dpm | P1 | PM80.13 | Tserver | nature=socclk | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
49 | EX-FEAT-017 | GPO support |  | SB-01 | IMU | pmfeature=gpo | P2 | PM80.12 | Tserver | pmfeature=gpo | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | [5 empty] | 0 |  | 0 |  |  |  |  | 0 |  | 0
50 | EX-FEAT-022 | MM CLK DPM |  | SB-01 | CLK-DPM | force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
51 | EX-FEAT-077 | Voltage Controller |  | SB-01 | CLK-DPM | force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
52 | EX-FEAT-022 | MM CLK DPM |  | SB-01 | CLK-DPM | nature | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
53 | EX-FEAT-073 | DPM Controller/HUB |  | SB-01 | CLK-DPM | nature | P1 | PM80.12 | TNG |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
54 | EX-FEAT-024 | Fan Controller |  | SB-01 | FAN | 0-rpm | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
55 | EX-FEAT-067 | GPIO Handler |  | SB-01 | FAN | 0-rpm | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
56 | EX-FEAT-051 | GPIO to turn off Fan |  | SB-01 | FAN | 0-rpm | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
57 | EX-FEAT-053 | Zero Fan control |  | SB-01 | FAN | 0-rpm | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
58 | EX-FEAT-024 | Fan Controller |  | SB-01 | FAN | fan speed | P1 | PM14.1 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
59 | EX-FEAT-029 | BACO Support |  | SB-01 | D-State |  | P1 | PM31.05 | TNG |  | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | Emulator | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
60 | EX-FEAT-030 | BAMACO |  | SB-01 | D-State |  | P1 | PM31.06 | TNG |  | 1 | 1 | Delta | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
61 | EX-FEAT-034 | VCN Off |  | SB-01 | PG |  | P1 | PM80.805 | TNG |  | 1 | 1 | Delta | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
62 | EX-FEAT-041 | SOC ULV |  | SB-01 | D-State |  | P1 | PM80.808 | TNG |  | 1 | 1 | Delta | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
63 | EX-FEAT-047 | DF C-state |  | SB-01 | D-State |  | P1 | PM80.808 | TNG |  | 1 | 1 | Delta | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
64 | EX-FEAT-063 | Out Of Band Monitoring and Management |  | SB-01 | OOB |  | P1 | PM13.16 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
65 | EX-FEAT-074 | Feature Enablement Arbiter |  | SB-01 | PPLIB |  | P1 | ./agt-ppmode=1 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
66 | EX-FEAT-076 | MP1 <-> IMU Message Interface |  | SB-01 |  | sclk dpm | P1 | PM80.12 | Tserver |  | 1 | 1 | Legacy | 0.8 | 1 | 1 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
67 | EX-FEAT-078 | Message Hub |  | SB-01 | SMN-IF |  | P1 | PM80.5 | Tserver |  | 1 | 1 | Legacy | 0.8 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | 0
68 | EX-FEAT-079 | I2C Arbiter |  | SB-01 | I2C | read e2prom | P1 | PM80.993 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
69 | EX-FEAT-083 | Mode 1 reset |  | SB-02 | reset |  | P1 | Pm36.1 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.5 | 0.5 | N-1 | 1 | 0 | [6 empty] | 0
70 | EX-FEAT-089 | Temperature tracking and Control/Thermal Throttling |  | SB-01 | Throttling | monitor_perf -monitorperf_select=metrics | P1 | PM80.12 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
71 | EX-FEAT-101 | MEMIO/MVDD DVS |  | SB-01 | CLK-DPM | TBD | P1 | PM80.12 | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
72 | EX-FEAT-062 | PSM log |  | SB-01 | PSM | PSM logging | P1 | pm80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
73 | EX-FEAT-090 | GFX IMU Interaction |  | SB-01 | GFXOFF | GFXOFF | P1 | pm80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.6 | 0.6 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
74 | EX-FEAT-122 | GFXOFF |  | SB-01 | GFXOFF | GFXOFF | P1 | pm80.12 | TNG |  | 1 | 1 | Legacy | 0.8 | 0.6 | 0.6 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
75 | EX-FEAT-055 | GFX in OFF State at Boot |  | SB-01 | GFX power up | GFX power up | P1 | pm74.3 | Tserver |  | 1 | 1 | Legacy | 0.8 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | 0
76 | EX-FEAT-109 | Acoustics-CoilWhine |  | SB-01 | Acoustics | Acoustics handler | P1 | Acoustics=sweep/force | Tserver |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
77 | EX-FEAT-110 | SCPM |  | SB-01 | Acoustics | scpm-security | P1 | scpm-security | Tserver |  | 1 | 1 | New | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
78 | EX-FEAT-120 | RAS support |  | SB-01 | RAS | RAS support | P1 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
79 | EX-FEAT-013 | Link DPM |  | SB-01 |  |  | P2 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0 | 0 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
80 | EX-FEAT-015 | ASPCLK DPM |  | SB-01 |  |  | P2 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0 | 0 |  | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
81 | EX-FEAT-016 | FW DPM Tester and Frequency Request Management |  | SB-01 |  | all clocks natural DPM | P1 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
82 | EX-FEAT-023 | Workload Based DPM Policy |  | SB-01 |  | all clocks natural DPM | P1 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
83 | EX-FEAT-020 | DCN DPM |  | SB-01 |  |  | P2 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
84 | EX-FEAT-038 | CPWDCLK Deep Sleep |  | SB-01 |  |  | P1 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
85 | EX-FEAT-039 | Dynamic RM |  | SB-01 |  |  | P2 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
86 | EX-FEAT-115 | PPTable |  | SB-01 |  |  | P2 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
87 | EX-FEAT-123 | GFXCLK DS |  | SB-01 |  |  | P2 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
88 | EX-FEAT-124 | GFX ULV |  | SB-01 |  |  | P2 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
89 | EX-FEAT-130 | PPVMIN, Dynamic RM, RTAVFS, Smart Shift enablement status check |  | SB-01 |  |  | P1 | PMxx.xx | TNG |  | 1 | 1 | Legacy | 0.8 | 0 | 0 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | 0
90 | EX-FEAT-057 | PPVmin |  | SB-01 |  |  | P3 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0 | 0 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
91 | EX-FEAT-058 | TDVmin |  | SB-01 |  |  | P3 | PMxx.xx | Tserver |  | 1 | 1 | Legacy | 0.8 | 0 | 0 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0