## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | PMFW-1808 | Core Cstates |  | PMM | CC1 Feature | CC1 test | P2 | PM004.011 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | 1 | 1 |  |  |  |  | 0 | Could not really enter CC1 in SimNow | 1 |  |  |  |  | 0 |  | WK
1 | PMFW-1808 | Core Cstates |  | PMM | CC6 Feature | CC6 test | P2 | PM004.016 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
2 | PMFW-1808 | Core Cstates |  | PMM | PC6 Feature | PC6 test | P2 | PM004.019 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
3 | PMFW-1818 | VDDOFF |  | PMM | VDD OFF | VDDOFF test | P1 | PM004.020 | Panmi | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 | failed at GFXOFF | 1 |  |  |  |  | 0 |  | WK
4 | PMFW-1822 | Cstate Boost |  | PMM | C State Boost | C State Boost | P1 | PM004.026 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 | PMFW not supported this feature | WK
5 | PMFW-1823 | CCLK DPM |  | PMM | CCLK DPM | CCLK DPM Force test | P1 | PM34.1 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
6 | PMFW-1823 | CCLK DPM |  | PMM | CCLK DPM | CCLK AutoSweep Sanity test | P1 | PM80.100 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
7 | PMFW-1823 | CCLK DPM |  | PMM | CCLK DPM/Fine_Grain_P_State | CCLK AutoSweep Eventhandler test | P1 | PM80.12 | -autodpmtog=cclk,30,0 | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | 1 | 1 |  |  |  |  | 0 | Not hitting enough levels | 1 |  |  |  |  | 0 |  | WK
8 | PMFW-1824 | Core clock control - CPPC |  | PMM | CPPC test | CPPC,Collaborative Processor Performance Control - "OS pstates on steroids!" Hardware-directed performance-aware algorithms in SoCs with OS hints. Stepping stone to going away from OS-driven p-states. Includes BAM-like hints for low priority background task execution. RMB update (CB B0+): In upcoming OS releases, Microsoft is adding the capability to schedule high priority tasks on fast cores and low priority tasks on slow cores. In order to support this differentiation, a per-thread CPPC Capability 1 register is required. The definition for CPPC Capability 1 is unchanged. | P2 | PM004.030 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 | Not enabled in PMFW yet - Jan 29 | WK
9 | PMFW-1828 | Reliability Tracker/FIT controller |  | PMM | FIT Controller | FIT Controller | P2 | PM012.60 | Panmi | 0 | 0 | Legacy | [10 empty] | 0 | Asic is not a TMON fused part or All TMONs are bad! | [5 empty] | 0 |  | WK
10 | PMFW-1831 | CLDO: L2/L3 CLDO |  | PMM | CLDO | CLDO | P2 | PM33.11 |  | 0 | 0 | Legacy | 1 |  | 0.3 | [7 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
11 | PMFW-5400 | GFXOFF |  | PMM | GFX | CGCG | P1 | PM41.28 | -tl_cg | 1 | 1 | Legacy | 1 | 1 | 0.3 |  |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
12 | CTA-GFXOFF | CGPG |  | PMM | GFX | CGPG |  | covered in GFXOFF | Jane | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 |  | 0 |  |  |  |  | 0 | [6 empty] | 0
13 | PMFW-1840 | GFXOFF with MSMU |  | PMM | GFX | GFXOFF with MSMU |  | PM41.28 | Jane PM80.012: -bEnableIslandPowerGating=1 -tc_EnableAsyncGfxRing=1 -tl_cg -gfxoff -tglReadRegisterByPacket=1 STD: TBD | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 | PM80.12 | 1 |  |  |  |  | 0
14 | PMFW-1842 | GFXCLK DPM |  | PMM | DPM | GFXCLK DPM Force | P1 | PM21.1 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
15 | PMFW-1842 | GFXCLK DPM |  | PMM | DPM | GFXCLK AutoSweep Sanity test | P1 | PM80.39 | Cover by auto-dpm | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
16 | PMFW-1842 | GFXCLK DPM |  | PMM | DPM | GFXCLK AutoSweep Eventhandler test | P1 | PM80.12 | -autodpmtog=sclk,30,0 | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | 1 | 1 |  |  |  |  | 0 | Not hitting enough levels, hit 5 out of 8 | 1 |  |  |  |  | 0 |  | WK
17 | PMFW-1843 | Dynamic RM of VDDGFX SRAMs for Vmin optimization |  | PMM | GFX | DYN RM for GFX |  | PM51.6 | Not POR | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 | pending on GFX DPM
18 | PMFW-1847 | GFXCLK DFLL |  | PMM | GFX | Test GFXCLK SS in DFLL PI mode by RLC message | P2 | /. |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 | Covered by GFXCLK DPM | WK
19 | PMFW-1849 | GFX EDC control |  | PMM | GFX | GFX EDC stall on mode A | P2 | PM58.1 |  |  |  | Legacy | [10 empty] | 0 | Register mapping changed | [5 empty] | 0 |  | WK
20 | PMFW-1849 | GFX EDC control |  | PMM | GFX | GFX EDC stall on mode B | P2 | PM58.2 |  |  |  | Legacy | [10 empty] | 0 | [6 empty] | 0 |  | WK
21 | PMFW-1849 | GFX EDC control |  | PMM | GFX | GFX EDC stretch on mode A | P2 | PM58.3 |  |  |  | Legacy | [10 empty] | 0 | [6 empty] | 0 |  | WK
22 | PMFW-1849 | GFX EDC control |  | PMM | GFX | GFX EDC stretch on mode B | P2 | PM58.4 |  |  |  | Legacy | [10 empty] | 0 | [6 empty] | 0 |  | WK
23 | PMFW-1851 | SVI 3.0 support |  | PMM | SVI3 | SVI3 test by sending message to SMUFW | P1 | PM80.340,342.1-2 | -pm_voltage_margin=<0.8 - 1.2> | 2 | 2 | Legacy | 1 | 2 | 0.3 | N-1 | [6 empty] | 0 |  | 2 |  |  |  |  | 0 |  | WK
24 | PMFW-1853 | SVI 3.0 telemetry for all rails |  | PMM | SVI3 |  | P1 | Covered by SMU HW TP |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
25 | PMFW-1856 | DF Pstates |  | PMM | DF P-states | DF pstate Sanity Check | P1 | PM80.310 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
26 | PMFW-1856 | DF Pstates |  | PMM | DF P-states | FCLK DPM Loop Check | P1 | PM15.1 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
27 | PMFW-1866 | Memory P-states |  | PMM | Memory P-states | Memory Pstate switch test | P1 | Covered by DF Pstates |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | WK
28 | PMFW-1875 | VCN DPM |  | PMM | DPM | VCN DPM Force | P2 | PM18.1 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
29 | PMFW-1879 | PPT Controller |  | PMM | Throttle | Fast PPT throttle | P2 | PM12.30 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
30 | PMFW-1879 | PPT Controller |  | PMM | Throttle | Slow PPT throttle | P2 | PM12.31 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
31 | PMFW-1880 | TDC Controller |  | PMM | Throttle | Core TDC throttle | P2 | PM12.40 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
32 | PMFW-1880 | TDC Controller |  | PMM | Throttle | GFX TDC throttle | P2 | PM12.41 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 | No GFX power rail, remove this case | WK
33 | PMFW-1880 | TDC Controller |  | PMM | Throttle | SOC TDC throttle | P2 | PM12.42 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
34 | PMFW-1881 | STAPM |  | PMM | Throttle | STAPM throttle | P2 | PM12.50 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
35 | PMFW-1882 | Thermal Controller |  | PMM | THM | THM throttle | P2 | PM12.22 |  |  |  | Legacy | [10 empty] | 0 | Asic is not a TMON fused part or All TMONs are bad! | [5 empty] | 0 |  | WK
36 | PMFW-1883 | PROCHOT |  | PMM | THM | Prochot test | P1 | PM12.21 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
37 | PMFW-1889 | System temperature tracker STT |  | PMM | THM | APU STT throttle test | P2 | PM12.51 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
38 | PMFW-1889 | System temperature tracker STT |  | PMM | THM | dGPU STT throttle test | P2 | PM12.52 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
39 | PMFW-1891 | SHUBCLK DPM |  | PMM | DPM | SHUBCLK DPM Force | P2 | PM16.1 |  |  |  | Legacy | [10 empty] | 0 | [PM_DPM_SHUBCLK] Force Test: SMU(v4.69.26.0) Max Levels(1) | [5 empty] | 0 |  | WK
40 | PMFW-1896 | LCLK Deep Sleep |  | PMM | DS | Test LCLK Deep Sleep | P1 | PM10.33 |  |  |  | Legacy | [10 empty] | 0 | can not enter LCLK DS | [5 empty] | 0 |  | WK
41 | PMFW-1897 | SOCCLK Deep Sleep |  | PMM | DS | Test SOCCLK Deep Sleep | P1 | PM10.32 |  | 0 | 0 | Legacy | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
42 | PMFW-1898 | SHUBCLK Deep Sleep |  | PMM | DS | Test SHUBCLK Deep Sleep | P1 | PM10.39 | Manually tested by HDT | 0 | 0 | Legacy | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
43 | PMFW-1899 | GFXCLK Deep Sleep |  | PMM | DS | Test GFXCLK Deep Sleep |  | PM10.800 | not pursuing enablement of GFXCLK DS on RMB | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
44 | PMFW-1901 | SMNCLK Deep Sleep |  | PMM | DS | Test SMNCLK Deep Sleep | P1 | PM10.36 |  | 0 | 0 | Legacy | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
45 | PMFW-1902 | MP1CLK Deep Sleep |  | PMM | DS | Test MP1CLK Deep Sleep | P1 | PM10.35 |  | 0 | 0 | Legacy | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
46 | PMFW-1903 | MP1 SRAM deep sleep |  | PMM | DS | Test MP1 SRAM deep sleep | P1 | PM10.41 |  | 0 | 0 | Legacy | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
47 | PMFW-1906 | MP2CLK Deep Sleep |  | PMM | DS | Test MP2CLK Deep Sleep | P1 | PM10.43 | waive it since it's not supported in SMU FW | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
48 | PMFW-1907 | VCN CLK deep sleep - VCLK & DCLK |  | PMM | DS | Test VCN CLK deep sleep - VCLK & DCLK | P1 | PM10.42 |  |  |  | Legacy | [10 empty] | 0 | can not enter DS | [5 empty] | 0 |  | WK
49 | PMFW-1908 | ACLK deep sleep |  | PMM | DS | Test ACLK deep sleep | P1 | PM10.44 |  | 0 | 0 | Legacy | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
50 | PMFW-1910 | DCFCLK deep sleep |  | PMM | DS | Test DCFCLK deep sleep | P1 | PM10.37 |  | 0 | 0 | Legacy | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
51 | PMFW-1922 | LCLK DPM |  | PMM | DPM | LCLK DPM Force | P2 | PM24.1 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
52 | PMFW-1923 | DCFCLK DPM |  | PMM | DPM | DCFCLK DPM Force |  | PM85.20 | Manually tested by HDT |  |  | Legacy | [10 empty] | 0 | [6 empty] | 0 |  | WK
53 | PMFW-1925 | SOCCLK DPM |  | PMM | DPM | SOCCLK Force DPM | P2 | PM20.01 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
54 | PMFW-1926 | MP0CLK DPM |  | PMM | DPM | MP0CLK DPM | P2 | PM85.10 | Saw a SMU FW issue, so have to manually tested by HDT |  |  | Legacy | [10 empty] | 0 | [6 empty] | 0 |  | WK
55 | PMFW-1927 | VDDSOC ULV |  | PMM | System power | ULV Entry and Exit test | P2 | PM68.2 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
56 | PMFW-1928 | PLL Power Down Monitor |  | PMM | PLL | PLL Power Down-If all DFS slices for a PLL are not in DFS mode, then power down the PLL. | P2 | PM060.112 or 118 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 | Not enabled in PMFW yet - Jan 29 | WK
57 | PMFW-1929 | PLL bypass |  | PMM | PLL | PLL Power Down - Turn off PLL and switch to 800MHz ref clock if all DFS slices are not greater than 800MHz. | P2 | PM060.112 or 118 | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
58 | PMFW-1921 | S3 |  | PMM | System power | Suspend to Ram | P1 | PM4.21 |  | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
59 | PMFW-1932 | Whisper Mode |  | PMM | System power | Whisper Mode Entry and Exit test | P2 | PM68.3? | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
60 | PMFW-1934 | Dynamic Power & Thermal Control (DPTC) |  | PMM | System power | DPTC test | P2 | Covered PPT,STAPM,Vrm limits,PSI3 limits,PROCHOT | Not in test plan | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
61 | PMFW-1936 | RAPL |  | PMM | System power | Core RAPL | P2 | PM069.001 | Panmi PLAT-75684 |  |  | Legacy | [10 empty] | 0 | Error Rate between AGM and RAPL energy is greater than 0.010. AGM(0.000000 W), RAPL(0.000031 W) | [5 empty] | 0 |  | WK
62 | PMFW-1936 | RAPL |  | PMM | System power | Package RAPL | P2 | PM069.002 |  |  |  | Legacy | [10 empty] | 0 | Rate between AGM and RAPL energy is greater than 0.010. AGM(14.808940 W), RAPL(4.442673 W) | [5 empty] | 0 |  | WK
63 | PMFW-1937 | DRAM logging |  | PMM | Dram log | DRAM (CAC Data) Logging | P2 | PM80.12 | -dram_log |  |  | Legacy | [10 empty] | 0 | TESTSMC_MSG_StopSltDataLogging failed, but PM Lib code is OK | [5 empty] | 0 |  | WK
64 | PMFW-1938 | SLT logging |  | PMM | SLT log | SLT Data Logging | P1 | PM80.12 | -sltdata_log |  |  | Legacy | [10 empty] | 0 | TESTSMC_MSG_StopSltDataLogging failed | [5 empty] | 0 |  | WK
65 | PMFW-1939 | AGM logging |  | PMM | AGM log | AGM Data Logging | P2 | PM80.12 | -nature_dpm -power_tune_log_config=all -dump_agmlog=true |  |  | Legacy | [10 empty] | 0 | [6 empty] | 0 |  | WK
66 | CTA-RSMU | RSMU Clock Gating |  | PMM | RSMU CG | RSMU Clock Gating test | P1 | PM51.10 | -pm_rsmu_inst=gc | 1 | 1 | Legacy | 1 | 1 | 0.3 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
67 | CTA-GFX-CG | GFX CGCG |  | PMM | GFX CGCG | GFX Coarse grain clock gating | P1 | Covered in GFXOFF |  |  |  | Legacy | 1 |  | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | WK
68 | PMFW-1855 | DF C-states |  | PMM | DF cstate | DF C-State | P1 | Covered by DF team | Owned by DF team | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
69 | PMFW-1859 | DF-based deep C-states |  | PMM | DF cstate | DF-based deep C-State | P1 | Covered by DF team | Owned by DF team | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
70 | PMFW-1871 | Display clocks DPM |  | PMM | DPM | Covered by Display diagnostic team |  |  | No committed | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
71 | PMFW-1872 | ACLK DPM |  | PMM | DPM | Covered by ACP diagnostic team | P2 |  | No committed | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
72 | PMFW-1873 | I2S-MCLK DPM |  | PMM | DPM | Covered by ACP diagnostic team | P2 |  | No committed | 0 | 0 | Legacy | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
73 | PMFW-5490 | Z8 state |  | PMM | System power | Z9 Entry/Exit test | P1 | PM68.7 |  | 1 | 1 | New | 1 | 1 | 0.3 |  | 0 | [5 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
74 | PMFW-5489 | Z10 state |  | PMM | System power | Z10 Entry/Exit test | P1 | PM68.6 | -skiptextbuffering=1 -d=1 -test=PM68.6 -pm_bringup=true -pm_c_state_loops=50 -bEnableIslandPowerGating=1 -tc_EnableAsyncGfxRing=1 -tl_cg -tglReadRegisterByPacket=1 -tc_MapAsyncGfxQueuesWithKIQ=1 -tglEnableMCBP=1 -tglShadowContextRegisters -tglShadowPersistentRegisters -tglShadowUConfigRegisters -tc_DefaultCopyUtil=CpDma -gpu_copyengine=tcore -tc_GfxRingRegMode=1 -v=debug -dmcub_keep_alive | 1 | 1 | New | 1 | 1 | 0.3 | N-1 | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK
75 | PMFW-5497 | S0i3 |  | PMM | System power | Z11/S0i3 Entry/Exit test | P1 | ? |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
76 | PMFW-3257 | Graphics Power Optimizer |  | PMM | GFX | Graphics Power Optimizer | P2 | PM012.071 | Not in test plan | 0 | 0 | New |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
77 | PMFW-5234 | Core C1e c-state |  | PMM | CC1 Feature |  | P1 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
78 | PMFW-3228 | Delayed L3 Wake |  | PMM | GFX |  | P3 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
79 | PMFW-3231 | Expose Fastest Core |  | PMM | Core |  | P3 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
80 | PMFW-3238 | AVFS + BTC |  | PMM | Core |  | P3 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
81 | PMFW-6448 | STB |  | PMM | Core |  | P3 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
82 | PMFW-5417 | DF CPU idle success monitor |  | PMM | Core |  | P1 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
83 | PMFW-6676 | Smart Shift 3.0 |  | PMM | System power |  | P2 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
84 | PMFW-5535 | Fan Controller |  | PMM | Fan |  | P2 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
85 | PMFW-7288 | DVO |  | PMM | Core |  | P2 |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK
86 | PMFW-8928 | IPUCLK DPM |  | PMM | DPM |  | P1 | PM085.021 | Need to power up IPU first | 1 | 1 | New | 1 | 1 | 0.3 |  |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
87 | PMFW-9824 | VPE DPM |  | PMM | DPM | Covered by VPE team | P1 |  |  | 0 | 0 | New | 1 |  |  |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK
88 | PMFW-8455 | Per-CCX PC6 |  | PMM | CC6 feature |  |  |  |  | 1 | 1 | New | 1 | 1 | 0.3 |  |  | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0
89 | PMFW-8491 | Fast GFXOFF |  | PMM | GFXOFF |  | P1 | Covered in GFXOFF |  |  |  | New | 1 |  |  |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK
90 | PMFW-8459 | VDDOFF Dense CCX |  | PMM | VDDOFF |  | P1 |  |  | 1 | 1 | New | 1 | 1 | 0.3 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
91 | PMFW-8484 | VPE On/Off |  | PMM | Power Gate |  | P1 | PM041.961 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
92 | PMFW-8484 | VPE On/Off |  | PMM | Power Gate |  | P1 | PM041.962 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0
93 | PMFW-10450 | Power gate/ungate DPIA |  | PMM | Power Gate |  | P1 | PM041.963 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 | Covered by USB D3 case | WK
94 | PMFW-10450 | Power gate/ungate DPIA |  | PMM | Power Gate |  | P1 | PM041.964 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 | Covered by USB D3 case
95 | PMFW-11541 | Power gate/ungate LSDMA |  | PMM | Power Gate |  | P1 | PM041.965 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
96 | PMFW-11541 | Power gate/ungate LSDMA |  | PMM | Power Gate |  | P1 | PM041.966 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0
97 | PMFW-11886 | DFX power gating |  | PMM | Power Gate |  | P1 | PM041.935 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
98 | PMFW-11886 | DFX power gating |  | PMM | Power Gate |  | P1 | PM041.936 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0
99 | PMFW-10201 | Power gate ISP in vertical blank |  | PMM | Power Gate |  | P1 | PM041.967 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
100 | PMFW-10201 | Power gate ISP in vertical blank |  | PMM | Power Gate |  | P1 | PM041.968 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0
101 | PMFW-8818 | Power gate/ungate VCN |  | PMM | Power Gate |  | P1 | PM041.969 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK
102 | PMFW-8818 | Power gate/ungate VCN |  | PMM | Power Gate |  | P1 | PM041.970 |  | 0 | 0 | New | 1 | [9 empty] | 0 |  | 1 |  |  |  |  | 0
103 | PMFW-8450 | Dense C1e state support |  | PMM | Power Gate | configure SBIOS option for C1e, see if C1 state is still working | P2 | pm004.011 |  | 1 | 1 | New | 1 | 1 | 0.3 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 1 |  |  |  |  | 0 |  | WK
104 | PMFW-XXXX |  |  | PMM | Core |  |  |  |  | 0 | 0 | New | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0