## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | KRK-ACP-001 | Feature name - EX-FEAT-001 | Deepak Bhasin | Clock Test | Manual | Run tests at varying ACLK upto 1GHz | P2 | Manual | Tserver | Manual | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
1 | KRK-ACP-002 | Feature name - EX-FEAT-002 | Deepak Bhasin | Clock test | Manual | Run tests at varying SHUBCLK and ACLK ratios | P2 | Manual | Tserver | Manual | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
2 | KRK-ACP-003 | Feature name - EX-FEAT-003 | Deepak Bhasin | Clock Test | acp_dma_clk_en_dis | ACP Clock Enable Disable | P2 | acpaz67 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
3 | KRK-ACP-004 | Feature name - EX-FEAT-004 | Deepak Bhasin | VAD clock gating |  | Clock gate the PDM/VAD clocks | P2 | acpaz68 | Tserver | enable_cg=0-15 disable_cg=0-15 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
4 | KRK-ACP-005 | Feature name - EX-FEAT-005 | Deepak Bhasin | PGFSM | acp_pgfsm_dsp_dma_acc | ACP PGFSM power gating | P2 | acpaz63.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
5 | KRK-ACP-006 | Feature name - EX-FEAT-006 | Deepak Bhasin | PGFSM | acp_cac_gen_check | CAC indicator test | P2 | acpaz69.1 | Tserver | targ_mem_type=1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
6 | KRK-ACP-007 | Feature name - EX-FEAT-007 | Deepak Bhasin | PGFSM | acp_pgmem_phx_all_banks | ACP Deep sleep all memory banks | P2 | acpaz292.1-2 | TNG |  | 2 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
7 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test |  | Soft Reset with AZ transfer | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
8 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test | acp_dma_aud_soft_reset | ACP Soft reset mode 0 during DMA transfer | P2 | acpaz31.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
9 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test | acp_dma_aud_soft_reset | DMA Soft reset mode 0 during DMA transfer | P2 | acpaz31.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
10 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test | acp_dsp_soft_reset | DSP Soft reset mode 0 during DMA transfer | P2 | acpaz32.1 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
11 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test | acp_dma_hard_reset | Hard Reset with DMA transfer | P2 | acpaz34 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
12 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test | acp_dma_aud_soft_reset | ACP Soft reset mode 1 during DMA transfer | P2 | acpaz31.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
13 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test | acp_dma_aud_soft_reset | DMA Soft reset mode 1 during DMA transfer | P2 | acpaz31.4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
14 | KRK-ACP-008 | Feature name - EX-FEAT-008 | Deepak Bhasin | Reset Test | acp_dsp_soft_reset | DSP Soft reset mode 1 during DMA transfer | P2 | acpaz32.2 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
15 | KRK-ACP-009 | Feature name - EX-FEAT-009 | Deepak Bhasin | DMA | acp_multithreaded_dma_test | DMA with all channels active with maximum transfer count (with transfers to DSP DRAM, ACP scratch memory and system memory) | P2 | acpaz4.1-3 | TNG | targ_mem_type=1 | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
16 | KRK-ACP-010 | Feature name - EX-FEAT-010 | Deepak Bhasin | DMA | acp_dma_1chl_1desc | DMA with single channel single descriptor | P2 | acpaz2 | Tserver | targ_mem_type=1 ch_num=0-7 desc_num=0-4095 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
17 | KRK-ACP-010 | Feature name - EX-FEAT-010 | Deepak Bhasin | DMA | acp_dma_1chl_mul_desc | DMA with single channel multiple descriptor | P2 | acpaz3.1-4 | Tserver | targ_mem_type=1 ch_num=0-7 | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 4 | [5 empty] | 0 | [6 empty] | 0
18 | KRK-ACP-011 | Feature name - EX-FEAT-011 | Deepak Bhasin | DMA | acp_multithreaded_dma_test | Maximum DMA channel transfer test | P2 | acpaz4.1-3 | TNG | targ_mem_type=1 | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
19 | KRK-ACP-012 | Feature name - EX-FEAT-012 | Deepak Bhasin | DMA | acp_dma_1chl_1desc | Maximum DMA channel transfer test | P2 | acpaz2 | Tserver | targ_mem_type=1 ch_num=0-7 desc_num=0-4095 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
20 | KRK-ACP-013 | Feature name - EX-FEAT-013 | Deepak Bhasin | DMA | acp_dma_err_config | DMA Error config (multiple sub-tests) | P2 | acpaz7.1-5 | Tserver | targ_mem_type=1 ch_num=0-7 | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 5 | [5 empty] | 0 | [6 empty] | 0
21 | KRK-ACP-014 | Feature name - EX-FEAT-014 | Deepak Bhasin | DMA | acp_dma_reset_circ_dma | channel graceful reset with circular DMA | P2 | acpaz5 | Tserver | targ_mem_type=1 ch_num=0-7 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
22 | KRK-ACP-015 | Feature name - EX-FEAT-015 | Deepak Bhasin | DMA | acp_dma_1chl_1desc | DMA interrupt on completion | P2 | acpaz2 | Tserver | targ_mem_type=1 ch_num=0-7 desc_num=0-4095 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
23 | KRK-ACP-016 | Feature name - EX-FEAT-016 | Deepak Bhasin | DMA | acp_dma_1chl_1desc | Assign random priorities and check nothing is broken Add address ranges in DMA to access increased memory, execute with increased descriptors | P2 | acpaz2 | Tserver | targ_mem_type=1 ch_num=0-7 desc_num=0-4095 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
24 | KRK-ACP-016 | Feature name - EX-FEAT-016 | Deepak Bhasin | DMA | acp_dma_comb_1ch_1desc | Direct DMA transfer path ways between DRAM and SRAM and Viceversa. | P2 | acpaz203 | TNG | targ_mem_type=0-11 ch_num=0-7 desc_num=0-4095 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
25 | KRK-ACP-017 | Feature name - EX-FEAT-017 | Deepak Bhasin | DMA | acp_sha_dma_idram_access | DMA access to DRAM | P2 | acpaz27.1 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
26 | KRK-ACP-018 | Feature name - EX-FEAT-018 | Deepak Bhasin | Position tracking counters | Manual | DMA Position tracking counters | P2 | Manual | Tserver | Manual | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
27 | KRK-ACP-019 | Feature name - EX-FEAT-019 | Deepak Bhasin | DSP Test | acp_master_loopback | SMN Master Interface Test | P2 | acpaz66 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
28 | KRK-ACP-020 | Feature name - EX-FEAT-020 | Deepak Bhasin | DSP Test | acp_dsp_syshub_rand_acc_test | DSP Master Interface Test | P2 | acpaz20.1-7 | TNG | targ_mem_type=1-4 -dsp_image_no=10-17, -dsp_num=2 | 1 | 448 | Delta | 1 | 448 | 1 | FPGA | 448 | [5 empty] | 0 | [6 empty] | 0
29 | KRK-ACP-021 | Feature name - EX-FEAT-021 | Deepak Bhasin | DSP Test | acp_dsp_syshub_rand_acc_test | FW image in system memory, need to use all cache windows | P2 | acpaz20.1-7 | TNG | targ_mem_type=1-4 -dsp_image_no=10-17, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
30 | KRK-ACP-022 | Feature name - EX-FEAT-022 | Deepak Bhasin | Interrupt Test | acp_dsp0_all_timers_check | ACP Timer interrupt check | P2 | acpaz41.1-3 | Tserver |  | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
31 | KRK-ACP-023 | Feature name - EX-FEAT-023 | Deepak Bhasin | Interrupt Test | acp_watchdog_timer_check | 1 Watchdog timer interrupt check | P2 | acpaz42.1-2 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
32 | KRK-ACP-024 | Feature name - EX-FEAT-024 | Deepak Bhasin | Interrupt Test | acp_sw_interrupt_check | DSP software interrupt check | P2 | acpaz43.1-3 | TNG |  | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
33 | KRK-ACP-025 | Feature name - EX-FEAT-025 | Deepak Bhasin | Interrupt Test | acp_dsp_exception_handler | ACP interrupt check | P2 | acpaz25.1-14 | Tserver | dsp_image_no=0-1, -dsp_num=2 | 1 | 28 | Delta | 1 | 28 | 1 | FPGA | 28 | [5 empty] | 0 | [6 empty] | 0
34 | KRK-ACP-026 | Feature name - EX-FEAT-026 | Deepak Bhasin | Interrupt Test | multi_dsp_bint_intr_handler_test.cpp | ACP to host interrupt check for error | P2 | acpaz94.1-4 | TNG | N/A, -dsp_num=2 | 1 | 8 | Delta | 1 | 8 | 1 | FPGA | 8 | [5 empty] | 0 | [6 empty] | 0
35 | KRK-ACP-027 | Feature name - EX-FEAT-027 | Deepak Bhasin | Interrupt Test | multi_dsp_bint_intr_handler_test.cpp | DSP status and error interrupt Interrupt routing from different sources to the different pins | P2 | acpaz94.1-4 | TNG | N/A, -dsp_num=2 | 1 | 8 | Delta | 1 | 8 | 1 | FPGA | 8 | [5 empty] | 0 | [6 empty] | 0
36 | KRK-ACP-028 | Feature name - EX-FEAT-028 | Deepak Bhasin | Interrupt Test | acp_dsp_intr_handler.cpp | Internal DSP interrupt for debugging | P2 | acpaz30.1-5 | Tserver | N/A, -dsp_num=2 | 1 | 10 | Delta | 1 | 10 | 1 | FPGA | 10 | [5 empty] | 0 | [6 empty] | 0
37 | KRK-ACP-029 | Feature name - EX-FEAT-029 | Deepak Bhasin | Interrupt Test | multi_dsp_bint_intr_handler_test.cpp | Xtensa internal interrupts | P2 | acpaz94.1-4 | TNG | N/A, -dsp_num=2 | 1 | 8 | Delta | 1 | 8 | 1 | FPGA | 8 | [5 empty] | 0 | [6 empty] | 0
38 | KRK-ACP-030 | Feature name - EX-FEAT-030 | Deepak Bhasin | Syshub Interface |  | Signal asserted if no response from SYSHUB interface | P2 |  | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
39 | KRK-ACP-031 | Feature name - EX-FEAT-031 | Deepak Bhasin | Syshub Interface |  | Urgent interrupt check | P2 |  | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
40 | KRK-ACP-032 | Feature name - EX-FEAT-032 | Deepak Bhasin | Syshub Interface | acp_deep_sleep_support | Deep sleep check | P2 | acpaz64.1-108 | Tserver | outstanding_rd_val=0,1,2,3,4,5 -outstanding_wr_val=0,1,2,3,4,5 -sleep_ctrl_val=0,1,2 | 1 | 108 | Legacy | 1 | 108 | 1 | FPGA | 108 | [5 empty] | 0 | [6 empty] | 0
41 | KRK-ACP-033 | Feature name - EX-FEAT-033 | Deepak Bhasin | Syshub Interface | acp_axi2axi_page_2mb_features_chk_debug_reg | ACP Axi2Axi debug counter check | P2 | acpaz16.1-3 | Tserver | targ_mem_type=1 dscr_addr_sel=0 atu_addr_sel=0 | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
42 | KRK-ACP-034 | Feature name - EX-FEAT-034 | Deepak Bhasin | Syshub Interface | acp_axi2axi_page_2mb_features_chk_perf_cntr_en | ACP Axi2Axi performance counter check | P2 | acpaz15.1-3 | Tserver | targ_mem_type=1 dscr_addr_sel=0 atu_addr_sel=0 | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
43 | KRK-ACP-035 | Feature name - EX-FEAT-035 | Deepak Bhasin | Syshub Interface | acp_deep_sleep_support | 1/8/16/32 outstanding transactions | P2 | acpaz64 | Tserver | outstanding_rd_val=0,1,2,3,4,5 -outstanding_wr_val=0,1,2,3,4,5 -sleep_ctrl_val=0,1,2 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
44 | KRK-ACP-036 | Feature name - EX-FEAT-036 | Deepak Bhasin | System memory address translation | acp_axi2axi_page_rd_wt_test.cpp | Axi2Axi transfer with 2MB page size | P2 | acpaz8.1-3 | TNG | targ_mem_type=1 dscr_addr_sel=0 atu_addr_sel=0 | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
45 | KRK-ACP-036 | Feature name - EX-FEAT-036 | Deepak Bhasin | System memory address translation | acp_axi2axi_page_rd_wt_test.cpp | Axi2Axi transfer with 64KB page size | P2 | acpaz9.1-3 | TNG | targ_mem_type=1 dscr_addr_sel=0 atu_addr_sel=0 | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
46 | KRK-ACP-036 | Feature name - EX-FEAT-036 | Deepak Bhasin | System memory address translation | acp_axi2axi_page_rd_wt_test.cpp | Axi2Axi transfer with 4KB page size | P2 | acpaz10.1-3 | TNG | targ_mem_type=0 dscr_addr_sel=0 atu_addr_sel=0 | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
47 | KRK-ACP-037 | Feature name - EX-FEAT-037 | Deepak Bhasin | System memory address translation |  | Axi2Axi transfer with 2MB page size | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
48 | KRK-ACP-037 | Feature name - EX-FEAT-037 | Deepak Bhasin | System memory address translation |  | Axi2Axi transfer with 64KB page size | P2 |  | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
49 | KRK-ACP-037 | Feature name - EX-FEAT-037 | Deepak Bhasin | System memory address translation |  | Axi2Axi transfer with 4KB page size | P2 |  | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
50 | KRK-ACP-038 | Feature name - EX-FEAT-038 | Deepak Bhasin | System memory address translation | acp_axi2axi_page_2mb_atu_clr_check | Axi2Axi ATU clear check | P2 | acpaz14.1-3 | Tserver | targ_mem_type=1 dscr_addr_sel=0 atu_addr_sel=0 | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
51 | KRK-ACP-039 | Feature name - EX-FEAT-039 | Deepak Bhasin | System memory address translation | acp_axi2axi_page_2mb_rd_wr_rt_alt_page_dis | 2MB page transfer with alternate page disabled | P2 | acpaz11 | Tserver | targ_mem_type=1 dscr_addr_sel=1 atu_addr_sel=1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
52 | KRK-ACP-039 | Feature name - EX-FEAT-039 | Deepak Bhasin | System memory address translation | acp_axi2axi_page_64kb_rd_wr_all_page_dis | 64KB page transfer with all pages disabled | P2 | acpaz12 | Tserver | targ_mem_type=1 dscr_addr_sel=1 atu_addr_sel=1 | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
53 | KRK-ACP-039 | Feature name - EX-FEAT-039 | Deepak Bhasin | System memory address translation | acp_axi2axi_page_4kb_rd_wr_all_page_dis | 4KB page transfer with all pages disabled | P2 | acpaz13 | Tserver | targ_mem_type=1 dscr_addr_sel=1 atu_addr_sel=1 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
54 | KRK-ACP-040 | Feature name - EX-FEAT-040 | Deepak Bhasin | Xtensa processing for audio | acp_hifi_ext_instr | ACP DSP HiFi3z instruction set execute | P2 | acpaz99.1-2 | Tserver | dsp_image_no=0-1783, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
55 | KRK-ACP-041 | Feature name - EX-FEAT-041 | Deepak Bhasin | Xtensa processing for audio | acp_hifi_ext_instr | ACP DSP HiFi3z instruction set execute | P2 | acpaz99.1-2 | Tserver | dsp_image_no=0-1783, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
56 | KRK-ACP-042 | Feature name - EX-FEAT-042 | Deepak Bhasin | Xtensa processing for audio | acp_dsp_syshub_rand_acc_test | Firmware writes to all address space | P2 | acpaz20.1-7 | Tserver | targ_mem_type=1-4 -dsp_image_no=10-17, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
57 | KRK-ACP-043 | Feature name - EX-FEAT-043 | Deepak Bhasin | Xtensa processing for audio | acp_dsp_ideram_syshub_rand_acc_test | Firmware writes to dram/sram/syshub parallel to IRAM | P2 | acpaz21.1-7 | Tserver | dsp_image_no=1, -dsp_num=2 | 1 | 14 | Delta | 1 | 14 | 1 | FPGA | 14 | [5 empty] | 0 | [6 empty] | 0
58 | KRK-ACP-044 | Feature name - EX-FEAT-044 | Deepak Bhasin | Xtensa processing for audio | acp_dsp_ideram_syshub_rand_acc_test | Different Syshub address access via Firmware | P2 | acpaz21.1-7 | Tserver | dsp_image_no=1, -dsp_num=2 | 1 | 14 | Delta | 1 | 14 | 1 | FPGA | 14 | [5 empty] | 0 | [6 empty] | 0
59 | KRK-ACP-045 | Feature name - EX-FEAT-045 | Deepak Bhasin | Xtensa processing for audio | acp_dsp_iram_acc_test | DSP IRAM access test | P2 | acpaz18.1-3 | TNG |  | 1 | 6 | Delta | 1 | 6 | 1 | FPGA | 6 | [5 empty] | 0 | [6 empty] | 0
60 | KRK-ACP-046 | Feature name - EX-FEAT-046 | Deepak Bhasin | Xtensa processing for audio | acp_dsp_dram_acc_test | DSP DRAM access test | P2 | acpaz19.1-3 | TNG | mFence=0-1, -dsp_num=2 | 1 | 6 | Delta | 1 | 6 | 1 | FPGA | 6 | [5 empty] | 0 | [6 empty] | 0
61 | KRK-ACP-047 | Feature name - EX-FEAT-047 | Deepak Bhasin | Xtensa processing for audio | acp_hifi_ext_instr | ACP DSP HiFi3z instruction set execute | P2 | acpaz99.1-2 | Tserver | dsp_image_no=0-1, -dsp_num=-2 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
62 | KRK-ACP-047 | Feature name - EX-FEAT-047 | Deepak Bhasin | Xtensa processing for audio | acp_memio_instr_set | ACP MEMIO instrution set | P2 | acpaz101.1-20 | Tserver | dsp_image_no=0-9, -dsp_num=2 | 1 | 20 | Delta | 1 | 20 | 1 | FPGA | 20 | [5 empty] | 0 | [6 empty] | 0 |  | wk-2
63 | KRK-ACP-048 | Feature name - EX-FEAT-048 | Deepak Bhasin | Xtensa processing for audio | Manual | Manual | P2 | Manual | Tserver | Manual | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
64 | KRK-ACP-049 | Feature name - EX-FEAT-049 | Deepak Bhasin | Xtensa processing for audio | All dsp tests check for sha config interrupt | DSP SHA config interrupt check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
65 | KRK-ACP-050 | Feature name - EX-FEAT-050 | Deepak Bhasin | Xtensa processing for audio | acp_dsp_win_size_viol_chk | DSP error access to different address space regions, data errors | P2 | acpaz24.1-6 | Tserver | dsp_image_no=0, -dsp_num=2 | 1 | 12 | Delta | 1 | 12 | 1 | FPGA | 12 | [5 empty] | 0 | [6 empty] | 0
66 | KRK-ACP-051 | Feature name - EX-FEAT-051 | Deepak Bhasin | Xtensa processing for audio | acp_dsp_bint_intr_handler | DSP exception handler check | P2 | acpaz24.1-6 | Tserver | dsp_image_no=1, -dsp_num=2 | 1 | 12 | Delta | 1 | 12 | 1 | FPGA | 12 | [5 empty] | 0 | [6 empty] | 0
67 | KRK-ACP-052 | Feature name - EX-FEAT-052 | Deepak Bhasin | Xtensa processing for audio | covered in all dsp tests | <Covered in all DSP tests> | P2 |  | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
68 | KRK-ACP-053 | Feature name - EX-FEAT-053 | Deepak Bhasin | Xtensa processing for audio | acp_pgmem_phx_bankwise | PGMEM Shutting down IRAM/DRAM memory bankwise | P2 | acpaz293.1-8 | Tserver |  | 1 | 8 | Delta | 1 | 8 | 1 | N-1 | 8 | [5 empty] | 0 | [6 empty] | 0
69 | KRK-ACP-054 | Feature name - EX-FEAT-054 | Deepak Bhasin | IRAM/DRAM Mux combination | acp_sha_dma_idram_access | Verify all IRAM/DRAM combination | P2 | acpaz27.1 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
70 | KRK-ACP-055 | Feature name - EX-FEAT-055 | Deepak Bhasin | SHA | covered in all dsp tests | SHA secure hash access check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
71 | KRK-ACP-056 | Feature name - EX-FEAT-056 | Deepak Bhasin | SHA | covered in all dsp tests | PSP interrupt after transfer for hash validation | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
72 | KRK-ACP-057 | Feature name - EX-FEAT-057 | Deepak Bhasin | SHA | covered in all dsp tests | SHA DMA test using DSP firmware | P2 |  | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
73 | KRK-ACP-058 | Feature name - EX-FEAT-058 | Deepak Bhasin | SHA | acp_dsp_dram_acc_header | Header enable feature need to check | P2 | acpaz40.1-3 | Tserver | N/A, -dsp_num=2 | 1 | 6 | Delta | 1 | 6 | 1 | FPGA | 6 | [5 empty] | 0 | [6 empty] | 0
74 | KRK-ACP-059 | Feature name - EX-FEAT-059 | Deepak Bhasin | SHA Error Test | acp_sha_error_tests | SHA DMA Syshub range violation error | P2 | acpaz29.8 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
75 | KRK-ACP-059 | Feature name - EX-FEAT-059 | Deepak Bhasin | SHA Error Test | acp_sha_error_tests | SHA DMA IRAM address violation error | P2 | acpaz29.9 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
76 | KRK-ACP-059 | Feature name - EX-FEAT-059 | Deepak Bhasin | SHA Error Test | acp_sha_error_tests | SHA DMA IRAM/DRAM address violationfor data length | P2 | acpaz29.3 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
77 | KRK-ACP-059 | Feature name - EX-FEAT-059 | Deepak Bhasin | SHA Error Test | acp_sha_error_tests | SHA DMA out of fence configuration error | P2 | acpaz29.10 | Tserver | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
78 | KRK-ACP-060 | Feature name - EX-FEAT-060 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | TX and RX via I2S-TDM channel | P2 | acpaz255.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 60 | Delta | 1 | 60 | 1 | N-1 | 60 | [5 empty] | 0 | [6 empty] | 0
79 | KRK-ACP-061 | Feature name - EX-FEAT-061 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | Support driving an external clock source for I2S | P2 | acpaz255.2/256.2/259/2 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 60 | Delta | 1 | 60 | 1 | N-1 | 60 | [5 empty] | 0 | [6 empty] | 0
80 | KRK-ACP-062 | Feature name - EX-FEAT-062 | Deepak Bhasin | I2S Test | acp_i2s_bt_tdm_tx_rx_transfer_chk | TX and RX via I2S-TDM BT channel | P2 | acpaz256.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
81 | KRK-ACP-063 | Feature name - EX-FEAT-063 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | TX and RX via I2S-TDM channel | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
82 | KRK-ACP-064 | Feature name - EX-FEAT-064 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | Slave mode access | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
83 | KRK-ACP-065 | Feature name - EX-FEAT-065 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | Master mode access | P2 | acpaz55.2 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
84 | KRK-ACP-066 | Feature name - EX-FEAT-066 | Deepak Bhasin | I2S Test |  | Mixed mode access | P2 |  | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
85 | KRK-ACP-067 | Feature name - EX-FEAT-067 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | I2S controller input sample rate check | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
86 | KRK-ACP-068 | Feature name - EX-FEAT-068 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | I2S controller input sample rate check | P2 | acpaz55.2 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
87 | KRK-ACP-069 | Feature name - EX-FEAT-069 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | I2S ACP DRAM access via circular DMA | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
88 | KRK-ACP-070 | Feature name - EX-FEAT-070 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk |  | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
89 | KRK-ACP-071 | Feature name - EX-FEAT-071 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | TX and RX via I2S-TDM channel | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
90 | KRK-ACP-072 | Feature name - EX-FEAT-072 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | Graceful exit of I2S TDM TX/RX channel | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
91 | KRK-ACP-072 | Feature name - EX-FEAT-072 | Deepak Bhasin | I2S Test | acp_i2s_bt_tdm_tx_rx_transfer_chk | Graceful exit of I2S BT TDM TX/RX channel | P2 | acpaz56.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
92 | KRK-ACP-073 | Feature name - EX-FEAT-073 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | TX and RX via I2S-TDM channel | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
93 | KRK-ACP-074 | Feature name - EX-FEAT-074 | Deepak Bhasin | I2S Test | acp_i2s_error_chk | I2S Bus error generation (Multiple sub-tests) | P2 | acpaz58.1-2 | Tserver |  | 1 | 2 | New | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
94 | KRK-ACP-075 | Feature name - EX-FEAT-075 | Deepak Bhasin | I2S Test | Manual | I2S Wake-up enable | P2 | Manual | Tserver | Manual | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
95 | KRK-ACP-076 | Feature name - EX-FEAT-076 | Deepak Bhasin | I2S Test | acp_i2s_tdm_tx_rx_transfer_chk | I2S interrupt after programmable transfer size | P2 | acpaz55.1 | Tserver | i2s_mode=0,1 sample_sz=8,12,16,24,32 slot_sz=32 num_slots=2,3,4,5,6,7,8 mem_option=0,1 | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
96 | KRK-ACP-077 | Feature name - EX-FEAT-077 | Deepak Bhasin | LRCLK | Manual | LRCLK generation | P2 | Manual | Tserver | Manual | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
97 | KRK-ACP-078 | Feature name - EX-FEAT-078 | Deepak Bhasin | Debug bus connectivity | Manual | Manual | P2 | Manual | Tserver | Manual | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
98 | KRK-ACP-079 | Feature name - EX-FEAT-079 | Deepak Bhasin | Register Test | acp_reg_test | Internal register check tool | P2 | acpaz1.1-2 | Tserver |  | 1 | 2 | New | 1 | 2 | 1 | FPGA/N-1 | 2 | [5 empty] | 0 | [6 empty] | 0
99 | KRK-ACP-080 | Feature name - EX-FEAT-080 | Deepak Bhasin | Register Test | acp_sem_reg_access | Semaphore Register access | P2 | acpz33 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
100 | KRK-ACP-081 | Feature name - EX-FEAT-081 | Deepak Bhasin | Register Test |  | Scratch Register access | P2 |  | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
101 | KRK-ACP-082 | Feature name - EX-FEAT-082 | Deepak Bhasin | PDM Decoder | acp_wov_pdm_en_test | PDM decoder with 2 channels | P2 | acpaz38.1-96 | Tserver | brm_clk_ctrl=0,1,2,3,4,5,6,7 fence_val=0,1,2,3,4,5,6,7 mem_type=1,2 vad_ctrl=0,1 vad_ch_ctrl=0,1 dec_fac=16,32,64 | 1 | 96 | New | 1 | 96 | 1 | N-1 | 96 | [5 empty] | 0 | [6 empty] | 0
102 | KRK-ACP-083 | Feature name - EX-FEAT-083 | Deepak Bhasin | DMIC Interface | acp_wov_pdm_en_test | Verify all clock combinations | P2 | acpaz38 | Tserver | brm_clk_ctrl=0,1,2,3,4,5,6,7 fence_val=0,1,2,3,4,5,6,7 mem_type=1,2 vad_ctrl=0,1 vad_ch_ctrl=0,1 dec_fac=16,32,64 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
103 | KRK-ACP-084 | Feature name - EX-FEAT-084 | Deepak Bhasin | DMIC Interface | acp_wov_pdm_en_test | Data transfers at supported PDM Interface clocks | P2 | acpaz38 | Tserver | brm_clk_ctrl=0,1,2,3,4,5,6,7 fence_val=0,1,2,3,4,5,6,7 mem_type=1,2 vad_ctrl=0,1 vad_ch_ctrl=0,1 dec_fac=16,32,64 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
104 | KRK-ACP-085 | Feature name - EX-FEAT-085 | Deepak Bhasin | DMIC Interface | acp_wov_pdm_en_test | DMA from PDM to host | P2 | acpaz38 | Tserver | brm_clk_ctrl=0,1,2,3,4,5,6,7 fence_val=0,1,2,3,4,5,6,7 mem_type=1,2 vad_ctrl=0,1 vad_ch_ctrl=0,1 dec_fac=16,32,64 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
105 | KRK-ACP-086 | Feature name - EX-FEAT-086 | Deepak Bhasin | DMIC Interface | acp_wov_pdm_en_test | DMA from PDM to SRAM | P2 | acpaz38 | Tserver | brm_clk_ctrl=0,1,2,3,4,5,6,7 fence_val=0,1,2,3,4,5,6,7 mem_type=1,2 vad_ctrl=0,1 vad_ch_ctrl=0,1 dec_fac=16,32,64 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
106 | KRK-ACP-087 | Feature name - EX-FEAT-087 | Deepak Bhasin | Doorbell access | acp_gfx_doorbell_interrupt | ACP to CP doorbell access | P2 | acpaz98.1-6 | Tserver |  | 1 | 6 | Delta | 1 | 6 | 1 | N-1 | 6 | [5 empty] | 0 | [6 empty] | 0
107 | KRK-ACP-088 | Feature name - EX-FEAT-088 | Deepak Bhasin | IRAM/DRAM Security | acp_sram_secure_en_bit_acc | Check access to IRAM/DRAM secure and unsecure areas | P2 | acpaz92.2-5 | TNG |  | 1 | 4 | Delta | 1 | 4 | 1 | FPGA | 4 | [5 empty] | 0 | [6 empty] | 0
108 | KRK-ACP-089 | Feature name - EX-FEAT-089 | Deepak Bhasin | Azalia Test |  | HD Audio Codec detection | P2 | shd3.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
109 | KRK-ACP-090 | Feature name - EX-FEAT-090 | Deepak Bhasin | Azalia Test |  | CORB/RIRB DMA transfer | P2 | shd4.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
110 | KRK-ACP-090 | Feature name - EX-FEAT-090 | Deepak Bhasin | Azalia Test |  | Single stream multichannel loopback | P2 | shd4.12 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
111 | KRK-ACP-091 | Feature name - EX-FEAT-091 | Deepak Bhasin | Azalia Test |  | AZ register access from DSP and host | P2 | acpaz70.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
112 | KRK-ACP-092 | Feature name - EX-FEAT-092 | Deepak Bhasin | Azalia Test |  | CORB/RIRB DMA transfer with ACP DRAM | P2 | acpaz70.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
113 | KRK-ACP-093 | Feature name - EX-FEAT-093 | Deepak Bhasin | Azalia Test |  | Azalia Wakeup | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
114 | KRK-ACP-094 | Feature name - EX-FEAT-094 | Deepak Bhasin | Azalia Test |  | Programmable BCLK frequency check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
115 | KRK-ACP-095 | Feature name - EX-FEAT-095 | Deepak Bhasin | Azalia Test |  | HD Audio Codec detection | P2 | shd3.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
116 | KRK-ACP-096 | Feature name - EX-FEAT-096 | Deepak Bhasin | SoundWire |  | Soundwire all TX RX stream check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
117 | KRK-ACP-097 | Feature name - EX-FEAT-097 | Deepak Bhasin | SoundWire |  | Soundwire all TX RX stream check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
118 | KRK-ACP-098 | Feature name - EX-FEAT-098 | Deepak Bhasin | SoundWire |  | Soundwire CORB/RIRB DMA transfer check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
119 | KRK-ACP-099 | Feature name - EX-FEAT-099 | Deepak Bhasin | SoundWire |  | Soundwire all TX RX stream check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
120 | KRK-ACP-100 | Feature name - EX-FEAT-100 | Deepak Bhasin | SoundWire |  | ACP BPT soundwire check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
121 | KRK-ACP-101 | Feature name - EX-FEAT-101 | Deepak Bhasin | SoundWire |  | Change Clock value during TX/RX stream transfer | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
122 | KRK-ACP-102 | Feature name - EX-FEAT-102 | Deepak Bhasin | SoundWire |  | Soundwire immediate tagged commands check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
123 | KRK-ACP-103 | Feature name - EX-FEAT-103 | Deepak Bhasin | SoundWire |  | Soundwire slave status check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
124 | KRK-ACP-104 | Feature name - EX-FEAT-104 | Deepak Bhasin | SoundWire |  | Soundwire audio corb check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
125 | KRK-ACP-104 | Feature name - EX-FEAT-104 | Deepak Bhasin | SoundWire |  | Soundwire BT corb check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
126 | KRK-ACP-104 | Feature name - EX-FEAT-104 | Deepak Bhasin | SoundWire |  | Soundwire HS corb check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
127 | KRK-ACP-105 | Feature name - EX-FEAT-105 | Deepak Bhasin | SoundWire |  | Soundwire audio circular dpch RX | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
128 | KRK-ACP-105 | Feature name - EX-FEAT-105 | Deepak Bhasin | SoundWire |  | Soundwire audio linear dpch RX | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
129 | KRK-ACP-106 | Feature name - EX-FEAT-106 | Deepak Bhasin | SoundWire |  |  | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
130 | KRK-ACP-107 | Feature name - EX-FEAT-107 | Deepak Bhasin | SoundWire |  | Soundwire all TX RX stream check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
131 | KRK-ACP-108 | Feature name - EX-FEAT-108 | Deepak Bhasin | SoundWire |  | Soundwire audio corb check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
132 | KRK-ACP-108 | Feature name - EX-FEAT-108 | Deepak Bhasin | SoundWire |  | Soundwire BT corb check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
133 | KRK-ACP-108 | Feature name - EX-FEAT-108 | Deepak Bhasin | SoundWire |  | Soundwire HS corb check | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
134 | KRK-ACP-109 | Feature name - EX-FEAT-109 | Deepak Bhasin | SoundWire |  | PRBS error | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
135 | KRK-ACP-109 | Feature name - EX-FEAT-109 | Deepak Bhasin | SoundWire |  | Command response error | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
136 | KRK-ACP-109 | Feature name - EX-FEAT-109 | Deepak Bhasin | SoundWire |  | Transmit-Receive error | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
137 | KRK-ACP-110 | Feature name - EX-FEAT-110 | Deepak Bhasin | Urgency interrupts |  |  | P2 |  | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
138 | KRK-ACP-111 | Feature name - EX-FEAT-111 | Deepak Bhasin | Fusion Test | acp_fusion_ext_instr | ACP Fusion DSP instruction set execute | P2 | acpaz299 | Tserver | dsp_image_no=0-843 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
139 | KRK-ACP-112 | Feature name - EX-FEAT-112 | Deepak Bhasin | Fusion Test | acp_fusion_memio_instr_set | ACP Fusion MEMIO instrution set | P2 | acpaz201.1-10 | Tserver | dsp_image_no=0-9 | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | [5 empty] | 0 | [6 empty] | 0 |  | wk-4
140 | KRK-ACP-113 | Feature name - EX-FEAT-113 | Deepak Bhasin | Fusion Test | acp_dsp_iram_acc_test_fusion | Fusion IRAM Access | P2 | acpaz218.1-3 | TNG |  | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
141 | KRK-ACP-114 | Feature name - EX-FEAT-114 | Deepak Bhasin | Fusion Test | acp_dsp_dram_acc_test_fusion | Fusion DRAM Access | P2 | acpaz219.1-3 | TNG | mFence=0-1 | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
142 | KRK-ACP-115 | Feature name - EX-FEAT-115 | Deepak Bhasin | Fusion Test | acp_dsp_syshub_rand_acc_test_fusion | FW image in system memory, need to use all cache windows | P2 | acpaz220.1-7 | Tserver | targ_mem_type=1-3 -dsp_image_no=0-8 | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
143 | KRK-ACP-116 | Feature name - EX-FEAT-116 | Deepak Bhasin | Fusion Test | acp_dsp_ideram_syshub_rand_acc_test_fusion | Firmware writes to dram/sram/syshub parallel to IRAM | P2 | acpaz221.1-7 | Tserver | dsp_image_no=0-1 | 1 | 7 | Delta | 1 | 7 | 1 | FPGA | 7 | [5 empty] | 0 | [6 empty] | 0
144 | KRK-ACP-117 | Feature name - EX-FEAT-117 | Deepak Bhasin | Fusion Test | acp_dsp_eram_acc_test_fusion | ESRAM access | P2 | acpaz222.1-5 | Tserver |  | 1 | 5 | Delta | 1 | 5 | 1 | FPGA | 5 | [5 empty] | 0 | [6 empty] | 0
145 | KRK-ACP-118 | Feature name - EX-FEAT-118 | Deepak Bhasin | Fusion Test | acp_dsp_win_size_viol_chk_fusion | Fusion DSP error access to different address space regions, data errors | P2 | acpaz224.1-6 | Tserver | dsp_image_no=0-1 and 3 | 1 | 6 | Delta | 1 | 6 | 1 | FPGA | 6 | [5 empty] | 0 | [6 empty] | 0
146 | KRK-ACP-119 | Feature name - EX-FEAT-119 | Deepak Bhasin | Fusion Test | acp_dsp_exception_handler_fusion | Fusion DSP exception handler check | P2 | acpaz225.1-14 | Tserver |  | 1 | 14 | Delta | 1 | 14 | 1 | FPGA | 14 | [5 empty] | 0 | [6 empty] | 0
147 | KRK-ACP-120 | Feature name - EX-FEAT-120 | Deepak Bhasin | Fusion Test | acp_sha_dma_rand_len_fusion | SHA DMA IDRAM Access | P2 | acpaz226 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
148 | KRK-ACP-121 | Feature name - EX-FEAT-121 | Deepak Bhasin | Fusion Test | acp_sha_dma_idram_access_fusion | SHA DMA IDRAM Access | P2 | acpaz227.1 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
149 | KRK-ACP-122 | Feature name - EX-FEAT-122 | Deepak Bhasin | Fusion Test | acp_sha_error_tests_fusion | SHA Error Test | P2 | acpaz229.1-3 | Tserver |  | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
150 | KRK-ACP-123 | Feature name - EX-FEAT-123 | Deepak Bhasin | Fusion Test | acp_dsp_intr_handler_fusion | Internal DSP interrupt for debugging | P2 | acpaz230.1-5 | Tserver |  | 1 | 5 | Delta | 1 | 5 | 1 | FPGA | 5 | [5 empty] | 0 | [6 empty] | 0
151 | KRK-ACP-124 | Feature name - EX-FEAT-124 | Deepak Bhasin | Fusion Test | acp_fusion_dsp_all_timers_check | Fusion Timer interrupt check | P2 | acpaz241.1-3 | Tserver |  | 1 | 3 | Delta | 1 | 3 | 1 | N-1 | 3 | [5 empty] | 0 | [6 empty] | 0
152 | KRK-ACP-125 | Feature name - EX-FEAT-125 | Deepak Bhasin | Fusion Test | acp_watchdog_timer_check | 1 Watchdog timer interrupt check | P2 | acpaz242 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
153 | KRK-ACP-126 | Feature name - EX-FEAT-126 | Deepak Bhasin | Fusion Test | acp_dsp_bint_intr_handler_fusion | ACP to host interrupt check for error | P2 | acpaz294.1-5 | Tserver |  | 1 | 5 | Delta | 1 | 5 | 1 | FPGA | 5 | [5 empty] | 0 | [6 empty] | 0
154 | KRK-ACP-127 | Feature name - EX-FEAT-127 | Deepak Bhasin | Fusion DSP Accessing register Test | acp_dsp_acc_reg_test_fusion | Fusion DSP Accessing register test | P2 | acpaz303.1-15 | Tserver | dsp_image_no=0-14 | 1 | 15 | Delta | 1 | 15 | 1 | N-1 | 15 | [5 empty] | 0 | [6 empty] | 0
155 | KRK-ACP-128 | Feature name - EX-FEAT-128 | Deepak Bhasin | Hifi5-Xtensa DSP1 Test | acp_dsp1_all_timers_check_phx | ACP Timer interrupt check | P2 | acpaz341.1-3 | Tserver |  | 1 | 3 | Delta | 1 | 3 | 1 | FPGA | 3 | [5 empty] | 0 | [6 empty] | 0
156 | KRK-ACP-129 | Feature name - EX-FEAT-129 | Deepak Bhasin | Hifi5-Xtensa DSP Test | acp_dsp_reg_acc_bint4_test | Xtensa internal interrupts | P2 | acpaz105.1-2 | TNG | N/A, -dsp_num=2 | 1 | 2 | Delta | 1 | 2 | 1 | FPGA | 2 | [5 empty] | 0 | [6 empty] | 0
157 | KRK-ACP-130 | Feature name - EX-FEAT-130 | Deepak Bhasin | ACP DSP Multi master test | acp_all_dsps_sha_rand_test | ACP DSP Multi master test | P2 | acpaz342 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
158 | KRK-ACP-131 | Feature name - EX-FEAT-131 | Deepak Bhasin | ACP DSP cross acc IRAM/DRAM | acp_dsp_cross_acc_iram_dram | ACP DSP cross acc IRAM/DRAM | P2 | acpaz343.1-6 | Tserver |  | 1 | 6 | Delta | 1 | 6 | 1 | N-1 | 6 | [5 empty] | 0 | [6 empty] | 0
159 | KRK-ACP-132 | Feature name - EX-FEAT-132 | Deepak Bhasin | ACP Efuse test | acp_efuse_test_strix1 | ACP Efuse test | P2 | acpaz108.1-4 | Tserver |  | 1 | 4 | Delta | 1 | 4 | 1 | N-1 | 4 | [5 empty] | 0 | [6 empty] | 0
160 | KRK-ACP-133 | Feature name - EX-FEAT-133 | Deepak Bhasin | Hifi DSP Accessing register Test | acp_dsp_acc_reg_test | Hifi DSP Accessing register test | P2 | acpaz103.1-30 | Tserver | dsp_image_no=0-14, -dsp_num=2 | 1 | 30 | Delta | 1 | 30 | 1 | N-1 | 30 | [5 empty] | 0 | [6 empty] | 0
161 | KRK-ACP-134 | Feature name - EX-FEAT-134 | Deepak Bhasin | Validate the LPFLL Source Clock Generation | Manual | Validate the LPFLL Source Clock Generation | P2 | Manual | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0
162 | KRK-ACP-135 | Feature name - EX-FEAT-135 | Deepak Bhasin | ACP Tiny NNE AINR Test Enablement | acp_tiny_nne_xnne_network_tests | ACP Tiny NNE AINR Test Enablement | P2 | acpaz107 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
163 | KRK-ACP-136 | ACP DMA IO Stutter Feature | Deepak Bhasin | ACP DMA IO Stutter Feature | acp_dma_1chl_1desc | ACP DMA IO Stutter Feature Enablement | P2 | acpaz2 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0
164 | KRK-ACP-137 | ACP Direct SRAM Access | Deepak Bhasin | ACP Direct SRAM Access | Manual | ACP Direct SRAM Access | P2 | Manual | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | [6 empty] | 0