## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | N100 | N100 SendByteTest | zhilzhan | APML | Network Layer | N100 SendByteTest | P2 | N100 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
1 | N120 | N120 WriteByteTest | zhilzhan | APML | Network Layer | N120 WriteByteTest | P2 | N120 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
2 | N130 | N130 ReadByteTest | zhilzhan | APML | Network Layer | N130 ReadByteTest | P2 | N130 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
3 | N140 | N140 ARATest | zhilzhan | APML | Network Layer | N140 ARATest | P2 | N140 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
4 | N150 | N150 WriteWord | zhilzhan | APML | Network Layer | N150 WriteWord | P2 | N150 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
5 | N160 | N160 ReadWord | zhilzhan | APML | Network Layer | N160 ReadWord | P2 | N160 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
6 | N170 | N170 ProcessCall | zhilzhan | APML | Network Layer | N170 ProcessCall | P2 | N170 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
7 | N180 | N180 BlockWrite | zhilzhan | APML | Network Layer | N180 BlockWrite | P2 | N180 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
8 | N190 | N190 BlockRead | zhilzhan | APML | Network Layer | N190 BlockRead | P2 | N190 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
9 | N200 | N200 BWBRPCTest | zhilzhan | APML | Network Layer | N200 BWBRPCTest | P2 | N200 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
10 | N210 | N210 SlaveACK | zhilzhan | APML | Network Layer | N210 SlaveACK | P2 | N210 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
11 | N230 | N230 SlaveARA | zhilzhan | APML | Network Layer | N230 SlaveARA | P2 | N230 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
12 | N260 | N260 SBI Addr | zhilzhan | APML | Network Layer | N260 SBI Addr | P2 | N260 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
13 | N270 | N270 Reserved Addr | zhilzhan | APML | Network Layer | N270 Reserved Addr | P2 | N270 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
14 | N290 | N290 Invalid Cmd | zhilzhan | APML | Network Layer | N290 Invalid Cmd | P2 | N290 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
15 | N300 | N300 ARPTests | zhilzhan | APML | Network Layer | N300 ARPTests | P2 | N290 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
16 | N310 | N310 10bit Addr | zhilzhan | APML | Network Layer | N310 10bit Addr | P2 | N290 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
17 | N320 | N320 MultiCmd | zhilzhan | APML | Network Layer | N320 MultiCmd | P2 | N320 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
18 | N330 | N330 VariLength | zhilzhan | APML | Network Layer | N330 VariLength | P2 | N330 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
19 | N340 | N340 Special BWBRPC | zhilzhan | APML | Network Layer | N340 SpecialBWBRPC | P2 | N340 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
20 | N350 | N350 BadPEC | zhilzhan | APML | Network Layer | N350 Bad PEC test | P2 | N350 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
21 | P120 | P120 SIClowTimeout | zhilzhan | APML | Physical Layer | P120 SIClowTimeout | P2 | P120 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
22 | P140 | P140 ReceiveAfterSIClow | zhilzhan | APML | Physical Layer | P140 ReceiveAfterSIClow | P2 | P140 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
23 | P190 | P190 DynamicSpeedChange | zhilzhan | APML | Physical Layer | P190 DynamicSpeedChange | P2 | P190 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
24 | F1000 | F1000 CpuidCommand | zhilzhan | APML | RMI Functional | F1000 CpuidCommand | P1 | F1000 | Other |  | 3 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
25 | F1001 | F1001 CPUIDnegativetest | zhilzhan | APML | RMI Functional | F1001 CPUIDnegativetest | P1 | F1001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
26 | F1200 | F1200 MSRAccess | zhilzhan | APML | RMI Functional | F1200 MSRAccess | P1 | F1200 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
27 | F1201 | F1201 MsrNegativeTest | zhilzhan | APML | RMI Functional | F1201 MsrNegativeTest | P1 | F1201 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
28 | F1202 | F1202 MsrRWTest | zhilzhan | APML | RMI Functional | F1202 MsrRWTest | P1 | F1202 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
29 | F1300 | F1300 StatusCodes | zhilzhan | APML | RMI Functional | F1300 StatusCodes | P1 | F1300 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
30 | F1400 | F1400 RMIAlert | zhilzhan | APML | RMI Functional | F1400 RMIAlert | P1 | F1400 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
31 | F1401 | F1401 MCAalerts | zhilzhan | APML | RMI Functional | F1401 MCAalerts | P1 | F1401 | Other |  | 2 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
32 | F1500 | F1500 RMI PEC Test | zhilzhan | APML | RMI Functional | F1500 RMI PEC Test | P1 | F1500 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
33 | F1501 | F1501 Block read/write enable test | zhilzhan | APML | RMI Functional | F1501 Block read/write enable test | P1 | F1501 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
34 | F1502 | F1502 Alert mask test | zhilzhan | APML | RMI Functional | F1502 Alert mask test | P1 | F1502 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
35 | F1503 | F1503 Timeout disable test | zhilzhan | APML | RMI Functional | F1503 Timeout disable test | P1 | F1503 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
36 | F1504 | F1504 ARA disable test | zhilzhan | APML | RMI Functional | F1504 ARA disable test | P1 | F1504 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
37 | F1505 | F1505 Read size test | zhilzhan | APML | RMI Functional | F1505 Read size test | P1 | F1505 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
38 | F1600 | F1600 RMI MP0 Comm Test | zhilzhan | APML | RMI Functional | F1600 RMI MP0 Comm Test | P1 | F1600 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
39 | F1700 | F1700 Thread Number | zhilzhan | APML | RMI Functional | F1700 Thread Number | P1 | F1700 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
40 | F1800 | F1800 Thread Enable Status | zhilzhan | APML | RMI Functional | F1800 Thread Enable Status | P1 | F1800 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
41 | F1900 | F1900 RMI revtest | zhilzhan | APML | RMI Functional | F1900 RMI revtest | P1 | F1900 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
42 | F2000 | F2000 RMI Boot Status | zhilzhan | APML | RMI Functional | F2000 RMI Boot Status | P1 | F2000 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
43 | F5001 | F5001 SustainedPowerLimit Msg | zhilzhan | APML | RMI Functional | F5001 SustainedPowerLimit Msg | P1 | F5001 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
44 | F5002 | F5002 FastPPTLimit Msg | zhilzhan | APML | RMI Functional | F5002 FastPPTLimit Msg | P1 | F5002 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
45 | F5003 | F5003 SlowPPTLimit Msg | zhilzhan | APML | RMI Functional | F5003 SlowPPTLimit Msg | P1 | F5003 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
46 | F5004 | F5004 SlowPPTTimeConst Msg | zhilzhan | APML | RMI Functional | F5004 SlowPPTTimeConst Msg | P1 | F5004 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
47 | F5005 | F5005 ThermCtlLimit Msg | zhilzhan | APML | RMI Functional | F5005 ThermCtlLimit Msg | P1 | F5005 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
48 | F5006 | F5006 VddTDCLimit Msg | zhilzhan | APML | RMI Functional | F5006 VddTDCLimit Msg | P1 | F5006 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
49 | F5007 | F5007 VddEDCLimit Msg | zhilzhan | APML | RMI Functional | F5007 VddEDCLimit Msg | P1 | F5007 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
50 | F5008 | F5008 SocTDCLimit Msg | zhilzhan | APML | RMI Functional | F5008 SocTDCLimit Msg | P1 | F5008 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
51 | F5009 | F5009 SocEDCLimit Msg | zhilzhan | APML | RMI Functional | F5009 SocEDCLimit Msg | P1 | F5009 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
52 | F5010 | F5010 ProchotRampTime Msg | zhilzhan | APML | RMI Functional | F5010 ProchotRampTime Msg | P1 | F5010 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
53 | F5011 | F5011 SSTSensorValue Msg | zhilzhan | APML | RMI Functional | F5011 SSTSensorValue Msg | P1 | F5011 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
54 | F5012 | F5012 SlowPPTLimitAPU Msg | zhilzhan | APML | RMI Functional | F5012 SlowPPTLimitAPU Msg | P1 | F5012 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
55 | R200 | R200 Test read-only RMI Registers | zhilzhan | APML | RMI Registers | R200 Test read-only RMI Registers | P2 | R200 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
56 | R210 | R210 Test read-write RMI Registers | zhilzhan | APML | RMI Registers | R210 Test read-write RMI Registers | P2 | R210 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
57 | R220 | R220 Test write-1-to-clear RMI Registers | zhilzhan | APML | RMI Registers | R220 Test write-1-to-clear RMI Registers | P2 | R220 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
58 | R230 | R230 Test unimplemented RMI Registers | zhilzhan | APML | RMI Registers | R230 Test unimplemented RMI Registers | P2 | R230 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
59 | R240 | R240 Test Special RMI Registers | zhilzhan | APML | RMI Registers | R240 Test Special RMI Registers | P2 | R240 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
60 | F100 | TSI Functional | zhilzhan | APML | TSI Functional | F100 TSI CpuTempInt | P1 | F100 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
61 | F110 | F110 TSI TempLowAlert | zhilzhan | APML | TSI Functional | F110 TSI TempLowAlert | P1 | F110 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
62 | F120 | TSI Functional | zhilzhan | APML | TSI Functional | F120 TSI TempHighAlert | P1 | F120 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
63 | F130 | TSI Functional | zhilzhan | APML | TSI Functional | F130 TSI AraDis | P1 | F130 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
64 | F140 | TSI Functional | zhilzhan | APML | TSI Functional | F140 TSI ReadOrder | P1 | F140 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
65 | F150 | TSI Functional | zhilzhan | APML | TSI Functional | F150 TSI RunStop | P1 | F150 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
66 | F210 | F210 TSI CpuTempDec | zhilzhan | APML | TSI Functional | F210 TSI CpuTempDec | P1 | F210 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
67 | F220 | F220 TSI CpuTempOffset | zhilzhan | APML | TSI Functional | F220 TSI CpuTempIntOff | P1 | F220 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
68 | F240 | TSI Functional | zhilzhan | APML | TSI Functional | F240 TSI HiTempDec | P1 | F240 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
69 | F250 | TSI Functional | zhilzhan | APML | TSI Functional | F250 TSI LoTempDec | P1 | F250 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
70 | F270 | F270 TSI TjInt | zhilzhan | APML | TSI Functional | F270 TSI TjInt | P1 | F270 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
71 | F340 | F340 TSI Write Done | zhilzhan | APML | TSI Functional | F340 TSI Write Done | P1 | F340 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
72 | F380 | F380 Read Mode Test | zhilzhan | APML | TSI Functional | F380 Read Mode Test | P1 | F380 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
73 | F390 | F390 Temperature per Die Test | zhilzhan | APML | TSI Functional | F390 Temperature per Die Test | P1 | F390 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
74 | F410 | F410 SMU Cur Temp Test | zhilzhan | APML | TSI Functional | F410 SMU Cur Temp Test | P1 | F410 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
75 | R100 | R100 Test read-only TSI Registers | zhilzhan | APML | TSI Registers | R100 Test read-only TSI Registers | P2 | R100 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
76 | R110 | R110 Test read-write TSI Registers | zhilzhan | APML | TSI Registers | R110 Test read-write TSI Registers | P2 | R110 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
77 | R120 | R120 Test write-only TSI Registers | zhilzhan | APML | TSI Registers | R120 Test write-only TSI Registers | P2 | R120 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
78 | R130 | R130 Test Unimplemented TSI Registers | zhilzhan | APML | TSI Registers | R130 Test Unimplemented TSI Registers | P2 | R130 | Other |  | 0.1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1