## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RAS.007 | DRAM Scrubbers | Akash Dixit | CCX RAS | DRAM_Patrol_And_Redirect_Scrubber | DRAM_Patrol_And_Redirect_Scrubber | P2 | RAS.7 | CDL |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
1 | RAS.008 | DRAM Corrected Error Counters | Akash Dixit | CCX RAS | DRAM_Patrol_And_Redirect_Scrubber | DRAM_Patrol_And_Redirect_Scrubber | P2 | RAS.8 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
2 | RAS.009 | DRAM Bad Symbol ID | Akash Dixit | CCX RAS | ECC_Bad_Symbol_Identification | ECC_Bad_Symbol_Identification | P2 | RAS.9 | CDL |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
3 | RAS.010 | DRAM ECC Error Injection (HW validation) | Akash Dixit | CCX RAS | DRAM_Patrol_And_Redirect_Scrubber | DRAM_Patrol_And_Redirect_Scrubber | P2 | RAS.10 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
4 | RAS.011 | DRAM ECC | Akash Dixit | CCX RAS | DRAM_Patrol_And_Redirect_Scrubber | DRAM_Patrol_And_Redirect_Scrubber | P2 | RAS.11 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
5 | RAS.012 | Data Poisoning | Akash Dixit | CCX RAS | DRAM_Data_Poisoning | DRAM_Data_Poisoning | P2 | RAS.12 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
6 | RAS.014 | DDR5 Write CRC Error Injection (HW validation) | Akash Dixit | CCX RAS | Address_Command_Parity_Error_Replay | Address_Command_Parity_Error_Replay | P2 | RAS.14 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
7 | RAS.015 | DDR5 Read CRC Error Injection (HW validation) | Akash Dixit | CCX RAS | Address_Command_Parity_Error_Replay | Address_Command_Parity_Error_Replay | P2 | RAS.15 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-4
8 | RAS.026 | Scalable MCA 3.0 | Akash Dixit | CCX RAS | Software_Access_To_MCA_Banks | Software_Access_To_MCA_Banks | P2 | RAS.26 | CDL |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
9 | RAS.NBIO.010 | Test PCIe Legacy Error Reporting | Akash Dixit | NBIO-RAS | PCIe Legacy Error Reporting | PCIe Legacy Error Reporting | P2 | NBIO_RAS.10 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-1
10 | RAS.NBIO.011 | Test PCIe AER Error Reporting | Akash Dixit | NBIO-RAS | PCIe AER Error Reporting | PCIe AER Error Reporting | P2 | NBIO_RAS.11 | CDL |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-1
11 | RAS.NBIO.001 | PCIe AER LCRC Error Injection | Akash Dixit | NBIO-RAS | PCIe AER LCRC Error Injection | PCIe AER LCRC Error Injection | P2 | NBIO_RAS.1 | CDL |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-5
12 | RAS.NBIO.012 | PCIe AER ECRC Error Injection | Akash Dixit | NBIO-RAS | PCIe AER ECRC Error Injection | PCIe AER ECRC Error Injection | P2 | NBIO_RAS.12 | CDL |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
13 | RAS.NBIO.013 | PCIe AER ACS Error Injection | Akash Dixit | NBIO-RAS | PCIe AER ACS Error Injection | PCIe AER ACS Error Injection | P2 | NBIO_RAS.13 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-2
14 | RAS.NBIO.014 | PCIe eDPC Error | Akash Dixit | NBIO-RAS | PCIe eDPC Error | PCIe eDPC Error | P2 | NBIO_RAS.14 | CDL |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
15 | RAS.NBIO.021 | USB/SATA/PTDMA ECC/Parity Error | Akash Dixit | NBIO-RAS | USB/SATA/PTDMA ECC/Parity Error | USB/SATA/PTDMA ECC/Parity Error | P2 | NBIO_RAS.21 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3
16 | RAS.NBIO.023 | FCH Watchdog Timer | Akash Dixit | NBIO-RAS | FCH Watchdog Timer | FCH Watchdog Timer | P2 | NBIO_RAS.23 | CDL |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | WK-3