## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | FCH_001_FEAT | Set SmbusAsfIoEn by default (PM 0x00[4]=1) |  | ACPI |  | ASF | P1 | fch_tcid001.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
1 | FCH_002_FEAT | PCI Configuration registers accessing |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid002.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
2 | FCH_003_FEAT | Scratch registers in SMBUS PCI Configuration Space |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid003.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
3 | FCH_004_FEAT | PM registers accessing |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid004.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
4 | FCH_005_FEAT | PM2 registers accessing |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid005.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
5 | FCH_006_FEAT | Validate few GPIO pins for following functionality, 1. INPUT 2. OUTPUT (PullUp & PullDown disabled) 3. OUTPUT with PullUp & PullDown Enabled 4. Software Control IN for Interrupt status |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid006.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
6 | FCH_007_FEAT | Validate few GPIO pins for following functionality, 1. H/W debounce logic. (Timer setting, timer control trigger type & level) 2. Interrupt generation. 3. Wake. (Where it is applicable) 4. Driving strength 5. Status of Less than 2 or 10 seconds. (Where it is applicable) |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid007.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
7 | FCH_008_FEAT | BIOS RAM accessing |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid008.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
8 | FCH_009_FEAT | ACPI standard registers accessing |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid009.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
9 | FCH_010_FEAT | SMBUS PCI device ID and revision ID are to be changed to reflect as Waterton |  | ACPI |  | ACPI Register Spaces | P1 | fch_tcid010.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
10 | FCH_011_FEAT | Access MMIO address: 0xFED80200~0xFED802FF |  | ACPI |  | SMI/SCI features | P1 | fch_tcid011.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
11 | FCH_012_FEAT | Access AcpiSmiCmd register |  | ACPI |  | SMI/SCI features | P1 | fch_tcid012.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
12 | FCH_013_FEAT | SMI trigger/Smi enable/Smi status/Eos |  | ACPI |  | SMI/SCI features | P1 | fch_tcid013.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
13 | FCH_014_FEAT | SMI Long/Short timer |  | ACPI |  | SMI/SCI features | P1 | fch_tcid014.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
14 | FCH_015_FEAT | IO trapping |  | ACPI |  | SMI sources | P1 | fch_tcid015.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
15 | FCH_016_FEAT | Memory trapping |  | ACPI |  | SMI sources | P1 | fch_tcid016.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
16 | FCH_017_FEAT | PCI Cfg trapping |  | ACPI |  | SMI sources | P1 | fch_tcid017.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
17 | FCH_018_FEAT | SLP_TYP |  | ACPI |  | SMI sources | P1 | fch_tcid018.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
18 | FCH_019_FEAT | SMBUS generated |  | ACPI |  | SMI sources | P1 | fch_tcid019.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
19 | FCH_020_FEAT | Port 60/64 trapping |  | ACPI |  | SMI sources | P1 | fch_tcid020.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
20 | FCH_021_FEAT | ASF generated |  | ACPI |  | SMI sources | P1 | fch_tcid021.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
21 | FCH_022_FEAT | CF9 generated |  | ACPI |  | SMI sources | P1 | fch_tcid022.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
22 | FCH_023_FEAT | From other GPIOs, sleep trap, etc |  | ACPI |  | SMI sources | P1 | fch_tcid023.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
23 | FCH_024_FEAT | Write 0x06 or 0x0E or 0x04 to 0xCF9 register and observe H/W behavior |  | ACPI |  | Reset sources | P1 | fch_tcid024.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
24 | FCH_025_FEAT | Reset generation by attached keyboard |  | ACPI |  | Reset sources | P1 | fch_tcid025.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
25 | FCH_026_FEAT | 8254 Programmable Interval Timer |  | ACPI |  | Legacy & Timers | P1 | fch_tcid026.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
26 | FCH_027_FEAT | Per ACPI spec; checking the timer by IO and MMIO access |  | ACPI |  | Legacy & Timers | P1 | fch_tcid027.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
27 | FCH_028_FEAT | Per High Precision Event Timer spec. |  | ACPI |  | Legacy & Timers | P1 | fch_tcid028.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
28 | FCH_029_FEAT | NMI generation |  | ACPI |  | IRQ Generation | P1 | fch_tcid029.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
29 | FCH_030_FEAT | Software generated NMI |  | ACPI |  | IRQ Generation | P1 | fch_tcid030.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
30 | FCH_031_FEAT | 64bit payload, address and MT[3:0] definition |  | ACPI |  | SoC Platform | P1 | fch_tcid031.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
31 | FCH_032_FEAT | System in the different sleep states; S0, S1, S3, S4 & S5 |  | ACPI |  | Advanced ACPI | P1 | fch_tcid032.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
32 | FCH_033_FEAT | AZ_PME# side-band siganl has been added |  | ACPI |  | Advanced ACPI | P1 | fch_tcid033.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
33 | FCH_034_FEAT | USB3 IP will be outside of SCH; combine of PME# signal |  | ACPI |  | Advanced ACPI | P1 | fch_tcid034.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
34 | FCH_035_FEAT | Indication of a thermal trip has occurred. |  | ACPI |  | Advanced ACPI | P1 | fch_tcid035.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
35 | FCH_036_FEAT | PM 0xC0[9] is for internal Thermtrip event status |  | ACPI |  | Advanced ACPI | P1 | fch_tcid036.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
36 | FCH_037_FEAT | Implementation of a traffic counter |  | ACPI |  | Advanced ACPI | P1 | fch_tcid037.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
37 | FCH_038_FEAT | IO-80 (PostCode) is expanded to 32-bit |  | ACPI |  | Miscellaneous | P1 | fch_tcid038.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
38 | FCH_039_FEAT | It is enabled by H/W default and cannot be disabled. |  | ACPI |  | Miscellaneous | P1 | fch_tcid039.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
39 | FCH_040_FEAT | GPIO Bank3 will be added for 32 GPP port PME |  | ACPI |  | GPIO Function | P1 | fch_tcid040.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
40 | FCH_041_FEAT | iLA register access from Host |  | DFx |  | iLA Basic Features | P1 | fch_tcid041.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
41 | FCH_042_FEAT | iLA register access from JTAG |  | DFx |  | iLA Basic Features | P1 | fch_tcid042.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
42 | FCH_043_FEAT | iLA register changes |  | DFx |  | iLA Basic Features | P1 | fch_tcid043.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
43 | FCH_044_FEAT | Snapshot, manual trigger |  | DFx |  | iLA Basic Features | P1 | fch_tcid044.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
44 | FCH_045_FEAT | Snapshot |  | DFx |  | iLA Basic Features | P1 | fch_tcid045.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
45 | FCH_046_FEAT | Manual trigger |  | DFx |  | iLA Basic Features | P1 | fch_tcid046.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
46 | FCH_047_FEAT | Auto/Event trigger |  | DFx |  | iLA Basic Features | P1 | fch_tcid047.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
47 | FCH_048_FEAT | Event trigger |  | DFx |  | iLA Basic Features | P1 | fch_tcid048.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
48 | FCH_049_FEAT | Upstream filtering |  | DFx |  | iLA Basic Features | P1 | fch_tcid049.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
49 | FCH_050_FEAT | Downstream filtering |  | DFx |  | iLA Basic Features | P1 | fch_tcid050.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
50 | FCH_051_FEAT | ROM Protection range is extended (Up to 512KB) |  | LPC_SPI |  | LPC Block | P1 | fch_tcid051.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
51 | FCH_052_FEAT | The default setting of Port 80 decode will not be at LPC |  | LPC_SPI |  | LPC Block | P1 | fch_tcid052.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
52 | FCH_053_FEAT | Read/Write device access (Normal Mode) |  | LPC_SPI |  | LPC Block | P1 | fch_tcid053.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
53 | FCH_054_FEAT | ROM Protection range is extended (Up to 512KB) |  | LPC_SPI |  | SPI Block | P1 | fch_tcid054.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
54 | FCH_055_FEAT | Read/Write device access (Normal Mode) |  | LPC_SPI |  | SPI Block | P1 | fch_tcid055.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
55 | FCH_056_FEAT | Read device under different mode. (Dual, Dual I/O, Quad, Quad I/O & Fast Read) |  | LPC_SPI |  | SPI Block | P1 | fch_tcid056.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
56 | FCH_057_FEAT | 16M will be the default BIOS memory aperture size |  | LPC_SPI |  | LPC/SPI common features | P1 | fch_tcid057.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
57 | FCH_058_FEAT | RTC_CMOS |  | RTC |  | RTC Registers | P1 | fch_tcid058.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
58 | FCH_059_FEAT | Read/write protection |  | RTC |  | RTC Registers | P1 | fch_tcid059.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
59 | FCH_060_FEAT | Alternate rtc mapping |  | RTC |  | RTC Registers | P1 | fch_tcid060.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
60 | FCH_061_FEAT | Extra 16 bytes in CMOS |  | RTC |  | RTC Registers | P1 | fch_tcid061.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
61 | FCH_062_FEAT | RTC Rd/Wr Regs |  | RTC |  | RTC Registers | P1 | fch_tcid062.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
62 | FCH_063_FEAT | BCD Timer Read/Write |  | RTC |  | RTC Registers | P1 | fch_tcid063.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
63 | FCH_064_FEAT | BCD Timer Counting |  | RTC |  | RTC Registers | P1 | fch_tcid064.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
64 | FCH_065_FEAT | Non-Posted Memory Read Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid065.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
65 | FCH_066_FEAT | Posted Memory Write Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid066.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
66 | FCH_067_FEAT | Non-Posted IO Read Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid067.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
67 | FCH_068_FEAT | Non-Posted IO Write Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid068.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
68 | FCH_069_FEAT | Non-Posted Type 0 Configuration Read Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid069.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
69 | FCH_070_FEAT | Non-Posted Type 0 Configuration Write Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid070.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
70 | FCH_071_FEAT | Non-Posted Type 1 Configuration Read Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid071.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
71 | FCH_072_FEAT | Non-Posted Type 1 Configuration Write Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid072.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
72 | FCH_073_FEAT | Posted Message Transactions |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid073.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
73 | FCH_074_FEAT | AMD specific non-posted memory write support |  | SDP_AB |  | Basic AB Transaction Features | P1 | fch_tcid074.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
74 | FCH_075_FEAT | SDP Downstream cycles supported |  | SDP_AB |  | Basic SDP Transaction Features | P1 | fch_tcid075.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
75 | FCH_076_FEAT | SDP Upstream cycles supported. |  | SDP_AB |  | Basic SDP Transaction Features | P1 | fch_tcid076.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
76 | FCH_077_FEAT | 64 bit address DMA read/write |  | SDP_AB |  | Basic SDP Transaction Features | P1 | fch_tcid077.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
77 | FCH_078_FEAT | SDP Ordering Rules |  | SDP_AB |  | AB Flow Control Features | P1 | fch_tcid078.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
78 | FCH_079_FEAT | SDP Downstream and Upstream Throttling. |  | SDP_AB |  | Main Flow Control Features | P1 | fch_tcid079.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
79 | FCH_080_FEAT | SDP Transfers Larger than 16 bytes |  | SDP_AB |  | Main Flow Control Features | P1 | fch_tcid080.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
80 | FCH_081_FEAT | SDP/AB DMA write 16-byte mode |  | SDP_AB |  | Main Flow Control Features | P1 | fch_tcid081.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
81 | FCH_082_FEAT | SDP/AB DMA write 64-byte mode |  | SDP_AB |  | Main Flow Control Features | P1 | fch_tcid082.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
82 | FCH_083_FEAT | AB A-Link Debug Clock Gating |  | SDP_AB |  | Main AB PM Features | P1 | fch_tcid083.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
83 | FCH_084_FEAT | AB A-Link Clock Gating |  | SDP_AB |  | Main AB PM Features | P1 | fch_tcid084.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
84 | FCH_085_FEAT | AB B-Link Clock Gating |  | SDP_AB |  | Main AB PM Features | P1 | fch_tcid085.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
85 | FCH_086_FEAT | SDP Performance Counter |  | SDP_AB |  | Main Debug Features | P1 | fch_tcid086.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
86 | FCH_087_FEAT | SDP Register Access |  | SDP_AB |  | Basic SDP Register Access | P1 | fch_tcid087.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
87 | FCH_088_FEAT | AB ABCFG Registers |  | SDP_AB |  | Basic AB Register Access | P1 | fch_tcid088.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
88 | FCH_089_FEAT | SDP Downstream Control |  | SDP_AB |  | Basic SDP Register Access | P1 | fch_tcid089.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
89 | FCH_090_FEAT | SDP Upstream Control |  | SDP_AB |  | Basic SDP Register Access | P1 | fch_tcid090.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
90 | FCH_091_FEAT | SDP Misc Control |  | SDP_AB |  | Basic SDP Register Access | P1 | fch_tcid091.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
91 | FCH_092_FEAT | SDP Spare 0 |  | SDP_AB |  | Basic SDP Register Access | P1 | fch_tcid092.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
92 | FCH_093_FEAT | AB Pseudo-Random MST_CPL min/max Delay |  | SDP_AB |  | Advanced Features | P1 | fch_tcid093.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
93 | FCH_094_FEAT | AB Pseudo-Random Completion Throttle |  | SDP_AB |  | Advanced Features | P1 | fch_tcid094.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
94 | FCH_095_FEAT | SDP Pseudo-Random HOSTRSP min/max Delay |  | SDP_AB |  | Advanced Features | P1 | fch_tcid095.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
95 | FCH_096_FEAT | SDP Pseudo-Random HOSTRSP_DELAY_FREQ |  | SDP_AB |  | Advanced Features | P1 | fch_tcid096.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
96 | FCH_097_FEAT | SDP Pseudo-Random Completion Throttle |  | SDP_AB |  | Advanced Features | P1 | fch_tcid097.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
97 | FCH_098_FEAT | SDP SDP-NBIO DMA Completion Throttle |  | SDP_AB |  | Advanced Features | P1 | fch_tcid098.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
98 | FCH_099_FEAT | SDP BIF-SLV Downstream Throttle |  | SDP_AB |  | Advanced Features | P1 | fch_tcid099.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
99 | FCH_100_FEAT | SDP BIF-SLV Downstream Stall |  | SDP_AB |  | Advanced Features | P1 | fch_tcid100.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
100 | FCH_101_FEAT | AB AXI XDMA Write 64-byte Mode |  | SDP_AB |  | Main AXI Flow Control Features | P1 | fch_tcid101.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
101 | FCH_102_FEAT | AB AXI XDMA Arbitration |  | SDP_AB |  | Main AXI Flow Control Features | P1 | fch_tcid102.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
102 | FCH_103_FEAT | AB AXI PENDING NP Request Threshold |  | SDP_AB |  | Main AXI Flow Control Features | P1 | fch_tcid103.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
103 | FCH_104_FEAT | AB AXI Ordering |  | SDP_AB |  | MainAXI Flow Control Features | P1 | fch_tcid104.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
104 | FCH_105_FEAT | AB B-Link Debug Clock Gating |  | SDP_AB |  | Main AB PM Features | P1 | fch_tcid105.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
105 | FCH_106_FEAT | Gasket JTAG Registers |  | SDP_AB |  | Basic SDP Register Access | P1 | fch_tcid106.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
106 | FCH_107_FEAT | Debug bus access |  | SDP_AB |  | Advanced Features | P1 | fch_tcid107.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
107 | FCH_108_FEAT | NBIO-SDP Hostreq Throttle Control |  | SDP_AB |  | Advanced Features | P1 | fch_tcid108.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
108 | FCH_109_FEAT | AB AXI Slave Read Data Port |  | SDP_AB |  | Basic AXI Transaction Features | P1 | fch_tcid109.001 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
109 | FCH_110_FEAT | Secure Register Access |  | SDP_AB |  | FCH SDP Secure Register Access | P1 | fch_tcid110.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
110 | FCH_111_FEAT | RSMU Slave Address Re-mapping |  | SDP_AB |  | FCH Slave Address Remapping/Block Access | P1 | fch_tcid111.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
111 | FCH_112_FEAT | 12 FCH SDP Secure Range function |  | SDP_AB |  | Secure Access to RTC by PSP | P1 | fch_tcid112.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
112 | FCH_113_FEAT | UART Loopback Test |  | UART DMA |  | UART Loopback Test | P1 | fch_tcid113.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
113 | FCH_114_FEAT | UART rda Intrpt wintlb wofc wififo |  | UART DMA |  | UART rda Intrpt wintlb wofc wififo | P1 | fch_tcid114.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
114 | FCH_115_FEAT | UART thre empty Intrpt wintlb wofc wofifo test |  | UART DMA |  | UART thre empty Intrpt wintlb wofc wofifo test | P1 | fch_tcid115.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
115 | FCH_116_FEAT | uart rx fifo full triggerlevel |  | UART DMA |  | uart rx fifo full triggerlevel | P1 | fch_tcid116.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
116 | FCH_117_FEAT | uart tx fifo empty trigger leve test |  | UART DMA |  | uart tx fifo empty trigger leve test | P1 | fch_tcid117.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
117 | FCH_118_FEAT | uart register access test on uarts |  | UART DMA |  | uart register access test on uarts | P1 | fch_tcid118.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
118 | FCH_119_FEAT | uart reset feature test |  | UART DMA |  | uart reset feature test | P1 | fch_tcid119.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
119 | FCH_120_FEAT | uart Break itrpt Test |  | UART DMA |  | uart Break itrpt Test | P1 | fch_tcid120.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
120 | FCH_121_FEAT | memory_fill_read_test:64bytes |  | UART DMA |  | memory_fill_read_test:64bytes | P1 | fch_tcid121.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
121 | FCH_122_FEAT | uart data transfer test |  | UART DMA |  | uart data transfer test | P1 | fch_tcid122.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
122 | FCH_123_FEAT | uart datalength verification test |  | UART DMA |  | uart datalength verification test | P1 | fch_tcid123.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
123 | FCH_124_FEAT | uart_baudrate_verification_test |  | UART DMA |  | uart_baudrate_verification_test | P1 | fch_tcid124.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
124 | FCH_125_FEAT | uart_stopbit_verification_test |  | UART DMA |  | uart_stopbit_verification_test | P1 | fch_tcid125.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
125 | FCH_126_FEAT | uart_paritybit_verification_test |  | UART DMA |  | uart_paritybit_verification_test | P1 | fch_tcid126.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
126 | FCH_127_FEAT | uart DMA verification test |  | UART DMA |  | UART DMA data transfer test | P1 | fch_tcid127.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
127 | FCH_128_FEAT | I/O Read / Write PCI commands |  | ESPI |  | eSPI Memory Read/write | P1 | fch_tcid128.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
128 | FCH_129_FEAT | Memory Read / Write PCI commands |  | ESPI |  | eSPI Memory Read/write | P1 | fch_tcid129.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
129 | FCH_130_FEAT | Memory traffic Peripheral Channel trafic |  | ESPI |  | eSPI commands Test | P1 | fch_tcid130.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
130 | FCH_131_FEAT | IO traffic Peripheral Channel trafic |  | ESPI |  | eSPI commands Test | P1 | fch_tcid131.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
131 | FCH_132_FEAT | Msg/MsgD Peripheral Channel traffic |  | ESPI |  | eSPI commands Test | P1 | fch_tcid132.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
132 | FCH_133_FEAT | Slave to Master Virtual Wire Channel Intterupt Events |  | ESPI |  | eSPI commands Test | P1 | fch_tcid133.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
133 | FCH_134_FEAT | Master to Slave Virtual Wire Channel Intterupt Events |  | ESPI |  | eSPI commands Test | P1 | fch_tcid134.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
134 | FCH_135_FEAT | Slave to Master OOB Channel traffic |  | ESPI |  | eSPI OOB(Out Of Bands) Test | P1 | fch_tcid135.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
135 | FCH_136_FEAT | Master to Slave OOB Channel traffic |  | ESPI |  | eSPI OOB(Out Of Bands) Test | P1 | fch_tcid136.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
136 | FCH_137_FEAT | Register Test |  | ESPI |  | eSPI commands Test | P1 | fch_tcid137.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
137 | FCH_138_FEAT | MMIO Range and Decoding |  | ESPI |  | eSPI Memory Read/write | P1 | fch_tcid138.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
138 | FCH_139_FEAT | locking eSPI Master control register |  | ESPI |  | eSPI commands Test | P1 | fch_tcid139.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
139 | FCH_140_FEAT | Single, Dual and Quad IO Test |  | ESPI |  | eSPI commands Test | P1 | fch_tcid140.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
140 | FCH_141_FEAT | Operating support frequency test |  | ESPI |  | eSPI commands Test | P1 | fch_tcid141.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
141 | FCH_142_FEAT | Add register control on disabling eSPI_ALERT# |  | ESPI |  | eSPI commands Test | P1 | fch_tcid142.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
142 | FCH_143_FEAT | Basic I3C Register Access |  | I3C |  | I3C Test | P1 | fch_tcid143.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
143 | FCH_144_FEAT | I3C Bus Initialization and Dynamic Address Assignment Mode |  | I3C |  | I3C Test | P1 | fch_tcid144.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
144 | FCH_145_FEAT | I3C Timing Control |  | I3C |  | I3C Test | P1 | fch_tcid145.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
145 | FCH_146_FEAT | I3C Protocol SDR mode |  | I3C |  | I3C Test | P1 | fch_tcid146.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
146 | FCH_147_FEAT | I3C Interrupt |  | I3C |  | I3C Test | P1 | fch_tcid147.001 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
147 | FCH_148_FEAT | Boot from SAFS |  | ESPI |  | Boot from SAFS | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK6
148 | FCH_149_FEAT | MMIO read from or write to SAFS ROM |  | ESPI |  | MMIO read from or write to SAFS ROM | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK6
149 | FCH_150_FEAT | Security Fence for SAFS |  | ESPI |  | Security Fence for SAFS | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK6
150 | FCH_151_FEAT | ROM prefetch for SAFS |  | ESPI |  | ROM prefetch for SAFS | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
151 | FCH_152_FEAT | SAFS per register interface operations |  | ESPI |  | SAFS per register interface operations | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
152 | FCH_153_FEAT | SAFS flash modifier |  | ESPI |  | SAFS flash modifier | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
153 | FCH_154_FEAT | Ensure MAFS still works since design shares some logic between SAFS and MAFS. |  | ESPI |  | Ensure MAFS still works since design shares some logic between SAFS and MAFS. | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK6
154 | FCH_155_FEAT | OneNPCmd_EN check |  | ESPI |  | OneNPCmd_EN check | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK6
155 | FCH_156_FEAT | SAFS flash read mix with Get_OOB |  | ESPI |  | SAFS flash read mix with Get_OOB | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
156 | FCH_157_FEAT | Improve ESPI_CLK_SCAN to support 20/25/50MHz |  | ESPI |  | Improve ESPI_CLK_SCAN to support 20/25/50MHz | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
157 | FCH_158_FEAT | MGCG implementation |  | ESPI |  | MGCG implementation | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
158 | FCH_159_FEAT | PUT_FLASH_NP response cycletype mismatch handling |  | ESPI |  | PUT_FLASH_NP response cycletype mismatch handling | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
159 | FCH_160_FEAT | TAG field in PUT_MEMR_32_SHORT and IORD_SHORT |  | ESPI |  | TAG field in PUT_MEMR_32_SHORT and IORD_SHORT | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, there is no slave on board to verify these features which supports diagnostics. | WK8
160 | FCH_161_FEAT | Crash dump trigger via HW |  | DFx |  | Crash dump trigger via HW | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
161 | FCH_162_FEAT | Crash dump trigger via SW |  | DFx |  | Crash dump trigger via SW | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
162 | FCH_163_FEAT | rSMU access for crash dump |  | DFx |  | rSMU access for crash dump | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
163 | FCH_164_FEAT | Crash dump timeout control |  | DFx |  | Crash dump timeout control | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
164 | FCH_165_FEAT | Crash dump register check after warm reset |  | DFx |  | Crash dump register check after warm reset | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
165 | FCH_166_FEAT | Crash dump register check after cold reset |  | DFx |  | Crash dump register check after cold reset | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
166 | FCH_167_FEAT | Multi Crash dump after warm reset |  | DFx |  | Multi Crash dump after warm reset | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
167 | FCH_168_FEAT | Multi Crash dump after cold reset |  | DFx |  | Multi Crash dump after cold reset | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
168 | FCH_169_FEAT | Crash dump by rSMU access |  | DFx |  | Crash dump by rSMU access | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
169 | FCH_170_FEAT | Crash dump during warm reset |  | DFx |  | Crash dump during warm reset | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | This cant be covered because, this cant be automated as it is related to system crash and crash dump. | WK8
170 | FCH_171_FEAT | Locking PM xD4[31:8] |  | ACPI |  | Locking PM xD4[31:8] | P1 | fch_tcid171.001 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
171 | FCH_172_FEAT | RTC decoding control |  | RTC |  | RTC decoding control | P1 | fch_tcid172.001 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
172 | FCH_173_FEAT | Flash Idle Counter |  | LPC_SPI |  | Flash Idle Counter | P1 | fch_tcid173.001 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
173 | FCH_174_FEAT | PSP ROM Controlled by PSP xFC[15] |  | LPC_SPI |  | PSP ROM Controlled by PSP xFC[15] | P1 |  |  |  | 0 | 0 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 | Not Applicable for STX1 | WK8
174 | FCH_175_FEAT | Removal of SPI x38 & x3C |  | LPC_SPI |  | Removal of SPI x38 & x3C | P1 | fch_tcid175.001 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
175 | FCH_176_FEAT | I3C Shadow Register added |  | I3C |  | I3C Shadow Register added | P1 | fch_tcid176.001 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8