## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | KRACKAN1-IPU-001 | Register Test MMIO | Amine Akrout | Data Path - MMIO |  | x86 to access IPU Registers via MMIO prior to booting IPU |  | krackan1.ipu.mmio/IpuRegisterAccess |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
1 | KRACKAN1-IPU-002 | Register Test SMN | Amine Akrout | Data Path - SMN |  | x86 to access IPU Registers via SMN prior to booting IPU |  | krackan1..ipu.smoke.register_access/SpacePairs |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
2 | KRACKAN1-IPU-003 | Access PCIe SRAM BAR | Amine Akrout | Data Path - PCIe Access |  | x86 to access the PCIe SRAM BAR and configure interface |  | krackan1.ipu.mmio/IpuSramAccess |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
3 | KRACKAN1-IPU-004 | Access PCIe Registers BAR | Amine Akrout | Data Path - PCIe Access |  | x86 to access the PCIe Registers BAR and configure interface |  | krackan1.ipu.smoke/IpuSmuRegisterAccess |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
4 | KRACKAN1-IPU-005 | Access PCIe SMU BAR | Amine Akrout | Data Path - PCIe Access |  | x86 to access the PCIe SMU BAR and configure interface |  | krackan1.ipu.smoke/IpuAspRegisterAccess |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  |  | 0
5 | KRACKAN1-IPU-005 | Access PCIe ASP BAR | Amine Akrout | Data Path - PCIe Access |  | x86 to access the PCIe ASP BAR and configure interface |  | krackan1.ipu.smoke/IpuRegisterAccess |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
6 | KRACKAN1-IPU-006 | PSP handshake to load mpIPU FW | Amine Akrout | Data Path - PSP |  | x86 to Communicate to PSP and load/unload mpIPU FW |  | krackan1.ipu.message/IpuCheckHeaderHash |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
7 | KRACKAN1-IPU-007 | PMFW handshake for clocks & power on mpIPU | Amine Akrout | Data Path - PMFW |  | x86 to Communicate to PMFW to Enable Clocks, Disable Clocks, etc |  | krackan1.ipu.pm/IpuPowerCycle |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
8 | KRACKAN1-IPU-009 | Load mpIPU FW into OS memory | Amine Akrout | Boot Flow |  | x86 to load mpIPU FW into OS memory |  | krackan1.ipu.message/IpuCheckHeaderHash |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
9 | KRACKAN1-IPU-010 | Communicate to mpIPU FW Management Channels | Amine Akrout | Boot Flow |  | Upon Booting the mpIPU engage with FW to configure management channels |  | krackan1.ipu.message/IpuCheckHeaderHash |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
10 | KRACKAN1-IPU-011 | Permform mpIPU FW self checks -- this checks many paths such as ADMA to AIE2 Array tile, AIE2 SHIM DMAx to DRAM | Amine Akrout | Boot Flow |  | Attempt to trigger any mpIPU FW self Tests (whatever is available) |  | krackan1.ipu.message/IpuSelfTest |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
11 | KRACKAN1-IPU-012 | Test X2I/I2X Mailbox comminucation | Amine Akrout | Data Path |  | This is the X2I whole flow which includes the interrupt test. Getting the mpIPU FW revision should suffice |  | krackan1.ipu.message/IpuCheckHeaderHash |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
12 | KRACKAN1-IPU-013 | Normal IPU Cold Boot Flow (PMFW, PSP, LX6) | Amine Akrout | Everything |  | Standard IPU Cold Boot Flow |  | krackan1.ipu.message/IpuCheckHeaderHash |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
13 | KRACKAN1-IPU-014 | Standard Use Case (IOMMUL1 bypass) | Amine Akrout | Everything |  | Standard IPU Use Case IOMMUL1 bypass |  | krackan1.ipu.partition/DpuSelfTest |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
14 | KRACKAN1-IPU-015 | Standard Use Case (IOMMUL1 8 contiguous columns ) | Amine Akrout | IOMMUL1 |  | Standard IPU Use Case IOMMUL1 single |  | krackan1.ipu.partition/DpuSelfTest | -c +.diag.ipu.iommu.translationType=GuestOnly -c +.diag.osal.psmr=DiagReserved -c +.log.root.level=Verbose -c +.diag.ipu.fw-force-loading=true -c +.diag.ipu.partition.count=1 | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
15 | KRACKAN1-IPU-016 | Standard Use Case (TNG composite test, 8 contiguous columns) | Amine Akrout | Everything |  | Composite SOV IPU Use Case |  | ipu.composite/Resnet50 |  |  |  | Legacy | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0
16 | KRACKAN1-IPU-017 | IPU Suspend | Amine Akrout | Power Management |  | Send Suspend commands to PMFW |  | krackan1.ipu.pm/IpuSuspendResume |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 0 | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0