## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | IOAPIC_1 | PCI Configuration space test | Amelie Huang | IOAPIC | PCI Configuration space test | PCI Configuration space test | P1 | CASE_1 | CDL | ./Register_Check -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
1 | IOAPIC_2 | Direct memory mapped space | Amelie Huang | IOAPIC | Direct memory mapped space | Direct memory mapped space | P2 | CASE_2 | CDL | ./Register_Check -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
2 | IOAPIC_3 | Indirect memory mapped space | Amelie Huang | IOAPIC | Indirect memory mapped space | Indirect memory mapped space | P2 | CASE_3 | CDL | ./Register_Check -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
3 | IOAPIC_4 | Register availability within address space | Amelie Huang | IOAPIC | Register availability within address space | Register availability within address space | P1 | CASE_4 | CDL | ./Register_Check -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
4 | IOAPIC_5 | Interrupt Routing (includes swizzling) | Amelie Huang | IOAPIC | Interrupt Routing (includes swizzling) | Interrupt Routing (includes swizzling) | P1 | CASE_5.1-2.0 | CDL | Covered in Bank/Interrupt Swizzling TNG: ./tng_executor -x iommu.ioapic_interrupt/VerifyInterruptRouting --class nvme -c +/diag/gpu/interruptsEnabled=false | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
5 | IOAPIC_6 | Interrupt routing with software device remap | Amelie Huang | IOAPIC | Interrupt routing with software device remap | Interrupt routing with software device remap | P2 | CASE_6 | CDL | Interrupt_Routing_With_Software_Device_Remap.sh | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK1
6 | IOAPIC_7 | Fixed Interrupt | Amelie Huang | IOAPIC | Fixed Interrupt | Fixed Interrupt | P2 | CASE_7 | TNG | ./Irq_Channel -v --delivery-mode 0 TNG: ./tng_executor -x iommu.ioapic_interrupt/VerifyFixedInterrupt --class nvme -c +/diag/gpu/interruptsEnabled=false | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
7 | IOAPIC_8 | Low Priority Interrupt | Amelie Huang | IOAPIC | Low Priority Interrupt | Low Priority Interrupt | P2 | CASE_8 | CDL | ./Irq_Channel -v --delivery-mode 1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
8 | IOAPIC_9 | NMI Interrupt | Amelie Huang | IOAPIC | NMI Interrupt | NMI Interrupt | P2 | CASE_9 | CDL | ./Nmi_Interrupt_Test -v --pin 1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
9 | IOAPIC_10 | SMI Interrupt | Amelie Huang | IOAPIC | SMI Interrupt | SMI Interrupt | P1 | CASE_10 | CDL | ./Irq_Channel -v --delivery-mode 2 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
10 | IOAPIC_11 | INIT Interrupt (Manual Observation is required) | Amelie Huang | IOAPIC | INIT Interrupt (Manual Observation is required) | INIT Interrupt (Manual Observation is required) | P1 | CASE_11 | CDL | ./Irq_Channel -v --delivery-mode 5 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
11 | IOAPIC_12 | External (Legacy) Interrupt | Amelie Huang | IOAPIC | External (Legacy) Interrupt | External (Legacy) Interrupt | P2 | CASE_12 | CDL | ./Irq_Channel -v --delivery-mode 7 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
12 | IOAPIC_13 | Mask the Interrupt | Amelie Huang | IOAPIC | Mask the Interrupt | Mask the Interrupt | P1 | CASE_13 | CDL | ./Irq_Channel -v --mask 1 --trigger-mode 0 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
13 | IOAPIC_14 | Interrupt Generation through an external device | Amelie Huang | IOAPIC | Interrupt Generation through an external device | Interrupt Generation through an external device | P2 | CASE_14 | CDL | ./Load_Ioapic --pin pin_number -v --pci-addr x:x.x | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
14 | IOAPIC_15 | Bank/Interrupt Swizzling | Amelie Huang | IOAPIC | Bank/Interrupt Swizzling | Bank/Interrupt Swizzling | P1 | CASE_15.1-2.0 | TNG | TNG Command: tng_executor -x iommu.ioapic_interrupt.VerifyPcieBridgeIntx --class iommu -c +/diag/gpu/interruptsEnabled=false CDL Command: ./Load_Ioapic -v --pci-addr x:x.xAND2: ./PCIe_Bridges_Interrupt -v --pcie --msi ./PCIe_Bridges_Interrupt -v --nbif --msi | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
15 | IOAPIC_16 | Verify Delivery Status | Amelie Huang | IOAPIC | Verify Delivery Status | Verify Delivery Status | P2 | CASE_16 | CDL | ./Delivery_Status_Check | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
16 | IOAPIC_17 | Verify Remote_IRR | Amelie Huang | IOAPIC | Verify Remote_IRR | Verify Remote_IRR | P2 | CASE_17 | CDL | ./Irq_Channel -v --irr-bit 1 --pin 0 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3