## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | IOHC_1 | Host Memory Requests | Amelie Huang | Transaction Decoding and Routing (Host) | memory require test | TNG Comamnd: tng_executor -x iohc.host_request.VerifyMemoryRequest --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Comamnd: ./Host_Request --request-type memory_request -v | P1 | CASE_1.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK1
1 | IOHC_1 | Host Memory Requests | Amelie Huang | Transaction Decoding and Routing (Host) | nbif mmio request test | ./Host_Request --request-type nbif_mmio_request -v | P1 | CASE_1.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK1
2 | IOHC_2 | Forward Configuration Requests to RSMU or L1 | Amelie Huang | Transaction Decoding and Routing (Host) | Forward Configuration Requests to RSMU or L1 | TNG Command: tng_executor -x iohc.nbio_tool.reg_accessor.scratchRegAccess --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Comamnd: ./NBIO_Tool --read-size byte --target-space nbcfgd0f0 | P2 | CASE_2.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK1
3 | IOHC_2 | Forward Configuration Requests to RSMU or L1 | Amelie Huang | Transaction Decoding and Routing (Host) | smn index access register | TNG Command: tng_executor -x iohc.nbio_tool.reg_accessor.smnAccess --class root_complex -c +/diag/gpu/interruptsEnabled=false tng_executor -x iohc.nbio_tool.reg_accessor.smnAccess64 --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Comamnd: ./NBIO_Tool --read-size byte --target-space smn_index | P2 | CASE_2.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK1
4 | IOHC_2 | Forward Configuration Requests to RSMU or L1 | Amelie Huang | Transaction Decoding and Routing (Host) | direct access register | TNG Command: tng_executor -x iohc.nbio_tool.reg_accessor.allDirectAccess_Byte --class root_complex -c +/diag/gpu/interruptsEnabled=false tng_executor -x iohc.nbio_tool.reg_accessor.allDirectAccess_Word --class root_complex -c +/diag/gpu/interruptsEnabled=false tng_executor -x iohc.nbio_tool.reg_accessor.allDirectAccess_32 --class root_complex -c +/diag/gpu/interruptsEnabled=false tng_executor -x iohc.nbio_tool.reg_accessor.allDirectAccess_64 --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Comamnd: ./NBIO_Tool --read-size byte --target-space all_direct | P2 | CASE_2.3 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK1
5 | IOHC_2 | Forward Configuration Requests to RSMU or L1 | Amelie Huang | Transaction Decoding and Routing (Host) | indirect access register | TNG Command: tng_executor -x iohc.nbio_tool.reg_accessor.allIndirectAccess_Dword --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Comamnd: ./NBIO_Tool --read-size byte --target-space all_indirect | P2 | CASE_2.4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK1
6 | IOHC_3 | Forward Configuration Requests to PCIe or nBIF | Amelie Huang | Transaction Decoding and Routing (Host) | access NBIF PCI space | ./NBIO_Tool --read-size byte --target-space nbif1cfgd8f1 | P2 | CASE_3 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
7 | IOHC_4 | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | Amelie Huang | Transaction Decoding and Routing (Host) | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | TNG Command: tng_executor -x iohc.nbio_tool.reg_accessor.psp_bar --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: ./NBIO_Tool --private-bar psp_bar -v | P1 | CASE_4.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
8 | IOHC_4 | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | Amelie Huang | Transaction Decoding and Routing (Host) | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | TNG Command: tng_executor -x iohc.nbio_tool.reg_accessor.smu_bar --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: ./NBIO_Tool --private-bar smu_bar -v | P1 | CASE_4.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
9 | IOHC_4 | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | Amelie Huang | Transaction Decoding and Routing (Host) | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | ./NBIO_Tool --private-bar ioapic_bar -v | P1 | CASE_4.3 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
10 | IOHC_4 | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | Amelie Huang | Transaction Decoding and Routing (Host) | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | ./NBIO_Tool --private-bar fastreg_bar -v | P1 | CASE_4.4 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
11 | IOHC_4 | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | Amelie Huang | Transaction Decoding and Routing (Host) | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | ./NBIO_Tool --private-bar dbg_bar -v | P1 | CASE_4.5 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
12 | IOHC_4 | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | Amelie Huang | Transaction Decoding and Routing (Host) | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | ./NBIO_Tool --private-bar fastregcntl_bar -v | P1 | CASE_4.6 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
13 | IOHC_4 | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | Amelie Huang | Transaction Decoding and Routing (Host) | Private IOHC BAR (IOMMU, IOAPIC,1M Fast Reg, 4k Fast Regs Control, SMU, DBG, PSP) | ./NBIO_Tool --private-bar smmu_bar -v | P1 | CASE_4.7 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
14 | IOHC_5 | PCIe bridge memory requests | Amelie Huang | Transaction Decoding and Routing (Host) | PCIe bridge memory requests | TNG Command: ./tng_executor -x iohc.bridge.Memory_Request --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: ./Host_Request --request-type memory_request -v | P1 | CASE_5 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK4
15 | IOHC_6 | nBIF bridge memory requests | Amelie Huang | Transaction Decoding and Routing (Host) | nBIF bridge memory requests | TNG Command: ./tng_executor -x iohc.bridge.Memory_Request --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: ./Host_Request --request-type memory_request -v | P1 | CASE_6 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK1
16 | IOHC_7 | I/O Requests to PCIe/nBIF, check subtractive decode | Amelie Huang | Transaction Decoding and Routing (Host) | I/O Requests to PCIe/nBIF, check subtractive decode | TNG Comamnd: tng_executor -x iohc.host_request.VerifyIORequest --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: ./Host_Request --request-type io_request -v(subtractive decode to be verified by Ruby script depending on if the performance counters are working) | P2 | CASE_7 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK4
17 | IOHC_8 | Breaking Special Host Requests to 1DW | Amelie Huang | Transaction Decoding and Routing (Host) | Breaking Special Host Requests to 1DW | ./Host_Request -v --request-type break_up_request --split-request-size 16 --split-request-type split_write | P2 | CASE_8 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
18 | IOHC_9 | Conversion of Non-Posted Writes into Posted writes | Amelie Huang | Transaction Decoding and Routing (Host) | Conversion of Non-Posted Writes into Posted writes | TNG Comamnd: tng_executor -x iohc.host_request.VerifyNonPostWriteErrorRequest --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: ./Host_Request --request-type np_to_p_request -v | P2 | CASE_9 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
19 | IOHC_10 | IOHC internal registers access | Amelie Huang | Transaction Decoding and Routing (Host) | access psp bar | ./NBIO_Tool --private-bar psp_bar -v | P2 | CASE_10.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
20 | IOHC_10 | IOHC internal registers access | Amelie Huang | Transaction Decoding and Routing (Host) | access smu bar | ./NBIO_Tool --private-bar smu_bar -v | P2 | CASE_10.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
21 | IOHC_10 | IOHC internal registers access | Amelie Huang | Transaction Decoding and Routing (Host) | access ioapic bar | ./NBIO_Tool --private-bar ioapic_bar -v | P2 | CASE_10.3 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
22 | IOHC_10 | IOHC internal registers access | Amelie Huang | Transaction Decoding and Routing (Host) | access dbg bar | ./NBIO_Tool --private-bar dbg_bar -v | P2 | CASE_10.4 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
23 | IOHC_10 | IOHC internal registers access | Amelie Huang | Transaction Decoding and Routing (Host) | access fastreg bar | ./NBIO_Tool --private-bar fastreg_bar -v | P2 | CASE_10.5 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
24 | IOHC_10 | IOHC internal registers access | Amelie Huang | Transaction Decoding and Routing (Host) | access fastreg cntl bar | ./NBIO_Tool --private-bar fastregcntl_bar -v | P2 | CASE_10.6 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
25 | IOHC_10 | IOHC internal registers access | Amelie Huang | Transaction Decoding and Routing (Host) | access smmu bar | ./NBIO_Tool --private-bar smmu_bar -v | P2 | CASE_10.7 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK2
26 | IOHC_11 | Bus Master Disabled Bridge | Amelie Huang | Transaction Decoding and Routing (DMA) | Upstram read request when Bus Master Disabled Bridge | ./UPStream_Request --target-type Default_Range -v --dma-type read --bus-master-disabled-bridge 1 --dgpu-only | P2 | CASE_11.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
27 | IOHC_11 | Bus Master Disabled Bridge | Amelie Huang | Transaction Decoding and Routing (DMA) | Upstram write request when Bus Master Disabled Bridge | ./UPStream_Request --target-type Default_Range -v --dma-type write --bus-master-disabled-bridge 1 --dgpu-only | P2 | CASE_11.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
28 | IOHC_12 | DMA requests (regular DRAM address, TOM decoding) | Amelie Huang | Transaction Decoding and Routing (DMA) | DMA read requests in Default Range | TNG Command: ./tng_executor -x iohc.UpstreamRequest/DMA2DefaultRange--class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: /UPStream_Request --target-type Default_Range -v --dma-type read --dgpu-only | P1 | CASE_12.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
29 | IOHC_12 | DMA requests (regular DRAM address, TOM decoding) | Amelie Huang | Transaction Decoding and Routing (DMA) | DMA write requests in Default Range | TNG Command: ./tng_executor -x iohc.UpstreamRequest/DMA2DefaultRange--class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Command: /UPStream_Request --target-type Default_Range -v --dma-type write --dgpu-only | P1 | CASE_12.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
30 | IOHC_12 | DMA requests (regular DRAM address, TOM decoding) | Amelie Huang | Transaction Decoding and Routing (DMA) | DMA read requests in TOM Range | ./UPStream_Request --target-type TOM_Range -v --dma-type read --dgpu-only (raphael grub setting with mem=2500M) | P1 | CASE_12.3 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
31 | IOHC_12 | DMA requests (regular DRAM address, TOM decoding) | Amelie Huang | Transaction Decoding and Routing (DMA) | DMA write requests in TOM Range | ./UPStream_Request --target-type TOM_Range -v --dma-type write --dgpu-only (raphael grub setting with mem=2500M) | P1 | CASE_12.4 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
32 | IOHC_12 | DMA requests (regular DRAM address, TOM decoding) | Amelie Huang | Transaction Decoding and Routing (DMA) | DMA read requests in TOM2 Range | ./UPStream_Request --target-type TOM2_Range -v --dma-type read --dgpu-only | P1 | CASE_12.5 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
33 | IOHC_12 | DMA requests (regular DRAM address, TOM decoding) | Amelie Huang | Transaction Decoding and Routing (DMA) | DMA write requests in TOM2 Range | ./UPStream_Request --target-type TOM2_Range -v --dma-type write --dgpu-only | P1 | CASE_12.6 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
34 | IOHC_12 | DMA requests (regular DRAM address, TOM decoding) | Amelie Huang | Transaction Decoding and Routing (DMA) | DMA read requests in TOM3 Range | ./UPStream_Request --dma-type read_no_verify --transfer-size 1MiB --target-type TOM3_Range --target-address 0x300040000 --tom3-address 0x300000000 -v --dgpu-only | P1 | CASE_12.7 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
35 | 1 | P2P decode | Amelie Huang | Transaction Decoding and Routing (DMA) | P2p Mode 0 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 0 -v --dgpu-only |  | CASE_13.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0
36 | IOHC_13 | P2P decode | Amelie Huang | Transaction Decoding and Routing (DMA) | P2p Mode 1 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 1 -v --dgpu-only | P1 | CASE_13.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
37 | IOHC_13 | P2P decode | Amelie Huang | Transaction Decoding and Routing (DMA) | P2p Mode 2 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 2 -v --dgpu-only | P1 | CASE_13.3 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
38 | IOHC_13 | P2P decode | Amelie Huang | Transaction Decoding and Routing (DMA) | P2p Mode 3 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 3 -v --dgpu-only | P1 | CASE_13.4 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
39 | IOHC_14 | Mutex | Amelie Huang | IOHC Features | Mutex | TNG Command: tng_executor -x iohc.nbio_tool.reg_accessor.mutexSchemeAccess --class root_complex -c +/diag/gpu/interruptsEnabled=false CDL Comand: ./NBIO_Tool --test-mutex-scheme | P2 | CASE_14 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
40 | IOHC_15 | Bridge Enablement | Amelie Huang | IOHC Features | Specifies the SMN register for the bridge , then access memory | ./Host_Request --request-type memory_request --bridge-enablement 0 --iohc-bridge-cntl-reg-smn-addr 0x13b31404 -v TNG: tng_executor -x iohc.bridge.Memory_Request/VerifyMemReq2GpuWithBridgeDisable --class root_complex tng_executor -x iohc.bridge.Memory_Request/VerifyMemReq2NvmeWithBridgeDisable --class root_complex | P1 | CASE_15.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK5
41 | IOHC_15 | Bridge Enablement | Amelie Huang | IOHC Features | Specifies the SMN register for the bridge , then access nbif_mmio_space | ./Host_Request --request-type nbif_mmio_request --bridge-enablement 0 --iohc-bridge-cntl-reg-smn-addr 0x13b38004 -v ./Host_Request --request-type nbif_mmio_request --bridge-enablement 0 --iohc-bridge-cntl-reg-smn-addr 0x13b38404 -v ./Host_Request --request-type nbif_mmio_request --bridge-enablement 0 --iohc-bridge-cntl-reg-smn-addr 0x13b38804 -v TNG: tng_executor -x iohc.bridge.Memory_Request/VerifyMemReq2GpuWithBridgeDisable --class root_complex | P1 | CASE_15.2 | CDL |  | 3 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 |  |  |  |  | 1 | [6 empty] | 0 |  | WK5
42 | IOHC_15 | Bridge Enablement | Amelie Huang | IOHC Features | Bridge Enablement PCI D3 power status, data copy. | ./Host_Request --request-type non_d0_host -v | P1 | CASE_15.3 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK5
43 | IOHC_16 | Atomics ops | Amelie Huang | IOHC Features | Atomics ops : FetchAdd | ./IOHC_AtomicsOps --request-type FetchAdd -v --dgpu-only | P2 | CASE_16.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
44 | IOHC_16 | Atomics ops | Amelie Huang | IOHC Features | Atomics ops : Swap | ./IOHC_AtomicsOps --request-type swap -v --dgpu-only | P2 | CASE_16.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
45 | IOHC_16 | Atomics ops | Amelie Huang | IOHC Features | Atomics ops : CAS: campare data | ./IOHC_AtomicsOps --request-type cas -v --cmp-data 0x55aaaa55 --dgpu-only | P2 | CASE_16.3 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
46 | IOHC_16 | Atomics ops | Amelie Huang | IOHC Features | Atomics ops: CAS Campare and swap | ./IOHC_AtomicsOps --request-type cas -v --cmp-data 0x55aaaa55 --cas-swap --dgpu-only | P2 | CASE_16.4 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
47 | IOHC_17 | P2P Atomics | Amelie Huang | IOHC Features | p2p mode 0 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 0 -v --dgpu-only | P1 | CASE_17.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
48 | IOHC_17 | P2P Atomics | Amelie Huang | IOHC Features | p2p mode 1 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 1 -v --dgpu-only | P1 | CASE_17.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
49 | IOHC_17 | P2P Atomics | Amelie Huang | IOHC Features | p2p mode 2 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 2 -v --dgpu-only | P1 | CASE_17.3 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
50 | IOHC_17 | P2P Atomics | Amelie Huang | IOHC Features | p2p mode 3 test | ./UPStream_Request --target-type Peer_To_Peer --p2p-mode 3 -v --dgpu-only | P1 | CASE_17.4 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
51 | IOHC_18 | SMN Mastered SDP requests(SDP Master Request) | Amelie Huang | Remote SMU | SMN Mastered SDP requests(SDP Master Request) | ./Sdp_Master_Request -v --target "Scratch_0"./Sdp_Master_Request -v --target "MMIO" --num-dw 0 | P2 | CASE_18 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK5
52 | IOHC_19 | RSMU Register Access Interface Signals (RSMU AXI Master) | Amelie Huang | Remote SMU | RSMU Register Access Interface Signals (RSMU AXI Master) | Covered in Forward Configuration Requests to RSMU or L1 with SMN | P2 | CASE_19 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
53 | IOHC_20 | Register Aperture ID Map | Amelie Huang | Remote SMU | Register Aperture ID Map | Covered in Forward Configuration Requests to RSMU or L1 | P2 | CASE_20 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK5
54 | IOHC_21 | Indirect Register Access Scheme with 64 bit | Amelie Huang | Remote SMU | Indirect Register Access Scheme with 64 bit | ./NBIO_Tool --read-size dword --target-space smn_index_regs_64bit -v | P2 | CASE_21 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK5
55 | IOHC_22 | CPU Direct Register Access Scheme | Amelie Huang | IOHC Features | CPU Direct Register Access Scheme | ./NBIO_Tool --test-fastregs --cpu 0 | P2 | CASE_22 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK5
56 | IOHC_23 | PSP/SMU Blocking CPU/SDF NP | Amelie Huang | PSP / SMU related Features | PSP Blocking CPU/SDF NP | ./IOHC_Psp_Smu_Blocking_Cpu --psp-block-test --mem-test -v | P2 | CASE_23.1 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
57 | IOHC_23 | PSP/SMU Blocking CPU/SDF NP | Amelie Huang | PSP / SMU related Features | SMU Blocking CPU/SDF NP | ./IOHC_Psp_Smu_Blocking_Cpu --smu-block-test --mem-test -v | P2 | CASE_23.2 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3
58 | IOHC_24 | Dynamic clock gating | Amelie Huang | PMM Features | Dynamic clock gating | ./IOHC_Clk_Gating --ctrl-clk ctrl0_clk0 --test-clk-gating 0 | P1 | CASE_24 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  |  | 1 | [6 empty] | 0 |  | WK3