## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | UMC-001 | Stress Test | Manzoor | UMC |  | Memory | P1 | UMC-TEST-001.1-4.0 | TNG | ./tng_executor -d phoenix/cpu -c +/diag/gpu/interruptsEnabled=false umc.memorysequentialaccess/SEQ_WB8_96M_CBH --instance logical_cpu:all | 1 | 4 | Legacy | 1 | 4 | 1 |  |  | 0 |  |  |  |  | 0 |  | 4 | 4 |  |  |  | 1 |  | wk-1
1 | UMC-002 | Memory Exerciser | Manzoor | UMC |  | Memory | P3 | UMC-TEST-002.1-20.0 | TNG | ./tng_executor -d phoenix/cpu -c +/diag/gpu/interruptsEnabled=false umc.memorysequentialaccess/SEQ_WB1_96M_MPV2_STEP128 --instance logical_cpu:all | 1 | 20 | Legacy | 1 | 20 | 1 | N-1 | 20 | 20 | 20 |  |  |  | 1 |  | 20 | 20 |  |  |  | 1 | Using Memory_Exerciser_Express | wk-1
2 | UMC-003 | Memory_p_state | Manzoor | UMC |  | Memory_p_state | P2 | UMC-TEST-003 | CDL | /CPU/Validation/Support/Script/validation_script.rb /CPU/Validation/Functional_Block/Memory/GME_Mem_Pstate.yaml | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Need to wait for POR MemClk Speed | wk-8
3 | UMC-004 | DRAM Maximum Utilization | Manzoor | UMC |  | DRAM Maximum Utilization | P1 | UMC-TEST-004 | CDL | #DRAM Maximum Utilization: ./DRAM_Maximum_Utilization --run-time 10m --reserve-memory 0 ./DRAM_Maximum_Utilization -t 64 --reserve-memory 0 #We need to use GPU to generate UMC traffic to saturate DCQ so we can check DCQ_Occupancy_GT90. the following steps will do it: ./UMC_PMC_Test -v --only-set-pmc-event 1 --event 0x21 ./tserverlite -no_toollib -load_ucode=tcore -nobios -disable_libdce -skiptextbuffering -skip_consoleblank_check -skip_iommu_check -pm4ib=system -pm4rb=system -tc_TCorePreferSysmemInternally -log -d=1 -test=umc56.25 ./UMC_PMC_Test -v --read-pmc-event-all-ch 1 --event 0x21 | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1
4 | UMC-005 | Early Page Activate (EPA) | Manzoor | UMC |  | Early Page Activate (EPA) | P1 | UMC-TEST-005 | CDL | ./Early_Page_Activate -v | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-2
5 | UMC-006 | Patrol Scrub Indicator on MCA status register | Manzoor | UMC |  | Patrol Scrub Indicator on MCA status register | P1 | UMC-TEST-006 | CDL | Utilize Diag from RAS team | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 1 |  |  | 1 | This is for Server program, RAS team do not support this for client program | wk-6
6 | UMC-007 | DCQ Read/Write Queue | Manzoor | UMC |  | DCQ_Read_Write_Queue | P3 | UMC-TEST-007 | CDL | ./CPU/Memory_Suite/DCQ_Read_Write_Queue.rb -v | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1 | 2
7 | UMC-008 | MEM Memory Throughput | Manzoor | UMC |  | Memory_Throughput | P3 | UMC-TEST-008 | CDL | ./Memory_Throughput --target-node 0 ./Memory_Throughput -v | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-2
8 | UMC-009 | General Memory Exerciser and P State Irritator | Manzoor | UMC |  | General Memory Exerciser and P State Irritator | P2 | UMC-TEST-009 | CDL | GME + PMM /CPU/Validation/Support/Script/validation_script.rb /CPU/Validation/Functional_Block/Memory/GME_Mem_Pstate.yaml | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-8
9 | UMC-010 | DDR Interface Margining Enhancements | Manzoor | UMC |  | No new development required | P1 | UMC-TEST-010 | CDL | ./Margin_Stress --show-memmap ./Margin_Stress --show-ranges ./Margin_Stress -v --base 4096 ./Margin_Stress -v --base 5120 ./Margin_Stress -v --dram-controller 0 --target-node 0 | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-2
10 | UMC-011 | DDR Address Map | Manzoor | UMC |  | No new development required | P2 | UMC-TEST-011 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
11 | UMC-012 | Basic_Coherency_Check_WAW | Manzoor | UMC |  | Basic_Coherency_Check_WAW | P1 | UMC-TEST-012 | CDL | ./Basic_Coherency_Check_SLT --WAW --cpu 0,1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-1
12 | UMC-013 | Basic_Coherency_Check_RAW | Manzoor | UMC |  | Basic_Coherency_Check_RAW | P1 | UMC-TEST-013 | CDL | ./Basic_Coherency_Check_SLT --RAW | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-1
13 | UMC-014 | Priority mapping | Manzoor | UMC |  | Cmobination of MaxByass Test | P2 | UMC-TEST-014 | CDL | ./Max_Bypass_Priority_Adjustment -v | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-2
14 | UMC-015 | Max bypass priority adjustment | Manzoor | UMC |  | LLTO Traffic Generator is complicated | P1 | UMC-TEST-015 | CDL | ./Max_Bypass_Priority_Adjustment -v | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-2
15 | UMC-016 | Performance monitor events | Manzoor | UMC |  | UMC_PMC_Test GME with Performance Monitors | P2 | UMC-TEST-016.1-16.0 | CDL | ./CPU/linux/Memory_Suite/UMC_PMC_Test -v --channel-index 0 --pmc-nu-0-to-4 0 --event 0x1b --launch-gme 1 | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 16 | 16 |  |  |  | 1 |  | 16 | 16 |  |  |  | 1 |  | wk-2
16 | UMC-017 | All Bank Auto-refresh | Manzoor | UMC |  | Auto_Refresh_Bank | P1 | UMC-TEST-017 | CDL | ./Auto_Refresh_Bank -v --auto-ref-opt 3 --trefi 3 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
17 | UMC-018 | Slave Error on non-existent register access | Manzoor | UMC |  | Non_Existent_Register | P3 | UMC-TEST-018 | CDL | ./Non_Existent_Register -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
18 | UMC-019 | VDDP_Limiter | Manzoor | UMC |  | VDDP_Limiter | P3 | UMC-TEST-019 | CDL | ./VDDP_Limiter --cycle-time-hi 4 --cycle-loops 2 | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1
19 | UMC-020 | Memclk_Bubble | Manzoor | UMC |  | Memclk_Bubble | P3 | UMC-TEST-020 | CDL | ./Memclk_Bubble --cpu all -t 30 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-1
20 | UMC-021 | DDR_Data_Rate | Manzoor | UMC |  | DDR_Data_Rate | P3 | UMC-TEST-021 | CDL | ./DDR_Data_Rate | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-1
21 | UMC-022 | Row_Address_Hammer | Manzoor | UMC |  | Row_Address_Hammer | P2 | UMC-TEST-022 | CDL | ./Row_Hammer -v -t 10m --cpu 0:all --shared-memory-key 1003 --pair0 0x248000 --pair1 0x328000 --base-address 0x200000000 | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1
22 | UMC-023 | LPDDR5 Link ECC | Manzoor | UMC |  | LPDDR5 Link ECC | P2 | UMC-TEST-023 | CDL | ./VDDP_Limiter_rx_r1 -v --umc0-bank 11 --injection-type 1 --target-code-word 2 --which-bit-flip 1 --override-reviewed-on-cpu --target-umc 0 | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-6
23 | UMC-024 | DDR Protocol | Manzoor | UMC |  | DDR Protocol | P1 | UMC-TEST-024 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1
24 | UMC-025 | LPDDR5 Support | Manzoor | UMC |  | LPDDR5 Support | P2 | UMC-TEST-025 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1
25 | UMC-026 | Support FCLK<UCLK (with VDCI) for DDR5 | Manzoor | UMC |  | Support FCLK<UCLK (with VDCI) for DDR5 | P1 | UMC-TEST-026 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-4
26 | UMC-027 | Support FCLK<UCLK (with SyncFIFO) for DDR5 | Manzoor | UMC |  | Support FCLK<UCLK (with SyncFIFO) for DDR5 | P1 | UMC-TEST-027 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-4
27 | UMC-028 | RFM Support | Manzoor | UMC |  | RFM Support | P1 | UMC-TEST-028.1-16.0 | CDL |  | 1 | 16 | New | 1 | 16 | 1 | N-1 | 16 | 16 | 16 |  |  |  | 1 |  | 16 | 16 |  |  |  | 1 |  | wk-2
28 | UMC-029 | LPDDR5 density (BG Mode) 2/4/6/8/12/16/24/32 Gb | Manzoor | UMC |  | LPDDR5 density (BG Mode) 2/4/6/8/12/16/24/32 Gb | P1 | UMC-TEST-029 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1
29 | UMC-030 | LPDDR5 Burst length 16 | Manzoor | UMC |  | LPDDR5 Burst length 16 | P1 | UMC-TEST-030 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | Legacy | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-1 | As per availability, validation of density
30 | UMC-031 | LPDDR5 deep sleep support | Manzoor | UMC |  | LPDDR5 deep sleep support | P2 | UMC-TEST-031 | CDL | ./Memory_Pstate -v --smu-msg-id 0x83 --target-mem-pstate 0 --channel-index 0 | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-6
31 | UMC-032 | DDR5 5600 MT/s devices Density | Manzoor | UMC |  | DDR5 5200 MT/s devices Density | P1 | UMC-TEST-032 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-6
32 | UMC-033 | LPDDR5-7500 MT/s 4x32bit channel devices Density | Manzoor | UMC |  | LPDDR5-6400 4x32bit channel devices Density | P1 | UMC-TEST-033 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-6
33 | UMC-034 | Support for self-refresh entry with PHY in LP1 | Manzoor | UMC |  | Support for self-refresh entry with PHY in LP1 | P1 | UMC-TEST-034 | CDL | ./Memory_Pstate -v --smu-msg-id 0x83 --target-mem-pstate 1 --channel-index 1 | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-4
34 | UMC-035 | Support for self-refresh entry with PHY in LP2 | Manzoor | UMC |  | Support for self-refresh entry with PHY in LP2 | P1 | UMC-TEST-035 | CDL | ./Memory_Pstate -v --smu-msg-id 0x83 --target-mem-pstate 2 --channel-index 0 | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-4
35 | UMC-036 | Support DDR5 on-die ECC | Manzoor | UMC |  | Support DDR5 on-die ECC | P2 | UMC-TEST-036 | CDL | ./Decode_Sys_Phy_Addr --information-only | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | wk-6
36 | UMC-037 | WCCAHP Memory Exerciser using Write Combining with Checkerboard Address Hash Pattern | Manzoor | UMC |  | byte access;Write Combining;Checkerboard Address Hash pattern word access;Write Combining;Checkerboard Address Hash pattern doubleword access;Write Combining;Checkerboard Address Hash pattern quadword access;Write Combining;Checkerboard Address Hash pattern double quadword access;Write Combining;Checkerboard Address Hash pattern 256-bit access;Write Combining;Checkerboard Address Hash pattern 512-bit access;Write Combining;Checkerboard Address Hash pattern | P3 | UMC-TEST-037.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 1 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
37 | UMC-038 | WBCAHP Memory Exerciser using Write Back with Checkerboard Address Hash Pattern | Manzoor | UMC |  | byte access;Write Back;Checkerboard Address Hash pattern word access;Write Back;Checkerboard Address Hash pattern doubleword access;Write Back;Checkerboard Address Hash pattern quadword access;Write Back;Checkerboard Address Hash pattern double quadword access;Write Back;Checkerboard Address Hash pattern 256-bit access;Write Back;Checkerboard Address Hash pattern 512-bit access;Write Back;Checkerboard Address Hash pattern | P1 | UMC-TEST-038.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 2 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
38 | UMC-039 | UCCAHP Memory Exerciser using Unchachable with Checkerboard Address Hash Pattern | Manzoor | UMC |  | byte access;Unchachable;Checkerboard Address Hash pattern word access;Unchachable;Checkerboard Address Hash pattern doubleword access;Unchachable;Checkerboard Address Hash pattern quadword access;Unchachable;Checkerboard Address Hash pattern double quadword access;Unchachable;Checkerboard Address Hash pattern 256-bit access;Unchachable;Checkerboard Address Hash pattern 512-bit access;Unchachable;Checkerboard Address Hash pattern | P2 | UMC-TEST-039.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 4 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
39 | UMC-040 | WTCAHP Memory Exerciser using Write Through with Checkerboard Address Hash Pattern | Manzoor | UMC |  | byte access;Write Through;Checkerboard Address Hash pattern word access;Write Through;Checkerboard Address Hash pattern doubleword access;Write Through;Checkerboard Address Hash pattern quadword access;Write Through;Checkerboard Address Hash pattern double quadword access;Write Through;Checkerboard Address Hash pattern 256-bit access;Write Through;Checkerboard Address Hash pattern 512-bit access;Write Through;Checkerboard Address Hash pattern | P1 | UMC-TEST-040.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 8 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
40 | UMC-041 | WCCRCAH Memory Exerciser using Write Combining with CRC Address Hash Pattern | Manzoor | UMC |  | byte access;Write Combining;CRC Address Hash word access;Write Combining;CRC Address Hash doubleword access;Write Combining;CRC Address Hash quadword access;Write Combining;CRC Address Hash double quadword access;Write Combining;CRC Address Hash 256-bit access;Write Combining;CRC Address Hash 512-bit access;Write Combining;CRC Address Hash | P1 | UMC-TEST-041.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 16 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
41 | UMC-042 | WBCRCAH Memory Exerciser using Write Back with CRC Address Hash Pattern | Manzoor | UMC |  | byte access;Write Back;CRC Address Hash word access;Write Back;CRC Address Hash doubleword access;Write Back;CRC Address Hash quadword access;Write Back;CRC Address Hash double quadword access;Write Back;CRC Address Hash 256-bit access;Write Back;CRC Address Hash 512-bit access;Write Back;CRC Address Hash | P1 | UMC-TEST-042.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 1 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
42 | UMC-043 | UCCRCAH Memory Exerciser using Unchachable with CRC Address Hash Pattern | Manzoor | UMC |  | byte access;Unchachable;CRC Address Hash word access;Unchachable;CRC Address Hash doubleword access;Unchachable;CRC Address Hash quadword access;Unchachable;CRC Address Hash double quadword access;Unchachable;CRC Address Hash 256-bit access;Unchachable;CRC Address Hash 512-bit access;Unchachable;CRC Address Hash | P3 | UMC-TEST-043.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 2 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
43 | UMC-044 | WTCRCAH Memory Exerciser using Wrkte Through with CRC Address Hash Pattern | Manzoor | UMC |  | byte access;Write Through;CRC Address Hash word access;Write Through;CRC Address Hash doubleword access;Write Through;CRC Address Hash quadword access;Write Through;CRC Address Hash double quadword access;Write Through;CRC Address Hash 256-bit access;Write Through;CRC Address Hash 512-bit access;Write Through;CRC Address Hash | P2 | UMC-TEST-044.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 4 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
44 | UMC-045 | WCCVP Memory Exerciser using Write Combining with Compressed Value Pattern | Manzoor | UMC |  | byte access;Write Combining;Compressed Value patterns word access;Write Combining;Compressed Value patterns doubleword access;Write Combining;Compressed Value patterns quadword access;Write Combining;Compressed Value patterns double quadword access;Write Combining;Compressed Value patterns 256-bit access;Write Combining;Compressed Value patterns 512-bit access;Write Combining;Compressed Value patterns | P1 | UMC-TEST-045.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 8 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
45 | UMC-046 | WBCVP Memory Exerciser using Write Back with Compressed Value Pattern | Manzoor | UMC |  | byte access;Write Back;Compressed Value patterns word access;Write Back;Compressed Value patterns doubleword access;Write Back;Compressed Value patterns quadword access;Write Back;Compressed Value patterns double quadword access;Write Back;Compressed Value patterns 256-bit access;Write Back;Compressed Value patterns 512-bit access;Write Back;Compressed Value patterns | P3 | UMC-TEST-046.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 16 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
46 | UMC-047 | UCCVP Memory Exerciser using Unchachable with Compressed Value Pattern | Manzoor | UMC |  | byte access;Unchachable;Compressed Value patterns word access;Unchachable;Compressed Value patterns doubleword access;Unchachable;Compressed Value patterns quadword access;Unchachable;Compressed Value patterns double quadword access;Unchachable;Compressed Value patterns 256-bit access;Unchachable;Compressed Value patterns 512-bit access;Unchachable;Compressed Value patterns | P2 | UMC-TEST-047.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 1 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
47 | UMC-048 | WTCVP Memory Exerciser using Write Through with Compressed Value Pattern | Manzoor | UMC |  | byte access;Write Through;Compressed Value patterns word access;Write Through;Compressed Value patterns doubleword access;Write Through;Compressed Value patterns quadword access;Write Through;Compressed Value patterns double quadword access;Write Through;Compressed Value patterns 256-bit access;Write Through;Compressed Value patterns 512-bit access;Write Through;Compressed Value patterns | P1 | UMC-TEST-048.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 2 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
48 | UMC-049 | WCMPV1 Memory Exerciser using Write Combining with MPV1 Pattern | Manzoor | UMC |  | byte access;Write Combining;MPV1 patterns word access;Write Combining;MPV1 patterns doubleword access;Write Combining;MPV1 patterns quadword access;Write Combining;MPV1 patterns double quadword access;Write Combining;MPV1 patterns 256-bit access;Write Combining;MPV1 patterns 512-bit access;Write Combining;MPV1 patterns | P2 | UMC-TEST-049.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 4 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
49 | UMC-050 | WBMPV1 Memory Exerciser using Write Back with MPV1 Pattern | Manzoor | UMC |  | byte access;Write Back;MPV1 patterns word access;Write Back;MPV1 patterns doubleword access;Write Back;MPV1 patterns quadword access;Write Back;MPV1 patterns double quadword access;Write Back;MPV1 patterns 256-bit access;Write Back;MPV1 patterns 512-bit access;Write Back;MPV1 patterns | P1 | UMC-TEST-050.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 8 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
50 | UMC-051 | UCMP1 Memory Exerciser using Unchachable with MPV1 Pattern | Manzoor | UMC |  | byte access;Unchachable;MPV1 patterns word access;Unchachable;MPV1 patterns doubleword access;Unchachable;MPV1 patterns quadword access;Unchachable;MPV1 patterns double quadword access;Unchachable;MPV1 patterns 256-bit access;Unchachable;MPV1 patterns 512-bit access;Unchachable;MPV1 patterns | P2 | UMC-TEST-051.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 16 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
51 | UMC-052 | WTMPV1 Memory Exerciser using Write Through with MPV1 Pattern | Manzoor | UMC |  | byte access;Write Through;MPV1 patterns word access;Write Through;MPV1 patterns doubleword access;Write Through;MPV1 patterns quadword access;Write Through;MPV1 patterns double quadword access;Write Through;MPV1 patterns 256-bit access;Write Through;MPV1 patterns 512-bit access;Write Through;MPV1 patterns | P3 | UMC-TEST-052.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WT --access-size 1 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
52 | UMC-053 | WCMPV2 Memory Exerciser using Write Combining with MPV2 Pattern | Manzoor | UMC |  | byte access;Write Combining;MPV2 patterns word access;Write Combining;MPV2 patterns doubleword access;Write Combining;MPV2 patterns quadword access;Write Combining;MPV2 patterns double quadword access;Write Combining;MPV2 patterns 256-bit access;Write Combining;MPV2 patterns 512-bit access;Write Combining;MPV2 patterns | P1 | UMC-TEST-053.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WT --access-size 2 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
53 | UMC-054 | WBMPV2 Memory Exerciser using Write Combining with MPV2 Pattern | Manzoor | UMC |  | byte access;Write Back;MPV2 patterns word access;Write Back;MPV2 patterns doubleword access;Write Back;MPV2 patterns quadword access;Write Back;MPV2 patterns double quadword access;Write Back;MPV2 patterns 256-bit access;Write Back;MPV2 patterns 512-bit access;Write Back;MPV2 patterns | P3 | UMC-TEST-054.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WT --access-size 4 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
54 | UMC-055 | UCMPV2 Memory Exerciser using Unchachable with MPV2 Pattern | Manzoor | UMC |  | byte access;Unchachable;MPV2 patterns word access;Unchachable;MPV2 patterns doubleword access;Unchachable;MPV2 patterns quadword access;Unchachable;MPV2 patterns double quadword access;Unchachable;MPV2 patterns 256-bit access;Unchachable;MPV2 patterns 512-bit access;Unchachable;MPV2 patterns | P1 | UMC-TEST-055.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WT --access-size 8 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
55 | UMC-056 | WTMPV2 Memory Exerciser using Write Through with MPV2 Pattern | Manzoor | UMC |  | byte access;Write Through;MPV2 patterns word access;Write Through;MPV2 patterns doubleword access;Write Through;MPV2 patterns quadword access;Write Through;MPV2 patterns double quadword access;Write Through;MPV2 patterns 256-bit access;Write Through;MPV2 patterns 512-bit access;Write Through;MPV2 patterns | P3 | UMC-TEST-056.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WT --access-size 16 --block-size 0x2000000 --pattern 1 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
56 | UMC-057 | WC0HP Memory Exerciser using Write Combining with Zero Hash Pattern | Manzoor | UMC |  | byte access;Write Combining;Zero hash pattern word access;Write Combining;Zero hash pattern doubleword access;Write Combining;Zero hash pattern quadword access;Write Combining;Zero hash pattern double quadword access;Write Combining;Zero hash pattern 256-bit access;Write Combining;Zero hash pattern 512-bit access;Write Combining;Zero hash pattern | P3 | UMC-TEST-057.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 1 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
57 | UMC-058 | WB0HP Memory Exerciser using Write Back with Zero Hash Pattern | Manzoor | UMC |  | byte access;Write Back;Zero hash pattern word access;Write Back;Zero hash pattern doubleword access;Write Back;Zero hash pattern quadword access;Write Back;Zero hash pattern double quadword access;Write Back;Zero hash pattern 256-bit access;Write Back;Zero hash pattern 512-bit access;Write Back;Zero hash pattern | P3 | UMC-TEST-058.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 2 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
58 | UMC-059 | UC0HP Memory Exerciser using Unchachable with Zero Hash Pattern | Manzoor | UMC |  | byte access;Unchachable;Zero hash pattern word access;Unchachable;Zero hash pattern doubleword access;Unchachable;Zero hash pattern quadword access;Unchachable;Zero hash pattern double quadword access;Unchachable;Zero hash pattern 256-bit access;Unchachable;Zero hash pattern/ 512-bit access;Unchachable;Zero hash pattern | P3 | UMC-TEST-059.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 4 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
59 | UMC-060 | WT0HP Memory Exerciser using Write Through with Zero Hash Pattern | Manzoor | UMC |  | byte access;Write Through;Zero hash pattern word access;Write Through;Zero hash pattern doubleword access;Write Through;Zero hash pattern quadword access;Write Through;Zero hash pattern double quadword access;Write Through;Zero hash pattern 256-bit access;Write Through;Zero hash pattern 512-bit access;Write Through;Zero hash pattern | P3 | UMC-TEST-060.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 8 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
60 | UMC-061 | WC1HP Memory Exerciser using Write Combining with One Hash Pattern | Manzoor | UMC |  | byte access;Write Combining;One hash pattern word access;Write Combining;One hash pattern doubleword access;Write Combining;One hash pattern quadword access;Write Combining;One hash pattern double quadword access;Write Combining;One hash pattern 256-bit access;Write Combining;One hash pattern 512-bit access;Write Combining;One hash pattern | P2 | UMC-TEST-061.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WC --access-size 16 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
61 | UMC-062 | WB1HP Memory Exerciser using Write Bac, with One Hash Pattern | Manzoor | UMC |  | byte access;Write Back;One hash pattern word access;Write Back;One hash pattern doubleword access;Write Back;One hash pattern quadword access;Write Back;One hash pattern double quadword access;Write Back;One hash pattern 256-bit access;Write Back;One hash pattern 512-bit access;Write Back;One hash pattern | P2 | UMC-TEST-062.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 1 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
62 | UMC-063 | UC1HP Memory Exerciser using Unchachable with One Hash Pattern | Manzoor | UMC |  | byte access;Unchachable;One hash pattern word access;Unchachable;One hash pattern doubleword access;Unchachable;One hash pattern quadword access;Unchachable;One hash pattern double quadword access;Unchachable;One hash pattern 256-bit access;Unchachable;One hash pattern 512-bit access;Unchachable;One hash pattern | P3 | UMC-TEST-063.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 2 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
63 | UMC-064 | WT1HP Memory Exerciser using Write Through with One Hash Pattern | Manzoor | UMC |  | byte access;Write Through;One hash pattern word access;Write Through;One hash pattern doubleword access;Write Through;One hash pattern quadword access;Write Through;One hash pattern double quadword access;Write Through;One hash pattern 256-bit access;Write Through;One hash pattern 512-bit access;Write Through;One hash pattern | P3 | UMC-TEST-064.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 4 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
64 | UMC-065 | WCW1 Memory Exerciser using Write Combinin with Walking Ones | Manzoor | UMC |  | byte access;Write Combining;Walking Ones word access;Write Combining;Walking Ones doubleword access;Write Combining;Walking Ones quadword access;Write Combining;Walking Ones double quadword access;Write Combining;Walking Ones 256-bit access;Write Combining;Walking Ones 512-bit access;Write Combining;Walking Ones | P3 | UMC-TEST-065.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 8 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
65 | UMC-066 | WBW1 Memory Exerciser using Write Back with Walking Ones | Manzoor | UMC |  | byte access;Write Back;Walking Ones word access;Write Back;Walking Ones doubleword access;Write Back;Walking Ones quadword access;Write Back;Walking Ones double quadword access;Write Back;Walking Ones 256-bit access;Write Back;Walking Ones 512-bit access;Write Back;Walking Ones | P3 | UMC-TEST-066.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WB --access-size 16 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
66 | UMC-067 | UCW1 Memory Exerciser using Unchachable with Walking Ones | Manzoor | UMC |  | byte access;Unchachable;Walking Ones word access;Unchachable;Walking Ones doubleword access;Unchachable;Walking Ones quadword access;Unchachable;Walking Ones double quadword access;Unchachable;Walking Ones 256-bit access;Unchachable;Walking Ones 512-bit access;Unchachable;Walking Ones | P3 | UMC-TEST-067.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 1 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
67 | UMC-068 | WTW1 Memory Exerciser using Write Through with Walking Ones | Manzoor | UMC |  | byte access;Write Through;Walking Ones word access;Write Through;Walking Ones doubleword access;Write Through;Walking Ones quadword access;Write Through;Walking Ones double quadword access;Write Through;Walking Ones 256-bit access;Write Through;Walking Ones 512-bit access;Write Through;Walking Ones | P2 | UMC-TEST-068.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 2 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
68 | UMC-069 | WCW0 Memory Exerciser using Write Combining with Walking Zeros | Manzoor | UMC |  | byte access;Write Combining;Walking Zeros word access;Write Combining;Walking Zeros doubleword access;Write Combining;Walking Zeros quadword access;Write Combining;Walking Zeros double quadword access;Write Combining;Walking Zeros 256-bit access;Write Combining;Walking Zeros 512-bit access;Write Combining;Walking Zeros | P2 | UMC-TEST-069.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 4 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
69 | UMC-070 | WBW0 Memory Exerciser using Write Back with Walking Zeros | Manzoor | UMC |  | byte access;Write Back;Walking Zeros word access;Write Back;Walking Zeros doubleword access;Write Back;Walking Zeros quadword access;Write Back;Walking Zeros double quadword access;Write Back;Walking Zeros 256-bit access;Write Back;Walking Zeros 512-bit access;Write Back;Walking Zeros | P2 | UMC-TEST-070.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 8 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
70 | UMC-071 | UCW0 Memory Exerciser using Unchachable with Walking Zeros | Manzoor | UMC |  | byte access;Unchachable;Walking Zeros word access;Unchachable;Walking Zeros doubleword access;Unchachable;Walking Zeros quadword access;Unchachable;Walking Zeros double quadword access;Unchachable;Walking Zeros 256-bit access;Unchachable;Walking Zeros 512-bit access;Unchachable;Walking Zeros | P2 | UMC-TEST-071.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type UC --access-size 16 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
71 | UMC-072 | WTW0 Memory Exerciser using Write Through with Walking Zeros | Manzoor | UMC |  | byte access;Write Through;Walking Zeros word access;Write Through;Walking Zeros doubleword access;Write Through;Walking Zeros quadword access;Write Through;Walking Zeros double quadword access;Write Through;Walking Zeros 256-bit access;Write Through;Walking Zeros 512-bit access;Write Through;Walking Zeros | P2 | UMC-TEST-072.1-7.0 | CDL | /CPU/linux/Traffic_Suite/General_Memory_Exerciser --cpu all --memory-type WT --access-size 1 --block-size 0x2000000 --pattern 2 -v | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 0 |  | 7 | 7 |  |  |  | 1 |  | wk-1
72 | UMC-073 | Fill Memory | Paul | UMC |  | UMC1.1,2,3,4 | P2 | UMC-TEST-073.1-4.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | wk-1
73 | UMC-074 | Memory Cell Pattern | Paul | UMC |  | UMC375.1 | P2 | UMC-TEST-074 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
74 | UMC-075 | Memory Cell Pattern using SDMA | Paul | UMC |  | umc381.1 | P2 | UMC-TEST-075 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
75 | UMC-076 | HDP version | Paul | UMC |  | umc3.1,2,3 | P2 | UMC-TEST-076.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
76 | UMC-077 | CP-DMA version | Paul | UMC |  | umc5.1,2,3 | P2 | UMC-TEST-077.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-4
77 | UMC-078 | CP-DMA/MCB version | Paul | UMC |  | umc6.1,2,3 | P2 | UMC-TEST-078.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-4
78 | UMC-079 | CB version | Paul | UMC |  | umc7.1,2,3 | P2 | UMC-TEST-079.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
79 | UMC-080 | CB/MCB version | Paul | UMC |  | umc8.1,2,3 | P2 | UMC-TEST-080.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
80 | UMC-081 | DRMDMA version | Paul | UMC |  | umc24.1 | P2 | UMC-TEST-081 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
81 | UMC-082 | DRMDMA/MCB version | Paul | UMC |  | umc25.1 | P2 | UMC-TEST-082 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
82 | UMC-083 | HDP version | Paul | UMC |  | umc9.1,2,3 | P2 | UMC-TEST-083.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
83 | UMC-084 | CP-DMA version | Paul | UMC |  | umc10.1,2,3 | P2 | UMC-TEST-084.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
84 | UMC-085 | CP-DMA/MCB version | Paul | UMC |  | umc11.1,2,3 | P3 | UMC-TEST-085.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
85 | UMC-086 | CB version | Paul | UMC |  | umc12.1,2,3 | P3 | UMC-TEST-086.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
86 | UMC-087 | CB/MCB version | Paul | UMC |  | umc13.1,2,3 | P3 | UMC-TEST-087.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
87 | UMC-088 | Rect Toggle Walkbit | Paul | UMC |  | umc369.2,3,5,6,8,9 | P2 | UMC-TEST-088.1-6.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1 |  | wk-2
88 | UMC-089 | Rect Toggle Randmask | Paul | UMC |  | umc370.2,3,5,6,8,9 | P3 | UMC-TEST-089.1-6.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1 |  | wk-2
89 | UMC-090 | Rect Toggle Randbit | Paul | UMC |  | umc371.2,3,5,6,8,9 | P3 | UMC-TEST-090.1-6.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1 |  | wk-2
90 | UMC-091 | Rect Toggle Walkbit with Nominal DC SSO | Paul | UMC |  | umc376.6-15 | P2 | UMC-TEST-091.1-10.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1 |  | wk-4
91 | UMC-092 | Rect Toggle Walkbit 128-bit SSO | Paul | UMC |  | umc382.1-146 | P2 | UMC-TEST-092.1-90.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 90 | Legacy | 1 | 90 | 1 | N-1 | 90 | 90 | 90 |  |  |  | 1 |  | 90 | 90 |  |  |  | 1 |  | wk-4
92 | UMC-093 | Rect Toggle Walkbit with Mask @16bpp | Paul | UMC |  | umc378.1-60 | P2 | UMC-TEST-093.1-60.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 60 | Legacy | 1 | 60 | 1 | N-1 | 60 | 60 | 60 |  |  |  | 1 |  | 60 | 60 |  |  |  | 1 |  | wk-4
93 | UMC-094 | Rect Toggle Walkbit with Mask @32bpp | Paul | UMC |  | umc379.* | P2 | UMC-TEST-094.1-124.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 124 | Legacy | 1 | 124 | 1 | N-1 | 124 | 124 | 124 |  |  |  | 1 |  | 124 | 124 |  |  |  | 1 |  | wk-4
94 | UMC-095 | CP-DMA version | Paul | UMC |  | umc372.1 | P3 | UMC-TEST-095 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
95 | UMC-096 | SDMA version | Paul | UMC |  | umc380.1 | P3 | UMC-TEST-096 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
96 | UMC-097 | UMC301 - Moving Blt Colorbar | Paul | UMC |  | umc301.2,3,5,6,7,9-13,21-22 | P3 | UMC-TEST-097.1-12.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | wk-4
97 | UMC-098 | UMC302 - Moving Blt Walkbit | Paul | UMC |  | umc302.2,3,5,6,7,9-13,21,22,101-105,501-505,511-515,551-555,561-565 | P2 | UMC-TEST-098.1-37.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 37 | Legacy | 1 | 37 | 1 | N-1 | 37 | 37 | 37 |  |  |  | 1 |  | 37 | 37 |  |  |  | 1 |  | wk-4
98 | UMC-099 | UMC303 – Moving Blt Walkpat | Paul | UMC |  | umc303.2,3,5-7,9-13,21,22,101-105,301-305 | P3 | UMC-TEST-099.1-22.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 22 | Legacy | 1 | 22 | 1 | N-1 | 22 | 22 | 22 |  |  |  | 1 |  | 22 | 22 |  |  |  | 1 |  | wk-4
99 | UMC-100 | UMC304 – Moving Blt Maskpat | Paul | UMC |  | umc304.2,3,5,6,101,201,301,401 | P3 | UMC-TEST-100.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
100 | UMC-101 | UMC305 – Moving Blt Randbit | Paul | UMC |  | umc305.2,3,5-7,9-13,21,22,101-105,201-205,301-305,401-405,501-505,511-515,551-555,561-565 | P2 | UMC-TEST-101.1-51.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 51 | Legacy | 1 | 51 | 1 | N-1 | 51 | 51 | 51 |  |  |  | 1 |  | 51 | 51 |  |  |  | 1 | umc305.302: intermittent failure, data mismatch. | wk-4
101 | UMC-102 | UMC306 – Moving Blt Randmask | Paul | UMC |  | umc306.2,3,5,6,101,201,301,401 | P2 | UMC-TEST-102.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
102 | UMC-103 | UMC307 - Horizontal Blt Colorbar | Paul | UMC |  | umc307.2,3,5,6,7,9-13,21-22 | P2 | UMC-TEST-103.1-12.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | wk-4
103 | UMC-104 | UMC308 - Horizontal Blt Walkbit | Paul | UMC |  | umc308.2,3,5,6,7,9-13,21,22,101-105,501-505,511-515,551-555,561-565 | P2 | UMC-TEST-104.1-37.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 37 | Legacy | 1 | 37 | 1 | N-1 | 37 | 37 | 37 |  |  |  | 1 |  | 37 | 37 |  |  |  | 1 |  | wk-4
104 | UMC-105 | UMC309 - Horizontal Blt Walkpat | Paul | UMC |  | umc309.2,3,5-7,9-13,21,22,101-105,301-305 | P3 | UMC-TEST-105.1-22.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 22 | Legacy | 1 | 22 | 1 | N-1 | 22 | 22 | 22 |  |  |  | 1 |  | 22 | 22 |  |  |  | 1 | umc309.304: intermittent failure, data mismatch | wk-4
105 | UMC-106 | UMC310 - Horizontal Blt Maskpat | Paul | UMC |  | umc310.2,3,5,6,101,201,301,401 | P3 | UMC-TEST-106.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
106 | UMC-107 | UMC311 - Horizontal Blt Randbit | Paul | UMC |  | umc311.2,3,5-7,9-13,21,22,101-105,201-205,301-305,401-405,501-505,511-515,551-555,561-565 | P2 | UMC-TEST-107.1-51.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 51 | Legacy | 1 | 51 | 1 | N-1 | 51 | 51 | 51 |  |  |  | 1 |  | 51 | 51 |  |  |  | 1 |  | wk-4
107 | UMC-108 | UMC312 - Horizontal Blt Randmask | Paul | UMC |  | umc312.2,3,5,6,101,201,301,401 | P3 | UMC-TEST-108.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
108 | UMC-109 | UMC313 - Diagonal Blt Colorbar | Paul | UMC |  | umc313.2,3,5,6,7,9-13,21-22 | P3 | UMC-TEST-109.1-12.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | wk-4
109 | UMC-110 | UMC314 - Diagonal Blt Walkbit | Paul | UMC |  | umc314.2,3,5,6,7,9-13,21,22,101-105,501-505,511-515,551-555,561-565 | P2 | UMC-TEST-110.1-37.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 37 | Legacy | 1 | 37 | 1 | N-1 | 37 | 37 | 37 |  |  |  | 1 |  | 37 | 37 |  |  |  | 1 |  | wk-4
110 | UMC-111 | UMC315 - Diagonal Blt Walkpat | Paul | UMC |  | umc315.2,3,5-7,9-13,21,22,101-105,301-305 | P2 | UMC-TEST-111.1-22.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 22 | Legacy | 1 | 22 | 1 | N-1 | 22 | 22 | 22 |  |  |  | 1 |  | 22 | 22 |  |  |  | 1 |  | wk-4
111 | UMC-112 | UMC316 - Diagonal Blt Maskpat | Paul | UMC |  | umc316.2,3,5,6,101,201,301,401 | P2 | UMC-TEST-112.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
112 | UMC-113 | UMC317 - Diagonal Blt Randbit | Paul | UMC |  | umc317.2,3,5-7,9-13,21,22,101-105,201-205,301-305,401-405,501-505,511-515,551-555,561-565 | P2 | UMC-TEST-113.1-51.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 51 | Legacy | 1 | 51 | 1 | N-1 | 51 | 51 | 51 |  |  |  | 1 |  | 51 | 51 |  |  |  | 1 | case 302, 304, 305 failure, data mismatch -> fixed with GFX diag patch for 11_5 dispatch list code | wk-4
113 | UMC-114 | UMC318 - Diagonal Blt Randmask | Paul | UMC |  | umc318.2,3,5,6,101,201,301,401 | P3 | UMC-TEST-114.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
114 | UMC-115 | UMC319 - Random Blt Colorbar | Paul | UMC |  | umc319.2,3,5,6,7,9-13,21-22 | P2 | UMC-TEST-115.1-12.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | wk-4
115 | UMC-116 | UMC320 - Random Blt Walkbit | Paul | UMC |  | umc320.2,3,5,6,7,9-13,21,22,101-105,501-505,511-515,551-555,561-565 | P3 | UMC-TEST-116.1-37.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 37 | Legacy | 1 | 37 | 1 | N-1 | 37 | 37 | 37 |  |  |  | 1 |  | 37 | 37 |  |  |  | 1 |  | wk-4
116 | UMC-117 | UMC321 - Random Blt Walkpat | Paul | UMC |  | umc321.2,3,5-7,9-13,21,22,101-105,301-305 | P3 | UMC-TEST-117.1-22.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 22 | Legacy | 1 | 22 | 1 | N-1 | 22 | 22 | 22 |  |  |  | 1 |  | 22 | 22 |  |  |  | 1 |  | wk-4
117 | UMC-118 | UMC322 - Random Blt Maskpat | Paul | UMC |  | umc322.2,3,5,6,101,201,301,401 | P2 | UMC-TEST-118.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
118 | UMC-119 | UMC323 - Random Blt Randbit | Paul | UMC |  | umc323.2,3,5-7,9-13,21,22,101-105,201-205,301-305,401-405,501-505,511-515,551-555,561-565 | P3 | UMC-TEST-119.1-51.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 51 | Legacy | 1 | 51 | 1 | N-1 | 51 | 51 | 51 |  |  |  | 1 |  | 51 | 51 |  |  |  | 1 | case 302 intermittent failure, data mismatch -> verified on strix1-adc-03 system | wk-4
119 | UMC-120 | UMC324 - Random Blt Randmask | Paul | UMC |  | umc324.2,3,5,6,101,201,301,401 | P3 | UMC-TEST-120.1-8.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk-4
120 | UMC-121 | UMC210 - Vertical Blt Colorbar | Paul | UMC |  | umc210.2,3,5,6,7,9-13,21-22 | P2 | UMC-TEST-121.1-12.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | wk-4
121 | UMC-122 | UMC211 - Vertical Blt Walkbit | Paul | UMC |  | umc211.2,3,5,6,7,9-13,21,22,101-105,501-505,511-515,551-555,561-565 | P2 | UMC-TEST-122.1-37.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 37 | Legacy | 1 | 37 | 1 | N-1 | 37 | 37 | 37 |  |  |  | 1 |  | 37 | 37 |  |  |  | 1 |  | wk-4
122 | UMC-123 | UMC212 - Vertical Blt Walkpat | Paul | UMC |  | umc212.2,3,5-7,9-13,21,22,101-105,301-305 | P2 | UMC-TEST-123.1-22.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 22 | Legacy | 1 | 22 | 1 | N-1 | 22 | 22 | 22 |  |  |  | 1 |  | 22 | 22 |  |  |  | 1 |  | wk-4
123 | UMC-124 | UMC213 - Vertical Blt Maskpat | Paul | UMC |  | umc213.2,3,5,6 | P2 | UMC-TEST-124.1-4.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | wk-4
124 | UMC-125 | UMC214 - Vertical Blt Randbit | Paul | UMC |  | umc214.2,3,5-7,9-13,21,22,101-105,201-205,301-305,401-405,501-505,511-515,551-555,561-565 | P3 | UMC-TEST-125.1-51.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 51 | Legacy | 1 | 51 | 1 | N-1 | 51 | 51 | 51 |  |  |  | 1 |  | 51 | 51 |  |  |  | 1 |  | wk-4
125 | UMC-126 | UMC215 - Vertical Blt Randmask | Paul | UMC |  | umc215.2,3,5,6 | P2 | UMC-TEST-126.1-4.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | wk-4
126 | UMC-127 | UMC216 - Vertical Blt SSOmask | Paul | UMC |  | umc216.2,3,5,6 | P3 | UMC-TEST-127.1-4.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | wk-4
127 | UMC-128 | Power Virus Test | Paul | UMC |  | umc56.153-159 | P3 | UMC-TEST-128.1-7.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 1 |  | 7 | 7 |  |  |  | 1 |  | wk-1
128 | UMC-129 | WAW – write after write | Paul | UMC |  | umc681.1 | P2 | UMC-TEST-129 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
129 | UMC-130 | RAW – read after write | Paul | UMC |  | umc681.2 | P3 | UMC-TEST-130 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-2
130 | UMC-131 | VC-based Priority Adjustment | Paul | UMC |  | umc683.1 | P3 | UMC-TEST-131 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-4
131 | UMC-132 | Bypass Priority Escalation Mode | Paul | UMC |  | umc684.1 | P2 | UMC-TEST-132 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-4
132 | UMC-133 | DRAM encryption test | Paul | UMC |  | mhub350.1-4 | P2 | UMC-TEST-133.1-4.0 | TServer | -d=1 -log -tcorelog -disable_libdce -skiptextbuffering -norlc -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -no_toollib -load_ucode=tcore -skip_iommu_check=1 -tmzmode=tmz -vm | 1 | 4 | Legacy | 1 | 4 | 1 | [7 empty] | 0 |  | 4 | 4 |  |  |  | 1 |  | wk-6
133 | UMC-134 | DRAM encryption test | Paul | UMC |  | mhub350.5-8 | P2 | UMC-TEST-134.1-4.0 | TServer | -d=1 -log -tcorelog -disable_libdce -skiptextbuffering -norlc -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -no_toollib -load_ucode=tcore -skip_iommu_check=1 -tmzmode=tmz -vm | 1 | 4 | Legacy | 1 | 4 | 1 | [7 empty] | 0 |  | 4 | 4 |  |  |  | 1 |  | wk-6
134 | UMC-135 | SLT Functional | Paul | UMC |  | umc401.1 | P2 | UMC-TEST-135 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-1
135 | UMC-136 | Board Functional | Paul | UMC |  | umc403.1,3,4 | P3 | UMC-TEST-136.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2
136 | UMC-137 | Board Stress | Paul | UMC |  | umc404.1-3 | P3 | UMC-TEST-137.1-3.0 | TServer | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -disable_libdce -log | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | wk-2