## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | KRK1-USB4-001 | SB Register Access Test | Harikrishnan P | USB4 |  | SB Register Access Test | P1 | USB4-LL-01.1-9 | Other |  | 1 | 9 | Legacy | 1 | 9 | 1 | N-1 | 9 | [5 empty] | 0 | [6 empty] | 0
1 | KRK1-USB4-002 | LT Transaction | Harikrishnan P | USB4 |  | Sideband transaction : LT | P1 | USB4-LL-02 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
2 | KRK1-USB4-003 | AT Transaction | Harikrishnan P | USB4 |  | Sideband transaction : AT | P1 | USB4-LL-03 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
3 | KRK1-USB4-004 | RT Transaction | Harikrishnan P | USB4 |  | Sideband transaction : RT | P1 | USB4-LL-04 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
4 | KRK1-USB4-005 | LLSM - Disabled | Harikrishnan P | USB4 |  | LLSM - Disabled | P1 | USB4-LL-05 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
5 | KRK1-USB4-006 | LLSM - CLd | Harikrishnan P | USB4 |  | LLSM - CLd | P1 | USB4-LL-06 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
6 | KRK1-USB4-007 | LLSM - Training | Harikrishnan P | USB4 |  | LLSM - Training | P1 | USB4-LL-07 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
7 | KRK1-USB4-008 | LLSM - CL0 | Harikrishnan P | USB4 |  | LLSM - CL0 | P1 | USB4-LL-08 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
8 | KRK1-USB4-009 | LLSM - Lane Bonding | Harikrishnan P |  |  | LLSM - Lane Bonding | P1 | USB4-LL-09 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
9 | KRK1-USB4-010 | LLSM - Low Power (CL0s, CL1, and CL2) | Harikrishnan P |  |  | LLSM - Low Power (CL0s, CL1, and CL2) | P1 | USB4-LL-10 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
10 | KRK1-USB4-011 | Transition from One Single-Lane Link to Two Single-Lane Links | Harikrishnan P |  |  | Transition from One Single-Lane Link to Two Single-Lane Links | P1 | USB4-LL-11 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
11 | KRK1-USB4-012 | Transition from Two Single-Lane Links to Dual-Lane Link | Harikrishnan P | USB4 |  | Transition from Two Single-Lane Links to Dual-Lane Link | P1 | USB4-LL-12 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
12 | KRK1-USB4-013 | Transition from Dual-Lane Link to Two Single-Lane Links | Harikrishnan P | USB4 |  | Transition from Dual-Lane Link to Two Single-Lane Links | P1 | USB4-LL-13 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
13 | KRK1-USB4-014 | Transition from Two Single-Lane Links to One Single-Lane Link | Harikrishnan P | USB4 |  | Transition from Two Single-Lane Links to One Single-Lane Link | P1 | USB4-LL-14 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
14 | KRK1-USB4-016 | RS-FEC Activation and Deactivation | Harikrishnan P | USB4 |  | RS-FEC Activation and Deactivation | P2 | USB4-LL-16 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
15 | KRK1-USB4-017 | Error Cases and Recovery | Harikrishnan P |  |  | Error Cases and Recovery | P2 | USB4-LL-17 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
16 | KRK1-USB4-018 | Downstream Port Disconnect | Harikrishnan P | USB4 |  | Downstream Port Disconnect | P2 | USB4-LL-18 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
17 | KRK1-USB4-019 | Lane Adapter Disable and Enable | Harikrishnan P |  |  | Lane Adapter Disable and Enable | P2 | USB4-LL-19 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
18 | KRK1-USB4-021 | Entry to Sleep | Harikrishnan P | USB4 |  | Entry to Sleep | P2 | USB4-LL-21 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
19 | KRK1-USB4-022 | Behavior in Sleep State | Harikrishnan P | USB4 |  | Behavior in Sleep State | P2 | USB4-LL-22 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [7 empty] | Test performed manually. Checked if PORT_CS_19 bits are copied to S5 shadow registers
20 | KRK1-USB4-023 | Wake Events | Harikrishnan P | USB4 |  | Wake Events | P2 | USB4-LL-23 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [7 empty] | Verified on Ubuntu 23.04 with Linux kernel 6.2 (enabled wakeup in usb4_port sysfs)
21 | KRK1-USB4-024 | Exit from Sleep | Harikrishnan P | USB4 |  | Exit from Sleep | P2 | USB4-LL-24 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
22 | KRK1-USB4-025 | Wake on USB4 Event | Harikrishnan P | USB4 |  | Wake on USB4 Event | P2 | USB4-LL-25 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [7 empty] | Verified with Ubuntu 23.04 OS (Linux kernel 6.2). wakeup needs to be enabled for both host router and second tier device router in linux sysfs
23 | KRK1-USB4-026 | Uninitialized Plugged State | Harikrishnan P |  |  | Uninitialized Plugged State | P2 | USB4-CL-01 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
24 | KRK1-USB4-027 | Enumerated State | Harikrishnan P |  |  | Enumerated State | P2 | USB4-CL-02 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
25 | KRK1-USB4-028 | Control Adapter | Harikrishnan P |  |  | Control Adapter | P2 | USB4-CL-03 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
26 | KRK1-USB4-029 | Control Packets | Harikrishnan P |  |  | Control Packets | P2 | USB4-CL-04 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
27 | KRK1-USB4-030 | Bit/Byte Conventions | Harikrishnan P |  |  | Bit/Byte Conventions | P2 | USB4-CL-05 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
28 | KRK1-USB4-031 | Format | Harikrishnan P |  |  | Format | P2 | USB4-CL-06 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
29 | KRK1-USB4-032 | Read Request | Harikrishnan P | USB4 |  | Read Request | P2 | USB4-CL-07 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
30 | KRK1-USB4-033 | Read Response | Harikrishnan P | USB4 |  | Read Response | P2 | USB4-CL-08 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
31 | KRK1-USB4-034 | Write Request | Harikrishnan P | USB4 |  | Write Request | P2 | USB4-CL-09 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
32 | KRK1-USB4-035 | Write Response | Harikrishnan P | USB4 |  | Write Response | P2 | USB4-CL-10 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
33 | KRK1-USB4-036 | Notification Packet | Harikrishnan P |  |  | Notification Packet | P2 | USB4-CL-11 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
34 | KRK1-USB4-037 | Notification Acknowledgement Packet | Harikrishnan P |  |  | Notification Acknowledgement Packet | P2 | USB4-CL-12 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
35 | KRK1-USB4-038 | Hot Plug Event Packet | Harikrishnan P |  |  | Hot Plug Event Packet | P2 | USB4-CL-13 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
36 | KRK1-USB4-039 | Inter-Domain Request | Harikrishnan P |  |  | Inter-Domain Request | P2 | USB4-CL-14 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
37 | KRK1-USB4-040 | Inter-Domain Response | Harikrishnan P |  |  | Inter-Domain Response | P2 | USB4-CL-15 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
38 | KRK1-USB4-041 | Downstream-Bound Packets | Harikrishnan P |  |  | Downstream-Bound Packets | P1 | USB4-CL-16 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
39 | KRK1-USB4-042 | Processing of Read and Write Requests | Harikrishnan P | USB4 |  | Processing of Read and Write Requests | P1 | USB4-CL-17 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
40 | KRK1-USB4-043 | Control Packet Reliability | Harikrishnan P |  |  | Control Packet Reliability | P1 | USB4-CL-18 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
41 | KRK1-USB4-066 | Router Configuration Space | Harikrishnan P | USB4 |  | Router Configuration Space | P1 | USB4-CS-01 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
42 | KRK1-USB4-067 | Basic Configuration Registers | Harikrishnan P | USB4 |  | Basic Configuration Registers | P1 | USB4-CS-02 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
43 | KRK1-USB4-068 | TMU Router Configuration Capability | Harikrishnan P | USB4 |  | TMU Router Configuration Capability | P1 | USB4-CS-03 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
44 | KRK1-USB4-069 | Vendor Specific Capability (VSC) | Harikrishnan P | USB4 |  | Vendor Specific Capability (VSC) | P1 | USB4-CS-04 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
45 | KRK1-USB4-070 | Vendor Specific Extended Capability (VSEC) | Harikrishnan P | USB4 |  | Vendor Specific Extended Capability (VSEC) | P1 | USB4-CS-05 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
46 | KRK1-USB4-071 | Adapter Configuration Space | Harikrishnan P | USB4 |  | Adapter Configuration Space | P1 | USB4-CS-06 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
47 | KRK1-USB4-072 | Basic Configuration Registers | Harikrishnan P | USB4 |  | Basic Configuration Registers | P1 | USB4-CS-07 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
48 | KRK1-USB4-073 | TMU Adapter Configuration Capability | Harikrishnan P | USB4 |  | TMU Adapter Configuration Capability | P1 | USB4-CS-08 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
49 | KRK1-USB4-074 | Lane Adapter Configuration Capability | Harikrishnan P | USB4 |  | Lane Adapter Configuration Capability | P1 | USB4-CS-09 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
50 | KRK1-USB4-075 | USB4 Port Capability | Harikrishnan P | USB4 |  | USB4 Port Capability | P1 | USB4-CS-10 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
51 | KRK1-USB4-076 | USB3 Adapter Configuration Capability | Harikrishnan P | USB4 |  | USB3 Adapter Configuration Capability | P1 | USB4-CS-11 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
52 | KRK1-USB4-077 | DP Adapter Configuration Capability | Harikrishnan P | USB4 |  | DP Adapter Configuration Capability | P1 | USB4-CS-12 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
53 | KRK1-USB4-078 | PCIe Adapter Configuration Capability | Harikrishnan P | USB4 |  | PCIe Adapter Configuration Capability | P1 | USB4-CS-13 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
54 | KRK1-USB4-079 | Path Configuration Space | Harikrishnan P | USB4 |  | Path Configuration Space | P1 | USB4-CS-14 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
55 | KRK1-USB4-080 | Path 0 Entry | Harikrishnan P | USB4 |  | Path 0 Entry | P1 | USB4-CS-15 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
56 | KRK1-USB4-081 | Lane Adapters | Harikrishnan P | USB4 |  | Lane Adapters | P1 | USB4-CS-16 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
57 | KRK1-USB4-082 | Protocol Adapters | Harikrishnan P | USB4 |  | Protocol Adapters | P1 | USB4-CS-17 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
58 | KRK1-USB4-083 | Path Configuration Space Access | Harikrishnan P | USB4 |  | Path Configuration Space Access | P1 | USB4-CS-18 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
59 | KRK1-USB4-084 | Counters Configuration Space | Harikrishnan P |  |  | Counters Configuration Space | P1 | USB4-CS-19 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
60 | KRK1-USB4-085 | Timing Parameters | Harikrishnan P |  |  | Timing Parameters | P2 | USB4-TS-01 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
61 | KRK1-USB4-086 | Host Interface Adaptor Test | Harikrishnan P | USB4 |  | Host Interface Adaptor Test | P2 | USB4-TS-02 | Other |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
62 | KRK1-USB4-087 | Time Synchronization Architecture | Harikrishnan P |  |  | Intra-Domain Hierarchy | P2 | USB4-TS-03 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0
63 | KRK1-USB4-089 | Type-C Flip Test | Harikrishnan P | USB |  | Type C flip test | P2 | USB4-TS-05 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0
64 | KRK1-USB4-090 | Time Sync Parameters | Harikrishnan P | USB4 |  | Time offset | P2 | USB4-TS-06 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0 | [7 empty] | Covered by TMU Adapter capability
65 | KRK1-USB4-091 | Time Sync Parameters | Harikrishnan P | USB4 |  | Frequency offset | P2 | USB4-TS-07 | Other |  | 0 | 0 | Legacy | 1 | 0 | 0 | N-1 | 0 | [5 empty] | 0 | [7 empty] | Covered by TMU Adapter capability
66 | KRK1-USB4-092 | USB4 Tunneling | Harikrishnan P | USB4 |  | USB4 Tunneling | P2 | USB4-ENH-01 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [7 empty] | Tested on Windows (DP, PCIe and USB)
67 | KRK1-USB4-093 | USB4 Gen3 x1 and x2 super speed tests | Harikrishnan P | USB4 |  | USB4 Gen3 x1 and x2 super speed tests | P2 | USB4-ENH-02 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [7 empty] | Test executed manually
68 | KRK1-USB4-094 | USB4 Alt Modes for Thunderbolt and Display | Harikrishnan P | USB4 |  | USB4 Alt Modes for Thunderbolt and Display | P2 | USB4-ENH-03 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [7 empty] | TBT3 verified. DP will only work in 4 lane mode. USB+DP won't work due to known USB bug with USB4 port. Hence, a type C to DP dongle was used to test this feature.
69 | KRK1-USB4-095 | USB4 PHY tests | Harikrishnan P | USB4 |  | USB4 PHY tests | P2 | USB4-ENH-04 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [7 empty] | SS/SSP PHY tests fails on USB4 ports |  | Silicon bug discussed in PLAT-134499
70 | KRK1-USB-001 | XHCI Block Registers | Harikrishnan P | USB |  | XHCI Block Registers | P3 | USB-01.1-2 | Other |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
71 | KRK1-USB-002 | USB1.1 Verification | Harikrishnan P | USB |  | Low Speed | P3 | USB-02.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
72 | KRK1-USB-003 | USB1.1 Verification | Harikrishnan P | USB |  | FS Device-Attach-Detach -Reset | P3 | USB-03.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
73 | KRK1-USB-004 | USB1.1 Verification | Harikrishnan P | USB |  | FS Bulk Stress testing | P3 | USB-04.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
74 | KRK1-USB-005 | USB1.1 Verification | Harikrishnan P | USB |  | FS Interrupt Stress testing | P3 | USB-05.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
75 | KRK1-USB-006 | USB1.1 Verification | Harikrishnan P | USB |  | FS Isoch Stress testing | P3 | USB-06.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
76 | KRK1-USB-007 | USB2.0 Verification | Harikrishnan P | USB |  | HS Device-Attach-Detach-Reset | P3 | USB-07.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
77 | KRK1-USB-008 | USB2.0 Verification | Harikrishnan P | USB |  | HS Bulk Stress testing | P3 | USB-08.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
78 | KRK1-USB-009 | USB2.0 Verification | Harikrishnan P | USB |  | HS Interrupt Stress testing | P3 | USB-09.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
79 | KRK1-USB-010 | USB2.0 Verification | Harikrishnan P | USB |  | HS Isoch Stress testing | P3 | USB-10.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
80 | KRK1-USB-011 | USB3.0 Verification | Harikrishnan P | USB |  | SS Device-Attach-Detach-Reset Test | P3 | USB-11.1-12 | Other |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | [5 empty] | 0 | [6 empty] | 0 | SS fails on USB4 ports | WK4 | Silicon bug discussed in PLAT-134499
81 | KRK1-USB-012 | USB3.0 Verification | Harikrishnan P | USB |  | SS Bulk Stress testing | P3 | USB-12.1-12 | Other |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | [5 empty] | 0 | [6 empty] | 0 | SS fails on USB4 ports | WK4 | Silicon bug discussed in PLAT-134499
82 | KRK1-USB-013 | USB3.0 Verification | Harikrishnan P | USB |  | SS Interrupt Stress testing | P3 | USB-13.1-12 | Other |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | [5 empty] | 0 | [6 empty] | 0 | SS fails on USB4 ports | WK4 | Silicon bug discussed in PLAT-134499
83 | KRK1-USB-014 | USB3.0 Verification | Harikrishnan P | USB |  | SS Isoch Stress testing | P3 | USB-14.1-12 | Other |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | [5 empty] | 0 | [6 empty] | 0 | SS fails on USB4 ports | WK4 | Silicon bug discussed in PLAT-134499
84 | KRK1-USB-015 | USB3.1 Verification | Harikrishnan P | USB |  | SSP Bulk Stress testing | P3 | USB-15.1-8 | Other |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | [5 empty] | 0 | [6 empty] | 0 | SSP fails on USB4 ports | WK4 | Silicon bug discussed in PLAT-134499
85 | KRK1-USB-016 | USB3.1 Verification | Harikrishnan P | USB |  | SSP Interrupt Stress testing | P3 | USB-16.1-8 | Other |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | [5 empty] | 0 | [6 empty] | 0 | SSP fails on USB4 ports | WK4 | Silicon bug discussed in PLAT-134499
86 | KRK1-USB-017 | USB3.1 Verification | Harikrishnan P | USB |  | SSP Isoch Stress testing | P3 | USB-17.1-8 | Other |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | [5 empty] | 0 | [6 empty] | 0 | SSP fails on USB4 ports | WK4 | Silicon bug discussed in PLAT-134499
87 | KRK1-USB-018 | USBx-Data Flow | Harikrishnan P | USB |  | Verify USB IN-OUT Data Flow | P3 | USB-18.1-8 | Other |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
88 | KRK1-USB-019 | USB3.1 Host Initialization | Harikrishnan P | USB |  | Verify USB3.1 Host Initialization | P3 | USB-19.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 | SSP fails on USB4 ports | WK6 | Silicon bug discussed in PLAT-134499
89 | KRK1-USB-020 | Support Larger Service Interval | Harikrishnan P | USB |  | XHCI SS / HS / FS Interrupt IN /OUT | P3 | USB-20.1-12 | Other |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | [5 empty] | 0 | [6 empty] | 0 | SS/SSP fails on USB4 ports | WK7 | Silicon bug discussed in PLAT-134499
90 | KRK1-USB-021 | USB Legacy testing | Harikrishnan P | USB |  | Legacy Testing on all ports of USB3.0/USB3.1 | P3 | USB-21.1-48 | Other |  | 1 | 48 | Legacy | 1 | 48 | 1 | N-1 | 48 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
91 | KRK1-USB-022 | Concurrent Transfer Robustness | Harikrishnan P | USB |  | HS transfer of BULK IN & OUT | P3 | USB-22.1-16 | Other |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
92 | KRK1-USB-023 | Concurrent Transfer Robustness | Harikrishnan P | USB |  | SS transfer of BULK IN & OUT | P3 | USB-23.1-12 | Other |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | [5 empty] | 0 | [6 empty] | 0 | USB4 ports failing for SS/SSP | WK5 | Silicon bug discussed in PLAT-134499
93 | KRK1-USB-024 | Concurrent Transfer Robustness | Harikrishnan P | USB |  | SSP transfer of BULK IN & OUT | P3 | USB-24.1-8 | Other |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | [5 empty] | 0 | [6 empty] | 0 | USB4 ports failing for SS/SSP | WK5 | Silicon bug discussed in PLAT-134499
94 | KRK1-USB-025 | Concurrent Transfer Robustness | Harikrishnan P | USB |  | HS/SS/SSP transfer of BULK IN & OUT | P3 | USB-25.1-8 | Other |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | [5 empty] | 0 | [6 empty] | 0 | USB4 ports failing for SS/SSP | WK5 | Silicon bug discussed in PLAT-134499
95 | KRK1-USB-026 | Support AOAC | Harikrishnan P | USB |  | D3 Cold Entry /Exit Sequence | P3 | USB-26.1-24 | Other |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 24 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
96 | KRK1-USB-027 | Support AOAC | Harikrishnan P | USB |  | Wake on Device Resume in S3/S4 | P3 | USB-27.1-24 | Other |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 24 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
97 | KRK1-USB-028 | Support AOAC | Harikrishnan P | USB |  | Wake on Device Connect and Disconnect in S0i3 | P3 | USB-28.1-12 | Other |  | 1 | 12 | Legacy | 1 | 12 | 1 |  | 12 | [5 empty] | 0 | [6 empty] | 0 | Wake events are verified for S3/S4 in Ubuntu. This should suffice as it is confirmed that USB IP is capable of generating the appropriate external wake events | WK6