## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | STRIX1-OSS-001 | Feature name - EX-FEAT-001 | Chuanqi Sun | SDMA | AQL Command + multi-producer support |  | P1 | sdma84.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
1 | STRIX1-OSS-002 | Feature name - EX-FEAT-002 | Chuanqi Sun | SDMA | Atomic Add |  | P3 | nsdma177 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
2 | STRIX1-OSS-003 | Feature name - EX-FEAT-003 | Chuanqi Sun | SDMA | Atomic Swap |  | P2 | nsdma178 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
3 | STRIX1-OSS-004 | Feature name - EX-FEAT-004 | Chuanqi Sun | SDMA | Atomic CompareSwap |  | P1 | nsdma179 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
4 | STRIX1-OSS-005 | Feature name - EX-FEAT-005 | Chuanqi Sun | SDMA | Burst NOPs |  | P1 | sdma65.101 | TServer |  | 1 | 1 | 1 | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
5 | STRIX1-OSS-006 | Feature name - EX-FEAT-006 | Chuanqi Sun | SDMA | CGCG enhancement |  | P1 | nsdma412.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  | 0 |  | 1
6 | STRIX1-OSS-007 | Feature name - EX-FEAT-007 | Chuanqi Sun | SDMA | Command Overlap |  | P3 | sdma27.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
7 | STRIX1-OSS-008 | Feature name - EX-FEAT-008 | Chuanqi Sun | SDMA | Conditional Exec Fail |  | P3 | nsdma27 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
8 | STRIX1-OSS-009 | Feature name - EX-FEAT-009 | Chuanqi Sun | SDMA | Conditional Exec Pass |  | P2 | nsdma26 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
9 | STRIX1-OSS-010 | Feature name - EX-FEAT-010 | Chuanqi Sun | SDMA | Const fill- byte |  | P2 | nsdma58 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
10 | STRIX1-OSS-011 | Feature name - EX-FEAT-011 | Chuanqi Sun | SDMA | Const-fill-Dword |  | P2 | nsdma59 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
11 | STRIX1-OSS-012 | Feature name - EX-FEAT-012 | Chuanqi Sun | SDMA | Normal-Preempt |  | P1 | nsdma215.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1
12 | STRIX1-OSS-013 | Feature name - EX-FEAT-013 | Chuanqi Sun | SDMA | Copy cmd format to support CUDA API(3D handle) |  | P1 | nsdma93.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
13 | STRIX1-OSS-014 | Feature name - EX-FEAT-014 | Chuanqi Sun | SDMA | Data Fill MULTI |  | P2 | nsdma65 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
14 | STRIX1-OSS-015 | Feature name - EX-FEAT-015 | Chuanqi Sun | SDMA | DCC compression/decompression copy |  | P1 | nsdma97 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
15 | STRIX1-OSS-016 | Feature name - EX-FEAT-016 | Chuanqi Sun | SDMA | Enable Host (CPU) access to F32 scratch RAM |  | P2 | nsdma81.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
16 | STRIX1-OSS-017 | Feature name - EX-FEAT-017 | Chuanqi Sun | SDMA | GMC Address |  | P1 | nsdma175 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
17 | STRIX1-OSS-018 | Feature name - EX-FEAT-018 | Chuanqi Sun | SDMA | Physical Address |  | P3 | nsdma176 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
18 | STRIX1-OSS-019 | Feature name - EX-FEAT-019 | Chuanqi Sun | SDMA | Legacy |  | P3 | nsdma205 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
19 | STRIX1-OSS-020 | Feature name - EX-FEAT-020 | Chuanqi Sun | SDMA | LightWeight |  | P3 | nsdma206 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
20 | STRIX1-OSS-021 | Feature name - EX-FEAT-021 | Chuanqi Sun | SDMA | Write-back |  | P3 | nsdma66 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
21 | STRIX1-OSS-022 | Feature name - EX-FEAT-022 | Chuanqi Sun | SDMA | Invalidate |  | P2 | nsdma67 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
22 | STRIX1-OSS-023 | Feature name - EX-FEAT-023 | Chuanqi Sun | SDMA | Discard |  | P2 | nsdma68 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
23 | STRIX1-OSS-024 | Feature name - EX-FEAT-024 | Chuanqi Sun | SDMA | Increase max copy size(4M-1G) |  | P1 | nsdma1.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
24 | STRIX1-OSS-025 | Feature name - EX-FEAT-025 | Chuanqi Sun | SDMA | L2 policy override on normal command |  | P2 | nsdma1.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
25 | STRIX1-OSS-026 | Feature name - EX-FEAT-026 | Chuanqi Sun | SDMA | Linear Copy |  | P2 | nsdma1.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
26 | STRIX1-OSS-027 | Feature name - EX-FEAT-027 | Chuanqi Sun | SDMA | Linear Backwards Copy |  | P2 | nsdma5.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
27 | STRIX1-OSS-028 | Feature name - EX-FEAT-028 | Chuanqi Sun | SDMA | Linear Copy Broadcast |  | P3 | nsdma4.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
28 | STRIX1-OSS-029 | Feature name - EX-FEAT-029 | Chuanqi Sun | SDMA | Linear Sub-Window Copy |  | P3 | nsdma7.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
29 | STRIX1-OSS-030 | Feature name - EX-FEAT-030 | Chuanqi Sun | SDMA | Linear large Sub-Window Copy |  | P1 | nsdma93.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
30 | STRIX1-OSS-031 | Feature name - EX-FEAT-031 | Chuanqi Sun | SDMA | Page Evicition Copy |  | P3 | nsdma8.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
31 | STRIX1-OSS-032 | Feature name - EX-FEAT-032 | Chuanqi Sun | SDMA | Tiled to Tiled Sub-Window Copy |  | P3 | nsdma10.1-10 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1
32 | STRIX1-OSS-033 | Feature name - EX-FEAT-033 | Chuanqi Sun | SDMA | Tiled Sub-Window Copy |  | P3 | nsdma9.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
33 | STRIX1-OSS-034 | Feature name - EX-FEAT-034 | Chuanqi Sun | SDMA | Linear to Linear Copy Command |  | P2 | nsdma1.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
34 | STRIX1-OSS-035 | Feature name - EX-FEAT-035 | Chuanqi Sun | SDMA | Linear to Linear sub-window copy |  | P1 | nsdma7.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
35 | STRIX1-OSS-036 | Feature name - EX-FEAT-036 | Chuanqi Sun | SDMA | Linear to Structured / Structured to Linear copy |  | P2 | nsdma13.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
36 | STRIX1-OSS-037 | Feature name - EX-FEAT-037 | Chuanqi Sun | SDMA | Linear to Tiled (frame to field) copy |  | P3 | nsdma12.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
37 | STRIX1-OSS-038 | Feature name - EX-FEAT-038 | Chuanqi Sun | SDMA | Linear to Tiled / Tiled to Linear Copy Command |  | P1 | nsdma2.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
38 | STRIX1-OSS-039 | Feature name - EX-FEAT-039 | Chuanqi Sun | SDMA | Linear to Tiled / Tiled to Linear Copy Command |  | P2 | nsdma3.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
39 | STRIX1-OSS-040 | Feature name - EX-FEAT-040 | Chuanqi Sun | SDMA | Linear to Tiled / Tiled to Linear sub-window copy |  | P1 | nsdma7.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
40 | STRIX1-OSS-041 | Feature name - EX-FEAT-041 | Chuanqi Sun | SDMA | Linear to Tiled copy broadcast |  | P1 | nsdma11.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
41 | STRIX1-OSS-042 | Feature name - EX-FEAT-042 | Chuanqi Sun | SDMA | Mid Command Buffer Preemption |  | P1 | nsdma217.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
42 | STRIX1-OSS-043 | Feature name - EX-FEAT-043 | Chuanqi Sun | SDMA | Mid Command Preemption |  | P3 | nsdma217.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
43 | STRIX1-OSS-044 | Feature name - EX-FEAT-044 | Chuanqi Sun | SDMA | RB Command Preemption |  | P2 | nsdma217.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
44 | STRIX1-OSS-045 | Feature name - EX-FEAT-045 | Chuanqi Sun | SDMA | Mid-command preemption when time quantum reached |  | P1 | nsdma218.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
45 | STRIX1-OSS-046 | Feature name - EX-FEAT-046 | Chuanqi Sun | SDMA | Memory Increment |  | P3 | nsdma160.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
46 | STRIX1-OSS-047 | Feature name - EX-FEAT-047 | Chuanqi Sun | SDMA | Page Eviction Copy |  | P2 | nsdma8.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
47 | STRIX1-OSS-048 | Feature name - EX-FEAT-048 | Chuanqi Sun | SDMA | PAGE_INT_ENABLE |  | P1 |  | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
48 | STRIX1-OSS-049 | Feature name - EX-FEAT-049 | Chuanqi Sun | SDMA | Physical linear copy |  | P1 | nsdma6.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
49 | STRIX1-OSS-050 | Feature name - EX-FEAT-050 | Chuanqi Sun | SDMA | Poll Memory/Register Command |  | P2 | nsdma16.1-12 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1
50 | STRIX1-OSS-051 | Feature name - EX-FEAT-051 | Chuanqi Sun | SDMA | Predicated Execution Command |  | P1 | nsdma182 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
51 | STRIX1-OSS-052 | Feature name - EX-FEAT-052 | Chuanqi Sun | SDMA | RAW dependency check |  | P2 | nsdma68.1-2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
52 | STRIX1-OSS-053 | Feature name - EX-FEAT-053 | Chuanqi Sun | SDMA | Ring Buffer Preemption between contexts |  | P3 | nsmda217.1 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
53 | STRIX1-OSS-054 | Feature name - EX-FEAT-054 | Chuanqi Sun | SDMA | Ring Buffer Preemption within a context |  | P1 | nsdma217.1 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
54 | STRIX1-OSS-055 | Feature name - EX-FEAT-055 | Chuanqi Sun | SDMA | SDMA Master Firewall |  | P3 | nsdma222.1-34 | TServer |  | 1 | 34 | Legacy | 1 | 34 | 1 | N-1 | 34 | 34 | 34 |  |  |  | 1 |  | 34 | 34 |  |  |  | 1
55 | STRIX1-OSS-056 | Feature name - EX-FEAT-056 | Chuanqi Sun | SDMA | SDMA Performance - Single Engine |  | P1 | nsdma401.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
56 | STRIX1-OSS-057 | Feature name - EX-FEAT-057 | Chuanqi Sun | SDMA | SDMA Stress Test - CGCG |  | P3 | nsdma412.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  | 0 |  | 1
57 | STRIX1-OSS-058 | Feature name - EX-FEAT-058 | Chuanqi Sun | SDMA | SDMA Stress Test - VDDGFX |  | P3 | nsmda410.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  | 0 |  | 1
58 | STRIX1-OSS-059 | Feature name - EX-FEAT-059 | Chuanqi Sun | SDMA | SRBM Writes |  | P3 | nsdma120.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1
59 | STRIX1-OSS-060 | Feature name - EX-FEAT-060 | Chuanqi Sun | SDMA | Support byte aligned Count in normal tiled copy |  | P3 | nsdma2.6 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
60 | STRIX1-OSS-061 | Feature name - EX-FEAT-061 | Chuanqi Sun | SDMA | Support Native TMZ support |  | P3 | nsdma152-nsdma159.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  | 0 |  | 1
61 | STRIX1-OSS-062 | Feature name - EX-FEAT-062 | Chuanqi Sun | SDMA | Poll Register Write Memory |  | P2 | nsdma16.3 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
62 | STRIX1-OSS-063 | Feature name - EX-FEAT-063 | Chuanqi Sun | SDMA | Conditional Execution |  | P2 | nsdma26.1-2,nsdma27.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
63 | STRIX1-OSS-064 | Feature name - EX-FEAT-064 | Chuanqi Sun | SDMA | Predicated Execution |  | P3 | nsdma182.1-2,nsdma183.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
64 | STRIX1-OSS-065 | Feature name - EX-FEAT-065 | Chuanqi Sun | SDMA | Generate PTE/PDE |  | P3 | nsdma30.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
65 | STRIX1-OSS-066 | Feature name - EX-FEAT-066 | Chuanqi Sun | SDMA | Copy Mask PTE/PDE |  | P3 | nsdma201.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
66 | STRIX1-OSS-067 | Feature name - EX-FEAT-067 | Chuanqi Sun | SDMA | RMW PTE/PDE |  | P3 | nsdma203.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
67 | STRIX1-OSS-068 | Feature name - EX-FEAT-068 | Chuanqi Sun | SDMA | Timestamp Commands |  | P3 | nsdma56.1-2,nsdms57.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
68 | STRIX1-OSS-069 | Feature name - EX-FEAT-069 | Chuanqi Sun | SDMA | Translation failure RESP MODE[4:0] |  | P2 | nsdma126-nsdma134.1-9 | TServer |  | 1 | 9 | Legacy | 1 | 9 | 1 | N-1 | 9 | 9 | 9 |  |  |  | 1 |  | 9 | 9 |  |  |  | 1
69 | STRIX1-OSS-070 | Feature name - EX-FEAT-070 | Chuanqi Sun | SDMA | VM_INVALIDATION |  | P3 | nsdma220.1-18 | TServer |  | 1 | 18 | Legacy | 1 | 18 | 1 | N-1 | 18 | 18 | 18 |  |  |  | 1 |  | 18 | 18 |  |  |  | 1
70 | STRIX1-OSS-071 | Feature name - EX-FEAT-071 | Chuanqi Sun | SDMA | Page Migration |  | P3 | nsdma8.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
71 | STRIX1-OSS-072 | Feature name - EX-FEAT-072 | Chuanqi Sun | SDMA | Trap Command |  | P2 | nsdma14.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
72 | STRIX1-OSS-073 | Feature name - EX-FEAT-073 | Chuanqi Sun | SDMA | VDDGFX power down support |  | P3 | nsdma228.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  | 0 |  | 1
73 | STRIX1-OSS-074 | Feature name - EX-FEAT-074 | Chuanqi Sun | SDMA | Support 8 general purpose HW queue with programmable queue scheduling/priority |  | P3 | nsdma213.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1
74 | STRIX1-OSS-075 | Feature name - EX-FEAT-075 | Chuanqi Sun | SDMA | Queue process detection and per-queue reset |  | P3 | nsdma216.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
75 | STRIX1-OSS-076 | Feature name - EX-FEAT-076 | Chuanqi Sun | SDMA | SDMA doorbell common range, daisy chain doorbell intf among SDMA controllers |  | P3 | nsdma1.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
76 | STRIX1-OSS-077 | Feature name - EX-FEAT-077 | Chuanqi Sun | SDMA | non-recoverable page fault reporting |  | P2 | nsdma126.1-3,127.1-3,128.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1
77 | STRIX1-OSS-078 | Feature name - EX-FEAT-078 | Chuanqi Sun | SDMA | Improved ucode exception/interrupt handling enhancement |  | P2 | nsdma14.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
78 | STRIX1-OSS-079 | Feature name - EX-FEAT-079 | Chuanqi Sun | SDMA | Enhanced RB preemption protocol |  | P3 | nsdma217.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
79 | STRIX1-OSS-080 | Feature name - EX-FEAT-080 | Chuanqi Sun | SDMA | ucode loading enhacement |  | P3 | nsdma801.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
80 | STRIX1-OSS-081 | Feature name - EX-FEAT-081 | Chuanqi Sun | SDMA | WPTR poll enhancement |  | P3 | nsdma1.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
81 | STRIX1-OSS-082 | Feature name - EX-FEAT-082 | Chuanqi Sun | SDMA | Support mid-command boundary on quantum expire |  | P3 | nsdma218.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
82 | STRIX1-OSS-083 | Feature name - EX-FEAT-083 | Chuanqi Sun | SDMA | Change SDMA's interrupt SourceID/RingID |  | P3 | nsdma14.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
83 | STRIX1-OSS-084 | Feature name - EX-FEAT-084 | Chuanqi Sun | SDMA | Const_fill count size expands to 1GB |  | P2 | nsdma59.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
84 | STRIX1-OSS-085 | Feature name - EX-FEAT-085 | Chuanqi Sun | LSDMA | Linear Copy(LSDMA) |  | P2 | nsdma1.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
85 | STRIX1-OSS-086 | Feature name - EX-FEAT-086 | Chuanqi Sun | LSDMA | Linear Backwards Copy(LSDMA) |  | P3 | nsdma5.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
86 | STRIX1-OSS-087 | Feature name - EX-FEAT-087 | Chuanqi Sun | LSDMA | Linear Copy Broadcast(LSDMA) |  | P3 | nsdma4.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
87 | STRIX1-OSS-088 | Feature name - EX-FEAT-088 | Chuanqi Sun | LSDMA | Linear Sub-Window Copy(LSDMA) |  | P3 | nsdma7.101-105 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
88 | STRIX1-OSS-089 | Feature name - EX-FEAT-089 | Chuanqi Sun | LSDMA | Linear large Sub-Window Copy(LSDMA) |  | P3 | nsdma93.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
89 | STRIX1-OSS-090 | Feature name - EX-FEAT-090 | Chuanqi Sun | LSDMA | Page Eviction Copy(LSDMA) |  | P2 | nsdma8.101-104 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
90 | STRIX1-OSS-091 | Feature name - EX-FEAT-091 | Chuanqi Sun | LSDMA | Tiled Copy(LSDMA) |  | P3 | nsdma7.101-105 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
91 | STRIX1-OSS-092 | Feature name - EX-FEAT-092 | Chuanqi Sun | LSDMA | Tiled to Tiled Sub-Window Copy(LSDMA) |  | P3 | nsdma9.101-105 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
92 | STRIX1-OSS-093 | Feature name - EX-FEAT-093 | Chuanqi Sun | LSDMA | Tiled Sub-Window Copy(LSDMA) |  | P2 | nsdma9.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
93 | STRIX1-OSS-094 | Feature name - EX-FEAT-094 | Chuanqi Sun | LSDMA | Linear to Linear Copy Command(LSDMA) |  | P3 | nsdma10.101-105 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
94 | STRIX1-OSS-095 | Feature name - EX-FEAT-095 | Chuanqi Sun | LSDMA | Linear to Structured / Structured to Linear copy(LSDMA) |  | P3 | nsdma13.101-102 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
95 | STRIX1-OSS-096 | Feature name - EX-FEAT-096 | Chuanqi Sun | LSDMA | Linear to Tiled (frame to field) copy(LSDMA) |  | P2 | nsdma12.101-105 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
96 | STRIX1-OSS-097 | Feature name - EX-FEAT-097 | Chuanqi Sun | LSDMA | Linear to Tiled / Tiled to Linear Copy Command(LSDMA) |  | P2 | nsdma2.101-105, nsdma3.101-105 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1
97 | STRIX1-OSS-098 | Feature name - EX-FEAT-098 | Chuanqi Sun | LSDMA | Linear to Tiled / Tiled to Linear sub-window copy(LSDMA) |  | P2 | nsdma10.101-110 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1
98 | STRIX1-OSS-099 | Feature name - EX-FEAT-099 | Chuanqi Sun | LSDMA | Linear to Tiled copy broadcast(LSDMA) |  | P2 | nsdma11.101-105 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
99 | STRIX1-OSS-100 | Feature name - EX-FEAT-100 | Chuanqi Sun | LSDMA | Mid Command Preemption(LSDMA) |  | P3 | nsdma217.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
100 | STRIX1-OSS-101 |  | Chuanqi Sun | LSDMA | Mid Command Buffer Preemption(LSDMA) |  |  | nsdma217.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
101 | STRIX1-OSS-102 |  | Chuanqi Sun | LSDMA | RB Command Preemption(LSDMA) |  |  | nsdma217.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
102 | STRIX1-OSS-103 |  | Chuanqi Sun | LSDMA | Structure Buffer Copy(LSDMA) |  |  | nsdma13.101-102 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
103 | STRIX1-OSS-104 |  | Chuanqi Sun | LSDMA | Constant Fill Command(LSDMA) |  |  | nsdma58.101;nsma59.101 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
104 | STRIX1-OSS-105 |  | Chuanqi Sun | LSDMA | Indirect Buffer Command(LSDMA) |  |  | nsdma17.101-106 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1
105 | STRIX1-OSS-106 |  | Chuanqi Sun | LSDMA | Fence(LSDMA) |  |  | nsdma175;nsdma176.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
106 | STRIX1-OSS-107 |  | Chuanqi Sun | LSDMA | Trap(LSDMA) |  |  | nsdma14.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
107 | STRIX1-OSS-108 |  | Chuanqi Sun | LSDMA | Memory Increment(LSDMA) |  |  | nsdma160.101 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
108 | STRIX1-OSS-109 |  | Chuanqi Sun | LSDMA | Poll Memory/Register(LSDMA) |  |  | nsdma16.101-102 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
109 | STRIX1-OSS-110 |  | Chuanqi Sun | LSDMA | Poll Register Write Memory(LSDMA) |  |  | nsdma16.103 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
110 | STRIX1-OSS-111 |  | Chuanqi Sun | LSDMA | Poll Dbit Write Memory(LSDMA) |  |  | nsdma181 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
111 | STRIX1-OSS-112 |  | Chuanqi Sun | LSDMA | Conditional Execution(LSDMA) |  |  | nsdma26.101;nsdma27.101 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
112 | STRIX1-OSS-113 |  | Chuanqi Sun | LSDMA | Predicated Execution(LSDMA) |  |  | nsdma182.101;nsdma183.101 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
113 | STRIX1-OSS-114 |  | Chuanqi Sun | LSDMA | Atomic Command(LSDMA) |  |  | nsdma177.101;nsdma178.101;nsdma179.101 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1
114 | STRIX1-OSS-115 |  | Chuanqi Sun | LSDMA | VM_INVALIDATION(LSDMA) |  |  | nsdma220.21-37 | TServer |  | 1 | 17 | New | 1 | 17 | 1 | N-1 | 17 | 17 | 17 |  |  |  | 1 |  | 17 | 17 |  |  |  | 1
115 | STRIX1-OSS-116 |  | Chuanqi Sun | LSDMA | SRBM Write(LSDMA) |  |  | nsdma120.101-106 | TServer |  | 1 | 6 | New | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1
116 | STRIX1-OSS-117 |  | Chuanqi Sun | LSDMA | Burst NOP(LSDMA) |  |  | nsdma223.101-102 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
117 | STRIX1-OSS-118 |  | Chuanqi Sun | LSDMA | Timestamp(LSDMA) |  |  | nsmda56.101;nsdma57.101 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
118 | STRIX1-OSS-119 |  | Chuanqi Sun | LSDMA | Generate PTE/PDE(LSDMA) |  |  | nsdma30.101 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
119 | STRIX1-OSS-120 |  | Chuanqi Sun | LSDMA | Copy Mask PTE/PDE(LSDMA) |  |  | nsmda202.101;nsdma201.101 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
120 | STRIX1-OSS-121 |  | Chuanqi Sun | LSDMA | RMW PTE/PDE(LSDMA) |  |  | nsmda203.101 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
121 | STRIX1-OSS-122 |  | Chuanqi Sun | LSDMA | Host Access LSDMA scratch ram (LSDMA) |  |  | nsdma81.101 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
122 | STRIX1-OSS-123 |  | Chuanqi Sun | LSDMA | AQL Support (LSDMA) |  |  | nsdma214.101 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
123 | STRIX1-OSS-124 |  | Chuanqi Sun | LSDMA | (LSDMA) 2 HW Queue |  |  | nsdma1.101 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
124 | STRIX1-OSS-125 |  | Chuanqi Sun | LSDMA | (LSDMA) PIO Queue support |  |  | nsdma212.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1
125 | STRIX1-OSS-126 |  | Chuanqi Sun | LSDMA | TMZ Support(LSDMA) |  |  | nsdma152-nsdma159.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  | 0 |  | 1
126 | STRIX1-OSS-128 |  | Chuanqi Sun | HDP | Host read |  |  | hdp2.1-12 | TNG |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1
127 | STRIX1-OSS-129 |  | Chuanqi Sun | HDP | Host write |  |  | hdp1.1-12 | TNG |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1
128 | STRIX1-OSS-130 |  | Chuanqi Sun | HDP | HDP RAW Coherency |  |  | hdp12.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1
129 | STRIX1-OSS-131 |  | Chuanqi Sun | HDP | HDP Cache Stress |  |  | hdp11.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1
130 | STRIX1-OSS-132 |  | Chuanqi Sun | HDP | Flush Invalidate Cache(HDP) |  |  | hdp10.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1