## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Test Case ID | Parameters | Framework | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (JIRA ticket ID?) | Priority
0 | FEAT-01 | Doorbell sub-decoding to avoid multicast for doorbell trans in SOC15 | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Doorbell Read test | AG011.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P1
1 | FEAT-01 | Doorbell sub-decoding to avoid multicast for doorbell trans in SOC15 | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Doorbell Write test | AG011.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P1
2 | FEAT-01 | Doorbell sub-decoding to avoid multicast for doorbell trans in SOC15 | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Doorbell Self-Ring Read test | AG011.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P1
3 | FEAT-01 | Doorbell sub-decoding to avoid multicast for doorbell trans in SOC15 | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Doorbell Self-Ring Write test | AG011.004 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P1
4 | FEAT-02 | Support Resizable for Doorbell Aper | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Doorbell Aperture size test (32b BAR) | pci.apersize/Doorbell |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P2
5 | FEAT-02 | Support Resizable for Doorbell Aper | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Doorbell Aperture size test (64b BAR) | pci.apersize/Doorbell |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P2
6 | FEAT-03 | Resizable BAR enhancement for gfx's FB aperture | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Video Memory Aperture size test (32b BAR) | pci.apersize/FrameBuffer |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P2
7 | FEAT-03 | Resizable BAR enhancement for gfx's FB aperture | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Video Memory Aperture size test (64b BAR) | pci.apersize/FrameBuffer |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P2
8 | FEAT-04 | Perf Counters | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Slave Performance Counter - Frame Buffer Read trans test | nbif.gpuperf/HostRead |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
9 | FEAT-04 | Perf Counters | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Slave Performance Counter - Frame Buffer Write (32-bit) test | nbif.gpuperf/HostWrite |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
10 | FEAT-04 | Perf Counters | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Slave Performance Counter - SMN Read test | nbif.gpuperf/MemMapRead |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
11 | FEAT-04 | Perf Counters | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Slave Performance Counter - SMN Write test | nbif.gpuperf/MemMapWrite |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
12 | FEAT-05 | Power Management Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Power Management Interface Capability Block | pci.smoke.cap/pmi |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P1
13 | FEAT-06 | MSI and MSI-X Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Message Signaled Interrupts Capability Block | pci.smoke.cap/msi |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK1 |  | P1
14 | FEAT-07 | PCIe Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | List PCI Standard Capabilities Blocks | pci.smoke.cap |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
15 | FEAT-08 | Vendor Specific Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Vendor Specific Capability Block | pci.smoke.cap |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
16 | FEAT-09 | DSN Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE Device Serial Number Extended capabilities block test | AG005.008 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
17 | FEAT-10 | AER Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Advanced Error Reporting Capability Block | AG005.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
18 | FEAT-11 | Re-sizable BAR Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Resizable BAR Block | AG005.004 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
19 | FEAT-12 | DPA Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE Dynamic Power Allocation Extended capabilities block test | AG005.012 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
20 | FEAT-13 | Secondary PCIe Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE Secondary PCI Express Extended capabilities block test | AG005.007 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
21 | FEAT-14 | ACS Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Access Control Services Capability Block | AG005.009 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
22 | FEAT-15 | ATS Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Address Translation Services Capability Block | AG005.010 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
23 | FEAT-16 | PRI Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Validate Page Request Capability Block | AG005.011 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK2 |  | P1
24 | FEAT-17 | PASID Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE Process Address Space ID Extended capabilities block test | AG005.013 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
25 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 32b Writes and 32b Reads | AG009.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
26 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 16b Writes and 32b Reads | AG009.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
27 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 8b Writes and 32b Reads | AG009.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
28 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 32b Writes and 16b Reads | AG009.004 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
29 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 16b Writes and 16b Reads | AG009.005 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
30 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 8b Writes and 16b Reads | AG009.006 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
31 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 32b Writes and 8b Reads | AG009.007 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
32 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 16b Writes and 8b Reads | AG009.008 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
33 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Register Access with 8b Writes and 8b Reads | AG009.009 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
34 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Indirect Register Access | AG012.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
35 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Direct Register Write and Indirect Register Read | AG012.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
36 | FEAT-18 | Register Accesses (direct and indirect) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Memory Mapped Indirect Register Write and Direct Register Read | AG012.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
37 | FEAT-19 | BAR allocation and Access | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | List Apertures | pci.apersize |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
38 | FEAT-19 | BAR allocation and Access | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Register Aperture size test (32b BAR) | pci.apersize/Register |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
39 | FEAT-19 | BAR allocation and Access | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Register Aperture size test (64b BAR) | pci.apersize/Register |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
40 | FEAT-19 | BAR allocation and Access | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | ROM Aperture size test | pci.apersize/BiosRom |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
41 | FEAT-19 | BAR allocation and Access | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI IO space BAR sanity check test | pci.ioaper/CheckAttribute |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
42 | FEAT-20 | BAR resizing | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | List PCIE resizable BAR capability block information | AG031.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
43 | FEAT-20 | BAR resizing | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE resizable BAR size test (32b BAR) | AG031.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
44 | FEAT-20 | BAR resizing | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE resizable BAR size test (64b BAR) | AG031.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
45 | FEAT-21 | Memory access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | HDP FB Access with FB Always ON | AG029.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK4 |  | P1
46 | FEAT-21 | Memory access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Indirect Video Memory Access with FB Always ON | AG029.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK4 |  | P1
47 | FEAT-21 | Memory access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Direct Video Memory Access with FB Read and Write ON | AG029.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK4 |  | P1
48 | FEAT-21 | Memory access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Indirect Video Memory Access with FB Read and Write ON | AG029.004 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK4 |  | P1
49 | FEAT-21 | Memory access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Direct Video Memory Access with FB Read ON and FB Write OFF | AG029.005 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK4 |  | P1
50 | FEAT-21 | Memory access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Indirect Video Memory Access with FB Read ON and FB Write OFF | AG029.006 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK4 |  | P1
51 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 32b Writes and 32b Reads | AG008.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
52 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 16b Writes and 32b Reads | AG008.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
53 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 8b Writes and 32b Reads | AG008.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
54 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 32b Writes and 16b Reads | AG008.004 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
55 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 16b Writes and 16b Reads | AG008.005 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
56 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 8b Writes and 16b Reads | AG008.006 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
57 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 32b Writes and 8b Reads | AG008.007 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
58 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 16b Writes and 8b Reads | AG008.008 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
59 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Register Access with 8b Writes and 8b Reads | AG008.009 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
60 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Indirect Register Access | AG013.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
61 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Direct Register Write and Indirect Register Read | AG013.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
62 | FEAT-22 | I/O access control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI I/O Mapped Indirect Register Write and Memory Mapped Direct Register Read | AG013.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
63 | FEAT-23 | FLR (Func 0/1/2) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | FLR to function 0 (Video) with FLR enabled | AG043.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 | Copy from Strix1: Passes with Mini-FW aka MP0 bootcode, fails with Full-FW aka MP1 FW | WK3 |  | P3
64 | FEAT-23 | FLR (Func 0/1/2) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | FLR to function 1 (Audio) with FLR enabled | AG043.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 | Copy from Strix1: Passes with Mini-FW aka MP0 bootcode, fails with Full-FW aka MP1 FW | WK3 |  | P3
65 | FEAT-23 | FLR (Func 0/1/2) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | FLR to function 2 with FLR enabled | AG043.005 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 | Copy from Strix1: Passes with Mini-FW aka MP0 bootcode, fails with Full-FW aka MP1 FW | WK3 |  | P3
66 | FEAT-24 | Bus_master_en control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE bus master enable test | AG065.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
67 | FEAT-24 | Bus_master_en control | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE bus master disable test | AG065.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
68 | FEAT-25 | Multi-function support | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Multifunction Configuration test | AG033.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P2
69 | FEAT-25 | Multi-function support | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Unmapped Function test | AG033.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P2
70 | FEAT-25 | Multi-function support | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCI Unmapped Function test - UR reporting disabled | AG033.003 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P2
71 | FEAT-26 | AER (See AER feature set for details) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Endpoint Uncorrectable Error Capabilities Test | AG024.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
72 | FEAT-26 | AER (See AER feature set for details) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Endpoint Correctable Error Capabilities Test | AG024.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
73 | FEAT-26 | AER (See AER feature set for details) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Single EP Basic Error Reporting Capabilities Test | AG026.001 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
74 | FEAT-26 | AER (See AER feature set for details) | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | Single EP Advanced Error Reporting Capabilities Test | AG026.002 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
75 | FEAT-27 | Data Link Feature Extended Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE data link feature Extended capabilities block test | AG005.019 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
76 | FEAT-28 | Physical layer 16GT/s Extended Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE Physical Layer 16GT/S Extended capabilities block test | AG005.020 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
77 | FEAT-29 | Lane Margining at the Receiver Extended Capability | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | PCIE Lane Margining Extended capabilities block test | AG005.021 |  | TServer | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
78 | FEAT-30 | link speed switch | tonychen | pcie | pcie | SSD link speed switch to GEN1 | pci.link.speed_switch.on_nvme/through_capability.to_gen1 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
79 | FEAT-30 | link speed switch | tonychen | pcie | pcie | SSD link speed switch to GEN2 | pci.link.speed_switch.on_nvme/through_capability.to_gen2 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
80 | FEAT-30 | link speed switch | tonychen | pcie | pcie | SSD link speed switch to GEN3 | pci.link.speed_switch.on_nvme/through_capability.to_gen3 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
81 | FEAT-30 | link speed switch | tonychen | pcie | pcie | SSD link speed switch to GEN4 | pci.link.speed_switch.on_nvme/through_capability.to_gen4 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
82 | FEAT-31 | PCIE PHY L1 PM Substates Test | tonychen | pcie | pcie | Substate 1 test with ASPM method | pci.link.l1ss/with_aspm.L11 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
83 | FEAT-31 | PCIE PHY L1 PM Substates Test | tonychen | pcie | pcie | Substate 1 test with PCI-PM method | pci.link.l1ss/with_pcipm.L11 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
84 | FEAT-31 | PCIE PHY L1 PM Substates Test | tonychen | pcie | pcie | Substate 2 test with ASPM method | pci.link.l1ss/with_aspm.L12 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
85 | FEAT-31 | PCIE PHY L1 PM Substates Test | tonychen | pcie | pcie | Substate 2 test with PCI-PM method | pci.link.l1ss/with_pcipm.L12 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK5 |  | P1
86 | FEAT-32 | Pcie Link quality test | tonychen | pcie | pcie | Pcie Link quality test | pci.nak.check |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  | WK3 |  | P1
87 | FEAT-33 | Pciephy_Equalization | tonychen | pcie | pcie | PCIe PHY Equalization Test | pci.link.equalization.from_rc/Gen3 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
88 | FEAT-33 | Pciephy_Equalization | tonychen | pcie | pcie | PCIe PHY Equalization Test | pci.link.equalization.from_rc/Gen4 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
89 | FEAT-34 | PCIe link traffic | tonychen | pcie | pcie | NVMe Read/Write | pci.link.traffic/ReadWrite |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
90 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/0 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
91 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/1 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
92 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/2 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
93 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/3 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
94 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/4 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
95 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/5 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
96 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/6 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
97 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor Test for nBIF | rsmu.smoke.cac.for_nbif/7 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
98 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/0 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
99 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/1 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
100 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/2 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
101 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/3 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
102 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/8 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
103 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/9 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
104 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/10 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1
105 | FEAT-35 | RSMU CAC test | tonychen | nBIF/SYSHUB4.6 | nBIF/SYSHUB4.6 | RSMU CAC Monitor for SYSHUB | rsmu.smoke.cac.for_shub/11 |  | TNG | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 |  | 1 |  |  |  |  | 0 |  |  |  | P1