## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run2 | Pass3 | Waived4 | Fail5 | Skip6 | % Pass Rate7 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | 11.5.010 | enable sp to execute 2 vcmp f16/f32 ops on the same cycle DEGFX11-9003 | Botao | SH |  |  | P1 | shci2042 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk1
1 | 11.5.008 | use 2x rate valu to double vinterp rate DEGFX11-9002 | Botao | SH |  |  | P1 | shci2041 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk1
2 | 11.5.007 | LSO sub-batching DEGFX11-9001 | Steven | PP |  | sanity test from dv | P1 | db53.3 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk1
3 | ext_001 | GCUTCL2 - VML2: Full GCR Support | Glenn | UTC |  | utc_gpuvm_gcr_support | P3 | utci7.1-4, 6.1-5 | -vm | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk12
4 | ext_002 | GCUTCL2 - VML2: Return invalid V=0 PA to GCR w/o generating an intr | Glenn | UTC |  | utc_gpuvm_gcr_support | P3 | utci7.5 | -vm | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk12
5 | ext_005 | GCEA - 64 byte single-operand atomics | Glenn | GLX |  | gl2_gcea_64B_atomics | P3 | glxi52 |  | 0 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk12
6 | 11.5.002 | GL2 Decompressor support for increased max compressed block size from 128B to 256B DEGFX11-8995 | Glen | CMM |  |  | P1 | glxi53.1-2 |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk2
7 | 11.5.021 | Optimize 32B compressed write for Strix1 DF DEGFX11-9012 | Glen | CMM |  |  | P2 | glxi54.1-4 |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk2
8 | 11.5.034 | This is a Jira for a Single Pass Wave64 Trans Issue Feature DEGFX11-8500 | Shuhui | SH |  | Indirectly coverage by existing SH test | P2 | shci20.1 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk2
9 | 11.5.013 | scalar ALU float support. Trans instruction tracked as another feature; This is the same as gfx 11 11.186 DEGFX11-9006 | Yu Xuan | SH |  |  | P2 | shci2037.1-2 |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk3
10 | 11.5.014 | Add additional F16 arithmetic and compare ins on top of 11.5.013 DEGFX11-9007 | Yu Xuan | SH |  |  | P2 | shci2037.1-2 |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk3
11 | 11.5.026 | remove support logic in 1x5 VGPR DEGFX11-9014 | Shuhui | SH |  |  |  | shci2017.1 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk3
12 | 11.5.011 | Point Sample Acceleration DEGFX11-9004 | Frank | TEX |  |  | P1 | txi81.1-3 |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk3
13 | 11.5.006 | Light Shaft 256b htile mask enhancement DEGFX11-9000 | Steven | PP |  | sanity tests (port from dv, reuse tests from 11.5.004 | P1 | db52.7-21, db53.9-14 |  | 1 | 21 | Legacy | 1 | 21 | 1 | N-1 | 21 | 21 | 21 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk3
14 | 11.5.015 | Separate virtual fifos for each RB subId DEGFX11-9008 | Glen | CMM |  |  | P2 | glxi56.1-8 |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk3
15 | 11.5.039 | Compiler assisted single use VGPR write kill DEGFX11-8985 | Shuhui | SH |  | sanity test | P2 | shci2038 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk4
16 | 11.5.039 | Compiler assisted single use VGPR write kill DEGFX11-8985 | Shuhui | SH |  | sanity co-issue test | P2 | shci2038.1 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk4
17 | 11.5.039 | Compiler assisted single use VGPR write kill DEGFX11-8985 | Shuhui | SH |  | sanity interaction test | P2 | shci2038.2,3.1-3,4.1-3 |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk4
18 | 11.5.012 | 2x sampler rate DEGFX11-9005 | Frank | TEX |  |  | P1 | txi80.1-10 |  | 10 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk4
19 | 11.5.005 | Batch Depth/Z Pre-Pass in PBB Performance Optimization DEGFX11-8999 | Matthew | PP |  | sanity tests from dv | P1 | db50.0-8,14-45.1-45,50-53.1-45 |  | 1 | 45 | Legacy | 1 | 45 | 1 | N-1 | 45 | 45 | 45 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk5
20 | 11.5.005 | Batch Depth/Z Pre-Pass in PBB Performance Optimization DEGFX11-8999 | Steven | PP |  | STD4.115(combine 11.5.005 pbb_zpp and with 11.5.017 pbb_tile_order_rev) | P1 | std4.115 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk5
21 | 11.5.017 | PBB screen space tile order reversal across batches DEGFX11-9010 | Steven | PP |  | STD4.115(combine 11.5.005 pbb_zpp and with 11.5.017 pbb_tile_order_rev) | P2 | std4.115 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk5
22 | 11.5.042 | TA footprint bug fix for PRT+ LOD-accum and status update | Frank | TEX |  | nv3_sample_vs_lod_accum_footprint_test | P2 | txi83.1-8, txi84.1-6 |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk6
23 | 11.5.030 | WGP&RB GRBM index remapping DEGFX11-9018 | Xiaojing | COM |  |  | P2 | gci1300.1-4 |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk6
24 | 11.5.004 | PBB Light Shaft Performance Optimization DEGFX11-8997 | Steven | PP |  | 3 stress tests | P1 | ppi300.1-2 |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | Passing locally, pending code review | 0 |  |  |  |  | 0 | Passing locally, pending code review | Wk6
25 | 11.5.004 | PBB Light Shaft Performance Optimization DEGFX11-8997 | Matthew | PP |  | sanity tests from dv | P1 | db52.0-23, db53.0-15, db54.0-4 |  | 1 | 45 | Legacy | 1 | 45 | 1 | N-1 | 45 | 45 | 45 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | Wk6
26 | 11.5.018 | Reuse decompressed texels. Use cross bar to share decompressed texels across quad DEGFX11-9011 | Frank | TEX |  |  | P2 | txi82.1 |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | Passing locally, pending code review | 0 |  |  |  |  | 0 | Passing locally, pending code review | Wk7
27 | 11.5.003 | Fast GFXOFF DEGFX11-8996 |  | COM/CTL |  | existing std2.6/std4.34 + gfxoff | P4 |  | "-gfxoff" | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 1 | To be covered by regular GFXOFF coverage by PMM team | 0 |  |  |  |  | 0 | To be covered by regular GFXOFF coverage by PMM team
28 | 11.5.035 | Replace SQ IS Store Ram with IS Cache DEGFX11-8421 | Shuhui | SH |  | No software visibility | P2 |  |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0
29 | 11.5.050 | 1x5VGPR_support | Botao | SH |  | vgpr_size_test (11.339 on NV31) | P1 | shci2017.0 |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | https://jira.amd.com/browse/CTANV31-3229 | 0 |  |  |  |  | 0 | https://jira.amd.com/browse/CTANV31-3229 | Wk3
30 | 11.5.051 | Dynamic GPU Scaling | Xiaojing | SH |  | DGS Harvesting Test | P1 |  |  |  | 1 | New |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
31 | 11.5.041 | Add constraints on Tile order reversal | Steven | PP |  | from discussion we don't need to support feature | P2 |  |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0