## MD-29 GFX
| Id | Name | % TP Done | # Written | % Code Done | ID | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-249 | 12.000 - Navi4x configuration changes | 1 | 1 | 1 | 12 | 0 | 12 | Navi4x configuration changes | Dennis | GFX |  |  | P1 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
1 | RQ-415 | 12.387 - Block Initiatives | 1 |  | 1 | 12.387 | 172 | 12.387 | Block Initiatives |  | GFX |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not a feature | 0 |  |  |  |  | 1
2 | RQ-418 | 12.396 - Airtight FIFO Design Robustness | 1 |  | 1 | 12.396 | 176 | 12.396 | Airtight FIFO Design Robustness | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | The change is a quality initiative, and transparent to software. | 0 |  |  |  |  | 1
3 | RQ-419 | 12.397 - Benchmark Stimulus Replay at Block | 1 |  | 1 | 12.397 | 177 | 12.397 | Benchmark Stimulus Replay at Block | Xiaojing | GFX |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1
4 | RQ-420 | 12.398 - Adoption of RDL2RTL | 1 |  | 1 | 12.398 | 178 | 12.398 | Adoption of RDL2RTL | Xiaojing | GFX |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1
5 | RQ-422 | 12.400 - SRAM Bit/byte write enable | 1 |  | 1 | 12.4 | 180 | 12.4 | SRAM Bit/byte write enable | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | This is a pure H/W change which impacts the SRAM access. This would be covered implicitly by running various 3D/Compute workload. There is no need to develop a target test case for this feature. | 0 |  |  |  |  | 1
6 | RQ-424 | 12.402 - Repeater Clock Gating (Clock Gating Efficiency focus) | 1 |  | 1 | 12.402 | 182 | 12.402 | Repeater Clock Gating (Clock Gating Efficiency focus) | Pierce | GFX |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Device level change, no in-out verification, indirect coverage through GFXOFF setting ClockGatingGfxRepeaterFgcg=1, PMM coverage through CGCG/PG features | 0 |  |  |  |  | 1
7 | RQ-482 | 12.403 - MGCG partitioning (Goal is to reduce gating residency of MGCG domains. Power saved is function of reduction in MGCG domain clock residency and physical partitioning of domain (size of domain clones ICG placement pre MGCG power). | 1 |  | 1 | 12.403 | 183 | 12.403 | MGCG partitioning (Goal is to reduce gating residency of MGCG domains. Power saved is function of reduction in MGCG domain clock residency, and physical partitioning of domain (size of domain, clones, ICG placement, pre MGCG power). | Pierce | GFX |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Device level change, no in-out verification, indirect coverage through GFXOFF setting ClockGatingGfxMgcg=1, PMM coverage through CGCG/PG features | 0 |  |  |  |  | 1
8 | RQ-483 | 12.406 - With GPO enabled perfmon clock and flops connected to it are currently not gated. Proposal is to improve clock gating of “event” flops and counters used in performance monitor logic | 1 |  | 1 | 12.406 | 184 | 12.406 | With GPO enabled, perfmon clock and flops connected to it are currently not gated. Proposal is to improve clock gating of “event” flops and counters used in performance monitor logic | Pierce | GFX |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Deferred GFX13, GFXIPARCH-785 | 0 |  |  |  |  | 1
9 | RQ-441 | 12.422 - Navi4c (chiplet) GFXIP STA Targets | 1 |  | 1 | 12.422 | 194 | 12.422 | Navi4c (chiplet) GFXIP STA Targets | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | The feature is not applicable to Navi44/48. Please remove this from your feature list. | 0 |  |  |  |  | 1

## MD-30 PP
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-250 | 12.001 - Separate color blend opt bits out of CB_COLORn_INFO | 1 |  | 0.5 | 1 | 12.001 | Separate color blend opt bits out of CB_COLORn_INFO | Steven/David | PP |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
1 | RQ-252 | 12.003 - Separate PS_ITER_SAMPLE out of PA_SC_MODE_CNTL_1 | 1 |  | 0.9 | 3 | 12.003 | Separate PS_ITER_SAMPLE out of PA_SC_MODE_CNTL_1 | Steven/David | PP |  |  | P1 | std4.34 | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
2 | RQ-253 | 12.004 - Separate SAMPLE_RATE out of DB_COUNT_CONTROL | 1 | 1 | 0.5 | 4 | 12.004 | Separate SAMPLE_RATE out of DB_COUNT_CONTROL | David/Faez | PP |  |  | P1 | PPI39 PPI100.65.1-2 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
3 | RQ-255 | 12.007 - PA_SC_AA_CONFIG changes | 1 |  | 0 | 6 | 12.007 | PA_SC_AA_CONFIG changes | David/Steven | PP |  |  | P1 | PPI101.5 | TServer |  | 1 | 1 | Delta | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
4 | RQ-256 | 12.008 - PA_SC_CONSERVATIVE_RASTERIZATION_CNTL changes | 1 |  | 0 | 7 | 12.008 | PA_SC_CONSERVATIVE_RASTERIZATION_CNTL changes | David/Steven | PP |  |  | P1 | PPI100.141 | TServer |  | 1 | 1 | Delta | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
5 | RQ-257 | 12.009 - Eliminate PA_SU_SC_MODE_CNTL.KEEP_TOGETHER_ENABLE | 1 | 1 | 1 | 8 | 12.009 | Eliminate PA_SU_SC_MODE_CNTL.KEEP_TOGETHER_ENABLE | David/Steven | PP |  |  | P1 | STD1.6 -tglEnableSCBinning=0 | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
6 | RQ-258 | 12.010 - Separate AUTO_RESET_CNTL from PA_SC_LINE_STIPPLE | 1 |  | 0 | 9 | 12.01 | Separate AUTO_RESET_CNTL from PA_SC_LINE_STIPPLE | David/Steven | PP |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
7 | RQ-259 | 12.011 - Implicit viewport scissoring | 1 | 6 | 0.85714 | 10 | 12.011 | Implicit viewport scissoring | David/Steven | PP |  |  | P1 | sc42.2 sc42.3 sc26.9 sc26.10 sc26.11 sc26.12 | TServer |  | 1 | 7 | New | C-Model | 6 | 2 | 2 |  |  |  | 0.33333 |  | 0 |  |  |  |  | 0 |  | WK4
8 | RQ-260 | 12.012 - Simplify workaround for DEGGIGXX0-4644 | 1 |  | 1 | 11 | 12.012 | Simplify workaround for DEGGIGXX0-4644 | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | Delta |  | 0 | 0 |  |  |  |  | 1 | Feature dropped | 0 |  |  |  |  | 1
9 | RQ-262 | 12.014 - Split DB_RENDER_OVERRIDE | 1 |  | 0 | 13 | 12.014 | Split DB_RENDER_OVERRIDE | David/Steven | PP |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
10 | RQ-263 | 12.015 - DB_STENCILREFMASK refactor | 1 |  | 0 | 14 | 12.015 | DB_STENCILREFMASK refactor | David/Steven | PP |  |  | P1 |  | TServer |  | 1 | 1 | Delta | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
11 | RQ-264 | 12.016 - Per target control for CB BIG_PAGE/L2_BYPASS | 1 |  | 0.5 | 15 | 12.016 | Per target control for CB BIG_PAGE/L2_BYPASS | Steven/David | PP |  |  | P1 |  | TServer |  | 1 | 5 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
12 | RQ-265 | 12.017 - MSAA shader write support for D/S images | 1 |  | 1 | 16 | 12.017 | MSAA shader write support for D/S images | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Covered by 12.164 hybrid_depth_comp | 0 |  |  |  |  | 1
13 | RQ-478 | 12.031 - Support greater than 16k x 16k x 8k textures (64k x 64k x 16k inc. 16 mip levels to support 64k). Reduce/simplify swizzle modes. | 1 | 2 | 1 | 21 | 12.031 | Support greater than 16k x 16k x 8k textures (64k x 64k x 16k, inc. 16 mip levels to support 64k). Reduce/simplify swizzle modes. | Steven/David | PP |  |  | P1 | ppi302.3,ppi302.5 | TServer |  | 1 | 2 | New | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
14 | RQ-337 | 12.164 - Hybrid Depth Compression | 1 | 54 | 1 | 85 | 12.164 | Hybrid Depth Compression | David/Faez | PP |  |  | P1 | PPI406.1-8 PPI406.11-18 PPI406.21-28 PPI406.31-38 PPI406.41-48 | TServer |  | 1 | 54 | New | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
15 | RQ-338 | 12.165 - HiZ/S in SC | 1 | 1 | 1 | 86 | 12.165 | HiZ/S in SC | Steven/David | PP |  |  | P1 | std5.9 | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | run with -tZTileBuffer=0 and 1 | 0 |  |  |  |  | 0 |  | WK2
16 | RQ-339 | 12.167 - CB codec removal/simplifications | 1 | 1 | 0.5 | 87 | 12.167 | CB codec removal/simplifications | David/Steven | PP |  |  | P1 | Same to 12.164 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
17 | RQ-340 | 12.168 - VRS fragment compression | 1 |  | 1 | 88 | 12.168 | VRS fragment compression | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Descoped, can drop | 0 |  |  |  |  | 1
18 | RQ-363 | 12.223 - Update PA/SC support for 1 to 9SE and updated pix distribution algorithm | 1 | 2 | 1 | 112 | 12.223 | Update PA/SC support for 1 to 9SE and updated pix distribution algorithm | David/Steven | PP |  |  | P1 | STD1.6 GCI30.3 | TServer |  | 1 | 2 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
19 | RQ-364 | 12.224 - Drop the FSR support from SC PBB implementation | 1 |  | 1 | 113 | 12.224 | Drop the FSR support from SC PBB implementation | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | No direct coverage required | 0 |  |  |  |  | 1
20 | RQ-365 | 12.225 - DB design simplificaitons while updating for hybrid depth compression | 1 | 1 | 0.5 | 114 | 12.225 | DB design simplificaitons while updating for hybrid depth compression | David/Steven | PP |  |  | P1 | Same to 12.164 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
21 | RQ-414 | 12.382 - [Strix] pbb_tile_order_rev -- from BRP:11.5.017 | 1 |  | 1 | 171 | 12.382 | [Strix] pbb_tile_order_rev -- from BRP:11.5.017 | Steven/David | PP |  |  | P2 |  |  |  | 1 | 0 | Legacy |  | 0 | 0 |  |  |  |  | 1 | Driver team will verify this | 0 |  |  |  |  | 1
22 | RQ-421 | 12.399 - Remove Coverage into Render Targets | 1 |  | 1 | 179 | 12.399 | Remove Coverage into Render Targets | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Design confirmed feature is fully dropped | 0 |  |  |  |  | 1
23 | RQ-463 | 12.458 - Descope VRS Compression feature | 1 |  | 1 | 216 | 12.458 | Descope VRS Compression feature | Steven/David | PP |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
24 | RQ-467 | 12.462 - Descope Verification of 16xaa for VRS Coarse Rates | 1 |  | 1 | 220 | 12.462 | Descope Verification of 16xaa for VRS Coarse Rates (1x2, 2x2, 2x1) | Steven/David | PP |  |  | P3 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1

## MD-31 SIO
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-251 | 12.002 - Change SPI_VS_OUT_CONFIG and SPI_PS_IN_CONTROL from context to persistent state regs | 1 | 2 | 1 | 2 | 12.002 | Change SPI_VS_OUT_CONFIG and SPI_PS_IN_CONTROL from context to persistent state regs | Xiaojing | SIO |  |  | P1 | spi20.0,spi20.1 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
1 | RQ-261 | 12.013 - Separate event enable bits out of SPI_CONFIG_CNTL | 1 | 1 | 0.5 | 12 | 12.013 | Separate event enable bits out of SPI_CONFIG_CNTL | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 2 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
2 | RQ-301 | 12.078 - Move SQG outside of SPI | 1 |  | 1 | 51 | 12.078 | Move SQG outside of SPI | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Hardware feature change, no software visibility. | 0 |  |  |  |  | 1
3 | RQ-316 | 12.124 - CSC Group Launch guarantee | 1 | 2 | 1 | 66 | 12.124 | CSC Group Launch guarantee | Xiaojing | SIO |  |  | P2 | spi124.0,spi124.1 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
4 | RQ-317 | 12.125 - GFX Pipe Group Launch Guarantee | 1 | 0.75 | 0.75 | 67 | 12.125 | GFX Pipe Group Launch Guarantee | Xiaojing | SIO |  |  | P2 | spi125 | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 | Issues in gfx_pm4_packets | 0 |  |  |  |  | 0 |  | WK6
5 | RQ-323 | 12.139 - Simplify software debugger register change process | 1 | 2 | 1 | 73 | 12.139 | Simplify software debugger register change process | Xiaojing | SIO |  |  | P1 | spi1390.1-2,spi1391.1-2 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
6 | RQ-325 | 12.143 - Remove SA Affinity for Pixel Shaders | 1 |  | 1 | 75 | 12.143 | Remove SA Affinity for Pixel Shaders | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Driver team will verify this | 0 |  |  |  |  | 1
7 | RQ-336 | 12.163 - Architected SGPR Values | 1 | 1 | 0.5 | 84 | 12.163 | Architected SGPR Values | Xiaojing | SIO |  |  | P2 | sh1630.1-2 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 | may need write in TNG | 0 |  |  |  |  | 0 |  | WK6
8 | RQ-350 | 12.197 - Ping-Pong walking for dispatches | 1 | 1 | 1 | 98 | 12.197 | Ping-Pong walking for dispatches | Xiaojing | SIO |  |  | P2 | spi197 | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
9 | RQ-351 | 12.201 - Compute Grid Programmable Walk Order (cs_grid_walk_order) | 1 | 2 | 1 | 99 | 12.201 | Compute Grid Programmable Walk Order (cs_grid_walk_order). If not doing morton'ish (ex. 2x2) then improving launch rate for existing typewriter (ex 4x1) is P1) | Xiaojing | SIO |  |  | P1 | spi2010.1-2,spi2011.1-2 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
10 | RQ-352 | 12.202 - Compute Thread Walk Order (cs_thread_walk_order) | 1 | 1.5 | 0.75 | 100 | 12.202 | Compute Thread Walk Order (cs_thread_walk_order) | Xiaojing | SIO |  |  | P1 | spi2020.1-2,spi2021.1-2 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 | Issues in gfx_pm4_packets | 0 |  |  |  |  | 0 |  | WK4
11 | RQ-384 | 12.294 - Improve SPI work limiting controls (spi_work_limit_ctrl) | 1 | 2 | 1 | 137 | 12.294 | Improve SPI work limiting controls (spi_work_limit_ctrl) | Xiaojing | SIO |  |  | P1 | spi2940.1-2, spi2941.1-2 | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
12 | RQ-389 | 12.312 - Convert PAL implementation of streamout to sw solution enables GDS removal | 1 |  | 1 | 145 | 12.312 | Convert PAL implementation of streamout to sw solution enables GDS removal | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
13 | RQ-439 | 12.420 - Increase max scratch allocation | 1 |  | 0 | 192 | 12.42 | Increase max scratch allocation | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
14 | RQ-445 | 12.438 - Remove Soft Lock feature | 1 |  | 1 | 198 | 12.438 | Remove Soft Lock feature | Xiaojing | SIO |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | This is a removal, and no direct coverage is required. Makhan/Wanshou to check with Arch and waive from PostSi coverage. | 0 |  |  |  |  | 1
15 | RQ-448 | 12.441 - reduce VGPRs for LS and ES stages | 1 |  | 1 | 201 | 12.441 | reduce VGPRs for LS and ES stages | Xiaojing | SIO |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Feature removal inside hardware, no software visibility. | 0 |  |  |  |  | 1
16 | RQ-459 | 12.453 - Add HS and GS Stages to event collection for PS_DONE and PS_PARTIAL_FLUSH | 1 | 1 | 1 | 212 | 12.453 | Add HS and GS Stages to event collection for PS_DONE and PS_PARTIAL_FLUSH | Xiaojing | SIO |  |  | P2 | spi453 | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
17 | RQ-461 | 12.455 - Decrease CS max grid size support | 1 | 1 | 1 | 214 | 12.455 | Decrease CS max grid size support to X,Y,Z = 32b,16b,16b | Xiaojing | SIO |  |  | P2 | gfx.linpack_gfx_compute | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
18 | RQ-476 | 12.471 - Save and Restore of perfcounter and ttrace enable for GFXOFF/SRIOV | 1 |  | 0 | 229 | 12.471 | Save and Restore of perfcounter and ttrace enable for GFXOFF/SRIOV | Xiaojing | SIO |  |  | P2 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8

## MD-32 GEO
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-254 | 12.006 - GE_CNTL and VGT_LS_HS_CONFIG changes | 1 | 2 | 1 | 5 | 12.006 | GE_CNTL and VGT_LS_HS_CONFIG changes | Yu Xuan | GEO |  |  | P1 | ge1.0, ge1.1 | TServer |  | 1 | 2 | New | C-Model | 2 | 2 | 2 |  |  |  | 1 | ./tserverlite -test=ge1.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; ./tserverlite -test=ge1.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
1 | RQ-313 | 12.118 - PH Memory Queues | 1 | 3 | 1 | 63 | 12.118 | PH Memory Queues | Yu Xuan | GEO |  |  | P1 | ge2.0, ge2.1, std1.6 | TServer |  | 1 | 3 | New | Gopher | 3 | 3 | 2 |  | 1 |  | 0.66667 | ./tserverlite -test=ge2.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; ./tserverlite -test=ge2.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
2 | RQ-358 | 12.213 - deprecate HPG | 1 |  | 1 | 106 | 12.213 | deprecate HPG | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Deprecated, not visible to diags | 0 |  |  |  |  | 1
3 | RQ-484 | 12.214 - reduce GE_DIST to GE_SE wire count | 1 |  | 1 | 107 | 12.214 | reduce GE_DIST to GE_SE wire count | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | We expect indirect coverage for this feature from many Graphics workloads including Geometry shader. There is no need to plan for direct/dedicated test case for this one. | 0 |  |  |  |  | 1
4 | RQ-360 | 12.219 - ge_se in sed. Sub item under basic configuration | 1 | 1 | 1 | 109 | 12.219 | ge_se in sed. Sub item under basic configuration | Xiaojing | GEO |  |  | P1 | gfx.red_triangle_draw_composite | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
5 | RQ-361 | 12.220 - register cleanup | 1 | 1 | 1 | 110 | 12.22 | register cleanup | Xiaojing | GEO |  |  | P1 | navi48.gfx.ge.register_access | TNG |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
6 | RQ-366 | 12.247 - Register remap to match M1 | 1 | 3 | 1 | 119 | 12.247 | Register remap to match M1 | Xiaojing | GEO |  |  | P1 | food_store.1-3,mountain_range.1-3,navi48.gfx.ge.register_access.1-3 | TNG |  | 1 | 3 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
7 | RQ-377 | 12.282 - rename GE BIA containers | 1 | 1 | 1 | 130 | 12.282 | rename GE BIA containers | Xiaojing | GEO |  |  | P1 | navi48.gfx.ge.register_access | TNG |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
8 | RQ-380 | 12.286 - Remove passthru_en/esgs_ring_itemsize/old gs fastlaunch | 1 |  | 1 | 133 | 12.286 | Remove passthru_en/esgs_ring_itemsize/old gs fastlaunch | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
9 | RQ-383 | 12.292 - move offchip lds manager to GE | 1 | 2 | 1 | 136 | 12.292 | move offchip lds manager to GE | Yu Xuan | GEO |  |  | P1 | ge3.0, std4.34 | TServer |  | 1 | 2 | New | C-Model | 2 | 2 | 1 |  | 1 |  | 0.5 | ./tserverlite -test=ge3.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
10 | RQ-412 | 12.373 - Modification of GS throttle (due to 12.118 ph_memory_queues) | 1 | 4 | 1 | 169 | 12.373 | Modification of GS throttle (due to 12.118 ph_memory_queues) | Xiaojing | GEO |  |  | P1 | std1.1-4,2.1-4,3.1-4,4.1-4 | TServer |  | 1 | 4 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
11 | RQ-442 | 12.425 - GE WD_QOS.DRAW_STALL behavior | 1 |  | 1 | 195 | 12.425 | GE WD_QOS.DRAW_STALL behavior | Xiaojing | GEO |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Feature removal, no software visibility. | 0 |  |  |  |  | 1

## MD-33 TEX
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-266 | 12.019 - Broadcast stores | 1 | 2 | 1 | 17 | 12.019 | Broadcast stores | Faez/Frank | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | Gopher | 2 | 1 | 1 |  |  |  | 0.5 |  | 0 |  |  |  |  | 0 |  | WK5
1 | RQ-267 | 12.020 - out of order per-wave vmem returns | 1 | 6 | 1 | 18 | 12.02 | out of order per-wave vmem returns | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 6 | New | Gopher | 6 | 6 | 6 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
2 | RQ-272 | 12.033 - Unclamped image load/store support | 1 |  | 0 | 22 | 12.033 | Unclamped image load/store support | Frank | TEX |  |  | P2 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK9
3 | RQ-273 | 12.034 - Move PRT++ atomic ops out of TCP tags | 1 |  | 1 | 23 | 12.034 | Move PRT++ atomic ops out of TCP tags | Frank | TEX |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not an implemented feature in Navi4x | 0 |  |  |  |  | 1
4 | RQ-274 | 12.036 - Double Ray Tracing Intersect Engine | 1 | 1 | 1 | 24 | 12.036 | Double Ray Tracing Intersect Engine | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
5 | RQ-275 | 12.037 - RT instance node transform | 1 | 1 | 1 | 25 | 12.037 | RT instance node transform | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
6 | RQ-276 | 12.040 - 64B RT node | 1 | 1 | 1 | 26 | 12.04 | 64B RT node | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
7 | RQ-378 | 12.284 - Data return for clamped PRT is "0" only (no longer needs to be programable) | 1 |  | 1 | 131 | 12.284 | Data return for clamped PRT is "0" only (no longer needs to be programable) | Frank | TEX |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
8 | RQ-443 | 12.429 - HP64 child reuse | 1 | 1 | 1 | 196 | 12.429 | HP64 child reuse | Frank | TEX |  |  | P1 |  | Tserver |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | de-featured | 0 |  |  |  |  | 0 |  | WK5
9 | RQ-444 | 12.430 - Ray Tracing Tri Pair optimization | 1 | 2 | 1 | 197 | 12.43 | Ray Tracing Tri Pair optimization | Faez | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
10 | RQ-450 | 12.444 - Expand V# const_stride from 14 to 17 bit width | 1 | 3 | 0.75 | 203 | 12.444 | Expand V# const_stride from 14 to 17 bit width | Frank | TEX |  |  | P2 |  | TServer |  | 1 | 4 | New | Gopher | 4 | 3 | 3 |  |  |  | 0.75 |  | 0 |  |  |  |  | 0 |  | WK8
11 | RQ-454 | 12.448 - Change flags encoded in barycentrics to simplify detection of procedural nodes | 1 | 1 | 1 | 207 | 12.448 | Change flags encoded in barycentrics to simplify detection of procedural nodes | Faez | TEX |  |  | P2 |  | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
12 | RQ-455 | 12.449 - Remove culling with skip_triangles in TA | 1 | 2 | 1 | 208 | 12.449 | Remove culling with skip_triangles in TA | Faez | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
13 | RQ-457 | 12.451 - Extend compression control support in Texture | 1 | 1 | 0.5 | 210 | 12.451 | Extend compression control support in Texture | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 2 | New | Gopher | 2 | 1 | 1 |  |  |  | 0.5 |  | 0 |  |  |  |  | 0 |  | WK6
14 | RQ-465 | 12.460 - BVH Footprint Improvement | 1 | 3 | 0.75 | 218 | 12.46 | BVH Footprint Improvement | Frank | TEX |  |  | P2 |  | TServer |  | 1 | 4 | New | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
15 | RQ-466 | 12.461 - RT support for OBB and Instance Node Intersection | 1 | 2 | 0.25 | 219 | 12.461 | RT support for OBB and Instance Node Intersection | Frank | TEX |  |  | P2 |  | TServer |  | 1 | 8 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8

## MD-34 CMM
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-268 | 12.027 - Configuration agnostic memory scope and policy control (dup of 12.041) | 1 | 5 | 1 | 19 | 12.027 | Configuration agnostic memory scope and policy control (dup of 12.041) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 5 | New | C-Model | 5 | 5 | 5 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
1 | RQ-277 | 12.041 - New GL2 policies (same/child of 12.027) | 1 | 18 | 1 | 27 | 12.041 | New GL2 policies (same/child of 12.027) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 18 | New | Gopher | 18 | 18 | 18 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
2 | RQ-278 | 12.042 - Unify GLC->EA request interface | 1 |  | 0 | 28 | 12.042 | Unify GLC->EA request interface | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
3 | RQ-279 | 12.044 - GLC guarantee of same address order for any op or scope (dep. On 12.042) | 1 |  | 0 | 29 | 12.044 | GLC guarantee of same address order for any op or scope (dep. On 12.042) | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
4 | RQ-280 | 12.046 - GLC Cascading Read-Mod-Write Atomic Ops (includes retaining gfx11 atomic ops) | 1 |  | 0 | 30 | 12.046 | GLC Cascading Read-Mod-Write Atomic Ops (includes retaining gfx11 atomic ops) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
5 | RQ-281 | 12.048 - GLC Full CL sized write support | 1 | 1 | 1 | 31 | 12.048 | GLC Full CL sized write support | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
6 | RQ-282 | 12.049 - GLC Up to 256B Write Support to EA | 1 | 1 | 1 | 32 | 12.049 | GLC Up to 256B Write Support to EA | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
7 | RQ-283 | 12.051 - cache last_use policy (child of 12.041/12.027) | 1 | 1 | 1 | 33 | 12.051 | cache last_use policy (child of 12.041/12.027) | Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | C-Model | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
8 | RQ-284 | 12.053 - Distributed compression architecture in CMM and client impacts (w/ physical meta-data) | 1 | 1 | 1 | 34 | 12.053 | Distributed compression architecture in CMM and client impacts (w/ physical meta-data) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
9 | RQ-304 | 12.092 - Documentation - UTCL* MAS | 1 |  | 1 | 54 | 12.092 | Documentation - UTCL* MAS | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not a feature, the MAS to be delivered by the DE team | 0 |  |  |  |  | 1
10 | RQ-305 | 12.096 - UTCL1: check page_size using the stored frag_size | 1 |  | 1 | 55 | 12.096 | UTCL1: check page_size using the stored frag_size | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Waived by UTCL1 design | 0 |  |  |  |  | 1
11 | RQ-306 | 12.098 - Remove unused client shootdown interface | 1 |  | 1 | 56 | 12.098 | Remove unused client shootdown interface | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
12 | RQ-308 | 12.111 - Deprecate metadata probe and client shootdown in UTCL0 | 1 |  | 1 | 58 | 12.111 | Deprecate metadata probe and client shootdown in UTCL0 | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
13 | RQ-309 | 12.112 - GCR single cycle UTC request interface | 1 | 0.5 | 0.5 | 59 | 12.112 | GCR single cycle UTC request interface | Steven | CMM |  |  | P2 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
14 | RQ-319 | 12.130 - add TCP out of order response support | 1 |  | 0 | 69 | 12.13 | add TCP out of order response support | Steven | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
15 | RQ-343 | 12.184 - GLx bus widths and configuration | 1 | 8 | 1 | 91 | 12.184 | GLx bus widths and configuration | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 8 | New | Gopher | 8 | 8 | 8 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
16 | RQ-344 | 12.185 - CH 256B read/write support | 1 | 2 | 1 | 92 | 12.185 | CH 256B read/write support | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 2 | New | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
17 | RQ-348 | 12.192 - UTCL2 UTCL1 Dummy INV interface removal | 1 |  | 1 | 96 | 12.192 | UTCL2 UTCL1 Dummy INV interface removal | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
18 | RQ-349 | 12.193 - Additional SAx client to UTCL1 (from 12. | 1 | 1 | 1 | 97 | 12.193 | Additional SAx client to UTCL1 (from 12. | Steven/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
19 | RQ-356 | 12.210 - Fully connect capability to use high and normal MALL reuse hint (child of 12.027/12.041) | 1 | 0.5 | 0.5 | 104 | 12.21 | Fully connect capability to use high and normal MALL reuse hint (child of 12.027/12.041) | Steven | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
20 | RQ-357 | 12.211 - UTCL1_identity_mode (SED Crest) | 1 |  | 1 | 105 | 12.211 | UTCL1_identity_mode (SED Crest) | Steven | CMM |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | For chiplet SED Crest, not applicable for NV4m | 0 |  |  |  |  | 1
21 | RQ-374 | 12.278 - DCC sector size to increase to 128B | 1 | 1 | 1 | 127 | 12.278 | DCC sector size to increase to 128B | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | Will be covered by any DCC tests | 0 |  |  |  |  | 0 |  | WK5
22 | RQ-375 | 12.280 - DCC auto-CT detection | 1 | 2 | 1 | 128 | 12.28 | DCC auto-CT detection | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 2 | New | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
23 | RQ-376 | 12.281 - Sector-separated DCC compressed data layout | 1 | 1 | 1 | 129 | 12.281 | Sector-separated DCC compressed data layout | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
24 | RQ-379 | 12.285 - Remove BIG_PAGE control for UTC probing | 1 |  | 1 | 132 | 12.285 | Remove BIG_PAGE control for UTC probing | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
25 | RQ-381 | 12.287 - VRS removal in DCC | 1 |  | 1 | 134 | 12.287 | VRS removal in DCC | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
26 | RQ-387 | 12.310 - SED client to 256B reads | 1 | 1 | 1 | 143 | 12.31 | SED client to 256B reads | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
27 | RQ-392 | 12.319 - GCRD->GCR response interface to credit/debit | 1 | 0.9 | 0.9 | 147 | 12.319 | GCRD->GCR response interface to credit/debit | Steven | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
28 | RQ-393 | 12.320 - GCRD_SE SAX client | 1 |  | 0 | 148 | 12.32 | GCRD_SE SAX client | Steven/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
29 | RQ-394 | 12.321 - Limit wires SED<->AID for PMM Ips | 1 |  | 1 | 149 | 12.321 | Limit wires SED<->AID for PMM Ips | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
30 | RQ-395 | 12.322 - GFX12 UTLC2 - Add idle sidebands | 1 |  | 1 | 150 | 12.322 | GFX12 UTLC2 - Add idle sidebands | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Waived by design/FET lead | 0 |  |  |  |  | 1
31 | RQ-396 | 12.329 - remove GCR dummy UTCL2 invalidation interface | 1 |  | 1 | 152 | 12.329 | remove GCR dummy UTCL2 invalidation interface | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
32 | RQ-397 | 12.332 - GFX12 EA - Add idle sidebands | 1 |  | 1 | 153 | 12.332 | GFX12 EA - Add idle sidebands | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
33 | RQ-403 | 12.344 - Faulting illegal ops to PCIE | 1 |  | 0 | 160 | 12.344 | Faulting illegal ops to PCIE | Steven/JJ/Anthony | CMM |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
34 | RQ-423 | 12.401 - Improving MBFF ratio (Octa/Hexa Flops) | 1 |  | 1 | 181 | 12.401 | Improving MBFF ratio (Octa/Hexa Flops) | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not applicable to our scope and waived | 0 |  |  |  |  | 1
35 | RQ-434 | 12.412 - Enable GPA in UTCL0 of SAx GL1C | 1 | 2 | 1 | 187 | 12.412 | Enable GPA in UTCL0 of SAx GL1C | David/Steven | CMM |  |  | P1 | cs16.0 wgs_gpa3_disable_dispatch_pm4_01 | TServer |  | 1 | 2 | New | C-Model | 2 | 2 | 2 |  |  |  | 1 | WGS dependent | 0 |  |  |  |  | 0 |  | WK5
36 | RQ-452 | 12.446 - Load_reserved/store_conditional support in SE | 1 |  | 1 | 205 | 12.446 | Load_reserved/store_conditional support in SE$ | David/Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | WGS related, covered by gaming exerciser with test firmware | 0 |  |  |  |  | 1
37 | RQ-453 | 12.447 - Load_reserved/store_conditional support in DF | 1 |  | 1 | 206 | 12.447 | Load_reserved/store_conditional support in DF | David/Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | WGS related, covered by gaming exerciser with test firmware | 0 |  |  |  |  | 1
38 | RQ-458 | 12.452 - Breaking SE reuse in Navi48 | 1 |  | 1 | 211 | 12.452 | Breaking SE reuse in Navi48 | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | No direct coverage required | 0 |  |  |  |  | 1
39 | RQ-460 | 12.454 - Proper Handling of the Force Decompression and Comp Key Read Command on compression-bypassed resources | 1 |  | 0 | 213 | 12.454 | Proper Handling of the Force Decompression and Comp Key Read Command on compression-bypassed resources | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
40 | RQ-475 | 12.470 - RS64: No support for OOO IO read and write memory transactions | 1 |  | 0 | 228 | 12.47 | RS64: No support for OOO IO read and write memory transactions | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | Emulator | 1 | 0 |  |  |  |  | 0 | Will use MHUB team's ATHUB RAW check and Single VC for GFX IO test's CPWD variation as coverage | 0 |  |  |  |  | 0 |  | WK5
41 | RQ-477 | 12.473 - GL2 shared across all SEs for Navi44/48 | 1 |  | 0 | 230 | 12.473 | GL2 shared across all SEs for Navi44/48 | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5

## MD-35 SH
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-269 | 12.030 - Add support for image atomics fp32 add (makes fp32 add orthogonal). Make fp behaviour among lds/cmm/df identical | 1 | 18 | 1 | 20 | 12.03 | Add support for image atomics fp32 add (makes fp32 add orthogonal). Make fp behaviour among lds/cmm/df identical | Botao | SH |  |  | P1 | gfx.inst_perf/atomic_denorm gfx.inst_perf/buffer_atomic_cond_sub_u32 gfx.inst_perf/buffer_atomic_pk_add_bf16 gfx.inst_perf/buffer_atomic_pk_add_f16 gfx.inst_perf/buffer_atomic_sub_clamp_u32 gfx.inst_perf/ds_cond_sub_u32 gfx.inst_perf/ds_pk_add_bf16 gfx.inst_perf/ds_pk_add_f16 gfx.inst_perf/ds_sub_clamp_u32 gfx.inst_perf/global_atomic_cond_sub_u32 gfx.inst_perf/global_atomic_pk_add_bf16 gfx.inst_perf/global_atomic_pk_add_f16 gfx.inst_perf/global_atomic_sub_clamp_u32 gfx.image_op/image_atomic_add_flt gfx.image_op/image_atomic_min_flt gfx.image_op/image_atomic_max_flt gfx.image_op/image_atomic_pk_add_f16 gfx.image_op/image_atomic_pk_add_bf16.1-18 | TNG |  | 1 | 18 | New | C-Model | 18 | 18 | 18 |  |  |  | 1 | gfx_inst/atomic_denorm can only run in GopherPlus env. Verify if single variation pass on gopher+ good enough | 0 |  |  |  |  | 0 |  | WK5
1 | RQ-285 | 12.054 - SQG Ring Bus conversion for multi-chip | 1 |  | 1 | 35 | 12.054 | SQG Ring Bus conversion for multi-chip | Botao | SH |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to software and diags | 0 |  |  |  |  | 1
2 | RQ-286 | 12.055 - Split workgroup barrier | 1 | 1 | 1 | 36 | 12.055 | Split workgroup barrier | Botao | SH |  |  | P1 | gci1301.0 | TServer | -ace_aql=0 | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
3 | RQ-287 | 12.056 - Shader Instruction Data Prefetch (viola item) | 1 | 1 | 1 | 37 | 12.056 | Shader Instruction Data Prefetch (viola item) | Botao | SH |  |  | P1 | gci1304.0 | TServer | -pv_proxy=true -counter=SQC_PERF_SEL_ICACHE_PREFETCH_REQ_CACHELINES,SQC_PERF_SEL_ICACHE_PREFETCH_MISSES -countertemp=counterfile | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
4 | RQ-288 | 12.057 - Shader software data dependency control | 1 | 2 | 1 | 38 | 12.057 | Shader software data dependency control | Botao | SH |  |  | P2 | gfx.inst_perf/sched_mode_dep_mode1 gfx.inst_perf/sched_mode_dep_mode2.1-2 | TNG |  | 1 | 2 | New | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
5 | RQ-289 | 12.059 - Shader SALU Float support (in M1/M2/gfx11.5) | 1 | 62 | 1 | 39 | 12.059 | Shader SALU Float support (in M1/M2/gfx11.5) | Botao | SH |  |  | P1 | gfx.inst_perf/s_.*_f32$ gfx.inst_perf/s_.*_f16$ gfx.inst_perf/s_cvt_f32_i32 gfx.inst_perf/s_cvt_f32_u32.1-62 | TNG |  | 1 | 62 | New | C-Model | 62 | 62 | 62 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
6 | RQ-290 | 12.060 - VGPR DMA for Function Calls (uniform mask only) | 1 | 4 | 1 | 40 | 12.06 | VGPR DMA for Function Calls (uniform mask only) | Botao | SH |  |  | P1 | gfx.inst_perf/global_load_block gfx.inst_perf/global_store_block gfx.inst_perf/scratch_load_block gfx.inst_perf/scratch_store_block.1-4 | TNG |  | 1 | 4 | New | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
7 | RQ-291 | 12.062 - Shader Debugger Enablement | 1 | 2 | 1 | 41 | 12.062 | Shader Debugger Enablement | Botao | SH |  |  | P1 | gci1305.0 gci1305.1 | TServer |  | 1 | 2 | New | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
8 | RQ-292 | 12.063 - Shader Illegal Instruction Detection | 1 | 1 | 1 | 42 | 12.063 | Shader Illegal Instruction Detection | Botao | SH |  |  | P2 | gci1305.2 | TServer |  | 1 | 1 | Delta | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
9 | RQ-293 | 12.064 - Support PERMUTE/BPERMUTE for wave64 | 1 | 2 | 1 | 43 | 12.064 | Support PERMUTE/BPERMUTE for wave64 | Botao | SH |  |  | P2 | gfx.inst_perf/ds_permute_b32_w64 gfx.inst_perf/ds_bpermute_b32_w64.1-2 | TNG |  | 1 | 2 | Delta | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
10 | RQ-294 | 12.065 - Shader VALU Improvements | 1 | 2 | 1 | 44 | 12.065 | Shader VALU Improvements | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_permlanex16_var_b32 gfx.inst_perf/v_permlane16_var_b32.1-2 | TNG |  | 1 | 2 | Delta | C-Model | 2 | 2 | 2 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8400 | 0 |  |  |  |  | 0 |  | WK2
11 | RQ-295 | 12.066 - Shader Scalar Improvements | 1 | 6 | 1 | 45 | 12.066 | Shader Scalar Improvements | Botao | SH |  |  | P2 | gfx.inst_perf/s_sleep_var gfx.inst_perf/s_sleep gfx.inst_perf/s_add_nc_u64 gfx.inst_perf/s_sub_nc_u64 gfx.inst_perf/s_mul_u64 gfx.inst_perf/s_mul_i32.1-6 | TNG |  | 1 | 6 | Delta | C-Model | 6 | 6 | 6 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
12 | RQ-296 | 12.067 - Fix SQG GRBM design | 1 | 1 | 1 | 46 | 12.067 | Fix SQG GRBM design | Botao | SH |  |  | P1 | gci1303.0 | TServer | -tt_enable=true -tt_config=tt.ini | 1 | 1 | Delta | Gopher | 1 | 1 | 1 |  |  |  | 1 | Indirect coverage: Can be covered by any test with thread trace enabled | 0 |  |  |  |  | 0 |  | WK5
13 | RQ-297 | 12.068 - SQC Latency reduction (inherit approach from mi300) | 1 |  | 1 | 47 | 12.068 | SQC Latency reduction (inherit approach from mi300) | Botao | SH |  |  | P1 |  |  |  | 1 | 0 | Legacy |  | 0 | 0 |  |  |  |  | 1 | Not visible to software and diags | 0 |  |  |  |  | 1
14 | RQ-298 | 12.069 - WGP-takeover mode | 1 | 3 | 1 | 48 | 12.069 | WGP-takeover mode | Botao | SH |  |  | P1 | gci1303.0 gci1303.1 gci1303.2 | TServer | -ace_aql=0 | 1 | 3 | New | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
15 | RQ-299 | 12.071 - Shader Instruction Store convert to Cache (likely in M2/gfx11.5) | 1 |  | 1 | 49 | 12.071 | Shader Instruction Store convert to Cache (likely in M2/gfx11.5) | Botao | SH |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to software and diags | 0 |  |  |  |  | 1
16 | RQ-300 | 12.073 - Shader signed memory offsets | 1 | 1 | 1 | 50 | 12.073 | Shader signed memory offsets | Botao | SH |  |  | P2 | gfx.inst_perf/vglobal_signed_offset | TNG |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
17 | RQ-302 | 12.079 - Dynamic VGPR allocation | 1 | 2 | 1 | 52 | 12.079 | Dynamic VGPR allocation | Shuhui | SH |  |  | P1 | gci1302.0 / gci1302.1 | TServer |  | 1 | 2 | New | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
18 | RQ-303 | 12.084 - Prep for Navi + MIx00 shader merge | 1 | 3 | 1 | 53 | 12.084 | Prep for Navi + MIx00 shader merge | Botao | SH |  |  | P2 | gfx.inst_perf/v_add_f64 gfx.inst_perf/v_mul_f64 gfx.inst_perf/v_lshlrev_b64.1-3 | TNG |  | 1 | 3 | New | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
19 | RQ-312 | 12.115 - Single Pass Wave64 Trans Issue (in M2) | 1 | 14 | 1 | 62 | 12.115 | Single Pass Wave64 Trans Issue (in M2) | Botao | SH |  |  | P1 | gfx.inst_perf/v_exp_f32_w64 gfx.inst_perf/v_log_f32_w64 gfx.inst_perf/v_rcp_f32_w64 gfx.inst_perf/v_rsq_f32_w64 gfx.inst_perf/v_sqrt_f32_w64 gfx.inst_perf/v_sin_f32_w64 gfx.inst_perf/v_cos_f32_w64 gfx.inst_perf/v_exp_f16_w64 gfx.inst_perf/v_log_f16_w64 gfx.inst_perf/v_rcp_f16_w64 gfx.inst_perf/v_rsq_f16_w64 gfx.inst_perf/v_sqrt_f16_w64 gfx.inst_perf/v_sin_f16_w64 gfx.inst_perf/v_cos_f16_w64.1-14 | TNG |  | 1 | 14 | New | C-Model | 14 | 14 | 14 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
20 | RQ-324 | 12.142 - Double shader DOT Int4 and Int8 rates | 1 | 7 | 1 | 74 | 12.142 | Double shader DOT Int4 and Int8 rates | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_dot4_i32_iu8 gfx.inst_perf/v_dot4_u32_u8 gfx.inst_perf/v_dot8_i32_iu4 gfx.inst_perf/v_dot8_u32_u4 gfx.inst_perf/v_wmma_i32_16x16x16_iu4 gfx.inst_perf/v_wmma_i32_16x16x32_iu4 gfx.inst_perf/v_wmma_i32_16x16x16_iu8.1-7 | TNG |  | 1 | 7 | Delta | Gopher | 7 | 7 | 7 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7782 | 0 |  |  |  |  | 0 |  | WK1
21 | RQ-330 | 12.157 - Shader pseudo-scalar trans ops (M2 item) | 1 | 10 | 1 | 80 | 12.157 | Shader pseudo-scalar trans ops (M2 item) | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_s_.*.1-10 | TNG |  | 1 | 10 | New | C-Model | 10 | 10 | 10 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8507 | 0 |  |  |  |  | 0 |  | WK8
22 | RQ-479 | 12.159 - Shader reduce VGPR writes (M2 item evaluate for gaming) | 1 | 5 | 1 | 81 | 12.159 | Shader reduce VGPR writes (M2 item, evaluate for gaming) | Shuhui | SH |  |  | P1 | shci2038.0-3,104.1-5 | TServer |  | 1 | 5 | New | Gopher | 5 | 5 | 5 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
23 | RQ-480 | 12.160 - Shader double wave64 VINTERP rate (por gfx11.5 evaluate gaming) | 1 | 1 | 1 | 82 | 12.16 | Shader double wave64 VINTERP rate (por gfx11.5, evaluate gaming) | Shuhui | SH |  |  | P2 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
24 | RQ-335 | 12.162 - Shader Performance Profiler Enablement | 1 | 14 | 1 | 83 | 12.162 | Shader Performance Profiler Enablement | Shuhui | SH |  |  | P1 | std1.1 std3.1 std4.1 rt1.300 rt1.320 gci1304 gci1305 gci1308 shci2033 shci2036 gssi212.10 | TServer | "-tt_enable=1 -tt_config=exclude_nondetail_wavestart_ext=1,exclude_nondetail_alloc=1,wavestart_mode=wg_id,tracese=0,wavetype=65,ctrlmode=on,stall_all_simds=1 -thread_trace_config=exclude_nondetail_wavestart_ext=1,exclude_nondetail_alloc=1,wavestart_mode=wg_id,tracese=0,wavetype=65,ctrlmode=on,stall_all_simds=1" | 1 | 14 | Delta | Gopher | 14 | 11 | 11 |  |  |  | 0.78571 | Thread trace related can only be verified in gopher and using thread trace viewer. There are a few perf counters that are not tested but the test is avaliable. SQ_PERF_SEL_INSTS_LOCK SQ_PERF_SEL_INST_CYCLES_VALU_WMMA SQ_PERF_SEL_INSTS_VEC32_VALU_WMMA SQ_PERF_SEL_INSTS_WMMA_LOAD SQ_PERF_SEL_INSTS_TEX_BLOCK_LOAD SQ_PERF_SEL_INSTS_TEX_BLOCK_STORE | 0 |  |  |  |  | 0 |  | WK5
25 | RQ-345 | 12.186 - Add SP support for float8 (fp8/bf8) dot products (ieee and/or non-ieee) | 1 | 15 | 1 | 93 | 12.186 | Add SP support for float8 (fp8/bf8) dot products (ieee and/or non-ieee) | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_wmma.* gfx.inst_perf/v_cvt.* gfx.inst_perf/v_dot4_f32.*.1-15 | TNG |  | 1 | 15 | New | C-Model | 15 | 15 | 15 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8491 | 0 |  |  |  |  | 0 |  | WK3
26 | RQ-346 | 12.188 - Make shader round-robin arb in workgroup usable by driver | 1 | 3 | 1 | 94 | 12.188 | Make shader round-robin arb in workgroup usable by driver | Shuhui | SH |  |  | P1 | gci1306.0-2, gssi212.11 | TServer |  | 1 | 3 | New | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
27 | RQ-347 | 12.191 - Capture shader memviol source to speed up bringup debug | 1 | 5 | 1 | 95 | 12.191 | Capture shader memviol source to speed up bringup debug | Shuhui | SH |  |  | P1 | gci1305.0,3.1-5,4.1-5,5.1-5,6.1-5 | TServer | For gci1305.3 only, "-vm -tc_ulVidmemFragmentSize=0" | 1 | 5 | New | C-Model | 5 | 5 | 5 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
28 | RQ-354 | 12.208 - wave64 FMAF32 power reduction (M2 item) -> large area | 1 | 32 | 0.5 | 102 | 12.208 | wave64 FMAF32 power reduction (M2 item) -> large area | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_sad.* gfx.inst_perf/v_swap.* gfx.inst_perf/v_perm.* gfx.inst_perf/v_sat_pk_u8_i16 gfx.inst_perf/v_max.* gfx.inst_perf/v_sub_co_ci_u32.* gfx.inst_perf/v_med.* gfx.inst_perf/v_min.* gfx.inst_perf/v_qsad.* gfx.inst_perf/v_mqsad.* gfx.inst_perf/v_mad.* gfx.inst_perf/v_lerp.* gfx.inst_perf/v_and.* gfx.inst_perf/v_cndmask_b16.1-64 | TNG |  | 1 | 64 | New | C-Model | 64 | 32 | 32 |  |  |  | 0.5 | https://ontrack-internal.amd.com/browse/TNG-8760 | 0 |  |  |  |  | 0 |  | WK8
29 | RQ-355 | 12.209 - Add Structured Sparsity Support | 1 | 11 | 0.5 | 103 | 12.209 | Add Structured Sparsity Support | Claire/Meiru | SH |  |  | P1 |  | TServer |  | 1 | 22 | New | C-Model | 22 | 2 | 2 |  |  |  | 0.090909 |  | 0 |  |  |  |  | 0 |  | WK3
30 | RQ-372 | 12.276 - Remove the data duplication for MLOPS | 1 | 0 | 0 | 125 | 12.276 | Remove the data duplication for MLOPS | Claire/Meiru | SH |  |  | P1 |  | TServer |  | 1 | 14 | New | C-Model | 14 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
31 | RQ-373 | 12.277 - Add Conditional-subtract memory atomic for locks | 1 | 8 | 1 | 126 | 12.277 | Add Conditional-subtract memory atomic for locks | Shuhui | SH |  |  | P2 | gfx.inst_perf/flat_atomic_cond_sub_u32_global gfx.inst_perf/flat_atomic_sub_clamp_u32_global gfx.inst_perf/ds_cond_sub_rtn_u32 gfx.inst_perf/ds_sub_clamp_rtn_u32 gci1307.0-3.1-8 | TNG |  | 1 | 8 | New | C-Model | 8 | 8 | 8 |  |  |  | 1 | Partially covered by 12.030 and in tserver gci1307 test. https://ontrack-internal.amd.com/browse/TNG-8541 | 0 |  |  |  |  | 0 |  | WK8
32 | RQ-388 | 12.311 - Shader VALU min/max IEEE compliant | 1 | 1 | 1 | 144 | 12.311 | Shader VALU min/max IEEE compliant | Shuhui | SH |  |  | P1 | gfx.ieee_min_max | TNG |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7987 | 0 |  |  |  |  | 0 |  | WK1
33 | RQ-399 | 12.336 - Remove harvesting connectivity/RTL mux in SP | 1 |  | 1 | 156 | 12.336 | Remove harvesting connectivity/RTL mux in SP | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
34 | RQ-408 | 12.360 - WMMA wave level matrix load Instruction | 1 | 2 | 1 | 165 | 12.36 | WMMA wave level matrix load Instruction | Shuhui | SH |  |  | P2 | gfx.inst_perf/global_load_tr.*.1-2 | TNG |  | 1 | 2 | New | C-Model | 2 | 2 | 2 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8759 | 0 |  |  |  |  | 0 |  | WK6
35 | RQ-409 | 12.361 - Perfmon: GFX - VMID Specific Profiling/Debugging | 1 | 1 | 1 | 166 | 12.361 | Perfmon: GFX - VMID Specific Profiling/Debugging | Shuhui | SH |  |  | P2 | shci2039.4 | TServer | "-tt_enable=1" | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | Requires thread trace viewer | 0 |  |  |  |  | 0 |  | WK8
36 | RQ-411 | 12.370 - Fix VOPD dual V_MOV | 1 | 1 | 1 | 168 | 12.37 | Fix VOPD dual V_MOV | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_dual_mov_b32 | TNG |  | 1 | 1 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8273 | 0 |  |  |  |  | 0 |  | WK6
37 | RQ-451 | 12.445 - Improve Thread Trace ExecPopCount bandwidth | 1 | 4 | 1 | 204 | 12.445 | Improve Thread Trace ExecPopCount bandwidth | Shuhui | SH |  |  | P2 | shci2039.0-3 | TServer | "-tt_enable -vm" | 1 | 4 | New | Gopher | 4 | 4 | 4 |  |  |  | 1 | Requires thread trace viewer | 0 |  |  |  |  | 0 |  | WK8
38 | RQ-456 | 12.450 - Add AtomicAdd packed math for F16 | 1 | 4 | 1 | 209 | 12.45 | Add AtomicAdd packed math for F16 | Shuhui | SH |  |  | P2 | gci1307.4-7 | TServer |  | 1 | 4 | New | Gopher | 4 | 4 | 4 |  |  |  | 1 | Tested on gopher+ Partially addresses by 12.030 | 0 |  |  |  |  | 0 |  | WK7
39 | RQ-464 | 12.459 - Remove support for Shared VGPRs and Subvector Execution | 1 |  | 1 | 217 | 12.459 | Remove support for Shared VGPRs and Subvector Execution | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
40 | RQ-469 | 12.464 - SP Throttling and the first DIDT droop | 1 |  | 1 | 222 | 12.464 | SP Throttling and the first DIDT droop | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
41 | RQ-470 | 12.465 - SP src operand invalidated by td/lds return | 1 | 1 | 1 | 223 | 12.465 | SP src operand invalidated by td/lds return | Shuhui | SH |  |  | P2 | gci1310 | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
42 | RQ-474 | 12.469 - F8 1.4.3 IEEE mode behavior change (match with NV) | 1 | 4 | 1 | 227 | 12.469 | F8 1.4.3 IEEE mode behavior change (match with NV) | Shuhui | SH |  |  | P2 | gci1309.0-3 | TServer |  | 1 | 4 | New | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7

## MD-36 UTCL2
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-307 | 12.104 - GPUVM PTE bits | 1 |  | 1 | 57 | 12.104 | GPUVM PTE bits | Steven | UTCL2 |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Waived from gfx coverage by IPSE | 0 |  |  |  |  | 1
1 | RQ-436 | 12.414 - Add an L1 TLB into the SDMA front-end | 1 |  | 1 | 189 | 12.414 | Add an L1 TLB into the SDMA front-end | Steven | UTCL2 |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | OSS diag will provide coverage | 0 |  |  |  |  | 1

## MD-37 CTL
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-310 | 12.113 - RLC dont disable CGCG while thread trace is active | 1 |  | 1 | 60 | 12.113 | RLC dont disable CGCG while thread trace is active | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this | 0 |  |  |  |  | 1
1 | RQ-311 | 12.114 - CP ucode use dispatch index for TTMP init | 1 |  | 1 | 61 | 12.114 | CP ucode use dispatch index for TTMP init | Meiru | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | This is a rejected feature | 0 |  |  |  |  | 1
2 | RQ-315 | 12.120 - WGP&RB GRBM Index Remapping (possible gfx11.5) | 1 | 4 | 1 | 65 | 12.12 | WGP&RB GRBM Index Remapping (possible gfx11.5) | Xiaojing | CTL |  |  | P1 | gci1300.0,gci1300.1,gci1300.2,gci1300.3 | TServer |  | 1 | 4 | New | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
3 | RQ-318 | 12.128 - Packet Hardening for Microsoft Telemetry | 1 | 1 | 1 | 68 | 12.128 | Packet Hardening for Microsoft Telemetry | Pierce | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
4 | RQ-320 | 12.132 - CP/RLC/SDMA 40-bit Register Addressing to GRBM<>RSMU | 1 | 2 | 1 | 70 | 12.132 | CP/RLC/SDMA 40-bit Register Addressing to GRBM<>RSMU | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | Gopher | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK2
5 | RQ-321 | 12.133 - Removal of Clear State Context 0 and reclamation for rendering | 1 |  | 0 | 71 | 12.133 | Removal of Clear State Context 0 and reclamation for rendering | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
6 | RQ-322 | 12.134 - MES Handling Doorbell Misses | 1 |  | 0 | 72 | 12.134 | MES Handling Doorbell Misses | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
7 | RQ-326 | 12.146 - RS64 L0 Instr Cache | 1 | 2 | 1 | 76 | 12.146 | RS64 L0 Instr Cache | Yu Xuan | CTL |  |  | P1 | std1.1, gci30.4 | TNG |  | 1 | 2 | New | C-Model | 2 | 2 |  |  | 2 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
8 | RQ-327 | 12.148 - RS64 L0 Data Cache | 1 | 2 | 1 | 77 | 12.148 | RS64 L0 Data Cache | Yu Xuan | CTL |  |  | P1 | std1.1, gci30.4 | TNG |  | 1 | 2 | New | C-Model | 2 | 2 |  |  | 2 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
9 | RQ-328 | 12.150 - RS64 Bit Manip Instructions | 1 | 1 | 1 | 78 | 12.15 | RS64 Bit Manip Instructions | Yu Xuan | CTL |  |  | P1 | gci3.12 | TNG |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=gci3.12 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
10 | RQ-329 | 12.152 - RS64 Dynamic TMR Loading | 1 |  | 1 | 79 | 12.152 | RS64 Dynamic TMR Loading | Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this | 0 |  |  |  |  | 1
11 | RQ-341 | 12.174 - RS64 64bit Stream Input | 1 |  | 1 | 89 | 12.174 | RS64 64bit Stream Input | Yu Xuan | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
12 | RQ-342 | 12.175 - RS64 Atomic ISA Ext | 1 | 1 | 1 | 90 | 12.175 | RS64 Atomic ISA Ext | Yu Xuan | CTL |  |  | P1 | gci30.3 | TNG |  | 1 | 1 | New | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
13 | RQ-353 | 12.206 - DC->SPI wire reduction | 1 |  | 1 | 101 | 12.206 | DC->SPI wire reduction |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Indirect | 0 |  |  |  |  | 1
14 | RQ-359 | 12.216 - All debug bus buffers to 4K size | 1 |  | 1 | 108 | 12.216 | All debug bus buffers to 4K size | Daniel G | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
15 | RQ-362 | 12.221 - Add support to the SDMA to dequeue similar to the way the CP does | 1 |  | 1 | 111 | 12.221 | Add support to the SDMA to dequeue similar to the way the CP does | Yu Xuan | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
16 | RQ-485 | 12.233 - add DRAM logging support for RLC | 1 |  | 1 | 115 | 12.233 | add DRAM logging support for RLC | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this, with RLC FW team support | 0 |  |  |  |  | 1
17 | RQ-486 | 12.235 - Add RLC SRM as an RLC_CH client | 1 |  | 1 | 116 | 12.235 | Add RLC SRM as an RLC_CH client | Pierce | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IPSE coverage | 0 |  |  |  |  | 1
18 | RQ-487 | 12.236 - change RLC LX7 config used for power management | 1 |  | 1 | 117 | 12.236 | change RLC LX7 config used for power management | Pierce | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Navi4x no longer has SED N/A | 0 |  |  |  |  | 1
19 | RQ-488 | 12.239 - increase adaptive stretch response of GDFLL | 1 |  | 1 | 118 | 12.239 | increase adaptive stretch response of GDFLL | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Indirect covered by regular clock stretch, not directly covered by diag | 0 |  |  |  |  | 1
20 | RQ-367 | 12.253 - GFX12 IMU - Remove CPAXI and send doorbells directly to CP/RLC/SDMA | 1 |  | 1 | 120 | 12.253 | GFX12 IMU - Remove CPAXI and send doorbells directly to CP/RLC/SDMA | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
21 | RQ-368 | 12.255 - GFX12 IMU - Modify doorbell interface from Syshub to IMU | 1 |  | 1 | 121 | 12.255 | GFX12 IMU - Modify doorbell interface from Syshub to IMU | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
22 | RQ-369 | 12.263 - GFX12 IMU - Add Resets and idle sidebands | 1 |  | 1 | 122 | 12.263 | GFX12 IMU - Add Resets and idle sidebands | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
23 | RQ-370 | 12.266 - GFX12 Firewall update for 40 bit address | 1 |  | 0 | 123 | 12.266 | GFX12 Firewall update for 40 bit address | David | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
24 | RQ-371 | 12.270 - Work Graph Scheduler | 1 | 7 | 1 | 124 | 12.27 | Work Graph Scheduler | David | CTL |  |  | P1 | wgs.6 :: wgs_dispatch_sanity_pm4_01 wgs.8 :: wgs_dispatch_two_pipes_pm4_01 wgs.1 :: wgs_ace_cwsr_pm4_01 wgs.100 :: wgs_dispatch_sanity_tacl_01 wgs.12 :: wgs_gl1_ret_xnack_pm4_01 linpack_wgs wgs_interrrupt_tacl | TServer |  | 1 | 7 | New | Gopher | 6 | 6 | 6 |  |  |  | 1 | TSERVER tests | 0 |  |  |  |  | 0 |  | WK5
25 | RQ-382 | 12.291 - Remove F32 from CPG and CPC; No BC support in PM4 parsers | 1 |  | 1 | 135 | 12.291 | Remove F32 from CPG and CPC; No BC support in PM4 parsers |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
26 | RQ-489 | 12.299 - [Navi4x] Move RTAVFS/DLDO/DFLL initialization to after CP is running workloads | 1 |  | 1 | 138 | 12.299 | [Navi4x] Move RTAVFS/DLDO/DFLL initialization to after CP is running workloads | David | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Indirect coverage with front door loading | 0 |  |  |  |  | 1
27 | RQ-385 | 12.300 - [Navi4x] SDMA ucode caching | 1 |  | 1 | 139 | 12.3 | [Navi4x] SDMA ucode caching | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
28 | RQ-490 | 12.301 - [Navi4x] CP ucode firmware execution speed-up via cache priming | 1 |  | 0 | 140 | 12.301 | [Navi4x] CP ucode firmware execution speed-up via cache priming | Daniel G | CTL |  |  | P2 |  | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
29 | RQ-491 | 12.302 - [Navi4x] Remove SDMA load/run commands or disallow DRAM access allowed for load/run commands | 1 |  | 1 | 141 | 12.302 | [Navi4x] Remove SDMA load/run commands or disallow DRAM access allowed for load/run commands |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
30 | RQ-386 | 12.308 - RS64 Debug Enablement | 1 |  | 1 | 142 | 12.308 | RS64 Debug Enablement | Daniel G | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
31 | RQ-492 | 12.328 - GFX12 SDMA - Add sidebands to control Idle request | 1 |  | 1 | 151 | 12.328 | GFX12 SDMA - Add sidebands to control Idle request | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
32 | RQ-398 | 12.334 - GTS support in GFX12 | 1 | 2 | 1 | 155 | 12.334 | GTS support in GFX12 | David | CTL |  |  | P1 |  | TNG |  | 1 | 2 | New | C-Model | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
33 | RQ-400 | 12.339 - GFX12 IH Gasket update for chiplet design | 1 | 2 | 1 | 157 | 12.339 | GFX12 IH Gasket update for chiplet design | Sid | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
34 | RQ-401 | 12.342 - GFX12 IMU - Add FIFO for blocked RSMU writes and keep read outstanding | 1 |  | 1 | 158 | 12.342 | GFX12 IMU - Add FIFO for blocked RSMU writes and keep read outstanding | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1
35 | RQ-402 | 12.343 - SPM sample sync across AID and GFX to DF | 1 | 1 | 1 | 159 | 12.343 | SPM sample sync across AID and GFX to DF | Yu Xuan | CTL |  |  | P1 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
36 | RQ-416 | 12.389 - GFX EDC Controller using XVmin/Mafdd | 1 |  | 1 | 173 | 12.389 | GFX EDC Controller using XVmin/Mafdd |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
37 | RQ-417 | 12.392 - NV4x: GFX Cac Events selection enhancement | 1 |  | 1 | 174 | 12.392 | NV4x: GFX Cac Events selection enhancement |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
38 | RQ-494 | 12.393 - GFX PCC latency optimization | 1 |  | 1 | 175 | 12.393 | GFX PCC latency optimization |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
39 | RQ-432 | 12.410 - User Data Scatter Engine (RS64) | 1 |  | 1 | 185 | 12.41 | User Data Scatter Engine (RS64) | Pierce | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Removed, DEGFX12-10852 | 0 |  |  |  |  | 1
40 | RQ-433 | 12.411 - Replace SDMA F32 with RS64 | 1 |  | 1 | 186 | 12.411 | Replace SDMA F32 with RS64 | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
41 | RQ-437 | 12.417 - GFX12 IMU - Add light sleep and deep sleep to SRAMs | 1 |  | 1 | 190 | 12.417 | GFX12 IMU - Add light sleep and deep sleep to SRAMs | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not POR for NV48/44 | 0 |  |  |  |  | 1
42 | RQ-438 | 12.418 - GFX12 IMU - Add deep sleep support and sideband for IMUCLK | 1 |  | 1 | 191 | 12.418 | GFX12 IMU - Add deep sleep support and sideband for IMUCLK | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not POR for NV48/44 | 0 |  |  |  |  | 1
43 | RQ-440 | 12.421 - TOC updates for RLC FW | 1 |  | 1 | 193 | 12.421 | TOC updates for RLC FW | David | CTL |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Indrect coverage with front door loading | 0 |  |  |  |  | 1
44 | RQ-446 | 12.439 - Improve register based invalidation | 1 |  | 0 | 199 | 12.439 | Improve register based invalidation | Steven/Glenn | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
45 | RQ-447 | 12.440 - Make SE CAC Counters accessible over Debug Bus | 1 |  | 1 | 200 | 12.44 | Make SE CAC Counters accessible over Debug Bus |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
46 | RQ-449 | 12.442 - EA and GL2CC move from GRBM to GRBMH | 1 |  | 1 | 202 | 12.442 | EA and GL2CC move from GRBM to GRBMH | Steven/Glenn | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IPSE confirmed chiplet only | 0 |  |  |  |  | 1
47 | RQ-462 | 12.457 - Decrompress BLTs via SDMA | 1 |  | 1 | 215 | 12.457 | Decrompress BLTs via SDMA | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1
48 | RQ-468 | 12.463 - GFXCLK Deep Sleep trigger based on XVMIN | 1 |  | 1 | 221 | 12.463 | GFXCLK Deep Sleep trigger based on XVMIN | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | PPA team will enable this, IPSE team will verify | 0 |  |  |  |  | 1
49 | RQ-471 | 12.466 - Distributed DIDT controller | 1 |  | 1 | 224 | 12.466 | Distributed DIDT controller | Pierce | CTL |  |  | P2 |  |  |  | 1 | 0 | New | C-Model | 1 | 0 |  |  |  |  | 0 | Leverage SMU coverage through feature enablement | 0 |  |  |  |  | 1 |  | WK8
50 | RQ-472 | 12.467 - GRBM/H SYNC registers | 1 |  | 0 | 225 | 12.467 | GRBM/H SYNC registers | Daniel G | CTL |  |  | P1 |  | TServer |  | 1 | 2 | New | C-Model | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3
51 | RQ-473 | 12.468 - RS64: Adding performance features for both Navi4x and MI400 | 1 |  | 1 | 226 | 12.468 | RS64: Adding performance features for both Navi4x and MI400 | Daniel G | CTL |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Risc-V features, will be tested by IPSE team | 0 |  |  |  |  | 1

## MD-38 GC
| Id | Name | % TP Done | # Written | % Code Done | Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | RQ-314 | 12.119 - Harvesting enabled by default | 1 |  | 1 | 64 | 12.119 | Harvesting enabled by default | Xiaojing | GC |  |  | P1 |  | TNG |  | 1 | 0 | New |  | 1 | 0 |  |  |  |  | 0 | Confirmed with arch, because this feature is RLC ROM to program the harvesting setting during fuse distribution stage, and there's no needed to test from diag side. | 0 |  |  |  |  | 1 |  | WK5
1 | RQ-481 | 12.318 - SED<>AID and AID<>AID interfaces must support arbitrary clk deviation so protocols like valid-only need to be converted. | 1 |  | 1 | 146 | 12.318 | SED<>AID and AID<>AID interfaces must support arbitrary clk deviation, so protocols like valid-only need to be converted. | David/Steven | GC |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | Invisible to diags, workload cross the original die interface will cover | 0 |  |  |  |  | 1
2 | RQ-493 | 12.333 - Swap PRIM_CONFIG register to SA_UNIT_DISABLE register | 1 | 4 | 1 | 154 | 12.333 | Swap PRIM_CONFIG register to SA_UNIT_DISABLE register | David | GC |  |  | P2 | STD1.6 GCI30.3 | TNG |  | 1 | 4 | New | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
3 | RQ-404 | 12.349 - Perfmon: GFX - Convert all counter modules to SPM-only mode | 1 | 1 | 1 | 161 | 12.349 | Perfmon: GFX - Convert all counter modules to SPM-only mode | Yu Xuan | GC |  |  | P2 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
4 | RQ-405 | 12.356 - Perfmon: GFX - GFX SPM sampling window to be driven by REFCLK | 1 | 1 | 1 | 162 | 12.356 | Perfmon: GFX - GFX SPM sampling window to be driven by REFCLK | Yu Xuan | GC |  |  | P1 | rlc1.0 | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=rlc1.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK5
5 | RQ-406 | 12.357 - Perfmon: GFX - SQ counters to support shader type filters per individual counter | 1 | 1 | 1 | 163 | 12.357 | Perfmon: GFX - SQ counters to support shader type filters per individual counter | Dennis | GC |  |  | P1 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
6 | RQ-407 | 12.358 - Perfmon: GFX - Custom data injection from CP into SPM with delta counters | 1 | 1 | 1 | 164 | 12.358 | Perfmon: GFX - Custom data injection from CP into SPM with delta counters | Yu Xuan | GC |  |  | P2 | rlc1.0, rlc1.1 | TServer |  | 1 | 1 | New | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=rlc1.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 0 |  |  |  |  | 0 |  | WK8
7 | RQ-410 | 12.366 - NV4x: Perfmon: Review and refinement of available perf counter events for GC and DF | 1 |  | 1 | 167 | 12.366 | NV4x: Perfmon: Review and refinement of available perf counter events for GC and DF | Dennis | GC |  |  | P2 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | GFX IPSE will cover the Perfmon related features | 0 |  |  |  |  | 1
8 | RQ-413 | 12.374 - MEM_PWR_CTRL Bus increase to support FGCG | 1 |  | 1 | 170 | 12.374 | MEM_PWR_CTRL Bus increase to support FGCG | Pierce | GC |  |  | P1 |  |  |  | 1 | 0 | New |  | 0 | 0 |  |  |  |  | 1 | IPSE coverage | 0 |  |  |  |  | 1
9 | RQ-435 | 12.413 - Switch GFX to Memgen-based SRAM FGCG | 1 |  | 1 | 188 | 12.413 | Switch GFX to Memgen-based SRAM FGCG | Pierce | GC |  |  | P1 | PMM coverage through CGCG/PG features |  |  | 1 | 0 | New | C-Model | 1 | 0 |  |  |  |  | 0 | Indirect coverage through FGCG | 0 |  |  |  |  | 1 |  | WK5