## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | NV48-OSS-004 | AQL Command + multi-producer support | Song, Sukey | SDMA | AQL Command + multi-producer support | Multi-producer support means SDMA may fetch a command which is not ready (because multiple producers can update doorbell) and should wait until the command is valid | P2 | sdma84.101-102 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
1 | NV48-OSS-005 | Atomic Command | Song, Sukey | SDMA | Atomic Add |  | P2 | nsdma177.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
2 | NV48-OSS-005 | Atomic Command | Song, Sukey | SDMA | Atomic Swap |  | P2 | nsdma178.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 |  | WK4
3 | NV48-OSS-005 | Atomic Command | Song, Sukey | SDMA | Atomic CompareSwap |  | P2 | nsdma179.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 |  | WK4
4 | NV48-OSS-006 | Burst NOPs | Song, Sukey | SDMA | Burst NOPs | for padding the command buffer | P2 | nsdma223.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
5 | NV48-OSS-007 | CGCG enhancement | Song, Sukey | SDMA | CGCG enhancement | medium grain CGCG control | P2 | nsdma207.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | wk8 ( 2 Wks after PMM enabled CGCG)
6 | NV48-OSS-009 | Command Overlap | Song, Sukey | SDMA | Command Overlap |  | P2 | sdma27.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
7 | NV48-OSS-010 | Conditional Execution Command | Song, Sukey | SDMA | Conditional Exec Fail |  | P2 | nsdma27.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 |  | WK4
8 | NV48-OSS-010 | Conditional Execution Command | Song, Sukey | SDMA | Conditional Exec Pass |  | P2 | nsdma26.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
9 | NV48-OSS-011 | Constant Fill Command | Song, Sukey | SDMA | Const fill- byte |  | P2 | nsdma58.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK4
10 | NV48-OSS-011 | Constant Fill Command |  | SDMA | Const-fill-Dword |  | P2 | nsdma59.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK4
11 | NV48-OSS-012 | Context Switch | Song, Sukey | SDMA | Normal-Preempt | de-asserting RB_CNTL.RB_ENABLE | P2 | nsdma215.1-3 | Tserver |  | 3 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | [5 empty] | 0 | [6 empty] | 0 |  | wk6
12 | NV48-OSS-013 | Copy cmd format to support CUDA API(3D handle) | Song, Sukey | SDMA | Copy cmd format to support CUDA API(3D handle) |  | P2 | nsdma81.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
13 | NV48-OSS-019 | Fence Command |  | SDMA | GMC Address |  | P2 | sdma.packet.fence | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [10 empty] | 0 |  | WK6
14 | NV48-OSS-019 | Fence Command | Song, Sukey | SDMA | Physical Address |  | P2 | sdma.packet.fence | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [10 empty] | 0 |  | WK6
15 | NV48-OSS-022 | GPUVM TLB Invalidation |  | SDMA | Legacy |  | P2 | nsdma205.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5
16 | NV48-OSS-022 | GPUVM TLB Invalidation | Song, Sukey | SDMA | LightWeight |  | P2 | nsdma206.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5
17 | NV48-OSS-023 | GCR request support | Song, Sukey | SDMA | Write-back |  | P2 | nsdma66.1-2 | Tserver | -vm | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  |  |  | 2 |  |  | 0 |  | WK5
18 | NV48-OSS-023 | GCR request support | Song, Sukey | SDMA | Invalidate |  | P2 | nsdma67.1-2 | Tserver | -vm | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  |  |  | 2 |  |  | 0 |  | WK5
19 | NV48-OSS-023 | GCR request support | Song, Sukey | SDMA | Discard |  | P2 | nsdma68.1-2 | Tserver | -vm | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 1 | [5 empty] | 0 |  |  |  | 2 |  |  | 0 |  | WK5
20 | NV48-OSS-025 | Increase max copy size(4M-1G) | Song, Sukey | SDMA | Increase max copy size(4M-1G) |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
21 | NV48-OSS-026 | L2 policy override on normal command | Song, Sukey | SDMA | L2 policy override on normal command |  | P2 | nsdma1.2 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | Emulator | 2 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
22 | NV48-OSS-027 | Linear Copy | Song, Sukey | SDMA | Linear Copy, Linear to Linear Copy Command |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
23 | NV48-OSS-035 | Linear to Linear Copy Command | Song, Sukey | SDMA | Linear Copy, Linear to Linear Copy Command |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
24 | NV48-OSS-028 | Linear Backwards Copy | Song, Sukey | SDMA | Linear Backwards Copy |  | P2 | nsdma5.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK2
25 | NV48-OSS-029 | Linear Copy Broadcast | Song, Sukey | SDMA | Linear Copy Broadcast |  | P2 | nsdma4.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
26 | NV48-OSS-030 | Linear Sub-Window Copy | Song, Sukey | SDMA | Linear Sub-Window Copy, Linear to Linear sub-window copy |  | P2 | nsdma7.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
27 | NV48-OSS-036 | Linear to Linear sub-window copy | Song, Sukey | SDMA | Linear Sub-Window Copy, Linear to Linear sub-window copy |  | P2 | nsdma7.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
28 | NV48-OSS-031 | Linear large Sub-Window Copy | Song, Sukey | SDMA | Linear large Sub-Window Copy |  | P2 | nsdma93.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5
29 | 5 | Tiled to Tiled Sub-Window Copy | Song, Sukey | SDMA | Tiled to Tiled Sub-Window Copy |  |  | nsdma9.1-5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
30 | NV48-OSS-034 | Tiled Sub-Window Copy | Song, Sukey | SDMA | Tiled Sub-Window Copy, Linear to Tiled / Tiled to Linear sub-window copy |  | P2 | nsdma10.1-10 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1
31 | NV48-OSS-040 | Linear to Tiled / Tiled to Linear sub-window copy | Song, Sukey | SDMA | Tiled Sub-Window Copy, Linear to Tiled / Tiled to Linear sub-window copy |  | P2 | nsdma10.1-10 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1
32 | NV48-OSS-037 | Linear to Structured / Structured to Linear copy | Song, Sukey | SDMA | Linear to Structured / Structured to Linear copy |  | P2 | nsdma13.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5
33 | NV48-OSS-038 | Linear to Tiled (frame to field) copy | Song, Sukey | SDMA | Linear to Tiled (frame to field) copy |  | P2 | nsdma12.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK5
34 | NV48-OSS-039 | Linear to Tiled / Tiled to Linear Copy Command | Song, Sukey | SDMA | Linear to Tiled / Tiled to Linear Copy Command | L2T | P2 | nsdma2.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | Wk5
35 | NV48-OSS-039 | Linear to Tiled / Tiled to Linear Copy Command |  | SDMA | Linear to Tiled / Tiled to Linear Copy Command | T2L | P2 | nsdma3.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | Wk5
36 | NV48-OSS-041 | Linear to Tiled copy broadcast | Song, Sukey | SDMA | Linear to Tiled copy broadcast |  | P2 | nsdma11.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK5
37 | NV48-OSS-042 | Mid Command Buffer Preemption | Song, Sukey | SDMA | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol |  | P2 | nsmda217.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
38 | NV48-OSS-043 | Mid Command Preemption | Song, Sukey | SDMA | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol |  | P2 | nsmda217.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
39 | NV48-OSS-044 | RB Command Preemption | Song, Sukey | SDMA | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol |  | P2 | nsmda217.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
40 | NV48-OSS-054 | Ring Buffer Preemption between contexts | Song, Sukey | SDMA | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol |  | P2 | nsmda217.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
41 | NV48-OSS-055 | Ring Buffer Preemption within a context | Song, Sukey | SDMA | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol |  | P2 | nsmda217.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
42 | NV48-OSS-095 | Enhanced RB preemption protocol | Song, Sukey | SDMA | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol |  | P2 | nsmda217.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
43 | NV48-OSS-045 | Mid-command preemption when time quantum reached | Song, Sukey | SDMA | Mid-command preemption when time quantum reached, Support mid-command boundary on quantum expire |  | P2 | nsmda218.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
44 | NV48-OSS-103 | Support mid-command boundary on quantum expire | Song, Sukey | SDMA | Mid-command preemption when time quantum reached, Support mid-command boundary on quantum expire |  | P2 | nsmda218.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
45 | NV48-OSS-046 | Memory Increment | Song, Sukey | SDMA | Memory Increment |  | P2 | nsdma160.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
46 | NV48-OSS-050 | Physical linear copy | Song, Sukey | SDMA | Physical linear copy |  | P2 | sdma.packet.physical_linear_copy/1-8,sdma.packet.physical_linear_copy/21-28 | TNG |  | 1 | 16 | Legacy | 1 | 16 | 1 | Emulator | 16 | 16 | 16 |  |  |  | 1 | [6 empty] | 0 |  | WK5
47 | NV48-OSS-051 | Poll Memory/Register Command | Song, Sukey | SDMA | Poll Memory/Register Command |  | P2 | nsdma16.1-10 | Tserver |  | 1 | 10 | Legacy | 1 | 10 | 1 | Emulator | 10 | 10 | 9 |  | 1 |  | 0.9 |  | 10 | 9 |  | 1 |  | 0.9 |  | WK4
48 | NV48-OSS-052 | Predicated Execution Command | Song, Sukey | SDMA | Predicated Execution Command |  | P2 | nsdma182.1,nsdma183.1 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
49 | NV48-OSS-053 | RAW dependency check | Song, Sukey | SDMA | RAW dependency check |  | P2 | nsdma68.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK5
50 | NV48-OSS-057 | SDMA Master Firewall | Song, Sukey | SDMA | SDMA Range Based Firewall, Upgrade 4KB firewalls with range check, add RESTORE flag to the new firewall registers in rdl file for RLC to do save/restore. |  | P2 | nsdma222.1-34 | Tserver |  | 4 | 34 | New | 1 | 34 | 1 | Emulator | 28 | 28 | 28 |  |  |  | 1 | [6 empty] | 0
51 | NV48-OSS-101 | Upgrade 4KB firewalls with range check, add RESTORE flag to the new firewall registers in rdl file for RLC to do save/restore. | Song, Sukey | SDMA | SDMA Range Based Firewall, Upgrade 4KB firewalls with range check, add RESTORE flag to the new firewall registers in rdl file for RLC to do save/restore. |  | P2 | nsdma222.1-34 | Tserver |  | 4 | 34 | New | 1 | 34 | 1 | Emulator | 28 | 28 | 28 |  |  |  | 1 | [6 empty] | 0
52 | NV48-OSS-058 | SDMA Performance - Multi Engine | Song, Sukey | SDMA | SDMA Performance - Multi Engine |  | P2 | nsmda402.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
53 | NV48-OSS-059 | SDMA Performance - Single Engine | Song, Sukey | SDMA | SDMA Performance - Single Engine |  | P2 | nsdma402.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
54 | NV48-OSS-061 | SDMA Stress Test - CGCG | Song, Sukey | SDMA | SDMA Stress Test - CGCG |  | P2 | nsmda409.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | wk8 ( 2 Wks after PMM enabled CGCG)
55 | NV48-OSS-063 | SDMA Stress Test - VDDGFX | Song, Sukey | SDMA | SDMA Stress Test - VDDGFX |  | P2 | nsmda410.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | wk 13( 2 Wks after PMM enabled VDDGFX)
56 | NV48-OSS-066 | SRBM Writes | Song, Sukey | SDMA | SRBM Writes |  | P2 | nsdma120.1-6 | Tserver |  | 1 | 6 | Legacy | 1 | 6 | 1 | Emulator | 6 | 6 | 6 |  |  |  | 1 | [6 empty] | 0 |  | WK4
57 | NV48-OSS-067 | Support byte aligned Count in normal tiled copy | Song, Sukey | SDMA | Support byte aligned Count in normal tiled copy |  | P2 | nsdma2.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
58 | NV48-OSS-068 | Support Native TMZ support | Song, Sukey | SDMA | Support Native TMZ support |  | P2 | nsdma152-nsdma159 | Tserver |  | 1 | 8 | Legacy | 1 | 8 | 1 | Emulator | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk 6( 2Wks after PSP enabled PSP)
59 | NV48-OSS-070 | Poll Register Write Memory | Song, Sukey | SDMA | Poll Register Write Memory |  | P2 | nsdma10.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
60 | NV48-OSS-072 | Conditional Execution | Song, Sukey | SDMA | Conditional Execution |  | P2 | nsdma26,nsdma27 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK5
61 | NV48-OSS-073 | Predicated Execution | Song, Sukey | SDMA | Predicated Execution |  | P2 | nsdma182,nsdma183 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK4
62 | NV48-OSS-074 | Generate PTE/PDE | Song, Sukey | SDMA | Generate PTE/PDE |  | P2 | gen,gte | TNG |  | 1 | 10 | Delta | 1 | 10 | 1 | Emulator | 10 | 10 | 10 |  |  |  | 1 | [6 empty] | 0 |  | WK4
63 | NV48-OSS-075 | Copy Mask PTE/PDE | Song, Sukey | SDMA | Copy Mask PTE/PDE |  | P2 | nsdma201.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
64 | NV48-OSS-076 | RMW PTE/PDE | Song, Sukey | SDMA | RMW PTE/PDE |  | P2 | nsdma203.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
65 | NV48-OSS-077 | Timestamp Commands | Song, Sukey | SDMA | Timestamp Commands |  | P2 | nsdma56,nsdms57 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
66 | NV48-OSS-078 | Translation failure RESP MODE[4:0] | Song, Sukey | SDMA | Translation failure RESP MODE[4:0] |  | P2 | nsdma126-nsdma134 | Tserver |  | 1 | 9 | Legacy | 1 | 9 | 1 | Emulator | 9 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
67 | NV48-OSS-079 | VM_INVALIDATION | Song, Sukey | SDMA | VM_INVALIDATION |  | P2 | nsdma222.1-18 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 18 | 18 | 18 |  |  |  | 1 | [6 empty] | 0 |  | WK5
68 | NV48-OSS-081 | Trap Command | Song, Sukey | SDMA | Trap Command |  | P2 | nsdma14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 | [6 empty] | 0 |  | WK2
69 | NV48-OSS-082 | VDDGFX power down support | Song, Sukey | SDMA | VDDGFX power down support |  | P2 | nsdma204.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK8
70 | NV48-OSS-085 | Support 8 general purpose HW queue with programmable queue scheduling/priority | Song, Sukey | SDMA | Support 8 general purpose HW queue with programmable queue scheduling/priority |  | P2 | nsdma213.1-4 | Tserver | '-oss_sdmaengines=sdma0_all -oss_no_fill_and_verify=true -sdma_copysize=4KiB -sdma_loops=2 | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 4 | 4 | 4 |  |  |  | 1 | [6 empty] | 0 |  | WK7
71 | NV48-OSS-086 | Queue process detection and per-queue reset | Song, Sukey | SDMA | Queue process detection and per-queue reset |  | P2 | nsdma216.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK8
72 | NV48-OSS-088 | standardize idle/busy reporting mechanism to RLC | Song, Sukey | SDMA | standardize idle/busy reporting mechanism to RLC |  | P2 | nsdma207.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK7
73 | NV48-OSS-090 | SDMA doorbell common range, daisy chain doorbell intf among SDMA controllers | Song, Sukey | SDMA | SDMA doorbell common range, daisy chain doorbell intf among SDMA controllers |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK7
74 | NV48-OSS-091 | non-recoverable page fault reporting | Song, Sukey | SDMA | non-recoverable page fault reporting |  | P2 | nsdma126,nsdma126127,nsdma126128 | Tserver |  | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK7
75 | NV48-OSS-093 | Improved ucode exception/interrupt handling enhancement | Song, Sukey | SDMA | Improved ucode exception/interrupt handling enhancement |  | P2 | nsdma14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
76 | NV48-OSS-094 | save/restore effeciency enhancement (change in RLC, no SDMA change) | Song, Sukey | SDMA | save/restore effeciency enhancement (change in RLC, no SDMA change) |  | P2 | nsdma410 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
77 | NV48-OSS-100 | WPTR poll enhancement | Song, Sukey | SDMA | WPTR poll enhancement |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK5
78 | NV48-OSS-110 | Change SDMA's interrupt SourceID/RingID | Song, Sukey | SDMA | Change SDMA's interrupt SourceID/RingID |  | P2 | nsdma14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK2
79 | NV48-OSS-116 | Const_fill count size expands to 1GB | Song, Sukey | SDMA | Const_fill count size expands to 1GB |  | P2 | nsdma59.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | WK4
80 | NV48-OSS-118 | Linear Copy | Song, Sukey | SDMA | Linear Copy(LSDMA), Linear to Linear Copy Command(LSDMA) |  | P2 | nsdma1.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
81 | NV48-OSS-127 | Linear to Linear Copy Command | Song, Sukey | SDMA | Linear Copy(LSDMA), Linear to Linear Copy Command(LSDMA) |  | P2 | nsdma1.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
82 | NV48-OSS-119 | Linear Backwards Copy | Song, Sukey | SDMA | Linear Backwards Copy(LSDMA) |  | P2 | nsdma5.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
83 | NV48-OSS-120 | Linear Copy Broadcast | Song, Sukey | SDMA | Linear Copy Broadcast(LSDMA) |  | P2 | nsdma4.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
84 | NV48-OSS-121 | Linear Sub-Window Copy | Song, Sukey | SDMA | Linear Sub-Window Copy(LSDMA), Linear to Linear sub-window copy(LSDMA) |  | P2 | nsdma7.101-105 | Tserver |  | 5 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
85 | NV48-OSS-128 | Linear to Linear sub-window copy | Song, Sukey | SDMA | Linear Sub-Window Copy(LSDMA), Linear to Linear sub-window copy(LSDMA) |  | P2 | nsdma7.101-105 | Tserver |  | 5 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
86 | NV48-OSS-122 | Linear large Sub-Window Copy | Song, Sukey | SDMA | Linear large Sub-Window Copy(LSDMA) |  | P2 | nsdma93.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
87 | NV48-OSS-124 | Tiled Copy | Song, Sukey | SDMA | Tiled Copy(LSDMA), Linear to Tiled / Tiled to Linear Copy Command(LSDMA) |  | P2 | nsdma2.101-105,nsdma3.101-105 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0
88 | NV48-OSS-131 | Linear to Tiled / Tiled to Linear Copy Command | Song, Sukey | SDMA | Tiled Copy(LSDMA), Linear to Tiled / Tiled to Linear Copy Command(LSDMA) |  | P2 | nsdma2.101-105,nsdma3.101-105 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0
89 | NV48-OSS-125 | Tiled to Tiled Sub-Window Copy | Song, Sukey | SDMA | Tiled to Tiled Sub-Window Copy(LSDMA) |  | P2 | nsdma9.101-105 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
90 | NV48-OSS-126 | Tiled Sub-Window Copy | Song, Sukey | SDMA | Tiled Sub-Window Copy(LSDMA), Linear to Tiled / Tiled to Linear sub-window copy(LSDMA) |  | P2 | nsdma10.101-110 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0
91 | NV48-OSS-132 | Linear to Tiled / Tiled to Linear sub-window copy | Song, Sukey | SDMA | Tiled Sub-Window Copy(LSDMA), Linear to Tiled / Tiled to Linear sub-window copy(LSDMA) |  | P2 | nsdma10.101-110 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0
92 | NV48-OSS-129 | Linear to Structured / Structured to Linear copy | Song, Sukey | SDMA | Linear to Structured / Structured to Linear copy(LSDMA) |  | P2 | nsdma13.101-102 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
93 | NV48-OSS-130 | Linear to Tiled (frame to field) copy | Song, Sukey | Lite-SDMA | Linear to Tiled (frame to field) copy(LSDMA) |  | P2 | nsdma12.101-105 | Tserver |  | 1 | 5 | New | 1 | 5 | 1 | Emulator | 5 | 1 | 1 | [5 empty] | 5 | 5 |  |  |  | 1 |  | WK4
94 | NV48-OSS-133 | Linear to Tiled copy broadcast | Song, Sukey | Lite-SDMA | Linear to Tiled copy broadcast(LSDMA) |  | P2 | nsdma11.101-105 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK4
95 | NV48-OSS-134 | Mid Command Preemption | Song, Sukey | Lite-SDMA | Mid Command Preemption(LSDMA), Mid Command Buffer Preemption(LSDMA), RB Command Preemption(LSDMA) |  | P2 | nsdma217.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
96 | NV48-OSS-135 | Mid Command Buffer Preemption | Song, Sukey | Lite-SDMA | Mid Command Preemption(LSDMA), Mid Command Buffer Preemption(LSDMA), RB Command Preemption(LSDMA) |  | P2 | nsdma217.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
97 | NV48-OSS-136 | RB Command Preemption | Song, Sukey | Lite-SDMA | Mid Command Preemption(LSDMA), Mid Command Buffer Preemption(LSDMA), RB Command Preemption(LSDMA) |  | P2 | nsdma217.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
98 | NV48-OSS-137 | Mid-command preemption when time quantum reached | Song, Sukey | Lite-SDMA | Mid-command preemption when time quantum reached(LSDMA) |  | P2 | nsdma217.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK8
99 | NV48-OSS-138 | Structure Buffer Copy | Song, Sukey | Lite-SDMA | Structure Buffer Copy(LSDMA) |  | P2 | nsdma13.101-102 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
100 | NV48-OSS-139 | Constant Fill Command | Song, Sukey | Lite-SDMA | Constant Fill Command(LSDMA) |  | P2 | lsdma.packet.constant_fill | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
101 | NV48-OSS-140 | Indirect Buffer Command | Song, Sukey | Lite-SDMA | Indirect Buffer Command(LSDMA) |  | P2 | nsdma17.101-106 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
102 | NV48-OSS-141 | Fence | Song, Sukey | Lite-SDMA | Fence(LSDMA) |  | P2 | nsdma175;nsdma176 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
103 | NV48-OSS-142 | Trap | Song, Sukey | Lite-SDMA | Trap(LSDMA) |  | P2 | nsdma14.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK2
104 | NV48-OSS-143 | Memory Increment | Song, Sukey | Lite-SDMA | Memory Increment(LSDMA) |  | P2 | nsdma160.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
105 | NV48-OSS-144 | Poll Memory/Register | Song, Sukey | Lite-SDMA | Poll Memory/Register(LSDMA) |  | P2 | nsdma16.101-102 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
106 | NV48-OSS-145 | Poll Register Write Memory | Song, Sukey | Lite-SDMA | Poll Register Write Memory(LSDMA) |  | P2 | nsdma16.103 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
107 | NV48-OSS-147 | Conditional Execution | Song, Sukey | Lite-SDMA | Conditional Execution(LSDMA) |  | P2 | nsdma26.101 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK4
108 | NV48-OSS-148 | Predicated Execution | Song, Sukey | Lite-SDMA | Predicated Execution(LSDMA) |  | P2 | nsdma182.101 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK4
109 | NV48-OSS-149 | Atomic Command | Song, Sukey | Lite-SDMA | Atomic Command(LSDMA) |  | P2 | nsdma177.101 | Tserver |  | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | WK4
110 | NV48-OSS-150 | VM_INVALIDATION | Song, Sukey | Lite-SDMA | VM_INVALIDATION(LSDMA) |  | P2 | nsdma220.21-37 | Tserver |  | 1 | 17 | Legacy | 1 | 17 | 1 | Emulator | 17 | 17 | 17 |  |  |  | 1 | [6 empty] | 0 |  | WK5
111 | NV48-OSS-151 | SRBM Write | Song, Sukey | Lite-SDMA | SRBM Write(LSDMA) |  | P2 | nsdma120.101-106 | Tserver |  | 1 | 6 | Legacy | 1 | 6 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK5
112 | NV48-OSS-152 | Burst NOP | Song, Sukey | Lite-SDMA | Burst NOP(LSDMA) |  | P2 | nsdma223.101-102 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
113 | NV48-OSS-153 | Timestamp | Song, Sukey | Lite-SDMA | Timestamp(LSDMA) |  | P2 | nsmda56.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
114 | NV48-OSS-154 | Generate PTE/PDE | Song, Sukey | Lite-SDMA | Generate PTE/PDE(LSDMA) |  | P2 | gen,gte | TNG |  | 1 | 10 | Delta | 1 | 10 | 1 | Emulator | [6 empty] | 0 | [6 empty] | 0 |  | WK5
115 | NV48-OSS-155 | Copy Mask PTE/PDE | Song, Sukey | Lite-SDMA | Copy Mask PTE/PDE(LSDMA) |  | P2 | nsmda38.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
116 | NV48-OSS-156 | RMW PTE/PDE | Song, Sukey | Lite-SDMA | RMW PTE/PDE(LSDMA) |  | P2 | nsmda39.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
117 | NV48-OSS-158 | TMZ Support(LSDMA) | Song, Sukey | Lite-SDMA | TMZ Support(LSDMA) |  | P2 | nsdma152-nsdma159 | Tserver |  | 8 | 8 | Legacy | 1 | 8 | 1 |  | 0 | [5 empty] | 0 |  | 8 | 8 |  |  |  | 1 |  | WK6
118 | NV48-OSS-159 | Host Access LSDMA scratch ram (LSDMA) | Song, Sukey | Lite-SDMA | Host Access LSDMA scratch ram (LSDMA) |  | P2 | nsdma81.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
119 | NV48-OSS-160 | AQL Support (LSDMA) | Song, Sukey | Lite-SDMA | AQL Support (LSDMA) |  | P2 | nsdma214.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
120 | NV48-OSS-161 | (LSDMA) 2 HW Queue | Song, Sukey | Lite-SDMA | (LSDMA) 2 HW Queue |  | P2 | nsdma1.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK2
121 | NV48-OSS-162 | (LSDMA) PIO Queue support | Song, Sukey | Lite-SDMA | (LSDMA) PIO Queue support |  | P2 | nsdma212.1-2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK2
122 | NV48-OSS-168 | Atomic Command (HDP) | Song, Sukey | HDP | Atomic Command |  | P2 | nsdma177.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 0 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
123 | NV48-OSS-169 | Host read | Song, Sukey | HDP | Host read |  | P2 | hdp2.1-12 | Tserver |  | 1 | 12 | Legacy | 1 | 12 | 1 | Emulator | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | WK4
124 | NV48-OSS-170 | Host write | Song, Sukey | HDP | Host write |  | P2 | hdp1.1-12 | Tserver |  | 1 | 12 | Legacy | 1 | 12 | 1 | Emulator | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | WK4
125 | NV48-OSS-171 | HDP RAW Coherency | Song, Sukey | HDP | HDP RAW Coherency |  | P2 | hdp12.1-4 | Tserver |  | 1 | 4 | Legacy | 1 | 4 | 1 | Emulator | 4 | [5 empty] | 0 |  | 4 | 4 |  |  |  | 1 |  | WK4
126 | NV48-OSS-192 | HDP performance target | Song, Sukey | HDP | HDP performance target |  | P1 | eg | Tserver |  | 1 | 4 | Legacy | 1 | 4 | 1 | [7 empty] | 0 | [6 empty] | 0 |  | 0
127 | NV48-OSS-182 | UTCL2 retry interrupt filter | Song, Sukey | IH | UTCL2 retry interrupt filter |  | P2 | nsdma229.1-2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | Wk4
128 | NV48-OSS-186 | Remove ring2 to save area, since only 2 IH rings are enough. Test 2 IH rings | Song, Sukey | IH | Remove ring2 to save area, since only 2 IH rings are enough. Test 2 IH rings |  | P2 | ih,ring | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
129 | NV48-OSS-194 | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command(LSDMA) | Song, Sukey | Lite-SDMA | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command(LSDMA) |  | P1 | linear,write | TNG |  | 3 | 30 | New | 1 | 30 | 1 | Emulator | 30 | 30 | 30
130 | NV48-OSS-195 | Centralized Compression Support | Song, Sukey | Lite-SDMA | Centralized Compression Support(Lite Sdma) |  | P1 | lite,sdma,dcc | TNG |  | 2 | 10 | New | 1 | 8 | 0.8 | Emulator | 10 | 2 | 2
131 | NV48-OSS-196 | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel | Song, Sukey | Lite-SDMA | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel |  | P1 | tiled,copy | TNG |  | 3 | 3 | New | 1 | 3 | 1 | Emulator | 1 | 1 | 1
132 | NV48-OSS-197 | GFX12 address lib support | Song, Sukey | Lite-SDMA | GFX12 address lib support |  | P1 | tiled,copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1
133 | NV48-OSS-199 | Support "Physical Linear Copy" command | Song, Sukey | Lite-SDMA | Support "Physical Linear Copy" command |  | P1 | physical,linear,copy | TNG |  | 1 | 14 | New | 1 | 14 | 1 | Emulator | 14 | 14 | 14
134 | NV48-OSS-200 | Add context switch status registers for each HW queue(SDMA) | Song, Sukey | SDMA | Add context switch status registers for each HW queue(SDMA) |  | P1 | context,switch | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
135 | NV48-OSS-201 | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command | Song, Sukey | SDMA | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command |  | P1 | linear,write | TNG |  | 3 | 30 | New | 1 | 30 | 1 | Emulator | 30 | 30 | 30
136 | NV48-OSS-202 | Centralized Compression Support | Song, Sukey | SDMA | Centralized Compression Support |  | P1 | sdma,dcc | Tserver |  | 2 | 10 | New | 1 | 8 | 0.8 | Emulator | 1
137 | NV48-OSS-203 | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel | Song, Sukey | SDMA | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel |  | P1 | tiled,copy | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1
138 | NV48-OSS-204 | Decompress BLTs via SDMA | Song, Sukey | SDMA | Decompress BLTs via SDMA |  | P1 | sdma,dcc | Tserver |  | 2 | 2 | New | 1 | 2 | 1 | Emulator | 2 | 2 | 2
139 | NV48-OSS-205 | Dedicated TLB L1 cache for address translation in non-copy memory access | Song, Sukey | SDMA | Dedicated TLB L1 cache for address translation in non-copy memory access |  | P1 | sdma,tlb | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
140 | NV48-OSS-206 | Doorbell interface: Get doorbell from dbhub | Song, Sukey | SDMA | Doorbell interface: Get doorbell from dbhub |  | P1 | doorbell | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1
141 | NV48-OSS-207 | Extended MALL reuse policy control | Song, Sukey | SDMA | Extended MALL reuse policy control |  | P1 | mall | Tserver |  | 2 | 4 | New | 1 | 4 | 1 | Emulator | 1
142 | NV48-OSS-208 | Firewall update | Song, Sukey | SDMA | Firewall update |  | P1 | firewall | Tserver |  | 1 | 5 | New | 1 | 5 | 1 | Emulator | 1 | 1 | 1
143 | NV48-OSS-209 | GFX12 address lib support | Song, Sukey | SDMA | GFX12 address lib support |  | P1 | tiled,copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
144 | NV48-OSS-210 | GPUVM PDE/PTE definition change | Song, Sukey | SDMA | GPUVM PDE/PTE definition change |  | P1 | gpuvm | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
145 | NV48-OSS-213 | IB base address aligning from 8DW to DW | Song, Sukey | SDMA | IB base address aligning from 8DW to DW |  | P1 | ib,packet | TNG |  | 1 | 4 | New | 1 | 4 | 1 | Emulator | 1
146 | NV48-OSS-214 | Native GPU fence object support | Song, Sukey | SDMA | Native GPU fence object support |  | P1 | fence,interrupt | TNG |  | 1 | 4 | New | 1 | 4 | 1 | Emulator | 1 | 1 | 1
147 | NV48-OSS-215 | PAGE_TRANSER command | Song, Sukey | SDMA | PAGE_TRANSER command |  | P1 | page,transer | TNG |  | 2 | 8 | New | 1 | 8 | 1 | Emulator | 6 | 6 | 6
148 | NV48-OSS-220 | SDMA ucode caching | Song, Sukey | SDMA | SDMA ucode caching |  | P1 | linear,copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1
149 | NV48-OSS-221 | Use RS64 as SDMA MCU core | Song, Sukey | SDMA | Use RS64 as SDMA MCU core |  | P1 | linear,copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | l
514

## Sheet2
Test Case ID | Framework | Parameters | Effort | Total Variations
context switch | TNG |  | 1 | 1 | sdma84.101-102 | sdma84.101-102 | 2
doorbell | TNG |  | 1 | 1 | nsdma177.1 | nsdma177.1 | Var OK
eg | Tserver |  | 1 | 4 | nsdma178.1 | nsdma178.1 | 1
fence interrupt | TNG |  | 1 | 4 | nsdma179.1 | nsdma179.1 | 1
firewall | Tserver |  | 1 | 5 | nsdma223.1-2 | nsdma223.1-2 | 2
gen gte | TNG |  | 1 | 10 | nsdma207.1 | nsdma207.1 | 1
gen gte | TNG |  | 1 | 10 | sdma27.1-2 | sdma27.1-2 | 2
gpuvm | Tserver |  | 1 | 1 | nsdma27.1 | nsdma27.1 | Var OK
hdp1.1-12 | Tserver |  | 1 | 12 | nsdma26.1 | nsdma26.1 | 1
hdp12.1-4 | Tserver |  | 1 | 4 | nsdma58.1 | nsdma58.1 | 1
hdp2.1-12 | Tserver |  | 1 | 12 | nsdma59.1 | nsdma59.1 | 1
ib packet | TNG |  | 1 | 4 | nsdma215.1-3 | nsdma215.1-3 | 3
ih ring | Tserver |  | 1 | 1 | nsdma81.1 | nsdma81.1 | Var OK
linear copy | TNG |  | 1 | 1 | sdma.packet.fence | sdma.packet.fence | Var OK
linear copy | TNG |  | 1 | 1 | sdma.packet.fence | sdma.packet.fence | Var OK
linear write | TNG |  | 3 | 30 | nsdma205.1-2 | nsdma205.1-2 | 2
linear write | TNG |  | 3 | 30 | nsdma206.1-2 | nsdma206.1-2 | 2
lite sdma dcc | TNG |  | 2 | 10 | nsdma66.1-2 | nsdma66.1-2 | 2
lsdma.packet.constant_fill | TNG |  | 1 | 1 | nsdma67.1-2 | nsdma67.1-2 | 2
mall | Tserver |  | 2 | 4 | nsdma68.1-2 | nsdma68.1-2 | 2
nsdma1.1 | Tserver |  | 1 | 1 | nsdma1.1 | OK | Var OK
nsdma1.1 | Tserver |  | 1 | 1 | nsdma1.2 | nsdma1.2 | 2
nsdma1.1 | Tserver |  | 1 | 1 | nsdma1.1 | OK | Var OK
nsdma1.1 | Tserver |  | 1 | 1 | nsdma1.1 | OK | Var OK
nsdma1.101 | Tserver |  | 1 | 1 | nsdma5.1 | nsdma5.1 | Var OK
nsdma1.101 | Tserver |  | 1 | 1 | nsdma4.1 | nsdma4.1 | Var OK
nsdma1.2 | TNG |  | 1 | 2 | nsdma7.1-5 | nsdma7.1-5 | 5
nsdma10.1 | Tserver |  | 1 | 1 | nsdma7.1-5 | nsdma7.1-5 | 5
nsdma10.101-110 | Tserver |  | 1 | 1 | nsdma93.1 | nsdma93.1 | Var OK
nsdma10.1-10 | Tserver |  | 1 | 5 | nsdma9.1-5 | nsdma9.1-5 | 1
nsdma11.101-105 | Tserver |  | 1 | 1 | nsdma10.1-10 | nsdma10.1-10 | 5
nsdma11.1-5 | Tserver |  | 1 | 5 | nsdma10.1-10 | nsdma10.1-10 | Var OK
nsdma12.101-105 | Tserver |  | 1 | 5 | nsdma13.1-2 | nsdma13.1-2 | 2
nsdma12.1-5 | Tserver |  | 1 | 5 | nsdma12.1-5 | OK | Var OK
nsdma120.101-106 | Tserver |  | 1 | 6 | nsdma2.1-5 | nsdma2.1-5 | 5
nsdma120.1-6 | Tserver |  | 1 | 6 | nsdma3.1-5 | nsdma3.1-5 | 5
nsdma126,127,128 | Tserver |  | 1 | 3 |  | nsdma11.1-5 | 5
nsdma126-nsdma134 | Tserver |  | 1 | 9 |  | nsmda217.1 | 1
nsdma13.101-102 | Tserver |  | 1 | 2 |  | nsmda217.1 | 1
nsdma13.101-102 | Tserver |  | 1 | 1 |  | nsmda217.1 | Var OK
nsdma13.1-2 | Tserver |  | 1 | 2 |  | nsmda217.1 | 1
nsdma14.1 | Tserver |  | 1 | 1 |  | nsmda217.1 | Var OK
nsdma14.1 | Tserver |  | 1 | 1 |  | nsmda217.1 | Var OK
nsdma14.1 | Tserver |  | 1 | 1 |  | nsmda218.1 | Var OK
nsdma14.101 | Tserver |  | 1 | 1 |  | nsmda218.1 | Var OK
nsdma152-nsdma159 | Tserver |  | 1 | 8 |  | nsdma160.1 | 1
nsdma152-nsdma159 | Tserver |  | 8 | 8 |  | sdma.packet.physical_linear_copy/1-8,sdma.packet.physical_linear_copy/21-28 | 16
nsdma16.101-102 | Tserver |  | 1 | 1 |  | nsdma16.1-10 | 10
nsdma16.103 | Tserver |  | 1 | 1 |  | nsdma182.1,nsdma183.1 | 2
nsdma16.1-10 | Tserver |  | 1 | 10 |  | nsdma68.1-2 | 2
nsdma160.1 | Tserver |  | 1 | 1 |  | nsdma222.1-34 | 34
nsdma160.101 | Tserver |  | 1 | 1 |  | nsdma222.1-34 | 34
nsdma17.101-106 | Tserver |  | 1 | 1 |  | nsmda402.1 | Var OK
nsdma175;nsdma176 | Tserver |  | 1 | 1 |  | nsdma402.2 | Var OK
nsdma177.1 | Tserver |  | 1 | 1 |  | nsmda409.1 | Var OK
nsdma177.1 | Tserver |  | 1 | 1 |  | nsmda410.1 | Var OK
nsdma177.101;nsdma178.101;nsdma179.101 | Tserver |  | 1 | 3 |  | nsdma120.1-6 | 6
nsdma178.1 | Tserver |  | 1 | 1 |  | nsdma2.6 | Var OK
nsdma179.1 | Tserver |  | 1 | 1 |  | nsdma152-nsdma159 | 8
nsdma182,nsdma183 | Tserver |  | 1 | 2 |  | nsdma10.1 | 1
nsdma182.1, nsdma183.1 | Tserver |  | 1 | 2 |  | nsdma26,nsdma27 | Var OK
nsdma182.101;nsdma183.101 | Tserver |  | 1 | 2 |  | nsdma182,nsdma183 | Var OK
nsdma2.101-105, nsdma3.101-105 | Tserver |  | 1 | 1 |  | gen,gte | 10
nsdma2.1-5 | Tserver |  | 1 | 5 |  | nsdma201.1 | 1
nsdma2.6 | Tserver |  | 1 | 1 |  | nsdma203.1 | Var OK
nsdma201.1 | Tserver |  | 1 | 1 |  | nsdma56,nsdms57 | 2
nsdma203.1 | Tserver |  | 1 | 1 |  | nsdma126-nsdma134 | 9
nsdma204.1 | Tserver |  | 1 | 1 |  | nsdma222.1-18 | Var OK
nsdma205.1-2 | Tserver |  | 1 | 2 |  | nsdma14.1 | 1
nsdma206.1-2 | Tserver |  | 1 | 2 |  | nsdma204.1 | 1
nsdma207.1 | Tserver |  | 1 | 1 |  | nsdma213.1-4 | Var OK
nsdma207.1 | Tserver |  | 1 | 1 |  | nsdma216.1 | Var OK
nsdma212.1-2 | Tserver |  | 1 | 1 |  | nsdma207.1 | Var OK
nsdma213.1-4 | Tserver | '-oss_sdmaengines=sdma0_all -oss_no_fill_and_verify=true -sdma_copysize=4KiB -sdma_loops=2 | 1 | 1 |  | nsdma1.1 | Var OK
nsdma214.101 | Tserver |  | 1 | 1 |  | nsdma126,nsdma126127,nsdma126128 | 3
nsdma215.1-3 | Tserver |  | 3 | 3 |  | nsdma14.1 | 1
nsdma216.1 | Tserver |  | 1 | 1 |  | nsdma410 | Var OK
nsdma217.101 | Tserver |  | 1 | 1 |  | nsdma1.1 | Var OK
nsdma217.101 | Tserver |  | 1 | 1 |  | nsdma14.1 | Var OK
nsdma220.21-37 | Tserver |  | 1 | 17 |  | nsdma59.1 | 1
nsdma222.1-18 | Tserver |  | 1 | 1 |  | nsdma1.101 | Var OK
nsdma222.1-34 | Tserver |  | 4 | 34 |  | nsdma1.101 | 1
nsdma223.101-102 | Tserver |  | 1 | 1 |  | nsdma5.101 | Var OK
nsdma223.1-2 | Tserver |  | 1 | 2 |  | nsdma4.101 | 1
nsdma229.1-2 | Tserver |  | 1 | 1 |  | nsdma7.101-105 | 5
nsdma26,nsdma27 | Tserver |  | 1 | 2 |  | nsdma7.101-105 | 5
nsdma26.1 | Tserver |  | 1 | 1 |  | nsdma93.101 | Var OK
nsdma26.101;nsdma27.101 | Tserver |  | 1 | 2 |  | nsdma2.101-105,nsdma3.101-105 | 1
nsdma27.1 | Tserver |  | 1 | 1 |  | nsdma2.101-105,nsdma3.101-105 | Var OK
nsdma3.1-5 | Tserver |  | 1 | 5 |  | nsdma9.101-105 | 1
nsdma4.1 | Tserver |  | 1 | 1 |  | nsdma10.101-110 | Var OK
nsdma4.101 | Tserver |  | 1 | 1 |  | nsdma10.101-110 | Var OK
nsdma402.2 | Tserver |  | 1 | 1 |  | nsdma13.101-102 | 2
nsdma410 | Tserver |  | 1 | 1 |  | nsdma12.101-105 | 5
nsdma5.1 | Tserver |  | 1 | 1 |  | nsdma11.101-105 | Var OK
nsdma5.101 | Tserver |  | 1 | 1 |  | nsdma217.101 | Var OK
nsdma56,nsdms57 | Tserver |  | 1 | 2 |  | nsdma217.101 | 1
nsdma58.1 | Tserver |  | 1 | 1 |  | nsdma217.101 | Var OK
nsdma59.1 | Tserver |  | 1 | 1 |  | nsdma217.101 | Var OK
nsdma59.1 | Tserver |  | 1 | 1 |  | nsdma13.101-102 | Var OK
nsdma66.1-2 | Tserver | -vm | 1 | 2 |  | lsdma.packet.constant_fill | 1
nsdma67.1-2 | Tserver | -vm | 1 | 2 |  | nsdma17.101-106 | 1
nsdma68.1-2 | Tserver | -vm | 1 | 2 |  | nsdma175;nsdma176 | 1
nsdma68.1-2 | Tserver |  | 1 | 2 |  | nsdma14.101 | 1
nsdma7.101-105 | Tserver |  | 5 | 5 |  | nsdma160.101 | 1
nsdma7.1-5 | Tserver |  | 1 | 5 |  | nsdma16.101-102 | 1
nsdma81.1 | Tserver |  | 1 | 1 |  | nsdma16.103 | Var OK
nsdma81.101 | Tserver |  | 1 | 1 |  | nsdma26.101 | 2
nsdma9.101-105 | Tserver |  | 1 | 1 |  | nsdma182.101 | 2
nsdma9.1-5 | Tserver |  | 1 | 1 |  | nsdma177.101 | 3
nsdma93.1 | Tserver |  | 1 | 1 |  | nsdma220.21-37 | 17
nsdma93.101 | Tserver |  | 1 | 1 |  | nsdma120.101-106 | 6
nsmda217.1 | Tserver |  | 1 | 1 |  | nsdma223.101-102 | Var OK
nsmda218.1 | Tserver |  | 1 | 1 |  | nsmda56.101 | Var OK
nsmda38.101 | Tserver |  | 1 | 1 |  | gen,gte | 10
nsmda39.101 | Tserver |  | 1 | 1 |  | nsmda38.101 | Var OK
nsmda402.1 | Tserver |  | 1 | 1 |  | nsmda39.101 | Var OK
nsmda409.1 | Tserver |  | 1 | 1 |  | nsdma152-nsdma159 | 8
nsmda410.1 | Tserver |  | 1 | 1 |  | nsdma81.101 | Var OK
nsmda56.101;nsdma57.101 | Tserver |  | 1 | 1 |  | nsdma214.101 | Var OK
page transer | TNG |  | 2 | 8 |  | nsdma1.101 | 1
physical linear copy | TNG |  | 1 | 14 |  | nsdma212.1-2 | 1
sdma dcc | Tserver |  | 2 | 10 |  | nsdma177.1 | 1
sdma dcc | Tserver |  | 2 | 2 |  | hdp2.1-12 | 12
sdma tlb | TNG |  | 1 | 1 |  | hdp1.1-12 | 12
sdma.packet.fence | TNG |  | 1 | 1 |  | hdp12.1-4 | 4
sdma.packet.fence | TNG |  | 1 | 1 |  | eg | 4
sdma.packet.physical_linear_copy/1-8 sdma.packet.physical_linear_copy/21-28 | TNG |  | 1 | 16 |  | nsdma229.1-2 | 1
sdma27.1-2 | Tserver |  | 1 | 2 |  | ih,ring | 1
sdma84.101-102 | Tserver |  | 1 | 2 |  | linear,write | 30
tiled copy | TNG |  | 3 | 3 |  | lite,sdma,dcc | 10
tiled copy | TNG |  | 1 | 1 |  | tiled,copy | 3
tiled copy | Tserver |  | 1 | 1 |  | tiled,copy | Var OK
tiled copy | TNG |  | 1 | 1 |  | physical,linear,copy | 14
| Tserver |  | 1 | 1 |  | context,switch | Var OK
| Tserver |  | 1 | 1 |  | linear,write | 30
| Tserver |  | 1 | 1 |  | sdma,dcc | 10
456
Note on A1: TServer or CDL or any type of Diags test case ID. Unique Test Case ID, as used in Diag suites and scripts. One Test Case ID per row. Do not use different designations for same test – i.e., "TestId7.1" and "TestId007.001". Pick one, and stick with it consistently.
Note on C1: Indicate any parameters that are required to run this test Saeed: How should this be used if different parameters need to be used for different runs?
Note on E1: Total # of test variations for the given row's particular test case