## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | NV48-DF-001 | Byte Enable Writes | sbalabat | DF |  | HDP,CPDMA Byte Enable Write | P3 | FEAT-1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK3
1 | NV48-DF-002 | Coherency | sbalabat | DF |  | DF Coherency Test | P1 | FEAT-2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK2
2 | NV48-DF-003 | I/O and Graphics Atomic | sbalabat | DF |  | DF Atomic Test | P1 | FEAT-3 | Tserver |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | WK2
3 | NV48-DF-003 | I/O and Graphics Atomic | sbalabat | DF |  | DF Atomic Test | P1 | FEAT-3 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | Emulator | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1 |  | WK2
4 | NV48-DF-004 | DF P-states with Memory stress | sbalabat | DF |  | DF Pstate Test | P2 | FEAT-5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
5 | NV48-DF-005 | DF_C_State | sbalabat | DF |  | DF Cstate Test | P1 | FEAT-6 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
6 | NV48-DF-006 | Display and Stutter Mode | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT-7 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
7 | NV48-DF-006 | Display and Stutter Mode | sbalabat | DF |  | DF Cstate Stutter Test | P1 | FEAT-8 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
8 | NV48-DF-007 | 128B Gfx Large Reads to Mall | sbalabat | DF |  | DF large read test | P1 | FEAT-9 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK2
9 | NV48-DF-008 | Performance Monitors | sbalabat | DF |  | DF large read test | P1 | FEAT-10 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK2
10 | NV48-DF-009 | Power Gate During DF C-State | sbalabat | DF |  | DF Cstate Stutter Test | P2 | FEAT-11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
11 | NV48-DF-010 | Unified Memory Fencing | sbalabat | DF |  | DF UMF test | P1 | FEAT-12 | Tserver |  | 1 | 4 | New | 1 | 1 | 0.25 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
12 | NV48-DF-011 | MALL Alloc / NoAlloc for GFX | sbalabat | DF |  | DF GFX No-Alloc Mall diag | P2 | FEAT-13 | Tserver |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
13 | NV48-DF-012 | MALL NoAlloc override for HDP | sbalabat | DF |  | DF NCM No-Alloc Mall diag | P2 | FEAT-14 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
14 | NV48-DF-013 | Streaming performance Monitor | sbalabat | DF |  | DF SPM diag | P1 | FEAT-15 | Tserver |  | 1 | 4 | Delta | 1 | 4 | 1 | Emulator | 4 | 4 | 4 |  |  |  | 1 | Considering KMD teams result on NV48 emulator. Basic functionality of SPM feature verified, aligned with IPSE | 0 |  |  |  |  | 0 |  | WK7
15 | NV48-DF-014 | Mall Hashing Support in NV4x | sbalabat | DF |  | DF EL3 diag | P2 | FEAT-16 | Tserver |  | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK11
16 | NV48-DF-015 | MALL support for UMC Perfmon event propagation | sbalabat | DF |  | DF SPM diag | P2 | FEAT-17 | Tserver |  | 1 | 4 | Delta | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
17 | NV48-DF-016 | Dual Edge Synchronous Buses (Double Pumping) | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT-18 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK4
18 | NV48-DF-016 | Dual Edge Synchronous Buses (Double Pumping) | sbalabat | DF | Traffic | DF stress traffic diag | P1 | FEAT-19 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | Partial coverage is done, low risk. Aligned with IPSE | 0 |  |  |  |  | 0
19 | NV48-DF-017 | GCM/NCM Large Write | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT-21 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | wk-6
20 | NV48-DF-017 | GCM/NCM Large Write | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT-22 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
21 | NV48-DF-017 | GCM/NCM Large Write | sbalabat | DF | Large Write | DF Large write diag | P1 | FEAT-23 | Tserver |  | 1 | 1 | New | 1 | 0.5 | 0.5 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
22 | NV48-DF-019 | NCM Subtype for CPWD | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT-25 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
23 | NV48-DF-020 | 2 PG Domain | sbalabat | DF |  |  | P1 | FEAT-26 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK9
24 | NV48-DF-021 | TCDX traffic stress case | sbalabat | DF |  | DF stress traffic diag | P1 | FEAT-26 | Tserver |  | 1 | 1 | New | 1 | 0.8 | 0.8 |  |  | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK4
25 | NV48-DF-022 | DF Tserverlite Lib | sbalabat | DF |  | DF library in Tserverlite | P1 | FEAT-27 | Tserver |  | 1 | 10 | Legacy | 1 | 10 | 1 | Emulator | 10 | 10 | 10 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK3
26 | NV48-DF-023 | DF TNG Lib | sbalabat | DF |  | DF library in TNG | P1 | FEAT-28 | TNG |  | 1 | 10 | New | 1 | 10 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK3