## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id | test_list_id
0 | DF-001 | APIC Timers | Sudharshana | PIE | APIC Timers | APIC_Timer_Reload | P1 | FEAT_1 | CDL | ./APIC_Timer_Reload --cpu all -t 1h -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-1 |  | 0 | 1 | FEAT_1 | 1
1 | DF-002 | Arbitrated Interrupt Delivery Enhancements | Sudharshana | PIE | Arbitrated Interrupt Delivery Enhancements | Lowest_Priority_Interrupts | P2 | FEAT_2 | CDL | ./Lowest_Priority_Interrupts --cpu all -t 1h -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-1 |  | 0 | 1 | FEAT_2 | 2
2 | DF-003 | Bus Locks | Sudharshana | DF | Bus Locks - uc | DF_Bus_Locks | P1 | FEAT_3 | CDL | /CPU/linux/Data_Fabric_Suite/DF_Bus_Locks --cpu 0 -t 1m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 0 | 1 | FEAT_3 | 3
3 | DF-003 | Bus Locks | Sudharshana | DF | Bus Locks - wb | DF_Bus_Locks | P1 | FEAT_3 | TNG | /CPU/linux/Data_Fabric_Suite/DF_Bus_Locks --cpu 0 --cache-lock -t 1m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 0 | 1 | FEAT_3 | 4
4 | DF-003 | Bus Locks | Sudharshana | DF | Bus Locks - apic region | DF_Bus_Locks | P1 | FEAT_3 | CDL | /CPU/linux/Data_Fabric_Suite/DF_Bus_Locks --cpu 0 --apic-region -t 1m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 0 | 1 | FEAT_3 | 5
5 | DF-003 | Bus Locks | Sudharshana | DF | Bus Locks - mmio region | DF_Bus_Locks | P1 | FEAT_3 | CDL | ./DF_Bus_Locks --mmio-region -v --mmio-address 0xfec00004 -t 1m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 0 | 1 | FEAT_3 | 6
6 | DF-004 | Byte Enable Writes | Sudharshana | DF | Byte Enable Writes | Streaming_Store_Instructions | P1 | FEAT_4 | CDL | ./Streaming_Stores_With_Clflush --cpu all -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 0 | 1 | FEAT_4 | 7
7 | DF-005 | CCM Ordering | Sudharshana | CCM | CCM Ordering | Producer_Consumer | P3 | FEAT_5 | TNG | ./Producer_Consumer –cpu all -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 0 | 1 | FEAT_5 | 8
8 | DF-006 | CCM Bypasses | Sudharshana | CCM | CCM Bypasses | Mix of traffic | P2 | FEAT_6 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-1 |  | 0 | 1 | FEAT_6 | 9
9 | DF-007 | CF8/CFC | Sudharshana | CCM | CF8/CFC | IO_Port_Accesses | P1 | FEAT_7.1 | CDL | ./IO_Port_Accesses --cpu 0 -v --write; ./IO_Port_Accesses --cpu 0 -v; ./CSR_Write_Tool --iocfc --cpu 0 --bus 0 --device 0 --address F0x068 --value 0xAAAAAAAA --compare -t 1m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 2 | 3 | FEAT_7.1-3 | 10
10 | DF-007 | CF8/CFC | Sudharshana | CCM | CF8/CFC | IO_Port_Accesses | P1 | FEAT_7.2 | CDL | ./IO_Port_Accesses --cpu 0 -v --write; ./IO_Port_Accesses --cpu 0 -v; ./CSR_Write_Tool --iocfc --cpu 0 --bus 0 --device 0 --address F0x068 --value 0xAAAAAAAA --compare -t 1m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 1 | 3 | FEAT_7.1-3 | 10
11 | DF-007 | CF8/CFC | Sudharshana | CCM | CF8/CFC | IO_Port_Accesses | P1 | FEAT_7.3 | CDL | ./IO_Port_Accesses --cpu 0 -v --write; ./IO_Port_Accesses --cpu 0 -v; ./CSR_Write_Tool --iocfc --cpu 0 --bus 0 --device 0 --address F0x068 --value 0xAAAAAAAA --compare -t 1m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 0 | 3 | FEAT_7.1-3 | 10
12 | DF-008 | CPU Downcoring | Sudharshana | DF | CPU Downcoring | CPU_Downcoring | P1 | FEAT_8 | CDL | Use BIOS settings to downcore the system to down core the system. System may hang. Warm reboot the system then run GME. ./General_Memory_Exerciser -v --cpu all; GME should work. | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 1 | FEAT_8 | 11
13 | DF-009 | CPU Lone Potato/Lightly Loaded | Sudharshana | CCM | CPU Lone Potato/Lightly Loaded | Will be tested during normal functionality of core; Mix of traffic from different cores. | P1 | FEAT_9 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_9 | 12
14 | DF-010 | CS Read-to-Read Forwarding | Sudharshana | CS | CS Read-to-Read Forwarding | GME along with PMC check | P3 | FEAT_10 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 0 | 1 | FEAT_10 | 13
15 | DF-011 | CS Write Combining | Sudharshana | CS | CS Write Combining | GME along with PMC check | P2 | FEAT_11 | CDL | ./CS_Write_Combining --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 0 | 1 | FEAT_11 | 14
16 | DF-012 | CS Write-to-Read Forwarding | Sudharshana | CS | CS Write-to-Read Forwarding | GME along with PMC check | P1 | FEAT_12 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 1 | FEAT_12 | 15
17 | DF-013 | CS-UMC Cancels | Sudharshana | CS | CS-UMC Cancels | Mix of traffic | P3 | FEAT_13 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 1 | FEAT_13 | 16
18 | DF-014 | Coherent Slave Bypasses | Sudharshana | CS | Coherent Slave Bypasses | Mix of traffic | P1 | FEAT_14 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 1 | FEAT_14 | 17
19 | DF-015 | Coherency | Sudharshana | CS | Coherency | Cache_Coherency | P1 | FEAT_15 | CDL | ./Cache_Coherency --cpu all -v -t 30m | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 1 | FEAT_15 | 18
20 | DF-016 | DF P-states | Sudharshana | PIE | DF P-states | DF_P_State | P1 | FEAT_16 | CDL | ./tserverlite -d=1 -log -disable_libdce -v=error -test=pm15.1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-8 |  | 0 | 1 | FEAT_16 | 19
21 | DF-017 | I/O and Graphic Atomics | Sudharshana | CS | I/O and Graphic Atomics | df104.0, df104.1 | P1 | FEAT_17.1 | TServer | ./tserverlite -d=1 -load_ucode=tcore -test=df104.0 -nobios -no_toollib -disable_libdce -norlc; ./tserverlite -d=1 -load_ucode=tcore -test=df104.1 -nobios -no_toollib -disable_libdce -norlc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 1 | 2 | FEAT_17.1-2 | 20
22 | DF-017 | I/O and Graphic Atomics | Sudharshana | CS | I/O and Graphic Atomics | df104.0, df104.1 | P1 | FEAT_17.2 | TServer | ./tserverlite -d=1 -load_ucode=tcore -test=df104.0 -nobios -no_toollib -disable_libdce -norlc; ./tserverlite -d=1 -load_ucode=tcore -test=df104.1 -nobios -no_toollib -disable_libdce -norlc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 2 | FEAT_17.1-2 | 20
23 | DF-018 | IOM Ordering | Sudharshana | IOM | IOM Ordering | Producer_Consumer | P2 | FEAT_18.1 | CDL | ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 3 | 4 | FEAT_18.1-4 | 21
24 | DF-018 | IOM Ordering | Sudharshana | IOM | IOM Ordering | Producer_Consumer | P2 | FEAT_18.2 | CDL | ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 2 | 4 | FEAT_18.1-4 | 21
25 | DF-018 | IOM Ordering | Sudharshana | IOM | IOM Ordering | Producer_Consumer | P2 | FEAT_18.3 | CDL | ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 1 | 4 | FEAT_18.1-4 | 21
26 | DF-018 | IOM Ordering | Sudharshana | IOM | IOM Ordering | Producer_Consumer | P2 | FEAT_18.4 | CDL | ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-flag --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data --mmio-address 0xfed00000 -v; ./Producer_Consumer --producer 2 --consumer 4 --mmio-data -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 0 | 4 | FEAT_18.1-4 | 21
27 | DF-019 | Interrupt Delivery Through SMN | Sudharshana | PIE | Interrupt Delivery Through SMN | Fixed_Interrupts | P3 | FEAT_19.1 | CDL | Set DisApcIcrAsyncFixed to Zero then run "./Fixed_Interrupts --cpu 0 -v ./SMI_Check --cpu all -t 1h -v ./NMI_Check --cpu all -t 1h -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 2 | 3 | FEAT_19.1-3 | 22
28 | DF-019 | Interrupt Delivery Through SMN | Sudharshana | PIE | Interrupt Delivery Through SMN | Fixed_Interrupts | P3 | FEAT_19.2 | CDL | Set DisApcIcrAsyncFixed to Zero then run "./Fixed_Interrupts --cpu 0 -v ./SMI_Check --cpu all -t 1h -v ./NMI_Check --cpu all -t 1h -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 1 | 3 | FEAT_19.1-3 | 22
29 | DF-019 | Interrupt Delivery Through SMN | Sudharshana | PIE | Interrupt Delivery Through SMN | Fixed_Interrupts | P3 | FEAT_19.3 | CDL | Set DisApcIcrAsyncFixed to Zero then run "./Fixed_Interrupts --cpu 0 -v ./SMI_Check --cpu all -t 1h -v ./NMI_Check --cpu all -t 1h -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 3 | FEAT_19.1-3 | 22
30 | DF-020 | Large Reads | Sudharshana | IOM | Large Reads | umc321.101, umc302.7 | P1 | FEAT_20 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_20 | 23
31 | DF-021 | MemCancels | Sudharshana | CS | MemCancels | Cache_Coherency | P3 | FEAT_21 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 1 | FEAT_21 | 24
32 | DF-022 | Multiple TCDX Pickers | Sudharshana | DF | Multiple TCDX Pickers | Mix of traffic | P1 | FEAT_22 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 1 | FEAT_22 | 25
33 | DF-023 | PCI IO/Configuration Splitting | Sudharshana | CCM | PCI IO/Configuration Splitting | CSR_Write_Tool | P3 | FEAT_23 | CDL | CSR_Write_Tool --cpu 0 --device 0 --address F0x069 --value 0xAAAAAAAA --compare -t 1s -v --bus 0; | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 0 | 1 | FEAT_23 | 26
34 | DF-024 | Performance Monitors | Sudharshana | DF | Performance Monitors | Verified by other diags which are using PMCs | P2 | FEAT_24 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 0 | 1 | FEAT_24 | 27
35 | DF-025 | Power Gate During DF C-states | Sudharshana | PIE | Power Gate During DF C-states |  | P2 | FEAT_25 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 0 | 1 | FEAT_25 | 28
36 | DF-026 | Priority Pickers | Sudharshana | DF_QOS | Priority Pickers | Mix of traffic | P1 | FEAT_26 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-3 |  | 0 | 1 | FEAT_26 | 29
37 | DF-027 | Request Limiters | Sudharshana | DF_QOS | Request Limiters | GME with MasterRequestControl.MstDramActReqLmt config | P2 | FEAT_27.1 | CDL | ./Request_Limiters --cpu 0 -v --graded-regime=unthrottle ./Request_Limiters --cpu 0 -v --graded-regime=light ./Request_Limiters --cpu 0 -v --graded-regime=heavy ./Request_Limiters --cpu 0 -v --graded-regime=stop | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 3 | 4 | FEAT_27.1-4 | 30
38 | DF-027 | Request Limiters | Sudharshana | DF_QOS | Request Limiters | GME with MasterRequestControl.MstDramActReqLmt config | P2 | FEAT_27.2 | CDL | ./Request_Limiters --cpu 0 -v --graded-regime=unthrottle ./Request_Limiters --cpu 0 -v --graded-regime=light ./Request_Limiters --cpu 0 -v --graded-regime=heavy ./Request_Limiters --cpu 0 -v --graded-regime=stop | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 2 | 4 | FEAT_27.1-4 | 30
39 | DF-027 | Request Limiters | Sudharshana | DF_QOS | Request Limiters | GME with MasterRequestControl.MstDramActReqLmt config | P2 | FEAT_27.3 | CDL | ./Request_Limiters --cpu 0 -v --graded-regime=unthrottle ./Request_Limiters --cpu 0 -v --graded-regime=light ./Request_Limiters --cpu 0 -v --graded-regime=heavy ./Request_Limiters --cpu 0 -v --graded-regime=stop | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 1 | 4 | FEAT_27.1-4 | 30
40 | DF-027 | Request Limiters | Sudharshana | DF_QOS | Request Limiters | GME with MasterRequestControl.MstDramActReqLmt config | P2 | FEAT_27.4 | CDL | ./Request_Limiters --cpu 0 -v --graded-regime=unthrottle ./Request_Limiters --cpu 0 -v --graded-regime=light ./Request_Limiters --cpu 0 -v --graded-regime=heavy ./Request_Limiters --cpu 0 -v --graded-regime=stop | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 4 | FEAT_27.1-4 | 30
41 | DF-028 | TCDX Bypass | Sudharshana | DF | TCDX Bypass | Mix of traffic | P1 | FEAT_28 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_28 | 31
42 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.1 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 9 | 10 | FEAT_29.1-10 | 32
43 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.2 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 8 | 10 | FEAT_29.1-10 | 32
44 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.3 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 7 | 10 | FEAT_29.1-10 | 32
45 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.4 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 6 | 10 | FEAT_29.1-10 | 32
46 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.5 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 5 | 10 | FEAT_29.1-10 | 32
47 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.6 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 4 | 10 | FEAT_29.1-10 | 32
48 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.7 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 3 | 10 | FEAT_29.1-10 | 32
49 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.8 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 2 | 10 | FEAT_29.1-10 | 32
50 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.9 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 1 | 10 | FEAT_29.1-10 | 32
51 | DF-029 | Trusted Memory Regions | Sudharshana | DF_SECURITY | Trusted Memory Regions | TMR_Test | P2 | FEAT_29.10 | CDL | ./TMR_Test_CCM --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 0 | 10 | FEAT_29.1-10 | 32
52 | DF-030 | Virtual Channels | Sudharshana | DF | Virtual Channels | Mix of traffic | P1 | FEAT_30 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 0 | 1 | FEAT_30 | 33
53 | DF-031 | Zero Data Compression | Sudharshana | CCM | Zero Data Compression | Zero_Data_Compression | P1 | FEAT_31 | CDL | ./Zero_Data_Compression --cpu 0 -v | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 0 | 1 | FEAT_31 | 34
54 | DF-032 | Save/Restore scoreboard | Sudharshana | PIE | Save/Restore scoreboard |  | P1 | FEAT_32 | CDL | Validated as part of DF C-state verification by IPSE | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_32 | 35
55 | DF-033 | DF_C_State | Sudharshana | PIE | DF_C_State | DF_C_State | P3 | FEAT_33 | CDL | ./DF_C_State_4_X --cpu 0 -v --test=df_c_state_residency | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_33 | 36
56 | DF-034 | TMR FMR Common region | Sudharshana | DF_SECURITY | TMR FMR Common region | TMR FMR Common region | P1 | FEAT_34 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 0 | 1 | FEAT_34 | 37
57 | DF-035 | Master Abort | Sudharshana | CCM | Master Abort | Master Abort | P3 | FEAT_35 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_35 | 38
58 | DF-036 | Extended Save restore APIC | Sudharshana | PIE | DF_ExtendedSave_Restore_APIC | DF_ExtendedSave_Restore_APIC | P1 | FEAT_36 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_36 | 39
59 | DF-037 | DF_SpecialSysFunctionFabricID_Check | Sudharshana | DF | DF_SpecialSysFunctionFabricID_Check | DF_SpecialSysFunctionFabricID_Check | P1 | FEAT_37 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-2 |  | 0 | 1 | FEAT_37 | 40
60 | DF-038 | DF Stress test | Sudharshana | DF | DF Stress test | DF Stress test | P2 | FEAT_38 | CDL | ./DF_Stress_CPU_Focused_SLT.yaml | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_38 | 41
61 | DF-039 | Light DF C-State | Sudharshana | PIE |  |  | P2 | FEAT_39 | CDL | ./DF_C_State_4_X --cpu 0 -v --test=df_light_c_state | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_39 | 42
62 | DF-040 | IO atomics with Bus locks | Sudharshana | DF |  |  | P2 | FEAT_40 | CDL |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_40 | 43
63 | DF-041 | Force DF C-state exit on MCA bank access | Sudharshana | PIE |  |  | P1 | FEAT_41 | CDL |  | 0 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 | It’s a debug feature not a POR feature, Validated by Validation team during PHX | 0 | 0 |  | 0 | 0 | 0 |  | wk-8 |  | 0 | 1 | FEAT_41 | 44
64 | DF-042 | DF exerciser | Sudharshana | DF |  |  | P2 | FEAT_42.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 3 | 4 | FEAT_42.1-4 | 45
65 | DF-042 | DF exerciser | Sudharshana | DF |  |  | P2 | FEAT_42.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 2 | 4 | FEAT_42.1-4 | 45
66 | DF-042 | DF exerciser | Sudharshana | DF |  |  | P2 | FEAT_42.3 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 1 | 4 | FEAT_42.1-4 | 45
67 | DF-042 | DF exerciser | Sudharshana | DF |  |  | P2 | FEAT_42.4 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-4 |  | 0 | 4 | FEAT_42.1-4 | 45
68 | DF-043 | Support for DF Segment Clock Gating | Sudharshana | PIE |  |  | P2 | FEAT_43.1 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-10 |  | 3 | 4 | FEAT_43.1-4 | 46
69 | DF-043 | Support for DF Segment Clock Gating | Sudharshana | PIE |  |  | P2 | FEAT_43.2 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-10 |  | 2 | 4 | FEAT_43.1-4 | 46
70 | DF-043 | Support for DF Segment Clock Gating | Sudharshana | PIE |  |  | P2 | FEAT_43.3 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-10 |  | 1 | 4 | FEAT_43.1-4 | 46
71 | DF-043 | Support for DF Segment Clock Gating | Sudharshana | PIE |  |  | P2 | FEAT_43.4 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 0 | 0 | 0 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-10 |  | 0 | 4 | FEAT_43.1-4 | 46
72 | DF-044 | IOM Cancel/Replay | Sudharshana | IOM | DF_IOM_Cancel_Replay | DF_IOM_Cancel_Replay | P1 | FEAT_44 | CDL | ./DF_IOM_Cancel_Replay --cpu 0 -v | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-8 |  | 0 | 1 | FEAT_44 | 47
73 | DF-045 | TgtReqGo command | Sudharshana | CS | DF_Tgt_Req_Go_Check | DF_Tgt_Req_Go_Check | P1 | FEAT_45 | CDL | ./DF_TgtReqGo_Command --cpu 0 -v | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-5 |  | 0 | 1 | FEAT_45 | 48
74 | DF-046 | Add Early Clock Enable for Early FTI fields | Sudharshana | DF |  |  | P1 | FEAT_46 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_46 | 49
75 | DF-047 | Drive FCI Bus Clock Enable efficiently | Sudharshana | DF |  |  | P1 | FEAT_47 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_47 | 50
76 | DF-048 | Filter Internal Registers before generating FCI accesses | Sudharshana | DF |  |  | P1 | FEAT_48 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_48 | 51
77 | DF-049 | Support for LPA Interrupt steering to performance and efficient clusters | Sudharshana | PIE |  |  | P1 | FEAT_49 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-9 |  | 0 | 1 | FEAT_49 | 52
78 | DF-050 | Support Dual Owner in Strix SPF | Sudharshana | CS |  |  | P1 | FEAT_50 | CDL |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_50 | 53
79 | DF-051 | QOS Throttle changes for large and compressed requests | Sudharshana | GCM |  |  | P1 | FEAT_51 | CDL |  | 1 | 1 | New | 1 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-8 |  | 0 | 1 | FEAT_51 | 54
80 | DF-052 | DF Cac Manager Events | Sudharshana | PIE |  |  | P1 | FEAT_52 | CDL |  | 1 | 1 | New | 1 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-9 |  | 0 | 1 | FEAT_52 | 55
81 | DF-053 | Reset group assignment | Sudharshana | PIE |  |  | P1 | FEAT_53 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_53 | 56
82 | DF-054 | Strix2/new Krackan1 UPF | Sudharshana | PIE |  |  | P1 | FEAT_54 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-7 |  | 0 | 1 | FEAT_54 | 57
83 | DF-055 | Finalize Strix2 feature define list for existing features by LSB | Sudharshana | PIE |  |  | P1 | FEAT_55 | CDL |  | 1 | 1 | New | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-9 |  | 0 | 1 | FEAT_55 | 58
84 | DF-056 | 4.5.67 IPU BW increase from 256b to 512b to support 4x8 array | Sudharshana | NCM |  |  | P1 | FEAT_56 | CDL |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | wk-6 |  | 0 | 1 | FEAT_56 | 59