## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID-OLD | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | DCN4.021 | DCN4.021 - Dchubbub wm change support |  | DCHB |  | Rotation & Mirroring Test | P2 | DCHB004 | DCHB004.1-36 | TNG |  | 1 | 36 | Delta | 1 | 36 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
1 | DCN4.025 | DCN4.025 - HW rotation and mirroring |  | DCHB |  | Rotation & Mirroring Test | P2 | DCHB004 | DCHB004.1-36 | TNG |  | 1 | 36 | Delta | 1 | 36 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
2 | DCN4.108 | DCN4.108 - Dmcu secure fw loading |  | DCHB |  | Rotation & Mirroring Test | P2 | DCHB004 | DCHB004.1-36 | TNG |  | 1 | 36 | Delta | 1 | 36 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
3 | DCN4.039 | DCN4.039 - VM support |  | DCHB |  | Basic Flip Test | P2 | DCHB005 | DCHB005.1-14 | TNG |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | Pre-si: FPGA: dchb5.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
4 | DCN4.144 | DCN4.144 - Vm pattern generator |  | DCHB |  | Basic Flip Test | P2 | DCHB005 | DCHB005.1-14 | TNG |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | Pre-si: FPGA: dchb5.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
5 | DCN4.158 | DCN4.039 - VM support, DCN4.144 - Vm pattern generator, DCN4.158 - 4 levels gpuvm, DCN4.026 - Immediate Flip, DCN4.027 - Vsync Flip DCN4.117 - Large DET VM row buffer |  | DCHB |  | Basic Flip Test |  | DCHB005 | DCHB005.1-14 | TNG |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | Pre-si: FPGA: dchb5.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
6 | DCN4.026 | DCN4.026 - Immediate Flip |  | DCHB |  | Basic Flip Test | P2 | DCHB005 | DCHB005.1-14 | TNG |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | Pre-si: FPGA: dchb5.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
7 | DCN4.027 | DCN4.027 - Vsync Flip |  | DCHB |  | Basic Flip Test | P2 | DCHB005 | DCHB005.1-14 | TNG |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | Pre-si: FPGA: dchb5.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
8 | DCN4.117 | DCN4.117 - Large DET VM row buffer |  | DCHB |  | Basic Flip Test | P2 | DCHB005 | DCHB005.1-14 | TNG |  | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | Pre-si: FPGA: dchb5.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
9 | DCN4.026 | DCN4.026 - Immediate Flip |  | DCHB |  | Stereoscopic Flip Test | P2 | DCHB006 | DCHB006.1-20 | TServer |  | 1 | 20 | Legacy | 1 | 20 | 1 | N-1 | 20 | 20 | 20 |  |  |  | 1 | Pre-si: FPGA: dchb6.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
10 | DCN4.027 | DCN4.027 - Vsync Flip |  | DCHB |  | Stereoscopic Flip Test | P2 | DCHB006 | DCHB006.1-20 | TServer |  | 1 | 20 | Legacy | 1 | 20 | 1 | N-1 | 20 | 20 | 20 |  |  |  | 1 | Pre-si: FPGA: dchb6.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
11 | DCN4.028 | DCN4.028 - GSL |  | DCHB |  | Viewport Panning Test | P2 | DCHB007 | DCHB007.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 11 | 11 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
12 | DCN4.025 | DCN4.025 - HW rotation and mirroring |  | DCHB |  | Viewport Panning Test | P2 | DCHB007 | DCHB007.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 11 | 11 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
13 | DCN4.128 | DCN4.128 - Larger viewport size |  | DCHB |  | Viewport Panning Test | P2 | DCHB007 | DCHB007.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 11 | 11 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
14 | DCN4.026 | DCN4.026 - Immediate Flip |  | DCHB |  | Immediate Flip Stress Test | P2 | DCHB008 | DCHB008.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | FPGA too much time N-1 passed | 0 | 0 | 0 | 0 | 0 | 0
15 | DCN4.027 | DCN4.027 - Vsync Flip |  | DCHB |  | Immediate Flip Stress Test | P2 | DCHB008 | DCHB008.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | FPGA too much time N-1 passed | 0 | 0 | 0 | 0 | 0 | 0
16 | NV48-DCN-029 | [DCHUB]Reader Line Position Support |  | DCHB |  | Reader Line Position Test |  | DCHB011 | DCHB011.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
17 | DCN4.030 | DCN4.030 - GFX Tiling |  | DCHB |  | GFX12 Tiling/Swizzle Modes Test | P2 | DCHB014 | DCHB014.1-259 | TNG |  | 1 | 259 | Legacy | 1 | 259 | 1 | N-1 | 259 | 259 | 259 |  |  |  | 1 | Pre-si: FPGA: dchb14.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
18 | DCN4.029 | DCN4.029 - Linear and 2d-tiled surface |  | DCHB |  | GFX12 Tiling/Swizzle Modes Test | P2 | DCHB014 | DCHB014.1-259 | TNG |  | 1 | 259 | Legacy | 1 | 259 | 1 | N-1 | 259 | 259 | 259 |  |  |  | 1 | Pre-si: FPGA: dchb14.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
19 | DCN4.032 | DCN4.032 - Cab |  | DCHB |  | UCLK PState change with MALL at sub-viewport mode Test | P2 | DCHB017 | DCHB017 | Tserver |  | 5 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 |  | 0 | 0 | 0
20 | DCN4.034 | DCN4.034 - Uclk pstate change using mall |  | DCHB |  | UCLK PState change with MALL at sub-viewport mode Test | P2 | DCHB017 | DCHB017 | Tserver |  | 5 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 |  | 0 | 0 | 0
21 | DCN4.036 | DCN4.036 - Sub-viewport mall prefetch |  | DCHB |  | UCLK PState change with MALL at sub-viewport mode Test | P2 | DCHB017 | DCHB017 | Tserver |  | 5 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 |  | 0 | 0 | 0
22 | DCN4.149 | DCN4.149 - Dchub sdp 2-bit no-alloc signaling |  | DCHB |  | UCLK PState change with MALL at sub-viewport mode Test | P2 | DCHB017 | DCHB017 | Tserver |  | 5 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 |  | 0 | 0 | 0
23 | DCN4.032 | DCN4.032 - Cab |  | DCHB |  | MALL Static Screen CAB Basic test | P2 | DCHB023 | DCHB023 | TServer |  | 5 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 |  | 0 | 0 | 0
24 | DCN4.039 | DCN4.039 - VM support |  | DCHB |  | Advanced Flip Test | P2 | DCHB021 | DCHB021.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 11 | 10 | 0 | 1 | 0 | 0.90909 | DCHB21.7 crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
25 | DCN4.158 | DCN4.039 - VM support, DCN4.158 - 4 levels gpuvm, DCN4.026 - Immediate Flip, DCN4.027 - Vsync Flip |  | DCHB |  | Advanced Flip Test |  | DCHB021 | DCHB021.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 11 | 10 | 0 | 1 | 0 | 0.90909 | DCHB21.7 crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
26 | DCN4.026 | DCN4.026 - Immediate Flip |  | DCHB |  | Advanced Flip Test | P2 | DCHB021 | DCHB021.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 11 | 10 | 0 | 1 | 0 | 0.90909 | DCHB21.7 crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
27 | DCN4.027 | DCN4.027 - Vsync Flip |  | DCHB |  | Advanced Flip Test | P2 | DCHB021 | DCHB021.1-11 | TServer |  | 1 | 11 | Legacy | 1 | 11 | 1 | N-1 | 11 | 11 | 10 | 0 | 1 | 0 | 0.90909 | DCHB21.7 crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
28 | DCN4.031 | DCN4.031 - TMZ |  | DCHB |  | Display Surface TMZ Test | P2 | DCHB030 | DCHB030.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 |  | 0 | 1 | 1 |  |  |  | 1 | pass on emulator ./tserverlite -cf=dcn.cf -test=dchb30.2 -gpu_copyengine=sdma_sysmem -sdma_copysize=32 -sdma_rb_size=256B -vm -oss_timeout=20000 -oss_verbose=2 -tcorelog | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
29 | DCN4.028 | DCN4.028 - GSL |  | DCHB |  | Colour Component Crossbar Test | P2 | DCHB033 | DCHB033 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 | FPGA too much time | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
30 | DCN4.039 | DCN4.039 - VM support |  | DCHB |  | Basic Virtual Memory(GPUVM) Testing | P2 | DCHB022 | DCHB022.1-24 | TServer |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 24 | 24 | 5 |  | 16 |  | 0.20833 | dchb22.1,101,201,998,999 pass | 0 | 0 | 0 | 0 | 0 | 0
31 | DCN4.144 | DCN4.144 - Vm pattern generator |  | DCHB |  | Basic Virtual Memory(GPUVM) Testing | P2 | DCHB022 | DCHB022.1-24 | TServer |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 24 | 24 | 5 |  | 16 |  | 0.20833 | dchb22.1,101,201,998,999 pass | 0 | 0 | 0 | 0 | 0 | 0
32 | DCN4.004 | DCN4.004 - Support 16k8k@60 |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
33 | DCN4.005 | DCN4.005 - Support 6k60 |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
34 | DCN4.139 | DCN4.139 - Single pipe 6k@60 |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
35 | DCN4.006 | DCN4.006 - Max pixel rate single pipe |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
36 | DCN4.022 | DCN4.022 - Dram self-refresh and cstate and stutter |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
37 | DCN4.023 | DCN4.023 - Stutter efficiency |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
38 | DCN4.009 | DCN4.009 - 64K surface pitch |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
39 | DCN4.135 | DCN4.135 - Dmcub zfb support |  | DPP |  | Display modeset test | P2 | dcn.msa.1 | dcn.msa.1.1-3 | TNG |  | 3 | 3 | New | 1 | 3 | 1 |  | 0
40 | DCN4.007 | DCN4.007 - Dma program 3dlut |  | DCHB |  | 3DLUT Fast loading | P2 | DCHB062 | DCHB062 | TNG |  | 1 | 1 | New | 1 | 0 | 0 | FPGA
41 | DCN4.008 | DCN4.008 - Distributed dcc |  | DCHB |  | Distributed dcc | P2 | DCHB064 | DCHB064 | TServer |  | 1 | 1 | New | 1 | 0 | 0 | Emulator | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0
42 | DCN4.040 | DCN4.040 - Format Conversion |  | DPP |  | CNVC Dynamic Pixel Expansion Test | P2 | DPP002 | DPP002.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | FPGA | 7 | 7 | 7 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
43 | DCN4.041 | DCN4.041 - Cursor |  | DPP |  | Stereoscopic Cursor Test | P2 | DPP005 | DPP005.1-3 | TNG |  | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w3
44 | DCN4.131 | DCN4.131 - 2 dscl configurable filter kernels |  | DPP |  | Scaler Hardcoded 2-Tap Sharpening Test | P2 | DPP008 | DPP008.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
45 | DCN4.055 | DCN4.055 - Scale underscan and overscan |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
46 | DCN4.057 | DCN4.057 - Scale boundary |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
47 | DCN4.049 | DCN4.049 - Downscale |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
48 | DCN4.048 | DCN4.048 - Prescale linearization |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
49 | DCN4.119 | DCN4.119 - DFS bypass switching for DISPCLK and DPPCLK |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
50 | DCN4.152 | DCN4.055 - Scale underscan and overscan, DCN4.057 - Scale boundary, DCN4.049 - Downscale, DCN4.048 - Prescale linearization DCN4.119 - DFS bypass switching for DISPCLK and DPPCLK DCN4.152 - G7 PPT - Chiplet DCN4.053 - Edge adaptive scaler and sharpening DCN4.052 - Scale sharpening |  | DPP |  | Scaler N-Tap Scaling Test |  | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
51 | DCN4.053 | DCN4.053 - Edge adaptive scaler and sharpening |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
52 | DCN4.052 | DCN4.052 - Scale sharpening |  | DPP |  | Scaler N-Tap Scaling Test | P2 | DPP009 | DPP009.1-43 | TNG |  | 1 | 43 | Delta | 1 | 43 | 1 | FPGA | 43 | 43 | 43 | 0 | 0 | 0 | 1 | 5 more variations for EASF and ImgSharpener pass on N-1, need verify case 1 on FPGA | 0 | 0 | 0 | 0 | 0 | 0
53 | DCN4.058 | DCN4.058 - LB dynamic allocation and partition |  | DPP |  | Line Buffer Memory Size Test | P2 | DPP010 | DPP010.1-35 | TServer |  | 1 | 35 | Legacy | 1 | 35 | 1 | FPGA | 35 | 35 | 34 |  | 1 |  | 0.97143 | Pre-si: FPGA: DPP10.1 Assertion `m_impl->m_feature_values.find(feature) != m_impl->m_feature_values.end() | 0 | 0 | 0 | 0 | 0 | 0
54 | DCN4.132 | DCN4.132 - Increased dscl line buffer size |  | DPP |  | Line Buffer Memory Size Test | P2 | DPP010 | DPP010.1-35 | TServer |  | 1 | 35 | Legacy | 1 | 35 | 1 | FPGA | 35 | 35 | 34 |  | 1 |  | 0.97143 | Pre-si: FPGA: DPP10.1 Assertion `m_impl->m_feature_values.find(feature) != m_impl->m_feature_values.end() | 0 | 0 | 0 | 0 | 0 | 0
55 | DCN4.040 | DCN4.040 - Format Conversion |  | DPP |  | Color Keyer Alpha Generation Test | P2 | DPP024 | DPP024 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
56 | DCN4.040 | DCN4.040 - Format Conversion |  | DPP |  | Alpha Expansion LUT Test | P2 | DPP031 | DPP031 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
57 | DCN4.048 | DCN4.048 - Prescale linearization |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
58 | DCN4.049 | DCN4.049 - Downscale |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
59 | DCN4.057 | DCN4.057 - Scale boundary |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
60 | DCN4.051 | DCN4.051 - Alpha scale |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
61 | DCN4.050 | DCN4.050 - Upscale |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
62 | DCN4.055 | DCN4.055 - Scale underscan and overscan |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
63 | DCN4.150 | DCN4.150 - Dpp Recin width and height upate |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
64 | DCN4.135 | DCN4.135 - Dmcub zfb support |  | DPP |  | Scaler Scenario Test | P2 | DPP034 | DPP034.1-13 | TServer |  | 1 | 13 | Delta | 1 | 13 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | core dump | 0 | 0 | 0 | 0 | 0 | 0
65 | DCN4.056 | DCN4.056 - Stereo scale |  | DPP |  | Stereoscopic Scaling Test | P2 | DPP036 | DPP036.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | OPTC underflow crc mismatch | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
66 | DCN4.043 | DCN4.043 - De-alpha and bias |  | DPP |  | De-alpha and Bias Test | P2 | DPP037 | DPP037 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w3
67 | DCN4.040 | DCN4.040 - Format Conversion |  | DPP |  | FCNV Clamp to Positive Test | P2 | DPP042 | DPP042.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
68 | DCN4.041 | DCN4.041 - Cursor |  | DPP |  | Cursor Blending Stereoscopic Test | P2 | DPP045 | DPP045.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
69 | DCN4.124 | DCN4.124 - Pre-dealpha |  | DPP |  | CNVC Pre-DeAlpha Test | P2 | DPP046 | DPP046 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w3
70 | DCN4.044 | DCN4.044 - Input csc |  | DPP |  | CNVC PreCSC S2.13 Coefcient Format Test | P2 | DPP047 | DPP047.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
71 | DCN4.044 | DCN4.044 - Input csc |  | DPP |  | CNVC PreCSC S3.12 Coefficient Format Test | P2 | DPP048 | DPP048.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
72 | DCN4.062 | DCN4.062 - Output csc |  | DPP |  | CM PostCSC S2.13 Coefcient Format Test | P2 | DPP049 | DPP049.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
73 | DCN4.125 | DCN4.125 - Post-scaler csc |  | DPP |  | CM PostCSC S2.13 Coefcient Format Test | P2 | DPP049 | DPP049.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
74 | DCN4.062 | DCN4.062 - Output csc |  | DPP |  | CM PostCSC S3.12 Coefficient Format Test | P2 | DPP050 | DPP050.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
75 | DCN4.125 | DCN4.125 - Post-scaler csc |  | DPP |  | CM PostCSC S3.12 Coefficient Format Test | P2 | DPP050 | DPP050.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
76 | DCN4.043 | DCN4.043 - De-alpha and bias |  | DPP |  | Pre-ReAlpha and De-Alpha Test | P2 | DPP052 | DPP052.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
77 | DCN4.126 | DCN4.126 - Pre-realpha |  | DPP |  | Pre-ReAlpha and De-Alpha Test | P2 | DPP052 | DPP052.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
78 | DCN4.127 | DCN4.127 - Gamma correction |  | DPP |  | CM Gamma Correction Test | P2 | DPP053 | DPP053.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w8
79 | DCN4.042 | DCN4.042 - Win10 cursor support |  | DPP |  | Win10 cursor Test | P2 | DPP055 | DPP055.1-4 | TNG |  | 1 | 4 | New | 1 | 0 | 0 | FPGA
80 | DCN4.156 | DCN4.156 - mpc top layer pass through |  | MPC |  | MPCC Mode Test | P2 | MPC003 | MPC003.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | FPGA | 6 | 6 | 5 | 0 | 0 | 0 | 0.83333 | Pre-si: tserver: MPC3.1 (core dumped) tng: crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
81 | DCN4.060 | DCN4.060 - Multi-plane composing with alpha |  | MPC |  | MPCC Mode Test | P2 | MPC003 | MPC003.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | FPGA | 6 | 6 | 5 | 0 | 0 | 0 | 0.83333 | Pre-si: tserver: MPC3.1 (core dumped) tng: crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
82 | DCN4.014 | DCN4.014 - Sram low power mode |  | MPC |  | MPCC Mode Test | P2 | MPC003 | MPC003.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | FPGA | 6 | 6 | 5 | 0 | 0 | 0 | 0.83333 | Pre-si: tserver: MPC3.1 (core dumped) tng: crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
83 | DCN4.148 | DCN4.148 - Support per OTG disable fuse |  | MPC |  | MPCC Mode Test | P2 | MPC003 | MPC003.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | FPGA | 6 | 6 | 5 | 0 | 0 | 0 | 0.83333 | Pre-si: tserver: MPC3.1 (core dumped) tng: crc mismatch | 0 | 0 | 0 | 0 | 0 | 0
84 | DCN4.157 | DCN4.157 - Stereo format blending |  | MPC |  | MPCC Stereo Mixing Test | P2 | MPC005 | MPC005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
85 | DCN4.060 | DCN4.060 - Multi-plane composing with alpha |  | MPC |  | Alpha Blending Per-Layer Gain Test | P2 | MPC007 | MPC007.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w1
86 | DCN4.134 | DCN4.134 - Out gamma |  | MPC |  | MPC Output CSC Test | P2 | MPC009 | MPC009.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
87 | DCN4.063 | DCN4.063 - Denorm and round and clamp |  | MPC |  | MPC Denormalization and Clamping Test | P2 | MPC010 | MPC010.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w3
88 | DCN4.123 | DCN4.123 - MPCC Gamut Remap |  | MPC |  | MPC Gamut Remap Test | P2 | MPC012 | MPC012 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | FPGA | 1 | 0 | 0 |  |  |  | 0 | all passed on tserver | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
89 | DCN4.123 | DCN4.123 - MPCC Gamut Remap |  | MPC |  | MPC Gamut Remap S3.12 Coefficient Format Test | P2 | MPC013 | MPC013 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
90 | DCN4.067 | DCN4.067 - Fmt subsample |  | MPC |  | MPCC Extend Output Gamma Test | P2 | MPC015 | MPC015.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 16 | 16 | 15 | 0 | 1 | 0 | 0.9375 | Pre-si: FPGA: MPC15.1 (crc mismatch) N-1: others | 0 | 0 | 0 | 0 | 0 | 0
91 | DCN4.061 | DCN4.061 - Output Gamma |  | MPC |  | MPCC Extend Output Gamma Test | P2 | MPC015 | MPC015.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 16 | 16 | 15 | 0 | 1 | 0 | 0.9375 | Pre-si: FPGA: MPC15.1 (crc mismatch) N-1: others | 0 | 0 | 0 | 0 | 0 | 0
92 | DCN4.047 | DCN4.047 - Relocatable gamut remap |  | MPC |  | MPCC 3D LUT test | P2 | MPC017 | MPC017.1-7 | TServer |  | 3 | 7 | Legacy | 1 | 7 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | crc mismatch
93 | DCN4.017 | DCN4.017 - Abm |  | ABM |  | ABM Histogram | P2 | ABM066 | ABM066.1-15 | TNG |  | 1 | 15 | Delta | 1 | 15 | 1 | N-1 | 15 | 15 | 15 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
94 | DCN4.153 | DCN4.153 - ABM Enhancement |  | ABM |  | ABM Histogram | P2 | ABM066 | ABM066.1-15 | TNG |  | 1 | 15 | Delta | 1 | 15 | 1 | N-1 | 15 | 15 | 15 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
95 | DCN4.017 | DCN4.017 - Abm |  | ABM |  | ABM Luma Statistics | P2 | ABM067 | ABM067 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | legacy all passed on tserver | 0 | 0 | 0 | 0 | 0 | 0
96 | DCN4.153 | DCN4.153 - ABM Enhancement |  | ABM |  | ABM Luma Statistics | P2 | ABM067 | ABM067 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | legacy all passed on tserver | 0 | 0 | 0 | 0 | 0 | 0
97 | DCN4.065 | DCN4.065 - Fmt truncate and round |  | FMT |  | FMT Truncation Test | P2 | FMT001 | FMT001.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
98 | DCN4.070 | DCN4.070 - Fmt dither |  | FMT |  | FMT Basic Spatial Dither Test | P2 | FMT002 | FMT002.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 16 | 16 | 16 |  |  |  | 1 | Pre-si: FPGA: FMT2.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
99 | DCN4.070 | DCN4.070 - Fmt dither |  | FMT |  | FMT Spatial Dither Mode Test | P2 | FMT003 | FMT003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
100 | DCN4.070 | DCN4.070 - Fmt dither |  | FMT |  | FMT Frame Random Spatial Dither Test | P2 | FMT004 | FMT004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
101 | DCN4.070 | DCN4.070 - Fmt dither |  | FMT |  | FMT Spatial Dither Frame Counter Test | P2 | FMT005 | FMT005.1-10 | TServer |  | 1 | 10 | Legacy | 1 | 10 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
102 | DCN4.070 | DCN4.070 - Fmt dither |  | FMT |  | FMT Temporal Dither Test | P2 | FMT006 | FMT006.1-52 | TServer |  | 1 | 52 | Legacy | 1 | 52 | 1 | FPGA | 52 | 52 | 52 |  |  |  | 1 | Pre-si: FPGA: FMT6.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
103 | DCN4.066 | DCN4.066 - Fmt clamp |  | FMT |  | FMT Clamping Test | P2 | FMT007 | FMT007.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
104 | DCN4.067 | DCN4.067 - Fmt subsample |  | FMT |  | FMT 4:2:2 Subsampling Test | P2 | FMT009 | FMT009.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
105 | DCN4.067 | DCN4.067 - Fmt subsample |  | FMT |  | FMT 4:2:0 Basic Subsampling Test | P2 | FMT010 | FMT010.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
106 | DCN4.067 | DCN4.067 - Fmt subsample |  | FMT |  | FMT 4:2:0 Stereoscopic (Side-by-Side Half) Subsampling Test | P2 | FMT011 | FMT011 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | Segmentation fault | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
107 | DCN4.067 | DCN4.067 - Fmt subsample |  | FMT |  | FMT 4:2:2 Subsampling with ODM Combine Test | P2 | FMT014 | FMT014.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
108 | DCN4.067 | DCN4.067 - Fmt subsample |  | FMT |  | Basic Subsampling with ODM Combine Test | P2 | FMT015 | FMT015.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
109 | DCN4.071 | DCN4.071 - DSC for DP |  | DSC |  | Multi-Stream DSC Test | P2 | DSC004 | DSC004.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
110 | DCN4.083 | DCN4.083 - Hdmi2.1 frl dsc vrr fva and qms |  | DSC |  | Multi-Stream DSC Test | P2 | DSC004 | DSC004.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
111 | DCN4.073 | DCN4.073 - DP FEC support |  | DSC |  | Multi-Stream DSC Test | P2 | DSC004 | DSC004.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
112 | NV48-DCN-xxx | DCN4.071 - DSC for DP, DCN4.083 - Hdmi2.1 frl dsc vrr fva and qms, DCN4.073 - DP FEC support, [OPP]DSC Resource Manager Support DCN4.072 - DSC area optimization |  | DSC |  | Multi-Stream DSC Test |  | DSC004 | DSC004.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
113 | DCN4.072 | DCN4.072 - DSC area optimization |  | DSC |  | Multi-Stream DSC Test | P2 | DSC004 | DSC004.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
114 | DCN4.074 | DCN4.074 - ODM Combine |  | ODM |  | ODM Combine Mode Basic Test | P2 | ODM001 | ODM001.1-20 | TServer |  | 1 | 20 | Delta | 1 | 20 | 1 | FPGA | 20 | 20 | 20 | 0 | 0 | 0 | 1 | Pre-si: FPGA: ODM1.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
115 | DCN4.075 | DCN4.075 - ODM Combine improvement |  | ODM |  | ODM Combine Mode Basic Test | P2 | ODM001 | ODM001.1-20 | TServer |  | 1 | 20 | Delta | 1 | 20 | 1 | FPGA | 20 | 20 | 20 | 0 | 0 | 0 | 1 | Pre-si: FPGA: ODM1.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
116 | DCN4.074 | DCN4.074 - ODM Combine |  | ODM |  | ODM Combine Mode DSC Test | P2 | ODM003 | ODM003.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 18 | 18 | 18 |  |  |  | 1 | Pre-si: FPGA: ODM3.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
117 | DCN4.075 | DCN4.075 - ODM Combine improvement |  | ODM |  | ODM Combine Mode DSC Test | P2 | ODM003 | ODM003.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 18 | 18 | 18 |  |  |  | 1 | Pre-si: FPGA: ODM3.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
118 | DCN4.074 | DCN4.074 - ODM Combine |  | ODM |  | ODM Combine Mode with HBR3 Test | P2 | ODM005 | ODM005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
119 | DCN4.075 | DCN4.075 - ODM Combine improvement |  | ODM |  | ODM Combine Mode with HBR3 Test | P2 | ODM005 | ODM005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
120 | DCN4.074 | DCN4.074 - ODM Combine |  | ODM |  | ODM Combine Mode (4:1) with DSC Test (DP DIO and HPO) | P2 | ODM004 | ODM004.1-13 | TNG |  | 2 | 13 | New | 1 | 13 | 1 | FPGA | 13
121 | DCN4.076 | DCN4.076 - Dynamic odm |  | ODM |  | Dynamic Switch Of ODM Test | P2 | ODM007 | ODM007.1-20 | TNG |  | 2 | 20 | Delta | 1 | 20 | 1 | FPGA | 20 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w6
122 | DCN4.075 | DCN4.075 - ODM Combine improvement |  | ODM |  | ODM Combine Mode (3:1) for DP/DP2/FRL | P2 | ODM013 | ODM013.1-12 | TNG |  | 2 | 12 | New | 1 | 12 | 1 | FPGA | 12
123 | DCN4.173 | DCN4.173 - Forced vsync support |  | OTG |  | OTG Force VSYNC Next Line Test |  | OTG007 | OTG007.1-215 | TServer |  | 1 | 215 | Legacy | 1 | 215 | 1 | N-1 | 215 | 215 | 206 |  |  | 9 | 0.95814 | Pre-si: FPGA: OTG7.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
124 | DCN4.038 | DCN4.038 - Stereoscopic display |  | OTG |  | OTG Frame-Sequential Stereoscopic Test | P2 | OTG009 | OTG009.1-215 | TServer |  | 1 | 215 | Legacy | 1 | 215 | 1 | N-1 | 215 | 215 | 215 |  |  |  | 1 | Pre-si: FPGA: OTG9.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
125 | DCN4.172 | DCN4.172 - Otg trigger |  | OTG |  | OTG Trigger Detection Test |  | OTG011 | OTG011 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
126 | DCN4.175 | DCN4.175 - Forced H and V counter |  | OTG |  | OTG Force Count Test |  | OTG013 | OTG013 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
127 | DCN4.081 | DCN4.081 - DRR |  | OTG |  | OTG Dynamic Refresh Rate Test | P2 | OTG014 | OTG014.1-199 | TServer |  | 1 | 199 | Legacy | 1 | 199 | 1 | N-1 | 199 | 199 | 199 |  |  |  | 1 | Pre-si: FPGA: OTG14.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
128 | DCN4.035 | DCN4.035 - Pstate change with drr |  | OTG |  | OTG Dynamic Refresh Rate Test | P2 | OTG014 | OTG014.1-199 | TServer |  | 1 | 199 | Legacy | 1 | 199 | 1 | N-1 | 199 | 199 | 199 |  |  |  | 1 | Pre-si: FPGA: OTG14.1 N-1: others | 0 | 0 | 0 | 0 | 0 | 0
129 | DCN4.028 | DCN4.028 - GSL |  | OTG |  | OTG Pixel Repetition Test | P2 | OTG017 | OTG017.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | segment fault | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
130 | DCN4.078 | DCN4.078 - Underflow Detection and Recovery |  | OTG |  | Underflow Recovery Test | P2 | OTG025 | OTG025.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | Assertion `pixclk' failed. | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
131 | DCN4.176 | DCN4.176 - Static screen |  | OTG |  | OTG Static Screen Event Test |  | OTG026 | OTG026.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | OTG should take frames = 59 to re-enter static screen state. Actually took 0 frames | 0 | 0 | 0 | 0 | 0 | 0
132 | DCN4.064 | DCN4.064 - Video blanking generation |  | OTG |  | Display Pattern Generator Test | P2 | OTG027 | OTG027.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
133 | DCN4.169 | DCN4.064 - Video blanking generation DCN4.169 - Dpg |  | OTG |  | Display Pattern Generator Test |  | OTG027 | OTG027.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
134 | DCN4.074 | DCN4.074 - ODM Combine |  | OTG |  | DPG with ODM test | P2 | OTG029 | OTG029.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
135 | DCN4.075 | DCN4.075 - ODM Combine improvement |  | OTG |  | DPG with ODM test | P2 | OTG029 | OTG029.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
136 | DCN4.080 | DCN4.080 - Vstartup Vupdate and Vready Interrupt |  | OTG |  | OTG VUPDATE Interrupt Test | P2 | OTG800 | OTG800.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | OTG0 VUPDATE interrupt of falling edge sticky bit erroneously stayed set after triggering pulse-based interrupt (interrupt enabled) | 0 | 0 | 0 | 0 | 0 | 0
137 | DCN4.109 | DCN4.109 - Interrupts Handler client support |  | OTG |  | OTG VUPDATE Interrupt Test | P2 | OTG800 | OTG800.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 | OTG0 VUPDATE interrupt of falling edge sticky bit erroneously stayed set after triggering pulse-based interrupt (interrupt enabled) | 0 | 0 | 0 | 0 | 0 | 0
138 | DCN4.080 | DCN4.080 - Vstartup Vupdate and Vready Interrupt |  | OTG |  | OTG Snapshot Interrupt Test | P2 | OTG801 | OTG801 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
139 | DCN4.174 | DCN4.080 - Vstartup Vupdate and Vready Interrupt, DCN4.174 - H, V and frame count snapshot |  | OTG |  | OTG Snapshot Interrupt Test |  | OTG801 | OTG801 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
140 | DCN4.109 | DCN4.109 - Interrupts Handler client support |  | OTG |  | OTG TRIGA Interrupt Test | P2 | OTG804 | OTG804 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
141 | DCN4.172 | DCN4.109 - Interrupts Handler client support DCN4.172 - Otg trigger |  | OTG |  | OTG TRIGA Interrupt Test |  | OTG804 | OTG804 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
142 | DCN4.109 | DCN4.109 - Interrupts Handler client support |  | OTG |  | OTG TRIGB Interrupt Test | P2 | OTG805 | OTG805 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
143 | DCN4.172 | DCN4.109 - Interrupts Handler client support DCN4.172 - Otg trigger |  | OTG |  | OTG TRIGB Interrupt Test |  | OTG805 | OTG805 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
144 | DCN4.080 | DCN4.080 - Vstartup Vupdate and Vready Interrupt |  | OTG |  | OTG VSTARTUP Interrupt Test | P2 | OTG809 | OTG809.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
145 | DCN4.080 | DCN4.080 - Vstartup Vupdate and Vready Interrupt |  | OTG |  | OTG VREADY Interrupt Test | P2 | OTG810 | OTG810 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w4
146 | DCN4.095 | DCN4.095 - Aux and i2c |  | DIO |  | Aux Channel DPCD Read/Write Tests | P2 | DIO003 | DIO003.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
147 | DCN4.096 | DCN4.096 - Hpd |  | DIO |  | Aux Channel DPCD Read/Write Tests | P2 | DIO003 | DIO003.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
148 | DCN4.155 | DCN4.155 - HDMI port I2C VOL level |  | DIO |  | Aux Channel DPCD Read/Write Tests | P2 | DIO003 | DIO003.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
149 | DCN4.038 | DCN4.038 - Stereoscopic display |  | DIO |  | HDMI 1.4 Frame Packing 3D Test | P2 | DIO220 | DIO220.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
150 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI 1.4 Frame Packing 3D Test | P2 | DIO220 | DIO220.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
151 | NV48-DCN-063 | DCN4.038 - Stereoscopic display, DCN4.082 - HDMI 1.4 and 2.0, [OPP]Stereo Dummy Data Insertion Support |  | DIO |  | HDMI 1.4 Frame Packing 3D Test |  | DIO220 | DIO220.1-7 | TNG |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
152 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI 2.0 Scrambler Test | P2 | DIO221 | DIO221.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
153 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Basic Output Test on PHYA | P2 | DIO217 | DIO217.1-116 | TServer |  | 1 | 116 | Legacy | 1 | 116 | 1 | N-1 | 116 | 116 | 114 |  | 2 |  | 0.98276 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
154 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Random Audio Test | P2 | DIO224 | DIO224.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
155 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Ramp Audio Test | P2 | DIO225 | DIO225.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
156 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia Basic Audio Test | P2 | DIO227 | DIO227.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
157 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia 2.0 Channel HD Audio Test | P2 | DIO228 | DIO228.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 16 | 16 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
158 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia 4.0 Channel HD Audio Test | P2 | DIO229 | DIO229.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 16 | 16 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
159 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia 5.1 Channel HD Audio Test | P2 | DIO230 | DIO230.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 16 | 16 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
160 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia 6.1 Channel HD Audio Test | P2 | DIO231 | DIO231.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 16 | 16 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
161 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia 7.1 Channel HD Audio Test | P2 | DIO232 | DIO232.1-16 | TServer |  | 1 | 16 | Legacy | 1 | 16 | 1 | N-1 | 16 | 16 | 16 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
162 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia HBR Audio Test | P2 | DIO233 | DIO233.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
163 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Multi-Channel Single Stream DMA Out | P2 | DIO234 | DIO234.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
164 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Deep Color Azalia 2.0 Channel HD Audio Test | P2 | DIO236 | DIO236.1-28 | TServer |  | 1 | 28 | Legacy | 1 | 28 | 1 | N-1 | 28 | 28 | 28 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
165 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Deep Color Azalia 7.1 Channel HD Audio Test | P2 | DIO237 | DIO237.1-28 | TServer |  | 1 | 28 | Legacy | 1 | 28 | 1 | N-1 | 28 | 28 | 28 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
166 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Deep Color Azalia HBR Audio Test | P2 | DIO238 | DIO238.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
167 | DCN4.082 | DCN4.082 - HDMI 1.4 and 2.0 |  | DIO |  | HDMI Azalia Audio Test | P2 | DIO253 | DIO253.1-72 | TNG |  | 1 | 72 | Legacy | 1 | 72 | 1 | N-1 | 72 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
168 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP Azalia Audio Test | P2 | DIO352 | DIO352.1-170 | TNG |  | 1 | 170 | Legacy | 1 | 170 | 1 | N-1 | 170 | 170 | 150 |  | 20 |  | 0.88235 | PHYE core dump | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
169 | DCN4.038 | DCN4.038 - Stereoscopic display |  | DIO |  | DP Frame Packing 3D Test | P2 | DIO365 | DIO365.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
170 | DCN4.038 | DCN4.038 - Stereoscopic display |  | DIO |  | DP Frame Packing 3D Test with Scaling | P2 | DIO366 | DIO366.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
171 | DCN4.077 | DCN4.077 - Ranged timing |  | DIO |  | DisplayPort Ranged Timing H/V TOTAL Change Test | P2 | DIO367 | DIO367 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
172 | DCN4.077 | DCN4.077 - Ranged timing |  | DIO |  | DisplayPort Ranged Timing Pixel Rate Change Test | P2 | DIO368 | DIO368 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w5
173 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 1.62GHz 1 Lane Test | P2 | DIO369 | DIO369.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
174 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 1.62GHz 1 Lane Test | P2 | DIO369 | DIO369.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
175 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 1.62GHz 1 Lane Test |  | DIO369 | DIO369.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
176 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 1.62GHz 2 Lane Test | P2 | DIO370 | DIO370.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
177 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 1.62GHz 2 Lane Test | P2 | DIO370 | DIO370.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
178 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 1.62GHz 2 Lane Test |  | DIO370 | DIO370.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
179 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 1.62GHz 4 Lane Test | P2 | DIO371 | DIO371.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
180 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 1.62GHz 4 Lane Test | P2 | DIO371 | DIO371.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
181 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 1.62GHz 4 Lane Test |  | DIO371 | DIO371.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
182 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 2.70GHz 1 Lane Test | P2 | DIO372 | DIO372.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
183 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 2.70GHz 1 Lane Test | P2 | DIO372 | DIO372.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
184 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 2.70GHz 1 Lane Test |  | DIO372 | DIO372.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
185 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 2.70GHz 2 Lane Test | P2 | DIO373 | DIO373.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
186 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 2.70GHz 2 Lane Test | P2 | DIO373 | DIO373.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
187 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 2.70GHz 2 Lane Test |  | DIO373 | DIO373.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
188 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 2.70GHz 4 Lane Test | P2 | DIO374 | DIO374.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
189 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 2.70GHz 4 Lane Test | P2 | DIO374 | DIO374.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
190 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 2.70GHz 4 Lane Test |  | DIO374 | DIO374.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
191 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 5.40GHz 1 Lane Test | P2 | DIO375 | DIO375.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
192 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 5.40GHz 1 Lane Test |  | DIO375 | DIO375.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
193 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 5.40GHz 1 Lane Test | P2 | DIO375 | DIO375.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
194 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 5.40GHz 2 Lane Test | P2 | DIO376 | DIO376.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
195 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 5.40GHz 2 Lane Test | P2 | DIO376 | DIO376.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
196 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 5.40GHz 2 Lane Test |  | DIO376 | DIO376.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
197 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 5.40GHz 4 Lane Test | P2 | DIO377 | DIO377.1-4 | TNG |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
198 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 5.40GHz 4 Lane Test | P2 | DIO377 | DIO377.1-4 | TNG |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
199 | NV48-DCN-092 | DCN4.092 - Dp1.4, [DIO]usb-c alt mode DCN4.138 - Display PHY |  | DIO |  | DP 5.40GHz 4 Lane Test |  | DIO377 | DIO377.1-4 | TNG |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
200 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 8.10GHz 1 Lane Test | P2 | DIO378 | DIO378.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
201 | DCN4.120 | DCN4.120 - Hbr3 Vmin 0.65v |  | DIO |  | DP 8.10GHz 1 Lane Test | P2 | DIO378 | DIO378.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
202 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP 8.10GHz 1 Lane Test | P2 | DIO378 | DIO378.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
203 | NV48-DCN-092 | DCN4.092 - Dp1.4, DCN4.120 - Hbr3 Vmin 0.65v DCN4.138 - Display PHY [DIO]usb-c alt mode |  | DIO |  | DP 8.10GHz 1 Lane Test |  | DIO378 | DIO378.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
204 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 8.10GHz 2 Lane Test | P2 | DIO379 | DIO379.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
205 | DCN4.120 | DCN4.120 - Hbr3 Vmin 0.65v |  | DIO |  | DP 8.10GHz 2 Lane Test | P2 | DIO379 | DIO379.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
206 | NV48-DCN-092 | DCN4.092 - Dp1.4, DCN4.120 - Hbr3 Vmin 0.65v [DIO]usb-c alt mode |  | DIO |  | DP 8.10GHz 2 Lane Test |  | DIO379 | DIO379.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
207 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP 8.10GHz 4 Lane Test | P2 | DIO380 | DIO380.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
208 | DCN4.120 | DCN4.120 - Hbr3 Vmin 0.65v |  | DIO |  | DP 8.10GHz 4 Lane Test | P2 | DIO380 | DIO380.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
209 | NV48-DCN-092 | DCN4.092 - Dp1.4, DCN4.120 - Hbr3 Vmin 0.65v [DIO]usb-c alt mode |  | DIO |  | DP 8.10GHz 4 Lane Test |  | DIO380 | DIO380.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
210 | DCN4.093 | DCN4.093 - Dp1.4 mst |  | DIO |  | DP MST Source Test | P2 | DIO322 | DIO322.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | N-1 | 4 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
211 | DCN4.093 | DCN4.093 - Dp1.4 mst |  | DIO |  | DP MST Combo Test: UNIPHYB | P2 | DIO324 | DIO324.1-15 | TServer |  | 1 | 15 | Legacy | 1 | 15 | 1 | N-1 | 15 | 15 | 2 |  | 13 |  | 0.13333 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
212 | DCN4.093 | DCN4.093 - Dp1.4 mst |  | DIO |  | DP MST Combo Test: UNIPHYC | P2 | DIO325 | DIO325.1-15 | TServer |  | 1 | 15 | Legacy | 1 | 15 | 1 | N-1 | 15 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
213 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DisplayPort 4:2:0 Subsampling Test | P2 | DIO381 | DIO381.1-15 | TServer |  | 1 | 15 | Legacy | 1 | 15 | 1 | N-1 | 15 | 15 | 11 |  | 4 |  | 0.73333 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
214 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DisplayPort 1.4 basic output Test on PHYA | P2 | DIO335 | DIO335.1-169 | TNG |  | 1 | 169 | Legacy | 1 | 169 | 1 | N-1 | 169 | 169 | 169 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
215 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DisplayPort Basic Output Test on PHYA/B | P2 | DIO337 | DIO337.1-272 | TServer |  | 1 | 272 | Legacy | 1 | 272 | 1 | N-1 | 272 | 272 | 272 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
216 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP Random Audio Test | P2 | DIO383 | DIO383.1-24 | TServer |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 24 | 24 | 24 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
217 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP Ramp Audio Test | P2 | DIO384 | DIO384.1-24 | TServer |  | 1 | 24 | Legacy | 1 | 24 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
218 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DP Azalia Audio Test | P2 | DIO385 | DIO385.1-34 | TServer |  | 1 | 34 | Legacy | 1 | 34 | 1 | N-1 | 34 | 34 | 34 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
219 | DCN4.101 | DCN4.101 - Hardware silient stream support |  | DIO |  | DisplayPort Keep-alive Enable Azalia Audio Test | P2 | DIO386 | DIO386.1-6 | TServer |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
220 | DCN4.092 | DCN4.092 - Dp1.4 |  | DIO |  | DisplayPort Tx-Rx CRC Test | P2 | DIO389 | DIO389.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 |  |  |  | 12 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
221 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DisplayPort Tx-Rx CRC Test | P2 | DIO389 | DIO389.1-12 | TServer |  | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 |  |  |  | 12 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
222 | DCN4.091 | DCN4.091 - Hdmi2.1 timing support |  | DIO |  | HPO Video Ouput test on PHYx | P2 | DIO620 | DIO620.1-63 | TNG |  | 1 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 63 | 63 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
223 | DCN4.083 | DCN4.083 - Hdmi2.1 frl dsc vrr fva and qms |  | DIO |  | HPO Video Ouput test on PHYx | P2 | DIO620 | DIO620.1-63 | TNG |  | 1 | 63 | Legacy | 1 | 63 | 1 | N-1 | 63 | 63 | 63 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
224 | DCN4.087 | DCN4.087 - Hdmi2.1 audio |  | DIO |  | HDMI2.1 Azalia 2.0 Channel HD Audio test | P2 | DIO602 | DIO602.1-7 | TServer |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 |  |  | 7 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
225 | DCN4.087 | DCN4.087 - Hdmi2.1 audio |  | DIO |  | HDMI2.1 Azalia 7.1 Channel HD Audio test | P2 | DIO603 | DIO603.1-7 | TServer |  | 1 | 7 | Legacy | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
226 | DCN4.087 | DCN4.087 - Hdmi2.1 audio |  | DIO |  | HDMI2.1 Azalia HBR Audio test | P2 | DIO604 | DIO604 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
227 | DCN4.088 | DCN4.088 - Hdmi2.1 stereoscopic |  | DIO |  | HPO Stereo test on PHYA | P2 | DIO605 | DIO605 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
228 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 10GHz 1 Lane Test | P2 | DIO650 | DIO650.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
229 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 10GHz 1 Lane Test | P2 | DIO650 | DIO650.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
230 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 10GHz 2 Lane Test | P2 | DIO651 | DIO651.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
231 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 10GHz 2 Lane Test | P2 | DIO651 | DIO651.1-5 | TServer |  | 1 | 5 | Legacy | 1 | 5 | 1 | N-1 | 5 | 5 | 5 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
232 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 10GHz 4 Lane Test | P2 | DIO652 | DIO652.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
233 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 10GHz 4 Lane Test | P2 | DIO652 | DIO652.1-6 | TNG |  | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
234 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO653 | DIO653.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
235 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO653 | DIO653.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
236 | NV48-DCN-131 | DCN4.137 - DP2.0 DCN4.138 - Display PHY [DIO] C20 combo PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test |  | DIO653 | DIO653.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
237 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO654 | DIO654.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
238 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO654 | DIO654.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
239 | NV48-DCN-131 | DCN4.137 - DP2.0 DCN4.138 - Display PHY [DIO] C20 combo PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test |  | DIO654 | DIO654.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
240 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO655 | DIO655.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
241 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test | P2 | DIO655 | DIO655.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
242 | NV48-DCN-131 | DCN4.137 - DP2.0 DCN4.138 - Display PHY [DIO] C20 combo PHY |  | DIO |  | DP2.0 13.5GHz 1 Lane Test |  | DIO655 | DIO655.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
243 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO656 | DIO656.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
244 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO656 | DIO656.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
245 | NV48-DCN-131 | DCN4.137 - DP2.0 DCN4.138 - Display PHY [DIO] C20 combo PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test |  | DIO656 | DIO656.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
246 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO657 | DIO657.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
247 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO657 | DIO657.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
248 | NV48-DCN-131 | DCN4.137 - DP2.0 DCN4.138 - Display PHY [DIO] C20 combo PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test |  | DIO657 | DIO657.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
249 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO658 | DIO658.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
250 | DCN4.138 | DCN4.138 - Display PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test | P2 | DIO658 | DIO658.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
251 | NV48-DCN-131 | DCN4.137 - DP2.0 DCN4.138 - Display PHY [DIO] C20 combo PHY |  | DIO |  | DP2.0 20GHz 1 Lane Test |  | DIO658 | DIO658.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
252 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 Random Audio Test | P2 | DIO660 | DIO660 | TServer |  | 0 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
253 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 Ramp Audio Test | P2 | DIO661 | DIO661 | TServer |  | 0 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
254 | DCN4.137 | DCN4.137 - DP2.0 |  | DIO |  | DP2.0 Azalia Audio Test | P2 | DIO662 | DIO662 | TServer |  | 0 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
255 | DCN4.106 | DCN4.106 - Dwb support 1080p60 444 32bpp |  | DWB |  | DWB Stereo | P2 | DWB002 | DWB002.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | 1 |  |  | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w6
256 | DCN4.097 | DCN4.097 - Hdcp |  | EB |  | HDCP Check Keys | P2 | EB001 | EB001.1-6 | TNG |  | 1 | 6 | Delta | 1 | 6 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w8
257 | DCN4.097 | DCN4.097 - Hdcp |  | EB |  | HDCP 1.x DVI Single Link Test: PHYD | P2 | EB117 | EB117 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w8
258 | DCN4.097 | DCN4.097 - Hdcp |  | EB |  | HDCP 1.x HDMI with Azalia Audio Test: PHYC | P2 | EB200 | EB200.1-5 | TServer |  | 1 | 5 | Delta | 1 | 5 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
259 | DCN4.103 | DCN4.103 - DP HDMI HDCP for audio |  | EB |  | HDCP 1.x HDMI with Azalia Audio Test: PHYC | P2 | EB200 | EB200.1-5 | TServer |  | 1 | 5 | Delta | 1 | 5 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
260 | DCN4.098 | DCN4.098 - Encryption required control in otg |  | EB |  | HDCP 1.x HDMI with Azalia Audio Test: PHYC | P2 | EB200 | EB200.1-5 | TServer |  | 1 | 5 | Delta | 1 | 5 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
261 | DCN4.097 | DCN4.097 - Hdcp |  | EB |  | HDCP 1.x HDMI 1.4 Frame Packing 3D with 7.1 LPCM Audio Test: PHYD | P2 | EB213 | EB213.1-4 | TServer |  | 1 | 4 | Delta | 1 | 4 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
262 | DCN4.103 | DCN4.103 - DP HDMI HDCP for audio |  | EB |  | HDCP 1.x HDMI 1.4 Frame Packing 3D with 7.1 LPCM Audio Test: PHYD | P2 | EB213 | EB213.1-4 | TServer |  | 1 | 4 | Delta | 1 | 4 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
263 | DCN4.098 | DCN4.098 - Encryption required control in otg |  | EB |  | HDCP 1.x HDMI 1.4 Frame Packing 3D with 7.1 LPCM Audio Test: PHYD | P2 | EB213 | EB213.1-4 | TServer |  | 1 | 4 | Delta | 1 | 4 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
264 | DCN4.097 | DCN4.097 - Hdcp |  | EB |  | HDCP 1.x DisplayPort Test | P2 | EB300 | EB300.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
265 | DCN4.098 | DCN4.098 - Encryption required control in otg |  | EB |  | HDCP 1.x DisplayPort Test | P2 | EB300 | EB300.1-18 | TServer |  | 1 | 18 | Delta | 1 | 18 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
266 | DCN4.097 | DCN4.097 - Hdcp |  | EB |  | DisplayPort with Audio HDCP Test | P2 | EB302 | EB302.1-42 | TServer |  | 1 | 42 | Delta | 1 | 42 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
267 | DCN4.103 | DCN4.103 - DP HDMI HDCP for audio |  | EB |  | DisplayPort with Audio HDCP Test | P2 | EB302 | EB302.1-42 | TServer |  | 1 | 42 | Delta | 1 | 42 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
268 | DCN4.098 | DCN4.098 - Encryption required control in otg |  | EB |  | DisplayPort with Audio HDCP Test | P2 | EB302 | EB302.1-42 | TServer |  | 1 | 42 | Delta | 1 | 42 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
269 | DCN4.097 | DCN4.097 - Hdcp |  | EB |  | HDCP 2.2 DisplayPort Cipher Test | P2 | EB303 | EB303.1-28 | TServer |  | 1 | 28 | Delta | 1 | 28 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w8
270 | DCN4.105 | DCN4.105 - External event and unsolicited response |  | CE |  | Auto payload in unsolicited response | P2 | CE005 | CE005.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w6
271 | DCN4.104 | DCN4.104 - Audio controller cg and deep sleep |  | CE |  | Azalia Controller Clock Gating Test | P2 | CE012 | CE012 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w6
272 | DCN4.105 | DCN4.105 - External event and unsolicited response |  | CE |  | Azalia Unsolicited Response Holding Test | P2 | CE013 | CE013.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w6
273 | DCN4.122 | DCN4.122 - Unallocated space access |  | DMU |  | Unallocated Register Access Test | P2 | DMU001 | DMU001.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
274 | DCN4.107 | DCN4.107 - RSMU-RBBM-DC Interface Support |  | DMU |  | Unallocated Register Access Test | P2 | DMU001 | DMU001.1-3 | TServer |  | 1 | 3 | Legacy | 1 | 3 | 1 | FPGA | 1 | 1 | 1 |  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
275 | DCN4.110 | DCN4.110 - Fine grain security gasket |  | DMU |  | Fine-Grained Security Gasket Test | P2 | DMU002 | DMU002.1-8 | TServer |  | 1 | 8 | Legacy | 1 | 8 | 1 | FPGA | 1 | 1 |  |  | 1 | Register write/read test Failed at secure level 5/6/7 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w7
276 | DCN4.107 | DCN4.107 - RSMU-RBBM-DC Interface Support |  | DMU |  | Register Access Timeout Test | P2 | DMU003 | DMU003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 |  |  | 1 | segmentation fault | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
277 | DCN4.121 | DCN4.121 - Register access and timeout Support |  | DMU |  | Register Access Timeout Test | P2 | DMU003 | DMU003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | 1 |  |  | 1 | segmentation fault | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
278 | DCN4.111 | DCN4.111 - Db register update |  | DISP |  | Display Register Double-Buffering Test | P2 | DISP002 | DISP002.1-4 | TServer |  | 1 | 4 | Legacy | 1 | 4 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
279 | DCN4.112 | DCN4.112 - Triple buffered register update |  | DISP |  | Triple Buffered Register Update Test | P2 | DISP007 | DISP007.1-2 | TServer |  | 1 | 2 | Legacy | 1 | 2 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w2
280 | DCN4.102 | DCN4.102 - Latency hiding |  | DISP |  | Display High Bandwidth Usage Test | P2 | DISP005 | DISP005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w6
281 | DCN4.140 | DCN4.140 - Fclk pstate change |  | DISP |  | Memory P-State Switching at High Refresh Rate | P2 | DISP014 | DISP014 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
282 | DCN4.020 | DCN4.020 - pstate dram clock switch |  | DISP |  | Memory P-State Switching at High Refresh Rate | P2 | DISP014 | DISP014 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
283 | DCN4.151 | DCN4.151 - Dmcub mailbox |  | DISP |  | Memory P-State Switching at High Refresh Rate | P2 | DISP014 | DISP014 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 1 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
284 | DCN4.118 | DCN4.118 - New display phy power down seq |  | DISP |  | Display Non-Stream Test | P2 | DISP016 | DISP016 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | FPGA | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | w3
285 | DCN4.002 | DCN4.002 - Ipx dldo pg |  | DLPC |  | IPS Transition Test | P2 | DLPC001 | DLPC001.1-2 | TNG |  | 80 | 2 | New | 1 | 2 | 1 | FPGA | 2 | [8 empty] | 0 | 0 | 0 | 0
286 | NV48-DCN-005 | SRAM retention in DPP & MPC to reduce restore time 0pin retention |  | DLPC |  | IPS SRAM / 0 pin flop retention test |  | DLPC002 | DLPC002 | TNG |  | 40 | 1 | New | 1 | 1 | 1 | FPGA | 1 | [8 empty] | 0 | 0 | 0 | 0
287 | NV48-DCN-006 | SRAM retention in DPP & MPC to reduce restore time 0pin retention |  | DLPC |  | IPS SRAM / 0 pin flop retention test |  | DLPC002 | DLPC002 | TNG |  | 40 | 1 | New | 1 | 1 | 1 | FPGA | 1 | [8 empty] | 0 | 0 | 0 | 0
288 | DCN4.003 | DCN4.003 - Display mode performance |  | DISP |  | Display multiple pipe test | P2 | disp.smoke.multi_stream | disp.smoke.multi_stream | TNG |  | 1 | 1 | New | 1 | 1 | 1 | FPGA | 1
289 | DCN4.151 | DCN4.151 - Dmcub mailbox |  | DISP |  | Display multiple pipe test | P2 | disp.smoke.multi_stream | disp.smoke.multi_stream | TNG |  | 1 | 1 | New | 1 | 1 | 1 | FPGA | 1
290 | DCN4.003 | DCN4.003 - Display mode performance |  | MSA |  | DPP Basic Pixel Unpacking Test | P2 | DPP001 | DPP001.1-15 | TServer |  | 5 | 15 | Legacy | 1 | 15 | 1 |  | 0
291 | DCN4.024 | DCN4.024 - QoS urgent latency |  | MSA |  | DPP Basic Pixel Unpacking Test | P2 | DPP001 | DPP001.1-15 | TServer |  | 5 | 15 | Legacy | 1 | 15 | 1 |  | 0
292 | DCN4.152 | DCN4.003 - Display mode performance DCN4.024 - QoS urgent latency DCN4.152 - G7 PPT - Chiplet DCN4.142 - Scalable crb and metatag buf size |  | MSA |  | DPP Basic Pixel Unpacking Test |  | DPP001 | DPP001.1-15 | TServer |  | 5 | 15 | Legacy | 1 | 15 | 1 |  | 0
293 | DCN4.142 | DCN4.142 - Scalable crb and metatag buf size |  | MSA |  | DPP Basic Pixel Unpacking Test | P2 | DPP001 | DPP001.1-15 | TServer |  | 5 | 15 | Legacy | 1 | 15 | 1 |  | 0