## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | NV48-OSS-004 | AQL Command + multi-producer support | Song, Sukey | SDMA | AQL Command + multi-producer support | Multi-producer support means SDMA may fetch a command which is not ready (because multiple producers can update doorbell) and should wait until the command is valid | P2 | sdma84.101-102 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
1 | NV48-OSS-005 | Atomic Command | Song, Sukey | SDMA | Atomic Add |  | P2 | nsdma177.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
2 | NV48-OSS-005 | Atomic Command | Song, Sukey | SDMA | Atomic Swap |  | P2 | nsdma178.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 |  | WK4
3 | NV48-OSS-005 | Atomic Command | Song, Sukey | SDMA | Atomic CompareSwap |  | P2 | nsdma179.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 |  | WK4
4 | NV48-OSS-006 | Burst NOPs | Song, Sukey | SDMA | Burst NOPs | for padding the command buffer | P2 | nsdma223.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
5 | NV48-OSS-007 | CGCG enhancement | Song, Sukey | SDMA | CGCG enhancement | medium grain CGCG control | P2 | nsdma207.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | wk8 ( 2 Wks after PMM enabled CGCG)
6 | NV48-OSS-009 | Command Overlap | Song, Sukey | SDMA | Command Overlap |  | P2 | sdma27.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
7 | NV48-OSS-010 | Conditional Execution Command | Song, Sukey | SDMA | Conditional Exec Fail |  | P2 | nsdma27.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 |  | WK4
8 | NV48-OSS-010 | Conditional Execution Command | Song, Sukey | SDMA | Conditional Exec Pass |  | P2 | nsdma26.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
9 | NV48-OSS-011 | Constant Fill Command | Song, Sukey | SDMA | Const fill- byte |  | P2 | nsdma58.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK4
10 | NV48-OSS-011 | Constant Fill Command |  | SDMA | Const-fill-Dword |  | P2 | nsdma59.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK4
11 | NV48-OSS-012 | Context Switch | Song, Sukey | SDMA | Normal-Preempt | de-asserting RB_CNTL.RB_ENABLE | P1 | nsdma215.1-3 | Tserver |  | 3 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | [5 empty] | 0 | [6 empty] | 0 |  | wk6
12 | NV48-OSS-013 | Copy cmd format to support CUDA API(3D handle) | Song, Sukey | SDMA | Copy cmd format to support CUDA API(3D handle) |  | P1 | nsdma81.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
13 | NV48-OSS-019 | Fence Command |  | SDMA | GMC Address |  | P2 | sdma.packet.fence | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [10 empty] | 0 |  | WK6
14 | NV48-OSS-019 | Fence Command | Song, Sukey | SDMA | Physical Address |  | P2 | sdma.packet.fence | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [10 empty] | 0 |  | WK6
15 | NV48-OSS-022 | GPUVM TLB Invalidation |  | SDMA | Legacy |  | P2 | nsdma205.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5
16 | NV48-OSS-022 | GPUVM TLB Invalidation | Song, Sukey | SDMA | LightWeight |  | P2 | nsdma206.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5
17 | NV48-OSS-023 | GCR request support | Song, Sukey | SDMA | Write-back |  | P2 | nsdma66.1-2 | Tserver | -vm | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  |  |  | 2 |  |  | 0 |  | WK5
18 | NV48-OSS-023 | GCR request support | Song, Sukey | SDMA | Invalidate |  | P2 | nsdma67.1-2 | Tserver | -vm | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  |  |  | 2 |  |  | 0 |  | WK5
19 | NV48-OSS-023 | GCR request support | Song, Sukey | SDMA | Discard |  | P2 | nsdma68.1-2 | Tserver | -vm | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 1 | [5 empty] | 0 |  |  |  | 2 |  |  | 0 |  | WK5
20 | NV48-OSS-025 | Increase max copy size(4M-1G) | Song, Sukey | SDMA | Increase max copy size(4M-1G) |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
21 | NV48-OSS-026 | L2 policy override on normal command | Song, Sukey | SDMA | L2 policy override on normal command |  | P2 | nsdma1.2 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | Emulator | 2 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
22 | NV48-OSS-027, NV48-OSS-035 | Linear Copy, Linear to Linear Copy Command | Song, Sukey | SDMA | Linear Copy, Linear to Linear Copy Command |  |  | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
23 | NV48-OSS-028 | Linear Backwards Copy | Song, Sukey | SDMA | Linear Backwards Copy |  | P2 | nsdma5.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK2
24 | NV48-OSS-029 | Linear Copy Broadcast | Song, Sukey | SDMA | Linear Copy Broadcast |  | P2 | nsdma4.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
25 | NV48-OSS-030, NV48-OSS-036 | Linear Sub-Window Copy, Linear to Linear sub-window copy | Song, Sukey | SDMA | Linear Sub-Window Copy, Linear to Linear sub-window copy |  |  | nsdma7.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
26 | NV48-OSS-031 | Linear large Sub-Window Copy | Song, Sukey | SDMA | Linear large Sub-Window Copy |  | P2 | nsdma93.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5
27 | 5 | Tiled to Tiled Sub-Window Copy | Song, Sukey | SDMA | Tiled to Tiled Sub-Window Copy |  |  | nsdma9.1-5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
28 | NV48-OSS-034, NV48-OSS-040 | Tiled Sub-Window Copy, Linear to Tiled / Tiled to Linear sub-window copy | Song, Sukey | SDMA | Tiled Sub-Window Copy, Linear to Tiled / Tiled to Linear sub-window copy |  |  | nsdma10.1-10 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1
29 | NV48-OSS-037 | Linear to Structured / Structured to Linear copy | Song, Sukey | SDMA | Linear to Structured / Structured to Linear copy |  | P2 | nsdma13.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5
30 | NV48-OSS-038 | Linear to Tiled (frame to field) copy | Song, Sukey | SDMA | Linear to Tiled (frame to field) copy |  | P2 | nsdma12.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK5
31 | NV48-OSS-039 | Linear to Tiled / Tiled to Linear Copy Command | Song, Sukey | SDMA | Linear to Tiled / Tiled to Linear Copy Command | L2T | P2 | nsdma2.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | Wk5
32 | NV48-OSS-039 | Linear to Tiled / Tiled to Linear Copy Command |  | SDMA | Linear to Tiled / Tiled to Linear Copy Command | T2L | P2 | nsdma3.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | Wk5
33 | NV48-OSS-041 | Linear to Tiled copy broadcast | Song, Sukey | SDMA | Linear to Tiled copy broadcast |  | P2 | nsdma11.1-5 | Tserver |  | 1 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK5
34 | NV48-OSS-042, NV48-OSS-043, NV48-OSS-044, NV48-OSS-054, NV48-OSS-055, NV48-OSS-095 | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol | Song, Sukey | SDMA | Mid Command Buffer Preemption, Mid Command Preemption, RB Command Preemption, Ring Buffer Preemption between contexts,Ring Buffer Preemption within a context, Enhanced RB preemption protocol |  | P1 | nsmda217.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
35 | NV48-OSS-045, NV48-OSS-103 | Mid-command preemption when time quantum reached, Support mid-command boundary on quantum expire | Song, Sukey | SDMA | Mid-command preemption when time quantum reached, Support mid-command boundary on quantum expire |  |  | nsmda218.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
36 | NV48-OSS-046 | Memory Increment | Song, Sukey | SDMA | Memory Increment |  | P2 | nsdma160.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
37 | NV48-OSS-050 | Physical linear copy | Song, Sukey | SDMA | Physical linear copy |  | P2 | sdma.packet.physical_linear_copy/1-8,sdma.packet.physical_linear_copy/21-28 | TNG |  | 1 | 16 | Legacy | 1 | 16 | 1 | Emulator | 16 | 16 | 16 |  |  |  | 1 | [6 empty] | 0 |  | WK5
38 | NV48-OSS-051 | Poll Memory/Register Command | Song, Sukey | SDMA | Poll Memory/Register Command |  | P2 | nsdma16.1-10 | Tserver |  | 1 | 10 | Legacy | 1 | 10 | 1 | Emulator | 10 | 10 | 9 |  | 1 |  | 0.9 |  | 10 | 9 |  | 1 |  | 0.9 |  | WK4
39 | NV48-OSS-052 | Predicated Execution Command | Song, Sukey | SDMA | Predicated Execution Command |  | P2 | nsdma182.1,nsdma183.1 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
40 | NV48-OSS-053 | RAW dependency check | Song, Sukey | SDMA | RAW dependency check |  | P2 | nsdma68.1-2 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK5
41 | NV48-OSS-057, NV48-OSS-101 | SDMA Range Based Firewall, Upgrade 4KB firewalls with range check, add RESTORE flag to the new firewall registers in rdl file for RLC to do save/restore. | Song, Sukey | SDMA | SDMA Range Based Firewall, Upgrade 4KB firewalls with range check, add RESTORE flag to the new firewall registers in rdl file for RLC to do save/restore. |  |  | nsdma222.1-34 | Tserver |  | 4 | 34 | New | 1 | 34 | 1 | Emulator | 28 | 28 | 28 |  |  |  | 1 | [6 empty] | 0
42 | NV48-OSS-058 | SDMA Performance - Multi Engine | Song, Sukey | SDMA | SDMA Performance - Multi Engine |  | P2 | nsmda402.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
43 | NV48-OSS-059 | SDMA Performance - Single Engine | Song, Sukey | SDMA | SDMA Performance - Single Engine |  | P2 | nsdma402.2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
44 | NV48-OSS-061 | SDMA Stress Test - CGCG | Song, Sukey | SDMA | SDMA Stress Test - CGCG |  | P2 | nsmda409.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | wk8 ( 2 Wks after PMM enabled CGCG)
45 | NV48-OSS-063 | SDMA Stress Test - VDDGFX | Song, Sukey | SDMA | SDMA Stress Test - VDDGFX |  | P2 | nsmda410.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | wk 13( 2 Wks after PMM enabled VDDGFX)
46 | NV48-OSS-066 | SRBM Writes | Song, Sukey | SDMA | SRBM Writes |  | P2 | nsdma120.1-6 | Tserver |  | 1 | 6 | Legacy | 1 | 6 | 1 | Emulator | 6 | 6 | 6 |  |  |  | 1 | [6 empty] | 0 |  | WK4
47 | NV48-OSS-067 | Support byte aligned Count in normal tiled copy | Song, Sukey | SDMA | Support byte aligned Count in normal tiled copy |  | P2 | nsdma2.6 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
48 | NV48-OSS-068 | Support Native TMZ support | Song, Sukey | SDMA | Support Native TMZ support |  | P2 | nsdma152-nsdma159 | Tserver |  | 1 | 8 | Legacy | 1 | 8 | 1 | Emulator | 8 | 8 | 8 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | wk 6( 2Wks after PSP enabled PSP)
49 | NV48-OSS-070 | Poll Register Write Memory | Song, Sukey | SDMA | Poll Register Write Memory |  | P2 | nsdma10.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
50 | NV48-OSS-072 | Conditional Execution | Song, Sukey | SDMA | Conditional Execution |  | P2 | nsdma26,nsdma27 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK5
51 | NV48-OSS-073 | Predicated Execution | Song, Sukey | SDMA | Predicated Execution |  | P2 | nsdma182,nsdma183 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK4
52 | NV48-OSS-074 | Generate PTE/PDE | Song, Sukey | SDMA | Generate PTE/PDE |  | P2 | gen_gte | TNG |  | 1 | 10 | Delta | 1 | 10 | 1 | Emulator | 10 | 10 | 10 |  |  |  | 1 | [6 empty] | 0 |  | WK4
53 | NV48-OSS-075 | Copy Mask PTE/PDE | Song, Sukey | SDMA | Copy Mask PTE/PDE |  | P2 | nsdma201.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
54 | NV48-OSS-076 | RMW PTE/PDE | Song, Sukey | SDMA | RMW PTE/PDE |  | P2 | nsdma203.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
55 | NV48-OSS-077 | Timestamp Commands | Song, Sukey | SDMA | Timestamp Commands |  | P2 | nsdma56,nsdms57 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
56 | NV48-OSS-078 | Translation failure RESP MODE[4:0] | Song, Sukey | SDMA | Translation failure RESP MODE[4:0] |  | P2 | nsdma126-nsdma134 | Tserver |  | 1 | 9 | Legacy | 1 | 9 | 1 | Emulator | 9 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
57 | NV48-OSS-079 | VM_INVALIDATION | Song, Sukey | SDMA | VM_INVALIDATION |  | P2 | nsdma222.1-18 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 18 | 18 | 18 |  |  |  | 1 | [6 empty] | 0 |  | WK5
58 | NV48-OSS-081 | Trap Command | Song, Sukey | SDMA | Trap Command |  | P2 | nsdma14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 |  |  |  |  | 0 | [6 empty] | 0 |  | WK2
59 | NV48-OSS-082 | VDDGFX power down support | Song, Sukey | SDMA | VDDGFX power down support |  | P2 | nsdma204.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK8
60 | NV48-OSS-085 | Support 8 general purpose HW queue with programmable queue scheduling/priority | Song, Sukey | SDMA | Support 8 general purpose HW queue with programmable queue scheduling/priority |  | P2 | nsdma213.1-4 | Tserver | '-oss_sdmaengines=sdma0_all -oss_no_fill_and_verify=true -sdma_copysize=4KiB -sdma_loops=2 | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 4 | 4 | 4 |  |  |  | 1 | [6 empty] | 0 |  | WK7
61 | NV48-OSS-086 | Queue process detection and per-queue reset | Song, Sukey | SDMA | Queue process detection and per-queue reset |  | P2 | nsdma216.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK8
62 | NV48-OSS-088 | standardize idle/busy reporting mechanism to RLC | Song, Sukey | SDMA | standardize idle/busy reporting mechanism to RLC |  | P2 | nsdma207.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK7
63 | NV48-OSS-090 | SDMA doorbell common range, daisy chain doorbell intf among SDMA controllers | Song, Sukey | SDMA | SDMA doorbell common range, daisy chain doorbell intf among SDMA controllers |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK7
64 | NV48-OSS-091 | non-recoverable page fault reporting | Song, Sukey | SDMA | non-recoverable page fault reporting |  | P2 | nsdma126,nsdma126127,nsdma126128 | Tserver |  | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK7
65 | NV48-OSS-093 | Improved ucode exception/interrupt handling enhancement | Song, Sukey | SDMA | Improved ucode exception/interrupt handling enhancement |  | P2 | nsdma14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
66 | NV48-OSS-094 | save/restore effeciency enhancement (change in RLC, no SDMA change) | Song, Sukey | SDMA | save/restore effeciency enhancement (change in RLC, no SDMA change) |  | P2 | nsdma410 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
67 | NV48-OSS-100 | WPTR poll enhancement | Song, Sukey | SDMA | WPTR poll enhancement |  | P2 | nsdma1.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK5
68 | NV48-OSS-110 | Change SDMA's interrupt SourceID/RingID | Song, Sukey | SDMA | Change SDMA's interrupt SourceID/RingID |  | P2 | nsdma14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK2
69 | NV48-OSS-116 | Const_fill count size expands to 1GB | Song, Sukey | SDMA | Const_fill count size expands to 1GB |  | P2 | nsdma59.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | WK4
70 | NV48-OSS-118, NV48-OSS-127 | Linear Copy(LSDMA), Linear to Linear Copy Command(LSDMA) | Song, Sukey | SDMA | Linear Copy(LSDMA), Linear to Linear Copy Command(LSDMA) |  |  | nsdma1.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
71 | NV48-OSS-119 | Linear Backwards Copy(LSDMA) | Song, Sukey | SDMA | Linear Backwards Copy(LSDMA) |  | P2 | nsdma5.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
72 | NV48-OSS-120 | Linear Copy Broadcast(LSDMA) | Song, Sukey | SDMA | Linear Copy Broadcast(LSDMA) |  | P2 | nsdma4.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK4
73 | NV48-OSS-121, NV48-OSS-128 | Linear Sub-Window Copy(LSDMA), Linear to Linear sub-window copy(LSDMA) | Song, Sukey | SDMA | Linear Sub-Window Copy(LSDMA), Linear to Linear sub-window copy(LSDMA) |  |  | nsdma7.101-105 | Tserver |  | 5 | 5 | Legacy | 1 | 5 | 1 | Emulator | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1
74 | NV48-OSS-122 | Linear large Sub-Window Copy(LSDMA) | Song, Sukey | SDMA | Linear large Sub-Window Copy(LSDMA) |  | P2 | nsdma93.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
75 | NV48-OSS-124, NV48-OSS-131 | Tiled Copy(LSDMA), Linear to Tiled / Tiled to Linear Copy Command(LSDMA) | Song, Sukey | SDMA | Tiled Copy(LSDMA), Linear to Tiled / Tiled to Linear Copy Command(LSDMA) |  |  | nsdma2.101-105,nsdma3.101-105 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0
76 | NV48-OSS-125 | Tiled to Tiled Sub-Window Copy(LSDMA) | Song, Sukey | SDMA | Tiled to Tiled Sub-Window Copy(LSDMA) |  | P2 | nsdma9.101-105 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
77 | NV48-OSS-126, NV48-OSS-132 | Tiled Sub-Window Copy(LSDMA), Linear to Tiled / Tiled to Linear sub-window copy(LSDMA) | Song, Sukey | SDMA | Tiled Sub-Window Copy(LSDMA), Linear to Tiled / Tiled to Linear sub-window copy(LSDMA) |  |  | nsdma10.101-110 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0
78 | NV48-OSS-129 | Linear to Structured / Structured to Linear copy(LSDMA) | Song, Sukey | SDMA | Linear to Structured / Structured to Linear copy(LSDMA) |  | P2 | nsdma13.101-102 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
79 | NV48-OSS-130 | Linear to Tiled (frame to field) copy(LSDMA) | Song, Sukey | Lite-SDMA | Linear to Tiled (frame to field) copy(LSDMA) |  | P2 | nsdma12.101-105 | Tserver |  | 1 | 5 | New | 1 | 5 | 1 | Emulator | 5 | 1 | 1 | [5 empty] | 5 | 5 |  |  |  | 1 |  | WK4
80 | NV48-OSS-133 | Linear to Tiled copy broadcast(LSDMA) | Song, Sukey | Lite-SDMA | Linear to Tiled copy broadcast(LSDMA) |  | P2 | nsdma11.101-105 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK4
81 | NV48-OSS-134, NV48-OSS-135, NV48-OSS-136 | Mid Command Preemption(LSDMA), Mid Command Buffer Preemption(LSDMA), RB Command Preemption(LSDMA) | Song, Sukey | Lite-SDMA | Mid Command Preemption(LSDMA), Mid Command Buffer Preemption(LSDMA), RB Command Preemption(LSDMA) |  |  | nsdma217.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
82 | NV48-OSS-137 | Mid-command preemption when time quantum reached(LSDMA) | Song, Sukey | Lite-SDMA | Mid-command preemption when time quantum reached(LSDMA) |  | P2 | nsdma217.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK8
83 | NV48-OSS-138 | Structure Buffer Copy(LSDMA) | Song, Sukey | Lite-SDMA | Structure Buffer Copy(LSDMA) |  | P2 | nsdma13.101-102 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
84 | NV48-OSS-139 | Constant Fill Command(LSDMA) | Song, Sukey | Lite-SDMA | Constant Fill Command(LSDMA) |  | P2 | lsdma.packet.constant_fill | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
85 | NV48-OSS-140 | Indirect Buffer Command(LSDMA) | Song, Sukey | Lite-SDMA | Indirect Buffer Command(LSDMA) |  | P2 | nsdma17.101-106 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
86 | NV48-OSS-141 | Fence(LSDMA) | Song, Sukey | Lite-SDMA | Fence(LSDMA) |  | P2 | nsdma175;nsdma176 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
87 | NV48-OSS-142 | Trap(LSDMA) | Song, Sukey | Lite-SDMA | Trap(LSDMA) |  | P2 | nsdma14.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK2
88 | NV48-OSS-143 | Memory Increment(LSDMA) | Song, Sukey | Lite-SDMA | Memory Increment(LSDMA) |  | P2 | nsdma160.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
89 | NV48-OSS-144 | Poll Memory/Register(LSDMA) | Song, Sukey | Lite-SDMA | Poll Memory/Register(LSDMA) |  | P2 | nsdma16.101-102 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
90 | NV48-OSS-145 | Poll Register Write Memory(LSDMA) | Song, Sukey | Lite-SDMA | Poll Register Write Memory(LSDMA) |  | P2 | nsdma16.103 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
91 | NV48-OSS-147 | Conditional Execution(LSDMA) | Song, Sukey | Lite-SDMA | Conditional Execution(LSDMA) |  | P2 | nsdma26.101 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK4
92 | NV48-OSS-148 | Predicated Execution(LSDMA) | Song, Sukey | Lite-SDMA | Predicated Execution(LSDMA) |  | P2 | nsdma182.101 | Tserver |  | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | WK4
93 | NV48-OSS-149 | Atomic Command(LSDMA) | Song, Sukey | Lite-SDMA | Atomic Command(LSDMA) |  | P2 | nsdma177.101 | Tserver |  | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | WK4
94 | NV48-OSS-150 | VM_INVALIDATION(LSDMA) | Song, Sukey | Lite-SDMA | VM_INVALIDATION(LSDMA) |  | P2 | nsdma220.21-37 | Tserver |  | 1 | 17 | Legacy | 1 | 17 | 1 | Emulator | 17 | 17 | 17 |  |  |  | 1 | [6 empty] | 0 |  | WK5
95 | NV48-OSS-151 | SRBM Write(LSDMA) | Song, Sukey | Lite-SDMA | SRBM Write(LSDMA) |  | P2 | nsdma120.101-106 | Tserver |  | 1 | 6 | Legacy | 1 | 6 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK5
96 | NV48-OSS-152 | Burst NOP(LSDMA) | Song, Sukey | Lite-SDMA | Burst NOP(LSDMA) |  | P2 | nsdma223.101-102 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
97 | NV48-OSS-153 | Timestamp(LSDMA) | Song, Sukey | Lite-SDMA | Timestamp(LSDMA) |  | P2 | nsmda56.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
98 | NV48-OSS-154 | Generate PTE/PDE(LSDMA) | Song, Sukey | Lite-SDMA | Generate PTE/PDE(LSDMA) |  | P2 | gen_gte | TNG |  | 1 | 10 | Delta | 1 | 10 | 1 | Emulator | [6 empty] | 0 | [6 empty] | 0 |  | WK5
99 | NV48-OSS-155 | Copy Mask PTE/PDE(LSDMA) | Song, Sukey | Lite-SDMA | Copy Mask PTE/PDE(LSDMA) |  | P2 | nsmda38.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
100 | NV48-OSS-156 | RMW PTE/PDE(LSDMA) | Song, Sukey | Lite-SDMA | RMW PTE/PDE(LSDMA) |  | P2 | nsmda39.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK5
101 | NV48-OSS-158 | TMZ Support(LSDMA) | Song, Sukey | Lite-SDMA | TMZ Support(LSDMA) |  | P2 | nsdma152-nsdma159 | Tserver |  | 8 | 8 | Legacy | 1 | 8 | 1 |  | 0 | [5 empty] | 0 |  | 8 | 8 |  |  |  | 1 |  | WK6
102 | NV48-OSS-159 | Host Access LSDMA scratch ram (LSDMA) | Song, Sukey | Lite-SDMA | Host Access LSDMA scratch ram (LSDMA) |  | P2 | nsdma81.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK6
103 | NV48-OSS-160 | AQL Support (LSDMA) | Song, Sukey | Lite-SDMA | AQL Support (LSDMA) |  | P2 | nsdma214.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | WK4
104 | NV48-OSS-161 | (LSDMA) 2 HW Queue | Song, Sukey | Lite-SDMA | (LSDMA) 2 HW Queue |  | P2 | nsdma1.101 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK2
105 | NV48-OSS-162 | (LSDMA) PIO Queue support | Song, Sukey | Lite-SDMA | (LSDMA) PIO Queue support |  | P2 | nsdma212.1-2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK2
106 | NV48-OSS-168 | Atomic Command | Song, Sukey | HDP | Atomic Command |  | P2 | nsdma177.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 0 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | WK4
107 | NV48-OSS-169 | Host read | Song, Sukey | HDP | Host read |  | P2 | hdp2.1-12 | Tserver |  | 1 | 12 | Legacy | 1 | 12 | 1 | Emulator | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | WK4
108 | NV48-OSS-170 | Host write | Song, Sukey | HDP | Host write |  | P2 | hdp1.1-12 | Tserver |  | 1 | 12 | Legacy | 1 | 12 | 1 | Emulator | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | WK4
109 | NV48-OSS-171 | HDP RAW Coherency | Song, Sukey | HDP | HDP RAW Coherency |  | P2 | hdp12.1-4 | Tserver |  | 1 | 4 | Legacy | 1 | 4 | 1 | Emulator | 4 | [5 empty] | 0 |  | 4 | 4 |  |  |  | 1 |  | WK4
110 | NV48-OSS-192 | HDP performance target | Song, Sukey | HDP | HDP performance target |  | P1 | eg | Tserver |  | 1 | 4 | Legacy | 1 | 4 | 1 | [7 empty] | 0 | [6 empty] | 0 |  | 0
111 | NV48-OSS-182 | UTCL2 retry interrupt filter | Song, Sukey | IH | UTCL2 retry interrupt filter |  | P2 | nsdma229.1-2 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | Wk4
112 | NV48-OSS-186 | Remove ring2 to save area, since only 2 IH rings are enough. Test 2 IH rings | Song, Sukey | IH | Remove ring2 to save area, since only 2 IH rings are enough. Test 2 IH rings |  | P2 | ih_ring | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0
113 | NV48-OSS-194 | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command(LSDMA) | Song, Sukey | Lite-SDMA | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command(LSDMA) |  | p1 | linear_write | TNG |  | 3 | 30 | New | 1 | 30 | 1 | Emulator | 30 | 30 | 30
114 | NV48-OSS-195 | Centralized Compression Support(Lite Sdma) | Song, Sukey | Lite-SDMA | Centralized Compression Support(Lite Sdma) |  | p1 | lite_sdma_dcc | TNG |  | 2 | 10 | New | 1 | 8 | 0.8 | Emulator | 10 | 2 | 2
115 | NV48-OSS-196 | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel | Song, Sukey | Lite-SDMA | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel |  | p1 | tiled_copy | TNG |  | 3 | 3 | New | 1 | 3 | 1 | Emulator | 1 | 1 | 1
116 | NV48-OSS-197 | GFX12 address lib support | Song, Sukey | Lite-SDMA | GFX12 address lib support |  | p1 | tiled_copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1
117 | NV48-OSS-199 | Support "Physical Linear Copy" command | Song, Sukey | Lite-SDMA | Support "Physical Linear Copy" command |  | p1 | physical_linear_copy | TNG |  | 1 | 14 | New | 1 | 14 | 1 | Emulator | 14 | 14 | 14
118 | NV48-OSS-200 | Add context switch status registers for each HW queue(SDMA) | Song, Sukey | SDMA | Add context switch status registers for each HW queue(SDMA) |  | p1 | context_switch | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
119 | NV48-OSS-201 | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command | Song, Sukey | SDMA | Add physical address indicator in LINEAR_WRITE, CONST_FILL, GEN_PTEPDE command |  | p1 | linear_write | TNG |  | 3 | 30 | New | 1 | 30 | 1 | Emulator | 30 | 30 | 30
120 | NV48-OSS-202 | Centralized Compression Support | Song, Sukey | SDMA | Centralized Compression Support |  | p1 | sdma_dcc | Tserver |  | 2 | 10 | New | 1 | 8 | 0.8 | Emulator | 1
121 | NV48-OSS-203 | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel | Song, Sukey | SDMA | Change "Tiled Copy", "Linear to Tiled Broadcast Copy" and "Linear to Tiled Frame to Field Copy" linear pitch/slice_pitch unit from byte to pixel |  | p1 | tiled_copy | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1
122 | NV48-OSS-204 | Decompress BLTs via SDMA | Song, Sukey | SDMA | Decompress BLTs via SDMA |  | p1 | sdma_dcc | Tserver |  | 2 | 2 | New | 1 | 2 | 1 | Emulator | 2 | 2 | 2
123 | NV48-OSS-205 | Dedicated TLB L1 cache for address translation in non-copy memory access | Song, Sukey | SDMA | Dedicated TLB L1 cache for address translation in non-copy memory access |  | p1 | sdma_tlb | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
124 | NV48-OSS-206 | Doorbell interface: Get doorbell from dbhub | Song, Sukey | SDMA | Doorbell interface: Get doorbell from dbhub |  | p1 | doorbell | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 | [5 empty] | 1 | 1
125 | NV48-OSS-207 | Extended MALL reuse policy control | Song, Sukey | SDMA | Extended MALL reuse policy control |  | p1 | mall | Tserver |  | 2 | 4 | New | 1 | 4 | 1 | Emulator | 1
126 | NV48-OSS-208 | Firewall update | Song, Sukey | SDMA | Firewall update |  | p1 | firewall | Tserver |  | 1 | 5 | New | 1 | 5 | 1 | Emulator | 1 | 1 | 1
127 | NV48-OSS-209 | GFX12 address lib support | Song, Sukey | SDMA | GFX12 address lib support |  | p1 | tiled_copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
128 | NV48-OSS-210 | GPUVM PDE/PTE definition change | Song, Sukey | SDMA | GPUVM PDE/PTE definition change |  | p1 | gpuvm | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1
129 | NV48-OSS-213 | IB base address aligning from 8DW to DW | Song, Sukey | SDMA | IB base address aligning from 8DW to DW |  | p1 | ib_packet | TNG |  | 1 | 4 | New | 1 | 4 | 1 | Emulator | 1
130 | NV48-OSS-214 | Native GPU fence object support | Song, Sukey | SDMA | Native GPU fence object support |  | p1 | fence_interrupt | TNG |  | 1 | 4 | New | 1 | 4 | 1 | Emulator | 1 | 1 | 1
131 | NV48-OSS-215 | PAGE_TRANSER command | Song, Sukey | SDMA | PAGE_TRANSER command |  | p1 | page_transer | TNG |  | 2 | 8 | New | 1 | 8 | 1 | Emulator | 6 | 6 | 6
132 | NV48-OSS-220 | SDMA ucode caching | Song, Sukey | SDMA | SDMA ucode caching |  | p1 | linear_copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1
133 | NV48-OSS-221 | Use RS64 as SDMA MCU core | Song, Sukey | SDMA | Use RS64 as SDMA MCU core |  | p1 | linear_copy | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | l