## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF | AG-PCIE Traffic Test | Wr max size Rx (WC) | P1 | AG002.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
1 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Wr max size Rx (WB) | P1 | AG002.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
2 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Wr min size Rx | P1 | AG002.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
3 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Wr rand size Rx (WC) | P1 | AG002.004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
4 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Wr rand size Rx (WB) | P1 | AG002.005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
5 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Wr rand size Rx 128B | P1 | AG002.006 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
6 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Rd max size Rx (WB) | P1 | AG002.007 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
7 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Rd min size Rx | P1 | AG002.008 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
8 | NV48-PCIe-nBIF-063 | Vendor ID and Device ID | Fanny | nBIF | Basic PCI Configuration Space Access Tests | Validate Basic PCI Configuration Space Access with 32b Writes and 32b Reads | P2 | AG003.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
9 | NV48-PCIe-nBIF-063 | Vendor ID and Device ID | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 16b Writes and 32b Reads | P2 | AG003.002 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
10 | NV48-PCIe-nBIF-016 | PCIe Register Accesses | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 8b Writes and 32b Reads | P2 | AG003.003 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
11 | NV48-PCIe-nBIF-016 | PCIe Register Accesses | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 32b Writes and 16b Reads | P2 | AG003.004 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
12 | NV48-PCIe-nBIF-072 | PCIe CFG layout check | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 16b Writes and 16b Reads | P2 | AG003.005 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
13 | NV48-PCIe-nBIF-072 | PCIe CFG layout check | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 8b Writes and 16b Reads | P2 | AG003.006 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
14 | NV48-PCIe-nBIF-072 | PCIe CFG layout check | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 32b Writes and 8b Reads | P2 | AG003.007 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
15 | NV48-PCIe-nBIF-072 | PCIe CFG layout check | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 16b Writes and 8b Reads | P2 | AG003.008 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
16 | NV48-PCIe-nBIF-072 | PCIe CFG layout check | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with 8b Writes and 8b Reads | P2 | AG003.009 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
17 | NV48-PCIe-nBIF-072 | PCIe CFG layout check | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access with Random Access Sizes and Offsets | P2 | AG003.010 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
18 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF | PCI Standard Capabilities Block Tests | List PCI Standard Capabilities Blocks | P2 | AG004.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
19 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF |  | Validate Power Management Interface Capability Block | P2 | AG004.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
20 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF |  | Validate PCI Express Capability Block | P2 | AG004.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
21 | NV48-PCIe-nBIF-059 | MSI and MSI-X | Fanny | nBIF |  | Validate Message Signaled Interrupts Capability Block | P2 | AG004.004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
22 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF |  | Validate Vendor Specific Capability Block | P2 | AG004.005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
23 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF | PCIE Extended Capabilities Block Tests | List PCIE Extended Capabilities Blocks | P2 | AG005.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
24 | NV48-PCIe-nBIF-055 | AER | Fanny | nBIF |  | Validate Advanced Error Reporting Capability Block | P2 | AG005.002 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
25 | NV48-PCIe-nBIF-057 | Vendor Specific Capability | Fanny | nBIF |  | Validate Vendor Specific Capability Block | P2 | AG005.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
26 | NV48-PCIe-nBIF-055 | AER | Fanny | nBIF |  | Validate Resizable BAR Block | P2 | AG005.004 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
27 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF |  | Validate Virtual Channel Capability Block | P2 | AG005.005 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
28 | NV48-PCIe-nBIF-053 | PWR budgeting | Fanny | nBIF |  | Validate Power Budgeting Capability Block | P2 | AG005.006 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
29 | NV48-PCIe-nBIF-051 | Secondary PCIe Capability | Fanny | nBIF |  | Validate Secondary PCI Express Capability Block | P2 | AG005.007 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
30 | NV48-PCIe-nBIF-056 | DSN | Fanny | nBIF |  | Validate Device Serial Number Capability Block | P2 | AG005.008 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
31 | NV48-PCIe-nBIF-050 | ACS | Fanny | nBIF |  | Validate Access Control Services Capability Block | P2 | AG005.009 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
32 | NV48-PCIe-nBIF-052 | DPA | Fanny | nBIF |  | Validate Dynamic Power Allocation Block | P2 | AG005.012 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
33 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF |  | Validate Process Address Space ID Block | P2 | AG005.013 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
34 | NV48-PCIe-nBIF-008 | GFX Device ID Strap | Fanny | nBIF |  | Validate All PCIE Extended Capabilities Blocks | P2 | AG005.014 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
35 | NV48-PCIe-nBIF-057 | Vendor Specific Capability | Fanny | nBIF |  | Validate Single Root IO Virtualization Extended capabilities block | P2 | AG005.015 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
36 | NV48-PCIe-nBIF-048 | ARI | Fanny | nBIF |  | Validate Alternative Routing Interpretation Extended capabilities block | P2 | AG005.016 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
37 | NV48-PCIe-nBIF-071 | GPUIOV | Fanny | nBIF |  | Validate GPU IO Virtualization Enhanced Extended capabilities block | P2 | AG005.017 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
38 | NV48-PCIe-nBIF-100 | L1 SS | Fanny | nBIF |  | Validate L1 PM Substates Extended capabilities block | P2 | AG005.018 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
39 | NV48-PCIe-nBIF-046 | data link feature extended capability | Fanny | nBIF |  | Validate data link feature Extended capabilities block | P3 | AG005.019 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
40 | NV48-PCIe-nBIF-045 | physical layer 16GT extended capability | Fanny | nBIF |  | Validate Physical Layer 16GT/S Extended capabilities block | P2 | AG005.020 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
41 | NV48-PCIe-nBIF-044 | lane margining at the receiver extended capability | Fanny | nBIF |  | Validate Lane Margining Extended capabilities block | P2 | AG005.021 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
42 | NV48-PCIe-nBIF-049 | PCIE Physical Layer 16GT/32GT | Fanny | nBIF |  | Validate Physical Layer 32GT/S Extended capabilities block | P2 | AG005.023 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
43 | NV48-PCIe-nBIF-058 | PCIe Capability | Fanny | nBIF |  | Validate Readiness Time Report Extended capabilities block | P2 | AG005.024 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
44 | NV48-PCIe-nBIF-040 | BAR allocation and Access | Fanny | nBIF | PCI configuration space memory mapped mirror address tests | PCI config space memory mapped mirror select test with write disabled | P2 | AG006.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
45 | NV48-PCIe-nBIF-040 | BAR allocation and Access | Fanny | nBIF |  | PCI config space memory mapped mirror select test with write enabled | P2 | AG006.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
46 | NV48-PCIe-nBIF-040 | BAR allocation and Access | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access using Memory Mapped Mirror Address with Write Enabled | P2 | AG006.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
47 | NV48-PCIe-nBIF-040 | BAR allocation and Access | Fanny | nBIF |  | Validate Basic PCI Configuration Space Access using Memory Mapped Mirror Address with Write Disabled | P2 | AG006.004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
48 | NV48-PCIe-nBIF-040 | BAR allocation and Access | Fanny | nBIF |  | PMCSR config space mirror test | P2 | AG006.005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
49 | NV48-PCIe-nBIF-039 | BAR resizing | Fanny | nBIF | PCI configuration space aperture size test | List Base Addresses | P2 | AG007.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
50 | NV48-PCIe-nBIF-018 | Resizable BAR enhancement for gfx's FB aperture | Fanny | nBIF |  | Validate Video Memory Aperture Sizes with 32b BAR | P2 | AG007.002 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
51 | NV48-PCIe-nBIF-018 | Resizable BAR enhancement for gfx's FB aperture | Fanny | nBIF |  | Validate Video Memory Aperture Sizes with 64b BAR | P2 | AG007.003 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
52 | NV48-PCIe-nBIF-062 | PCIE Function Aperture Size | Fanny | nBIF |  | Validate Register Aperture Sizes with 32b BAR | P2 | AG007.004 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
53 | NV48-PCIe-nBIF-062 | PCIE Function Aperture Size | Fanny | nBIF |  | Validate ROM Aperture size | P2 | AG007.006 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
54 | NV48-PCIe-nBIF-019 | Support Resizable for Doorbell Aper | Fanny | nBIF |  | Validate Doorbell Aperture Sizes with 32b BAR | P1 | AG007.007 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
55 | NV48-PCIe-nBIF-019 | Support Resizable for Doorbell Aper | Fanny | nBIF |  | Validate Doorbell Aperture Sizes with 64b BAR | P1 | AG007.008 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
56 | NV48-PCIe-nBIF-037 | I/O access control | Fanny | nBIF |  | PCI IO space BAR sanity check test | P1 | AG007.009 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
57 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF | PCI IO Mapped Register Read/Write tests | PCI I/O Mapped Register Access with 32b Writes and 32b Reads | P2 | AG008.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
58 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 16b Writes and 32b Reads | P2 | AG008.002 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
59 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 8b Writes and 32b Reads | P2 | AG008.003 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
60 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 32b Writes and 16b Reads | P2 | AG008.004 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
61 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 16b Writes and 16b Reads | P2 | AG008.005 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
62 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 8b Writes and 16b Reads | P2 | AG008.006 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
63 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 32b Writes and 8b Reads | P2 | AG008.007 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
64 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 16b Writes and 8b Reads | P2 | AG008.008 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
65 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI I/O Mapped Register Access with 8b Writes and 8b Reads | P2 | AG008.009 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
66 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI IO Mapped Register Access with I/O Access Disabled | P2 | AG008.010 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
67 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF | PCI Memory Mapped Register Read/Write tests | PCI Memory Mapped Register Access with 32b Writes and 32b Reads | P2 | AG009.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
68 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI Memory Mapped Register Access with 16b Writes and 32b Reads | P2 | AG009.002 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
69 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI Memory Mapped Register Access with 8b Writes and 32b Reads | P2 | AG009.003 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
70 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI Memory Mapped Register Access with 32b Writes and 16b Reads | P2 | AG009.004 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
71 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF |  | PCI Memory Mapped Register Access with 16b Writes and 16b Reads | P2 | AG009.005 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
72 | NV48-PCIe-nBIF-069 | Add normal RW registers for scratch usage by sw/fw | Fanny | nBIF |  | PCI Memory Mapped Register Access with 8b Writes and 16b Reads | P2 | AG009.006 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
73 | NV48-PCIe-nBIF-069 | Add normal RW registers for scratch usage by sw/fw | Fanny | nBIF |  | PCI Memory Mapped Register Access with 32b Writes and 8b Reads | P2 | AG009.007 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
74 | NV48-PCIe-nBIF-069 | Add normal RW registers for scratch usage by sw/fw | Fanny | nBIF |  | PCI Memory Mapped Register Access with 16b Writes and 8b Reads | P2 | AG009.008 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
75 | NV48-PCIe-nBIF-069 | Add normal RW registers for scratch usage by sw/fw | Fanny | nBIF |  | PCI Memory Mapped Register Access with 8b Writes and 8b Reads | P2 | AG009.009 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
76 | NV48-PCIe-nBIF-069 | Add normal RW registers for scratch usage by sw/fw | Fanny | nBIF |  | PCI Memory Mapped register access with Memory Access Disabled | P2 | AG009.010 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
77 | NV48-PCIe-nBIF-069 | Add normal RW registers for scratch usage by sw/fw | Fanny | nBIF |  | Memory Mapped register read/write with host aperture stresss test | P2 | AG009.012 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
78 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF | PCI Memory Mapped Video Memory Read/Write tests | PCI Memory Mapped Video Memory Access with 32b Writes and 32b Reads | P1 | AG010.001 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
79 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 16b Writes and 32b Reads | P1 | AG010.002 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
80 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 8b Writes and 32b Reads | P1 | AG010.003 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
81 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 32b Writes and 16b Reads | P1 | AG010.004 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
82 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 16b Writes and 16b Reads | P1 | AG010.005 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
83 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 8b Writes and 16b Reads | P1 | AG010.006 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
84 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 32b Writes and 8b Reads | P1 | AG010.007 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
85 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 16b Writes and 8b Reads | P1 | AG010.008 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
86 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Video Memory Access with 8b Writes and 8b Reads | P1 | AG010.009 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
87 | NV48-PCIe-nBIF-001 | Remote doorbell and doorbell remapping | Fanny | nBIF | PCI Memory Mapped Doorbell Read/Write tests | PCI Memory Mapped Doorbell Access with 32b Reads | P1 | AG011.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
88 | NV48-PCIe-nBIF-001 | Remote doorbell and doorbell remapping | Fanny | nBIF |  | PCI Memory Mapped Doorbell Access with 32b Writes | P1 | AG011.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
89 | NV48-PCIe-nBIF-002 | Early response and block doorbell per client | Fanny | nBIF |  | PCI Memory Mapped Doorbell Access with Self-ring 32b Read | P2 | AG011.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
90 | NV48-PCIe-nBIF-002 | Early response and block doorbell per client | Fanny | nBIF |  | PCI Memory Mapped Doorbell Access with Self-ring 32b Write | P2 | AG011.004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
91 | NV48-PCIe-nBIF-064 | HDP Flush and mmindex/data cross check | Fanny | nBIF | PCI Memory Mapped Indirect Register Read/Write tests | PCI Memory Mapped Indirect Register Access | P2 | AG012.001 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
92 | NV48-PCIe-nBIF-064 | HDP Flush and mmindex/data cross check | Fanny | nBIF |  | PCI Memory Mapped Direct Register Write and Indirect Register Read | P2 | AG012.002 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
93 | NV48-PCIe-nBIF-064 | HDP Flush and mmindex/data cross check | Fanny | nBIF |  | PCI Memory Mapped Indirect Register Write and Direct Register Read | P2 | AG012.003 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
94 | NV48-PCIe-nBIF-037 | I/O access control | Fanny | nBIF | PCI I/O Mapped Indirect Register Read/Write tests | PCI I/O Mapped Indirect Register Access | P1 | AG013.001 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
95 | NV48-PCIe-nBIF-037 | I/O access control | Fanny | nBIF |  | PCI I/O Mapped Direct Register Write and Indirect Register Read | P1 | AG013.002 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
96 | NV48-PCIe-nBIF-037 | I/O access control | Fanny | nBIF |  | PCI I/O Mapped Indirect Register Write and Memory Mapped Direct Register Read | P1 | AG013.003 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
97 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF | PCI Memory Mapped Indirect Video Memory Read/Write tests | PCI Memory Mapped Indirect Video Memory Access | P1 | AG014.001 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
98 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Direct Video Memory Write and Indirect Video Memory Read | P1 | AG014.002 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
99 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Indirect Video Memory Write and Memory Mapped Direct Video Memory Read | P1 | AG014.003 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
100 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF | PCI I/O Mapped Indirect Video Memory Read/Write tests | PCI I/O Mapped Indirect Video Memory Access | P1 | AG015.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
101 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI Memory Mapped Direct Video Memory Write and Indirect Video Memory Read | P1 | AG015.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
102 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCI I/O Mapped Indirect Video Memory Write and Memory Mapped Direct Video Memory Read | P1 | AG015.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
103 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF | PCI I/O Mapped PCIE Indirect Register Read/Write test | PCI I/O Mapped PCIE Indirect Register Access | P2 | AG016.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
104 | NV48-PCIe-nBIF-041 | Register Accesses | Fanny | nBIF | PCI Memory Mapped PCIE Indirect Register Read/Write test | PCI Memory Mapped PCIE Indirect Register Access | P2 | AG017.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
105 | NV48-PCIe-nBIF-010 | Link Quality check | Fanny | PCIE | PCIE link quality tests | PCIE Nak counter check initialize | P2 | AG020.003 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
106 | NV48-PCIe-nBIF-043 | Training Check (only DL_Active status bit) | Fanny | PCIE |  | PCIE Nak counter check test | P3 | AG020.004 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
107 | NV48-PCIe-nBIF-010 | Link Quality check | Fanny | PCIE |  | PCIE Link Quality check initialize | P2 | AG020.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
108 | NV48-PCIe-nBIF-043 | Training Check (only DL_Active status bit) | Fanny | PCIE |  | PCIE Link Quality check test | P3 | AG020.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
109 | NV48-PCIe-nBIF-078 | Training Check | Fanny | PCIE |  | PCIE Link Width Check | P2 | AG020.008 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
110 | NV48-PCIe-nBIF-078 | Training Check | Fanny | PCIE |  | PCIE Link Speed Check | P2 | AG020.010 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
111 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF | PCIE snoop tests | PCIE snoop transaction test | P1 | AG022.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
112 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCIE snoop transaction test, snooped source /w TX_SNR_CLEAR | P1 | AG022.004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
113 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | PCIE snoop transaction test, non-snooped source /w TX_SNR_CLEAR | P1 | AG022.006 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
114 | NV48-PCIe-nBIF-055 | AER | Fanny | nBIF |  | Endpoint Uncorrectable Error Capabilities Test | P2 | AG024.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
115 | NV48-PCIe-nBIF-055 | AER | Fanny | nBIF |  | Endpoint Correctable Error Capabilities Test | P2 | AG024.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
116 | NV48-PCIe-nBIF-055 | AER | Fanny | nBIF | PCIE Error Reporting tests | Single EP Basic Error Reporting Capabilities Test | P2 | AG026.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
117 | NV48-PCIe-nBIF-055 | AER | Fanny | nBIF |  | Single EP Advanced Error Reporting Capabilities Test | P2 | AG026.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
118 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF | Video Memory Read/Write Control tests | Direct Video Memory Access with FB Always ON | P1 | AG029.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
119 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Indirect Video Memory Access with FB Always ON | P1 | AG029.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
120 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Direct Video Memory Access with FB Read and Write ON | P1 | AG029.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
121 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Indirect Video Memory Access with FB Read and Write ON | P1 | AG029.004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
122 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Direct Video Memory Access with FB Read ON and FB Write OFF | P1 | AG029.005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
123 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Indirect Video Memory Access with FB Read ON and FB Write OFF | P1 | AG029.006 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
124 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Direct Video Memory Access with FB Read OFF and Dummy Data | P1 | AG029.007 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
125 | NV48-PCIe-nBIF-038 | Memory access control | Fanny | nBIF |  | Indirect Video Memory Access with FB Read OFF and Dummy Data | P1 | AG029.008 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
126 | NV48-PCIe-nBIF-039 | BAR resizing | Fanny | nBIF | PCIE Resizable BAR Capability tests | List PCIE resizable BAR capability block information | P2 | AG031.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
127 | NV48-PCIe-nBIF-039 | BAR resizing | Fanny | nBIF |  | PCIE resizable BAR size test (32b BAR) | P2 | AG031.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
128 | NV48-PCIe-nBIF-039 | BAR resizing | Fanny | nBIF |  | PCIE resizable BAR size test (64b BAR) | P2 | AG031.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
129 | NV48-PCIe-nBIF-053 | PWR budgeting | Fanny | nBIF |  | List PCIE power budget capability block information | P2 | AG032.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
130 | NV48-PCIe-nBIF-053 | PWR budgeting | Fanny | nBIF |  | PCIE power budget data validation | P2 | AG032.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
131 | NV48-PCIe-nBIF-053 | PWR budgeting | Fanny | nBIF |  | PCIE power budget capability validation | P2 | AG032.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
132 | NV48-PCIe-nBIF-023 | Multi-function support | Fanny | nBIF | Multifunction tests | PCI Multifunction Configuration Test | P2 | AG033.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
133 | NV48-PCIe-nBIF-023 | Multi-function support | Fanny | nBIF |  | PCI Unmapped Function with Error Reporting Disabled Test | P2 | AG033.003 | TServer | -use_kernel_driver=0 | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
134 | NV48-PCIe-nBIF-032 | Hot Reset | Fanny | nBIF | pcie_LinkResetTest | ASIC Reset Disable on Hot Reset test | P3 | AG038.004 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
135 | NV48-PCIe-nBIF-033 | Link Disable | Fanny | nBIF |  | ASIC Reset Disable on Link Disable Reset test | P2 | AG038.005 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
136 | NV48-PCIe-nBIF-065 | GPU reset finish indication(delta, per VF) | Fanny | nBIF |  | ASIC Reset Disable on Link Down Reset test | P2 | AG038.006 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
137 | NV48-PCIe-nBIF-030 | FLR (Func 0/1/2/??) | Fanny | nBIF | Function Level Reset (FLR) tests | FLR to function 0 (Video) with FLR enabled | P3 | AG043.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
138 | NV48-PCIe-nBIF-011 | Doorbell fence for VDDGFX | Fanny | nBIF | Doorbell Access Enable tests | Doorbell aperture read test with Doorbell Access Disabled | P2 | AG044.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
139 | NV48-PCIe-nBIF-011 | Doorbell fence for VDDGFX | Fanny | nBIF |  | Doorbell aperture read test with Doorbell Access Enabled | P2 | AG044.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
140 | NV48-PCIe-nBIF-020 | Doorbell sub-decoding to avoid multicast for doorbell trans in SOC15 | Fanny | nBIF |  | Doorbell aperture write test with Doorbell Access Disabled | P2 | AG044.003 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
141 | NV48-PCIe-nBIF-020 | Doorbell sub-decoding to avoid multicast for doorbell trans in SOC15 | Fanny | nBIF |  | Doorbell aperture write test with Doorbell Access Enabled | P2 | AG044.004 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
142 | NV48-PCIe-nBIF-036 | New RSMU_INDEX/DATA pair 0x50/0x54 | Fanny | nBIF | PCI SYSHUB Scratch Indirect Register Read/Write test | PCI SYSHUB Indirect Register Access | P2 | AG054.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
143 | NV48-PCIe-nBIF-067 | Expansion ROM Validation ECN | Fanny | nBIF | VBIOS ROM read performance tests | ROM aperture read test (1 byte) | P2 | AG055.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
144 | NV48-PCIe-nBIF-070 | ROM_OFFSET | Fanny | nBIF |  | ROM aperture read test (2 byte) | P2 | AG055.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
145 | NV48-PCIe-nBIF-070 | ROM_OFFSET | Fanny | nBIF |  | ROM aperture read test (4 byte) | P2 | AG055.003 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
146 | NV48-PCIe-nBIF-031 | Link Down | Fanny | PCIE | Switch Upstream Port Link reset test | ASIC Reset via Hot Reset test | P3 | AG056.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
147 | NV48-PCIe-nBIF-104 | PCIE link disable reset | Fanny | PCIE |  | ASIC Reset via Link Disable Reset test | P3 | AG056.002 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
148 | NV48-PCIe-nBIF-105 | PCIE link down reset | Fanny | PCIE |  | ASIC Reset via Link Down Reset test | P3 | AG056.003 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
149 | NV48-PCIe-nBIF-103 | PCIE hot reset | Fanny | nBIF | Switch Downstream Port Link reset test | ASIC Reset via Hot Reset test | P3 | AG057.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
150 | NV48-PCIe-nBIF-017 | Perf Counters | Fanny | nBIF | Slave Performance Counter test | Frame Buffer Read (32-bit) test | P2 | AG059.003 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
151 | NV48-PCIe-nBIF-017 | Perf Counters | Fanny | nBIF |  | Frame Buffer Write (32-bit) test | P2 | AG059.004 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
152 | NV48-PCIe-nBIF-017 | Perf Counters | Fanny | nBIF |  | SMN Read test | P2 | AG059.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
153 | NV48-PCIe-nBIF-017 | Perf Counters | Fanny | nBIF |  | SMN Write test | P2 | AG059.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
154 | NV48-PCIe-nBIF-036 | New RSMU_INDEX/DATA pair 0x50/0x54 | Fanny | nBIF | RSMU indirect register access test | RSMU Indirect Scratch register reading and writing | P2 | AG060.001,=,=1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
155 | NV48-PCIe-nBIF-068 | Common doorbell for SDMA | Fanny | nBIF | PCIE doorbell client test | PCI Memory Mapped Doorbell CP Write test | P2 | AG064.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
156 | NV48-PCIe-nBIF-068 | Common doorbell for SDMA | Fanny | nBIF |  | PCI Memory Mapped Doorbell SDMA Write test | P2 | AG064.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
157 | NV48-PCIe-nBIF-024 | Bus_master_en control | Fanny | nBIF | pcie_BusMasterEnableTest | bus master enable test with SDMA | P2 | AG065.001 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
158 | NV48-PCIe-nBIF-024 | Bus_master_en control | Fanny | nBIF |  | bus master disabled test with SDMA | P2 | AG065.002 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | Simnow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
159 | NV48-PCIe-nBIF-012 | NBIF_GFX_DOORBELL_SENT | Fanny | nBIF | NBIF_GFX_DOORBELL_SENT | GFX doorbell sent test | P2 | AG101.000 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
160 | NV48-PCIe-nBIF-099 | ASPM L1 | Fanny | PCIE | ASPM L1 | ASPM | P2 | AJ011.005 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
161 | NV48-PCIe-nBIF-101 | PCIE Performance counter | Fanny | PCIE | LC Performance Counter Test | LC Performance Counter Test | P2 | AJ013.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
162 | NV48-PCIe-nBIF-078 | Training Check | Fanny | PCIE | PCIE PHY Dynamic Link Speed Switching Test (Bridge Initiated) | Link speed change between Gen1 and Gen1 | P2 | AJ015.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
163 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | Link speed change between Gen1 and Gen2 | P1 | AJ015.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
164 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | Link speed change between Gen1 and Gen3 | P1 | AJ015.003 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
165 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen2 and Gen2 | P2 | AJ015.004 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
166 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | Link speed change between Gen2 and Gen3 | P1 | AJ015.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
167 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | Link speed change between Gen3 and Gen3 | P1 | AJ015.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
168 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE | PCIE standard Gen4 Link speed test | Link speed change between Gen1 and Gen4 (Bridge Initiated) | P1 | AJ015.007 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
169 | NV48-PCIe-nBIF-091 | Transmitter Precoding at 32.0 GT/s | Fanny | PCIE |  | Link speed change between Gen2 and Gen4 (Bridge Initiated) | P2 | AJ015.008 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
170 | NV48-PCIe-nBIF-091 | Transmitter Precoding at 32.0 GT/s | Fanny | PCIE |  | Link speed change between Gen3 and Gen4 (Bridge Initiated) | P2 | AJ015.009 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
171 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen4 and Gen4 (Bridge Initiated) | P2 | AJ015.010 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
172 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen1 and Gen5 (Bridge Initiated) | P2 | AJ015.011 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
173 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen2 and Gen5 (Bridge Initiated) | P2 | AJ015.012 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
174 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen3 and Gen5 (Bridge Initiated) | P2 | AJ015.013 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
175 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen4 and Gen5 (Bridge Initiated) | P2 | AJ015.014 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
176 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen5 and Gen5 (Bridge Initiated) | P2 | AJ015.015 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
177 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | Link speed change between Gen1 and Gen4 (Endpoint Initiated) | P1 | AJ016.007 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
178 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | Link speed change between Gen2 and Gen4 (Endpoint Initiated) | P1 | AJ016.008 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
179 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | Link speed change between Gen3 and Gen4 (Endpoint Initiated) | P1 | AJ016.009 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
180 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen4 and Gen4 (Endpoint Initiated) | P2 | AJ016.010 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
181 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen1 and Gen5 (Endpoint Initiated) | P2 | AJ016.011 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
182 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen2 and Gen5 (Endpoint Initiated) | P2 | AJ016.012 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
183 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen3 and Gen5 (Endpoint Initiated) | P2 | AJ016.013 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
184 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen4 and Gen5 (Endpoint Initiated) | P2 | AJ016.014 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
185 | NV48-PCIe-nBIF-076 | Forward Boot Gen1/2/3/4/5 | Fanny | PCIE |  | Link speed change between Gen5 and Gen5 (Endpoint Initiated) | P2 | AJ016.015 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
186 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE | PCIE PHY Dynamic Link Speed Switching Test (Endpoint Initiated) | EP initiated s/w link speed change between Gen1 and Gen1 | P1 | AJ016.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
187 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | EP initiated s/w link speed change between Gen1 and Gen2 | P1 | AJ016.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
188 | NV48-PCIe-nBIF-095 | Link Speed Renegotiation | Fanny | PCIE |  | EP initiated s/w link speed change between Gen1 and Gen3 | P1 | AJ016.003 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
189 | NV48-PCIe-nBIF-080 | Multi lane/port support (Only 1 port supported for GPU) | Fanny | PCIE |  | EP initiated s/w link speed change between Gen2 and Gen2 | P2 | AJ016.004 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
190 | NV48-PCIe-nBIF-080 | Multi lane/port support (Only 1 port supported for GPU) | Fanny | PCIE |  | EP initiated s/w link speed change between Gen2 and Gen3 | P2 | AJ016.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
191 | NV48-PCIe-nBIF-080 | Multi lane/port support (Only 1 port supported for GPU) | Fanny | PCIE |  | EP initiated s/w link speed change between Gen3 and Gen3 | P2 | AJ016.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
192 | NV48-PCIe-nBIF-094 | Link Width Reconfiguration | Fanny | PCIE |  | Link width change between x1 and x2 | P1 | AJ018.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
193 | NV48-PCIe-nBIF-094 | Link Width Reconfiguration | Fanny | PCIE |  | Link width change between x1 and x4 | P1 | AJ018.003 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
194 | NV48-PCIe-nBIF-094 | Link Width Reconfiguration | Fanny | PCIE |  | Link width change between x1 and x8 | P1 | AJ018.004 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
195 | NV48-PCIe-nBIF-094 | Link Width Reconfiguration | Fanny | PCIE |  | Link width change between x1 and x16 | P1 | AJ018.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
196 | NV48-PCIe-nBIF-094 | Link Width Reconfiguration | Fanny | PCIE |  | Link width change between x2 and x4 | P1 | AJ018.008 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
197 | NV48-PCIe-nBIF-094 | Link Width Reconfiguration | Fanny | PCIE |  | Link width change between x2 and x8 | P1 | AJ018.009 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
198 | NV48-PCIe-nBIF-094 | Link Width Reconfiguration | Fanny | PCIE |  | Link width change between x2 and x16 | P1 | AJ018.011 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
199 | NV48-PCIe-nBIF-097 | Link Bandwidth Management Status and Link Autonomous Bandwidth Status | Fanny | PCIE |  | Link width change between x4 and x8 | P2 | AJ018.013 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
200 | NV48-PCIe-nBIF-097 | Link Bandwidth Management Status and Link Autonomous Bandwidth Status | Fanny | PCIE |  | Link width change between x4 and x16 | P2 | AJ018.015 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
201 | NV48-PCIe-nBIF-097 | Link Bandwidth Management Status and Link Autonomous Bandwidth Status | Fanny | PCIE |  | Link width change between x8 and x16 | P2 | AJ018.018 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 | Splinter + XTX board + noKILL_noBYPASS_EQ_G281_BU_PA_XTX_16GB_NAVI48_Baseline_BRP004_93888_Link_Reset_debug3_PMFW_Patch.sbin
202 | NV48-PCIe-nBIF-082 | Standard Gen3 Equalization | Fanny | PCIE | PCIE Equalization Test | PCIE Gen3 Link Equalization Test | P1 | AJ019.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
203 | NV48-PCIe-nBIF-083 | Standard Gen4 Equalization | Fanny | PCIE |  | PCIE Gen4 Link Equalization Test | P2 | AJ019.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
204 | NV48-PCIe-nBIF-089 | Equalization with Phase 2 and Phase 3 | Fanny | PCIE |  | PCIE Gen3 Link Equalization Test | P2 | AJ019.003 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
205 | NV48-PCIe-nBIF-088 | equalization bypass to highest rate -- PCIe Compliant | Fanny | PCIE |  | PCIE Gen4 Link Equalization Test | P2 | AJ019.004 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
206 | NV48-PCIe-nBIF-084 | Standard Gen5 Equalization | Fanny | PCIE |  | PCIE Gen5 Link Equalization Test | P2 | AJ019.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
207 | NV48-PCIe-nBIF-090 | Equalization with Phase 2 (USP) or Phase 3 (DSP) Bypassed (3.17.2.15) | Fanny | PCIE | 1 Symbol Per Clock / 2 Symbol Per Clock Switch | SPC mode change between Gen1 1SPC and Gen2 1SPC | P2 | AJ020.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
208 | NV48-PCIe-nBIF-098 | SPC tests | Fanny | PCIE |  | SPC mode change between Gen1 1SPC and Gen2 2SPC | P2 | AJ020.002 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
209 | NV48-PCIe-nBIF-098 | SPC tests | Fanny | PCIE |  | SPC mode change between Gen1 2SPC and Gen2 1SPC | P2 | AJ020.003 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
210 | NV48-PCIe-nBIF-098 | SPC tests | Fanny | PCIE |  | SPC mode change between Gen1 2SPC and Gen2 2SPC | P2 | AJ020.004 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
211 | NV48-PCIe-nBIF-098 | SPC tests | Fanny | PCIE |  | SPC mode change between Gen2 1SPC and Gen2 2SPC | P2 | AJ020.007 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
212 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR001.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
213 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR001.002 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
214 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR001.003 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
215 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR001.004 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
216 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR001.005 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
217 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR001.006 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
218 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR001.007 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
219 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE | Transfer Rate using DMA FILL operation | Write to FB | P2 | CR008.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
220 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | Write to AGP | P2 | CR008.002 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
221 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | Write to PCI | P2 | CR008.003 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
222 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE | Transfer Rate using CPDMA | FB to FB | P2 | CR010.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
223 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | AGP to FB | P2 | CR010.002 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
224 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | FB to AGP | P2 | CR010.003 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
225 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | AGP to AGP | P2 | CR010.004 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
226 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to FB | P2 | CR010.005 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
227 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | FB to PCI | P2 | CR010.006 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
228 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | PCI to PCI | P2 | CR010.007 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
229 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE | Transfer Rate using sDMA0 and sDMA1 operations | sDMA0 and sDMA1: FB to FB | P2 | CR015.001 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
230 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE | Transfer Rate using sDMA0 and sDMA1 operations | sDMA0 and sDMA1: AGP to FB | P2 | CR015.002 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
231 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE | Transfer Rate using sDMA0 and sDMA1 operations | sDMA0 and sDMA1: FB to AGP | P2 | CR015.003 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
232 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE | Transfer Rate using sDMA0 and sDMA1 operations | sDMA0 and sDMA1: AGP to AGP | P2 | CR015.004 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
233 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | sDMA0 and sDMA1: PCI to FB | P2 | CR015.005 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
234 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | sDMA0 and sDMA1: FB to PCI | P2 | CR015.006 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
235 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | sDMA0 and sDMA1: PCI to PCI | P2 | CR015.007 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
236 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | sDMA0: FB to PCI, sDMA1: PCI to FB | P2 | CR015.008 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
237 | NV48-PCIe-nBIF-054 | Data Throughput | Fanny | PCIE |  | sDMA0: FB to AGP, sDMA1: AGP to FB | P2 | CR015.009 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
238 | NV48-PCIe-nBIF-025 | Atomic Op | Fanny | PCIE |  | pcie atomic test | P2 | AG902.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
239 | NV48-PCIe-nBIF-025 | Atomic Op | Fanny | PCIE |  | pcie atomic test | P2 | AG902.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
240 | NV48-PCIe-nBIF-025 | Atomic Op | Fanny | PCIE |  | pcie atomic test | P2 | AG902.3 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
241 | NV48-PCIe-nBIF-025 | Atomic Op | Fanny | PCIE |  | pcie atomic test | P2 | AG902.4 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
242 | NV48-PCIe-nBIF-025 | Atomic Op | Fanny | PCIE |  | pcie atomic test | P2 | AG902.5 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
243 | NV48-PCIe-nBIF-025 | Atomic Op | Fanny | PCIE |  | pcie atomic interrupt test | P2 | AG904.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | SimNow | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
244 | NV48-PCIe-nBIF-061 | USB in s5 domain | Fanny | nBIF |  | USB in s5 domain | P2 | AG901.1 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  | 0 |  | 0
245 | NV48-PCIe-nBIF-061 | USB in s5 domain | Fanny | nBIF |  | USB in s5 domain | P2 | AG901.2 | TServer |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  | 0 |  | 0
246 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf0 | P3 | AG550.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
247 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf0 | P3 | AG550.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
248 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf0 | P3 | AG550.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
249 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf0 | P3 | AG550.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
250 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf1 | P3 | AG551.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
251 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf1 | P3 | AG551.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
252 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf1 | P3 | AG551.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
253 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf1 | P3 | AG551.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
254 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf2 | P3 | AG552.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
255 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf2 | P3 | AG552.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
256 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf2 | P3 | AG552.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
257 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf2 | P3 | AG552.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
258 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf3 | P3 | AG563.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
259 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf3 | P3 | AG563.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
260 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for BIF Leaf3 | P3 | AG563.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
261 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for BIF Leaf3 | P3 | AG563.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
262 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf0 | P3 | AG553.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
263 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf0 | P3 | AG553.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
264 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf0 | P3 | AG553.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
265 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf0 | P3 | AG553.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
266 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf1 | P3 | AG554.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
267 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf1 | P3 | AG554.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
268 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf1 | P3 | AG554.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
269 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf1 | P3 | AG554.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
270 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf2 | P3 | AG555.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
271 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf2 | P3 | AG555.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
272 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf2 | P3 | AG555.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
273 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf2 | P3 | AG555.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
274 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf3 | P3 | AG556.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
275 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf3 | P3 | AG556.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
276 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf3 | P3 | AG556.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
277 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf3 | P3 | AG556.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
278 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf4 | P3 | AG557.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
279 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf4 | P3 | AG557.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
280 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf4 | P3 | AG557.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
281 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf4 | P3 | AG557.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1
282 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf5 | P3 | AG558.001 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
283 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf5 | P3 | AG558.002 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
284 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject PARITY error by PCIE debug bit for system Leaf5 | P3 | AG558.005 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
285 | NV48-PCIe-nBIF-106 | Ras | Fanny | nBIF |  | RAS controller test inject POISON error by PCIE debug bit for system Leaf5 | P3 | AG558.006 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
286 | NV48-PCIe-nBIF-003 | Hot-Plug Detect PME in D3 State for GFX Function | Fanny | nBIF |  | Scandump Over MMIO Support | P2 | AG120.001 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
287 | NV48-PCIe-nBIF-005 | Scandump Over MMIO Support | Fanny | nBIF |  | GUI flush merge sequence | P2 | AG121.001 | TNG |  | 1 | 1 | New | 1 | 1 | 1 |  | 0 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
288 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.001 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
289 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.002 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
290 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.003 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
291 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.004 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
292 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.005 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
293 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.006 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
294 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.007 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
295 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.008 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
296 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.009 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
297 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.010 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
298 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.011 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
299 | NV48-PCIe-nBIF-107 | SDP Ras | Fanny | nBIF |  | SDP IOHUB_ORIG RDRSPDATA_POISON error injection | P2 | AG700.012 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0