## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | EX-FEAT-009 | Tick-Counter |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
1 | EX-FEAT-003 | VCO Change/Fractional Divider/Multiplier |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
2 | EX-FEAT-075 | DPM Signal |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
3 | EX-FEAT-022 | Fcstate-Pstate change |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
4 | EX-FEAT-168 | Voltage control |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
5 | EX-FEAT-170 | RLC MSG box |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
6 | EX-FEAT-119 | AVFS VDDCR Soc domain |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK13
7 | EX-FEAT-117 | SPI Capability |  | CLK | DPM | DPM (all PPCLKs ) | P2 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK3
8 | EX-FEAT-061 | SMN address in Monolithic |  | CLK | DPM | DPM (all PPCLKs ) | P1 | PM80.12 | TNG | autodpmtog | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
9 | EX-FEAT-037 | Lx6 |  | MP1 | SMU sanity Check | [MP1] Tensilica | P1 | PM080.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0
10 | EX-FEAT-071 | AXI and Register Interface |  | MP1 | SMU sanity Check | [MP1] Tensilica | P1 | PM080.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0
11 | EX-FEAT-049 | AXI Interconnect |  | MP1 | SMU sanity Check | [MP1] Tensilica | P1 | PM080.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0
12 | EX-FEAT-040 | MP1_FIRMWARE_FLAGS register |  | MP1 | SMU sanity Check | [MP1] Tensilica | P1 | PM080.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0
13 | EX-FEAT-037 | Lx6 |  | MP1 | SMU sanity Check | [MP1] Tensilica-indirect sram access | P1 | PM080.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
14 | EX-FEAT-071 | AXI and Register Interface |  | MP1 | SMU sanity Check | [MP1] Tensilica-indirect sram access | P1 | PM080.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
15 | EX-FEAT-049 | AXI Interconnect |  | MP1 | RSMU AXI path | [Mp1]AXI and Register Interface | P1 | PM080.05 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0 |  | wk-4
16 | EX-FEAT-059 | Register Access SMN Apertures |  | MP1 | RSMU AXI path | [Mp1]AXI and Register Interface | P3 | PM080.05 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0 |  | wk-4
17 | EX-FEAT-139 | Temperature HW CTF Temp Sel |  | THM | THM | Critical Temperature Fault check | P1 | PM013.008 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
18 | EX-FEAT-140 | Thermal Trigger - temperature is higher than THM.GNB_TEMP_THRESHOLD |  | THM | THM | Critical Temperature Fault check | P1 | PM013.008 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
19 | EX-FEAT-128 | Signal going to PLL and SVI3 -> HW CTF |  | THM | THM | Critical Temperature Fault check | P2 | PM013.008 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
20 | EX-FEAT-158 | TSEN-CTF |  | THM | THM | Critical Temperature Fault check | P1 | PM013.008 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
21 | EX-FEAT-142 | TSEN Mission Mod |  | THM | THM | TSEN | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0
22 | EX-FEAT-145 | SMU<->CTSEN Interface |  | THM | THM | TSEN | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0
23 | EX-FEAT-144 | SMU TSEN Initialization Sequence |  | THM | THM | TSEN | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0
24 | EX-FEAT-134 | External Temp sensing /Skin temp |  | THM | THM | TSEN | P2 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0
25 | EX-FEAT-091 | Telemetry aggregation |  | MP1 | Data-Logging | Monitor_perf=thermal_metrics | P1 | PM80.12 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
26 | EX-FEAT-035 | DMA |  | MP1 | Data-Logging | agmlog | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 1 | 1 |  |  |  | 0
27 | EX-FEAT-067 | MMHUB TLB Mapping |  | MP1 | Data-Logging | agmlog | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 1 | 1 |  |  |  | 0
28 | EX-FEAT-049 | AXI Interconnect |  | MP1 | Data-Logging | agmlog | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 1 | 1 |  |  |  | 0
29 | EX-FEAT-122 | PSM |  | MP1 | Data-Logging | psmlogging | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0
30 | EX-FEAT-123 | PSM on VDDSOC |  | MP1 | Data-Logging | psmlogging | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0
31 | EX-FEAT-019 | Fcstate - Test check Functionality |  | MP1 | SOC ULV | SOC ULV | P2 | PM80.808 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
32 | EX-FEAT-019 | Fcstate - Test check Functionality |  | CLK | CLK-DPM | autodpm | P2 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
33 | EX-FEAT-022 | Fcstate-Pstate change |  | CLK | CLK-DPM | autodpm | P1 | PM80.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
34 | EX-FEAT-003 | VCO Change/Fractional Divider/Multiplier |  | MP1 | CLK-DPM | SOC CLK DPM:force | P1 | PM20.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
35 | EX-FEAT-009 | Tick-Counter |  | MP1 | CLK-DPM | SOC CLK DPM:force | P1 | PM20.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
36 | EX-FEAT-075 | DPM Signal |  | MP1 | CLK-DPM | SOC CLK DPM:force | P1 | PM20.1 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
37 | EX-FEAT-020 | VCN IP sideband to control VCN clock via VCN IP |  | MP1 | CLK-DPM | MM CLK DPM:force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
38 | EX-FEAT-003 | VCO Change/Fractional Divider/Multiplier |  | MP1 | CLK-DPM | MM CLK DPM:force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
39 | EX-FEAT-009 | Tick-Counter |  | MP1 | CLK-DPM | MM CLK DPM:force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
40 | EX-FEAT-075 | DPM Signal |  | MP1 | CLK-DPM | MM CLK DPM:force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
41 | EX-FEAT-165 | Fan Zero RPM Mode |  | THM | FAN | 0-rpm | P1 | PM14.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
42 | EX-FEAT-159 | Fan Dynamic Mode |  | THM | FAN | 0-rpm | P1 | PM14.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
43 | EX-FEAT-163 | Fan Static PWM Mode |  | THM | FAN | 0-rpm | P1 | PM14.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
44 | EX-FEAT-164 | Fan Static RPM Mode |  | THM | FAN | 0-rpm | P1 | PM14.11 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
45 | EX-FEAT-163 | Fan Static PWM Mode |  | THM | FAN | fan-rpm-report | P1 | PM14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
46 | EX-FEAT-164 | Fan Static RPM Mode |  | THM | FAN | fan-rpm-report | P1 | PM14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
47 | EX-FEAT-165 | Fan Zero RPM Mode |  | THM | FAN | fan-rpm-report | P1 | PM14.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
48 | EX-FEAT-134 | External Temp sensing /Skin temp |  | THM | OOB | SMBUS Out-of-Band Management | P2 | PM13.16 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
49 | EX-FEAT-135 | SB-AXI (SMBUS Reading |  | THM | OOB | SMBUS Out-of-Band Management | P1 | PM13.16 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
50 | EX-FEAT-072 | Check inbout/outbound register access |  | MP1 | SMN-IF | Message Hub | P1 | PM80.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 0 |  | 1 | 1 |  |  |  | 0
51 | EX-FEAT-103 | High Speed I2c |  | SMUIO | I2C | read e2prom | P1 | PM80.993 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
52 | EX-FEAT-104 | I2C Done interrupt to MP1 |  | SMUIO | I2C | read e2prom | P1 | PM80.993 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
53 | EX-FEAT-106 | Check I2C Communication for I2C Controller Instance |  | SMUIO | I2C | read e2prom | P2 | PM80.993 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 0 |  | 0 |  |  |  |  | 0
54 | EX-FEAT-178 | IMU Ucode loading |  | IMU | IMU | IMU Ucode loading | P1 | PM074.03 | Tserver |  | 1 | 1 | New | 1 | 1 | 1 | EMU | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0
55 | EX-FEAT-157 | TSEN-read -RDI |  | THM | THM | TSEN-read -RDI | P2 | PM13.33 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK8
56 | EX-FEAT-170 | RLC MSG box |  | IMU | IMU | RLC MSG Box | P1 | PM80.12 | Tserver |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5