## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | NV4x-MTAG-0006 | DF4.0 MemClear |  | DCQ |  | Full FB fill - HDP, CPDMA | P2 | umc1.1,umc1.2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | AB+1wk
1 | UMCRTG-IP10-24 | [GDDR6] Supported DRAM density |  | DCQ |  | Full FB fill - CPDMA/SDMA | P1 | umc1.4 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | AB+1wk
2 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Full FB fill - Compute Shader | P1 | umc1.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | AB+4wk
3 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Write Only | P1 | umc1.820,umc1.822 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | AB+3wk
4 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Read Only | P1 | umc1.821,umc1.823 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | AB+3wk
5 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Compute Shader Read/Compare | P1 | umc1.825 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
6 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | Memory Cell Pattern | P1 | umc375.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
7 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | Memory Cell Pattern using SDMA | P1 | umc381.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
8 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | HDP version | P1 | umc3.1,umc3.2,umc3.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
9 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CP-DMA version | P1 | umc5.1,umc5.2,umc5.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
10 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CP-DMA/MCB version | P1 | umc6.1,umc6.2,umc6.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
11 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CB version | P1 | umc7.1,umc7.2,umc7.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
12 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CB/MCB version | P1 | umc8.1,umc8.2,umc8.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
13 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | DRMDMA version | P1 | umc24.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
14 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | DRMDMA/MCB version | P1 | umc25.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
15 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | HDP version | P1 | umc9.1,umc9.2,umc9.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
16 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CP-DMA version | P1 | umc10.1,umc10.2,umc10.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
17 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CP-DMA/MCB version | P1 | umc11.1,umc11.2,umc11.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
18 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CB version | P1 | umc12.1,umc12.2,umc12.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
19 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CB/MCB version | P1 | umc13.1,umc13.2,umc13.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
20 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit | P1 | umc369.2,umc369.3,umc369.5,umc369.6,umc369.8,umc369.9,umc369.11,umc369.12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 7 | 7 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | AB+4wk
21 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Randmask | P1 | umc370.2,umc370.3,umc370.5,umc370.6,umc370.8,umc370.9,umc370.11,umc370.12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 6 | 6 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | AB+4wk
22 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Randbit | P1 | umc371.2,umc371.3,umc371.5,umc371.6,umc371.8,umc371.9,umc371.11,umc371.12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 6 | 6 |  |  |  | 1 |  | 8 | 8 |  |  |  | 1 |  | AB+4wk
23 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit with Nominal DC SSO | P1 | umc376.6-15 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 |  | 10 | 10 |  |  |  | 1 |  | AB+4wk
24 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit 128-bit SSO | P1 | umc382 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 90 | Legacy | 1 | 90 | 1 | N-1 | 90 | 90 | 90 |  |  |  | 1 |  | 90 | 90 |  |  |  | 1 |  | AB+4wk
25 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit with Mask @16bpp | P1 | umc378 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 60 | Legacy | 1 | 60 | 1 | N-1 | 60 | 60 | 60 |  |  |  | 1 |  | 60 | 60 |  |  |  | 1 |  | AB+4wk
26 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit with Mask @32bpp | P1 | umc379 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 124 | Legacy | 1 | 124 | 1 | N-1 | 124 | 124 | 124 |  |  |  | 1 |  | 124 | 124 |  |  |  | 1 |  | AB+4wk
27 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | CP-DMA version | P1 | umc372 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
28 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | SDMA version | P1 | umc380 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
29 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle with PRBS pattern | P1 | umc383.1-4,umc383.10-19 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
30 | NAVI40-IPNAVI4x-22 | DPM (Dynamic Power Management) on UCLK |  | SPAZ |  | UMC301 - Moving Blt Colorbar | P1 | umc301.2,umc301.3,umc301.5-7,umc301.9,umc301.11-13,umc301.21,umc301.22,umc301.24,umc301.25 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Delta | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 |  | 13 | 13 |  |  |  | 1 |  | AB+5wk
31 | UMCRTG-IP10-35 | [GDDR6] DPM State support for UCLK |  | SPAZ |  | UMC302 - Moving Blt Walkbit | P2 | umc302.2,umc302.3,umc302.5,umc302.6,umc302.7,umc302.9,umc302.11,umc302.12,umc302.13,umc302.21,umc302.22,umc302.24,umc302.25,umc302.101,umc302.102,umc302.103,umc302.104,umc302.105,umc302.501,umc302.502,umc302.503,umc302.504,umc302.505,umc302.511,umc302.512,umc302.513,umc302.514,umc302.515,umc302.551,umc302.552,umc302.553,umc302.554,umc302.555,umc302.561,umc302.562,umc302.563,umc302.564,umc302.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 |  | 38 | 38 |  |  |  | 1 |  | AB+3wk
32 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC303 – Moving Blt Walkpat | P1 | umc303.2,umc303.3,umc303.5,umc303.6,umc303.7,umc303.9,umc303.11,umc303.12,umc303.13,umc303.21,umc303.22,umc303.24,umc303.25,umc303.101,umc303.102,umc303.103,umc303.104,umc303.105,umc303.301,umc303.302,umc303.303,umc303.304,umc303.305 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 |  | 23 | 23 |  |  |  | 1 |  | AB+4wk
33 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC304 – Moving Blt Maskpat | P1 | umc304.2,umc304.3,umc304.5,umc304.6,umc304.8,umc304.9,umc304.11,umc304.12,umc304.101,umc304.201,umc304.301,umc304.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | AB+4wk
34 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC305 – Moving Blt Randbit | P1 | umc305.2,umc305.3,umc305.5,umc305.6,umc305.7,umc305.9,umc305.11,umc305.12,umc305.13,umc305.21,umc305.22,umc305.24,umc305.25,umc305.101,umc305.102,umc305.103,umc305.104,umc305.105,umc305.201,umc305.202,umc305.203,umc305.204,umc305.205,umc305.301,umc305.302,umc305.303,umc305.304,umc305.305,umc305.401,umc305.402,umc305.403,umc305.404,umc305.405,umc305.501,umc305.502,umc305.503,umc305.504,umc305.505,umc305.511,umc305.512,umc305.513,umc305.514,umc305.515,umc305.551,umc305.552,umc305.553,umc305.554,umc305.555,umc305.561,umc305.562,umc305.563,umc305.564,umc305.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
35 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC306 – Moving Blt Randmask | P1 | umc306.2,umc306.3,umc306.5,umc306.6,umc306.8,umc306.9,umc306.11,umc306.12,umc306.101,umc306.201,umc306.301,umc306.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
36 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC307 - Horizontal Blt Colorbar | P1 | umc307.2,umc307.3,umc307.5,umc307.6,umc307.7,umc307.9,umc307.11,umc307.12,umc307.13,umc307.21,umc307.22,umc307.24,umc307.25 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | AB+4wk
37 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC308 - Horizontal Blt Walkbit | P1 | umc308.2,umc308.3,umc308.5,umc308.6,umc308.7,umc308.9,umc308.11,umc308.12,umc308.13,umc308.21,umc308.22,umc308.24,umc308.25,umc308.101,umc308.102,umc308.103,umc308.104,umc308.105,umc308.501,umc308.502,umc308.503,umc308.504,umc308.505,umc308.511,umc308.512,umc308.513,umc308.514,umc308.515,umc308.551,umc308.552,umc308.553,umc308.554,umc308.555,umc308.561,umc308.562,umc308.563,umc308.564,umc308.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
38 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC309 - Horizontal Blt Walkpat | P1 | umc309.2,umc309.3,umc309.5,umc309.6,umc309.7,umc309.9,umc309.11,umc309.12,umc309.13,umc309.21,umc309.22,umc309.24,umc309.25,umc309.101,umc309.102,umc309.103,umc309.104,umc309.105,umc309.301,umc309.302,umc309.303,umc309.304,umc309.305 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
39 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC310 - Horizontal Blt Maskpat | P1 | umc310.2,umc310.3,umc310.5,umc310.6,umc310.8,umc310.9,umc310.11,umc310.12,umc310.101,umc310.201,umc310.301,umc310.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
40 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC311 - Horizontal Blt Randbit | P1 | umc311.2,umc311.3,umc311.5,umc311.6,umc311.7,umc311.9,umc311.11,umc311.12,umc311.13,umc311.21,umc311.22,umc311.24,umc311.25,umc311.101,umc311.102,umc311.103,umc311.104,umc311.105,umc311.201,umc311.202,umc311.203,umc311.204,umc311.205,umc311.301,umc311.302,umc311.303,umc311.304,umc311.305,umc311.401,umc311.402,umc311.403,umc311.404,umc311.405,umc311.501,umc311.502,umc311.503,umc311.504,umc311.505,umc311.511,umc311.512,umc311.513,umc311.514,umc311.515,umc311.551,umc311.552,umc311.553,umc311.554,umc311.555,umc311.561,umc311.562,umc311.563,umc311.564,umc311.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
41 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC312 - Horizontal Blt Randmask | P1 | umc312.2,umc312.3,umc312.5,umc312.6,umc312.8,umc312.9,umc312.11,umc312.12,umc312.101,umc312.201,umc312.301,umc312.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
42 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC313 - Diagonal Blt Colorbar | P1 | umc313.2,umc313.3,umc313.5,umc313.6,umc313.7,umc313.9,umc313.11,umc313.12,umc313.13,umc313.21,umc313.22,umc313.24,umc313.25 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
43 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC314 - Diagonal Blt Walkbit | P1 | umc314.2,umc314.3,umc314.5,umc314.6,umc314.7,umc314.9,umc314.11,umc314.12,umc314.13,umc314.21,umc314.22,umc314.24,umc314.25,umc314.101,umc314.102,umc314.103,umc314.104,umc314.105,umc314.501,umc314.502,umc314.503,umc314.504,umc314.505,umc314.511,umc314.512,umc314.513,umc314.514,umc314.515,umc314.551,umc314.552,umc314.553,umc314.554,umc314.555,umc314.561,umc314.562,umc314.563,umc314.564,umc314.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
44 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC315 - Diagonal Blt Walkpat | P1 | umc315.2,umc315.3,umc315.5,umc315.6,umc315.7,umc315.9,umc315.11,umc315.12,umc315.13,umc315.21,umc315.22,umc315.24,umc315.25,umc315.101,umc315.102,umc315.103,umc315.104,umc315.105,umc315.301,umc315.302,umc315.303,umc315.304,umc315.305 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
45 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC316 - Diagonal Blt Maskpat | P1 | umc316.2,umc316.3,umc316.5,umc316.6,umc316.8,umc316.9,umc316.11,umc316.12,umc316.101,umc316.201,umc316.301,umc316.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
46 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC317 - Diagonal Blt Randbit | P1 | umc317.2,umc317.3,umc317.5,umc317.6,umc317.7,umc317.9,umc317.11,umc317.12,umc317.13,umc317.21,umc317.22,umc317.24,umc317.25,umc317.101,umc317.102,umc317.103,umc317.104,umc317.105,umc317.201,umc317.202,umc317.203,umc317.204,umc317.205,umc317.301,umc317.302,umc317.303,umc317.304,umc317.305,umc317.401,umc317.402,umc317.403,umc317.404,umc317.405,umc317.501,umc317.502,umc317.503,umc317.504,umc317.505,umc317.511,umc317.512,umc317.513,umc317.514,umc317.515,umc317.551,umc317.552,umc317.553,umc317.554,umc317.555,umc317.561,umc317.562,umc317.563,umc317.564,umc317.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
47 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC318 - Diagonal Blt Randmask | P1 | umc318.2,umc318.3,umc318.5,umc318.6,umc318.8,umc318.9,umc318.11,umc318.12,umc318.101,umc318.201,umc318.301,umc318.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
48 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC319 - Random Blt Colorbar | P1 | umc319.2,umc319.3,umc319.5,umc319.6,umc319.7,umc319.9,umc319.11,umc319.12,umc319.13,umc319.21,umc319.22,umc319.24,umc319.25 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
49 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC320 - Random Blt Walkbit | P1 | umc320.2,umc320.3,umc320.5,umc320.6,umc320.7,umc320.9,umc320.11,umc320.12,umc320.13,umc320.21,umc320.22,umc320.24,umc320.25,umc320.101,umc320.102,umc320.103,umc320.104,umc320.105,umc320.501,umc320.502,umc320.503,umc320.504,umc320.505,umc320.511,umc320.512,umc320.513,umc320.514,umc320.515,umc320.551,umc320.552,umc320.553,umc320.554,umc320.555,umc320.561,umc320.562,umc320.563,umc320.564,umc320.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
50 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC320 - Random Blt WalkPat | P1 | umc321.2,umc321.3,umc321.5,umc321.6,umc321.7,umc321.9,umc321.11,umc321.12,umc321.13,umc321.21,umc321.22,umc321.24,umc321.25,umc321.101,umc321.102,umc321.103,umc321.104,umc321.105,umc321.301,umc321.302,umc321.303,umc321.304,umc321.305 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | Emulator | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
51 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC322 - Random Blt Maskpat | P1 | umc322.2,umc322.3,umc322.5,umc322.6,umc322.8,umc322.9,umc322.11,umc322.12,umc322.101,umc322.201,umc322.301,umc322.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
52 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC323 - Random Blt Randbit | P1 | umc323.2,umc323.3,umc323.5,umc323.6,umc323.7,umc323.9,umc323.11,umc323.12,umc323.13,umc323.21,umc323.22,umc323.24,umc323.25,umc323.101,umc323.102,umc323.103,umc323.104,umc323.105,umc323.201,umc323.202,umc323.203,umc323.204,umc323.205,umc323.301,umc323.302,umc323.303,umc323.304,umc323.305,umc323.401,umc323.402,umc323.403,umc323.404,umc323.405,umc323.501,umc323.502,umc323.503,umc323.504,umc323.505,umc323.511,umc323.512,umc323.513,umc323.514,umc323.515,umc323.551,umc323.552,umc323.553,umc323.554,umc323.555,umc323.561,umc323.562,umc323.563,umc323.564,umc323.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
53 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC324 - Random Blt Randmask | P1 | umc324.2,umc324.3,umc324.5,umc324.6,umc324.8,umc324.9,umc324.11,umc324.12,umc324.101,umc324.201,umc324.301,umc324.401 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
54 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC210 - Vertical Blt Colorbar | P1 | umc210.2,umc210.3,umc210.5,umc210.6,umc210.7,umc210.9,umc210.11,umc210.12,umc210.13,umc210.21,umc210.22,umc210.24,umc210.25 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
55 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC211 - Vertical Blt Walkbit | P1 | umc211.2,umc211.3,umc211.5,umc211.6,umc211.7,umc211.9,umc211.11,umc211.12,umc211.13,umc211.21,umc211.22,umc211.24,umc211.25,umc211.101,umc211.102,umc211.103,umc211.104,umc211.105,umc211.501,umc211.502,umc211.503,umc211.504,umc211.505,umc211.511,umc211.512,umc211.513,umc211.514,umc211.515,umc211.551,umc211.552,umc211.553,umc211.554,umc211.555,umc211.561,umc211.562,umc211.563,umc211.564,umc211.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
56 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC212 - Vertical Blt Walkpat | P1 | umc212.2,umc212.3,umc212.5,umc212.6,umc212.7,umc212.9,umc212.11,umc212.12,umc212.13,umc212.21,umc212.22,umc212.24,umc212.25,umc212.101,umc212.102,umc212.103,umc212.104,umc212.105,umc212.301,umc212.302,umc212.303,umc212.304,umc212.305 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
57 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC213 - Vertical Blt Maskpat | P1 | umc213.2,umc213.3,umc213.5,umc213.6,umc213.8,umc213.9,umc213.11,umc213.12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
58 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC214 - Vertical Blt Randbit | P1 | umc214.2,umc214.3,umc214.5,umc214.6,umc214.7,umc214.9,umc214.11,umc214.12,umc214.13,umc214.21,umc214.22,umc214.24,umc214.25,umc214.101,umc214.102,umc214.103,umc214.104,umc214.105,umc214.201,umc214.202,umc214.203,umc214.204,umc214.205,umc214.301,umc214.302,umc214.303,umc214.304,umc214.305,umc214.401,umc214.402,umc214.403,umc214.404,umc214.405,umc214.501,umc214.502,umc214.503,umc214.504,umc214.505,umc214.511,umc214.512,umc214.513,umc214.514,umc214.515,umc214.551,umc214.552,umc214.553,umc214.554,umc214.555,umc214.561,umc214.562,umc214.563,umc214.564,umc214.565 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
59 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC215 - Vertical Blt Randmask | P1 | umc215.2,umc215.3,umc215.5,umc215.6,umc215.8,umc215.9,umc215.11,umc215.12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
60 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC216 - Vertical Blt SSOmask | P1 | umc216.2,umc216.3,umc216.5,umc216.6,umc216.8,umc216.9,umc216.11,umc216.12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
61 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Power Virus Test | P1 | umc56.153,umc56.154,umc56.155,umc56.156,umc56.157,umc56.158,umc56.159 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 7 | Delta | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
62 | UMCRTG-IP10-30 | Clock Gating |  | SPAZ |  | MACO SR | P1 | umc49.1 | Tserver | -d=1 -v=error -cf=stutter.cf -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 | using umc1.1 test and -nogc -nobios due to BAMACO core off, and adding VCN power off command in advance | AB+8wk | DIAG-13378 having issue and fix
63 | UMCRTG-IP10-39 | PG (Power Gating) |  | SPAZ |  | Static Screen Stutter Mode | P2 | umc1.50 | Tserver | -d=1 -v=error -cf=stutter.cf -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 | -D702, BRP025 IFWI, -ppmode=1(agt 3.1.9.0), D701 BRP042diag IFWI | AB+8wk
64 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | REC |  | monitor edc counter | P1 | event_handler_3 | Tserver | -chkedc=all -edcthresh=1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
65 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | WAW – write after write | P1 | umc681.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  | 1 | 0 | [6 empty] | 0 |  | AB+4wk
66 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | RAW – read after write | P1 | umc681.2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
67 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | VC-based Priority Adjustment | P1 | umc683.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  | 1 | 0 | [6 empty] | 0 | display should be connected w/o "-disable_libdce" | AB+4wk
68 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | Bypass Priority Escalation Mode | P1 | umc684.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
69 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | SLT Functional | P1 | umc401.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
70 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Board Functional | P1 | umc413.1,umc413.2,umc413.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
71 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Board Stress | P1 | umc404.1-3,umc404.11-13 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
72 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Board Extra | P1 | umc405.1-5,umc405.11-15 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
73 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Memfa test | P1 | umc600.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+4wk
74 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Memfa test | P1 | umc601.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Legacy | 1 |  | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+4wk
75 | UMCRTG-IP10-21 | Bank Grouping |  | FEI |  | BW test | P1 | umc70.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | new | 1 | 3 | 1 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+6wk
76 | NAVI40-SOCPRS-312 | SOC and DF team support for each single MCD (or PHY) configuration. |  | PMC |  | general event monitor | P1 | event_handler_5 | Tserver | -mcpmcevents | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+2wk
77 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | MCA |  | UmcGeccErrorInjectionTest | P1 | umc751.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
78 | UMCRTG-IP10-15 | DRAM Error Injection |  | MCA |  | UmcGeccErrorInjectionTest | P1 | umc751.2,umc751.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+7wk
79 | UMCRTG-IP10-12 | UER is Fatal |  | MCA |  | UmcGeccErrorInjectionTest-IH | P1 | umc752.5 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+7wk
80 | UMCRTG-IP10-17 | Patrol Scrubber |  | MCA |  | Patrol Scrubber | P1 | umc753.1,umc753.2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+7wk
81 | UMCRTG-IP10-18 | Redirect scrubber |  | MCA |  | Redirect Scrubber | P1 | umc753.3,umc753.4 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+6wk
82 | UMCRTG-UMC130-15 | Parity check on MP sram |  | MCA |  | LM32 SRAM Parity | P2 | umc764.1,umc764.2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+8wk
83 | Internal_Debug | Internal debug purpose |  | Debug |  | FB Dump Test | P3 | umc510.1-4,umc510.6-9 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
84 | Internal_Debug | Internal debug purpose |  | Debug |  | Channel mapping verification | P3 | umc553.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
85 | Internal_Debug | Internal debug purpose |  | Debug |  | Tacl debug | P3 | umc506.1,umc506.2,umc506.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
86 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | power_virus_combo_composite | P1 | umc.pv.56.155 | TNG |  | 1 | 8 | new | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
87 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | stress_blt_composite | P1 | umc.bltcombo.404.14 | TNG |  | 1 | 9 | new | 1 | 9 | 1 | N-1 | 9 | 9 | 9 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
88 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Full FB fill - Compute Shader | P1 | umc.fbfill.1.3 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
89 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Write Only | P1 | umc.wrrdonly.1.822 | TNG |  | 1 | 3 | new | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+3wk
90 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Read Only | P1 | umc.wrrdonly.1.823 | TNG |  | 1 | 3 | new | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+3wk
91 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Compute Shader Read/Compare | P1 | umc.wrrdonly.1.825 | TNG |  | 1 | 3 | new | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
92 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC303 – Moving Blt Walkpat | P1 | umc.blt.3.3007 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
93 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC320 - Random Blt WalkPat | P1 | umc.blt.3.21025 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
94 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle with PRBS pattern | P1 | umc.rectog.383.16 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
95 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | REC |  | monitor edc counter | P1 | umc.checkedc | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+4wk
96 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | REC |  | inject edc error | P1 | umc.umc.edc_error_injection | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
97 | UMCRTG-IP10-30 | Clock Gating |  | SPAZ |  | MACO SR | P1 | umc.fbfill.1.49 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+8wk
98 | UMCRTG-IP10-39 | PG (Power Gating) |  | SPAZ |  | Static Screen Stutter Mode | P2 | umc.fbfill.1.50 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+8wk
99 | UMCRTG-UMC130-13 | PHB (Page Hit Burst) |  | BEQ |  | row_hammer_test | P1 | umc.hammer.1002.2 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  |  | 1 |  |  |  | 0 |  | AB+5wk
100 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.march01.405.13 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  |  | 1 |  |  |  | 0 |  | AB+4wk
101 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.hartmann.405.14 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  |  | 1 |  |  |  | 0 |  | AB+4wk
102 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.mod.405.15 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  |  | 1 |  |  |  | 0 |  | AB+4wk
103 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.xmarch.405.16 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 |  |  | 1 |  |  |  | 0 |  | AB+4wk
104 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | MCA |  | gecc_error_injection_irritator | P1 | umc.gecc_error_injection | TNG |  | 1 | 1 | new | 1 |  | 0 | N-1 | 1 | [12 empty] | 0 |  | AB+4wk
105 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Memfa test | P1 | umc.memfa_test | TNG |  | 1 | 1 | new | 1 |  | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+4wk
106 | Internal_Debug | Internal debug purpose |  | Debug |  | FB Dump Test | P3 | umc.fb_dump | TNG |  | 1 | 4 | new | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
107 | Internal_Debug | Internal debug purpose |  | Debug |  | Channel mapping verification | P3 | umc.channel_mapping | TNG |  | 1 | 1 | new | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
1231