## Sheet1
| Unnamed: 0 | Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id
0 | 0 | ASP-009 ASP-012 | ASP: Security Fencing: MP0 public space, private space, SRAM, ROM ASP: CRU: C2PMSG and interrupts |  | MPASP |  | Register Access Test |  | asp.basic.register_access | TNG |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk2 |  | 0 | 1 | asp.basic.register_access
1 | 1 | ASP-009 | ASP: Security Fencing: MP0 public space, private space, SRAM, ROM |  | MPASP |  | SRAM Access Test | P2 | asp.basic.sram_access | TNG |  | 24 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK2 |  | 0 | 1 | asp.basic.sram_access
2 | 2 | ASP-006 ASP-007 | ASP: HUBIF TLB mapping ASP: HUBIF inline AES computation |  | MPASP |  | HUBIF Access Test |  | asp.basic.hubif | TNG |  | 40 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | asp.basic.hubif
3 | 3 | ASP-015 | ASP: SMNIF TLB Mapping |  | MPASP |  | SMNIF Access Test | P3 | psp1.4 | TServer |  | 32 | 1 | Legacy | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 1 | psp1.4
4 | 4 | ASP-003 ASP-005 | ASP DRAM is encrypted and not accessible to any other processors Security: ASP Private DRAM 8MB area |  | MPASP |  | ASP Private Area Access Test |  | psp1.4 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | psp1.4
5 | 5 | ASP-014 | ASP: CRU: ASP SMU conmunication via P2SMSG/S2PMSG and interrupts |  | MPASP |  | ASP-SMU Test Message Access Test | P2 | psp1.7 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk4 |  | 0 | 1 | psp1.7
6 | 6 |  |  |  | MPASP |  | External IP RSMU Access Test |  | psp1.1 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | psp1.1
7 | 7 | ASP-013 | ASP: CRU: A5 interrupt to x86 CPU |  | MPASP |  | Interrupt Test | P3 | psp1.13 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk7 |  | 0 | 1 | psp1.13
8 | 8 | ASP-008 | ASP: HUBIF access violation and interrupt |  | MPASP |  | HUBIF Access Violation and Interrupt | P3 | psp1.15 | TServer |  | 32 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK6 |  | 0 | 1 | psp1.15
9 | 9 | ASP-016 | ASP: RSMU access violation and interrupt |  | MPASP |  | RSMU Access Violation and Interrupt | P3 | psp1.17 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK6 |  | 0 | 1 | psp1.17
10 | 10 | ASP-010 | ASP: CRU: Access Violation Interrupt control |  | MPASP |  | CRU Access Violation and Interrupt | P3 | psp1.97 | TServer |  | 32 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK6 |  | 0 | 1 | psp1.97
11 | 11 | ASP-011 | ASP: CRU: Timer control registers and interrupt |  | MPASP |  | Timer Control Registers and Interrupt | P3 | psp1.21 | TServer |  | 32 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 1 | psp1.21
12 | 12 | ASP-017 | ASP: Mutex |  | MPASP |  | Mutex Register Access | P3 | psp1.22 | TServer |  | 32 | 1 | Legacy | 1 | 1 | 1 |  | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK5 |  | 0 | 1 | psp1.22
13 | 13 | ASP-035 | ASP: SRAM/ROM Disable |  | MPASP |  | SRAM/ROM Disable | P1 | psp103 | TServer |  | 32 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK4 |  | 0 | 1 | psp103
14 | 14 | ASP-004 | ASP: TRNG Seed is available in public CRU |  | MPASP |  | TRNG Seed from Public CRU | P1 | psp1.26 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp1.26
15 | 15 |  |  |  | MPASP |  | TRNG Stress Test |  | psp1.30 | TServer |  | 32 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | psp1.30
16 | 16 | ASP-027 | CCP: Side channel attack countermeasure |  | CCP |  | CCP SCA Countermeasure Test | P1 | psp2.1 | TServer |  | 32 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK4 |  | 0 | 1 | psp2.1
17 | 17 | ASP-018 ASP-019 ASP-022 ASP-023 | CCP: AES engine CCP: SHA engine CCP: Zlib decompression CCP: Pass-through |  | CCP |  | CCP Multi-Frame Test |  | psp2.2 | TServer |  | 80 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp2.2
18 | 18 | ASP-026 | CCP: Memory interface |  | CCP |  | CCP Multi Queue Test | P1 | psp2.3 | TServer |  | 120 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp2.3
19 | 19 |  |  |  | CCP |  | CCP Job Delete Test |  | psp2.5 | TServer |  | 40 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | psp2.5
20 | 20 | ASP-025 | CCP: Interrupts and Status |  | CCP |  | CCP Interrupt Test | P1 | ccp.basic.interrupt | TNG |  | 40 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | ccp.basic.interrupt
21 | 21 | ASP-028 | CCP: Error handling for all CCP error cases |  | CCP |  | CCP Static/Dynamic Error Test | P3 | psp2.7 | TServer |  | 120 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk6 |  | 0 | 1 | psp2.7
22 | 22 | ASP-023 | CCP: Pass-through |  | CCP |  | CCP PT Engine Test | P1 | ccp.basic.pt | TNG |  | 40 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | ccp.basic.pt
23 | 23 | ASP-018 | CCP: AES engine |  | CCP |  | CCP AES Engine Test | P1 | ccp.basic.aes | TNG |  | 40 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | ccp.basic.aes
24 | 24 | ASP-019 | CCP: SHA engine |  | CCP |  | CCP SHA Engine Test | P1 | psp203.1 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp203.1
25 | 25 | ASP-020 | CCP: RSA engine |  | CCP |  | CCP RSA Engine Test | P1 | psp204.1 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp204.1
26 | 26 | ASP-021 | CCP: ECC engine |  | CCP |  | CCP ECC Engine Test | P1 | psp205.1 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp205.1
27 | 27 | ASP-022 | CCP: Zlib decompression |  | CCP |  | CCP ZLIB Engine Test | P1 | psp206.1 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp206.1
28 | 28 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP PT Engine Reset Test | P2 | psp201.3 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp201.3
29 | 29 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP AES Engine Reset Test | P2 | psp202.3 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp202.3
30 | 30 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP SHA Engine Reset Test | P2 | psp203.3 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp203.3
31 | 31 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP RSA Engine Reset Test | P2 | psp204.3 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp204.3
32 | 32 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP ECC Engine Reset Test | P2 | psp205.3 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp205.3
33 | 33 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP ZLIB Engine Reset Test | P2 | psp206.3 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp206.3
34 | 34 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP Queue Reset Test | P2 | psp2.201 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp2.201
35 | 35 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP IDMA/ODMA Reset Test | P2 | psp2.202 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp2.202
36 | 36 | ASP-034 | CCP: Module Reset |  | CCP |  | CCP JPM Reset Test | P2 | psp2.203 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | psp2.203
37 | 37 | ASP-019 | CCP: SHA engine |  | CCP |  | CCP SHA with PT | P1 | ccp.basic.sha | TNG |  | 40 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | ccp.basic.sha
38 | 38 | ASP-019 | CCP: SHA engine |  | CCP |  | CCP SHA with SW and HW IV | P1 | ccp.basic.sha | TNG |  | 40 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | WK3 |  | 0 | 1 | ccp.basic.sha
39 | 39 | ASP-029 | CCP: Clock gating |  | CCP |  | CCP Dynamic Clock Gating Test | P3 | psp2.106 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk6 |  | 0 | 1 | psp2.106
40 | 40 | ASP-036 | CCP: Memory range protection |  | CCP |  | CCP Memory Range Protection Test | P1 | psp2.23 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | psp2.23
41 | 41 | ASP-037 | SIB: KSB functional |  | SIB |  | KSB Access Test | P1 | sib.basic.ksb_access | TNG |  | 40 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | sib.basic.ksb_access
42 | 42 | ASP-037 | SIB: KSB functional |  | SIB |  | KSB Attributes Test | P1 | sib.basic.ksb_attributes | TNG |  | 40 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | sib.basic.ksb_attributes
43 | 43 | ASP-002 | Keys loaded into CCP are protected (read/write) from active and passive side channels and fault injection attacks |  | SIB |  | KSB RTL-Key Protection Test | P1 | sib.basic.ksb.rtl_key_protection | TNG |  | 24 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | sib.basic.ksb.rtl_key_protection
44 | 44 | ASP-038 | SIB: KSB errors |  | SIB |  | KSB Error Test | P2 | sib.basic.ksb_attributes | TNG |  | 40 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk5 |  | 0 | 1 | sib.basic.ksb_attributes
45 | 45 | ASP-039 | SIB: ISB functional |  | SIB |  | ISB Access Test | P1 | sib.basic.isb_access | TNG |  | 40 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | sib.basic.isb_access
46 | 46 | ASP-039 | SIB: ISB functional |  | SIB |  | ISB SRAM Key Clear Test | P1 | sib.basic.pkdb.isb_sram_clearing | TNG |  | 24 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | sib.basic.pkdb.isb_sram_clearing
47 | 47 | ASP-040 | SIB: ISB errors |  | SIB |  | ISB Error Test | P2 | TestID.PlaceHolder.49 | TNG |  | 24 | 1 | New | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk5 |  | 0 | 1 | TestID.PlaceHolder.49
48 | 48 | ASP-041 | SIB: TRNG, Health check function, and DRBG function |  | SIB |  | TRNG Dump | P1 | psp2.9 | TServer |  | 40 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | psp2.9
49 | 49 | ASP-041 | SIB: TRNG, Health check function, and DRBG function |  | SIB |  | TRNG Entropy Health Monitor Test | P1 | psp2.17 | TServer |  | 24 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | psp2.17
50 | 50 | ASP-042 | SIB: WDT |  | SIB |  | WDT and EH Test | P2 | psp1.27 | TServer |  | 32 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk4 |  | 0 | 1 | psp1.27
51 | 51 | ASP-043 | CCP: SHA3 Frame Size Update |  | CCP |  | CCP SHA3 Frame Size Test | P2 | psp203.4 | TServer |  | 32 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | psp203.4
52 | 52 | ASP-044 | CCP: SHA-PT Destination Address Pointer |  | CCP |  | CCP SHA-PT Dest2 Address Test | P2 | ccp.basic.sha | TNG |  | 32 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | ccp.basic.sha
53 | 53 | ASP-045 | CCP: SHA3 HMAC - Key update - 384/512 bits |  | CCP |  | CCP SHA3 HMAC 384/512 Test | P2 | TestID.PlaceHolder.55 | TNG |  | 32 | 1 | New | 1 | 0 | 0.5 | C-Model | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | TestID.PlaceHolder.55
54 | 54 | ASP-046 | CCP: SHAKE128/256 Digest Length |  | CCP |  | CCP SHAKE128/256 Digest Length Test | P2 | TestID.PlaceHolder.56 | TNG |  | 32 | 1 | New | 1 | 0 | 0.5 | C-Model | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk3 |  | 0 | 1 | TestID.PlaceHolder.56
55 | 55 | ASP-047 | SIB: KSB Errors ASP/CCP Seperation |  | SIB |  | KSB Error ASP/CCP Seperation | P3 | TestID.PlaceHolder.57 | TNG |  | 24 | 1 | New | 1 | 0 | 0.15 | C-Model | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk6 |  | 0 | 1 | TestID.PlaceHolder.57
56 | 56 | ASP-048 | SIB: KSB Mass Clear |  | SIB |  | KSB Mass Clear Test | P3 | TestID.PlaceHolder.58 | TNG |  | 24 | 1 | New | 1 | 0 | 0 | C-Model | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk6 |  | 0 | 1 | TestID.PlaceHolder.58
57 | 57 | ASP-049 | SIB: KSB Slot Search |  | SIB |  | KSB Slot Search Test | P3 | TestID.PlaceHolder.59 | TNG |  | 24 | 1 | New | 1 | 0 | 0 | C-Model | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk6 |  | 0 | 1 | TestID.PlaceHolder.59
58 | 58 | ASP-050 | ASP: Si-Five Mem Port/Front Port |  | ASP |  | CCP -> NIC400 -> SMNIF-> SoC Registers | P1 | psp207.1 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk7 |  | 0 | 1 | psp207.1
59 | 59 | ASP-050 | ASP: Si-Five Mem Port/Front Port |  | ASP |  | CCP -> MMHUBIF-> FB/System Memory | P1 | psp207.2 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk7 |  | 0 | 1 | psp207.2
60 | 60 | ASP-050 | ASP: Si-Five Mem Port/Front Port |  | ASP |  | CCP -> Front Port -> E6A(riscv) -> Memory Port -> MMHUBIF-> FB/System Memory | P1 | psp207.3 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk7 |  | 0 | 1 | psp207.3
61 | 61 | ASP-050 | ASP: Si-Five Mem Port/Front Port |  | ASP |  | E6A System Port -> NIC400 -> MMHUBIF -> MMHUB |  | psp107.3 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | psp107.3
62 | 62 | ASP-050 | ASP: Si-Five Mem Port/Front Port |  | ASP |  | E6A Memory Port -> NIC400 -> MMHUBIF -> MMHUB |  | psp107.4 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | psp107.4
63 | 63 | ASP-050 | ASP: Si-Five Mem Port/Front Port |  | ASP |  | E6A System Port -> NIC400 -> SMNIF -> SoC Registers |  | psp107.1 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | psp107.1
64 | 64 | ASP-050 | ASP: Si-Five Mem Port/Front Port |  | ASP |  | E6A Memory Port -> NIC400 -> SMNIF -> SoC Registers | P1 | psp107.2 | TServer |  | 24 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  | 1 | 0 | 1 |  | 0 | 0 |  | 0 | 0 | 0 |  | Wk7 |  | 0 | 1 | psp107.2