## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | EX-FEAT-002 | GFXCLK DFLL support |  | PMM | CLK-DPM | GFXCLK DFLL support; FW DPM Tester auto_dpm_tog=sclk | P1 | PM80.12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
1 | EX-FEAT-009 | FW DPM Tester |  | PMM | CLK-DPM | GFXCLK DFLL support; FW DPM Tester auto_dpm_tog=sclk | P1 | PM80.12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
2 | EX-FEAT-075 | Clock Management and Control |  | PMM | CLK-DPM | GFXCLK DFLL support; FW DPM Tester auto_dpm_tog=sclk | P1 | PM80.12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
3 | EX-FEAT-077 | Voltage Controller |  | PMM | CLK-DPM | GFXCLK DFLL support; FW DPM Tester auto_dpm_tog=sclk | P1 | PM80.12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
4 | EX-FEAT-102 | GFX AVFS |  | PMM | CLK-DPM | GFXCLK DFLL support; FW DPM Tester auto_dpm_tog=sclk | P1 | PM80.12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK13
5 | EX-FEAT-073 | DPM Controller/HUB |  | PMM | CLK-DPM | GFXCLK DFLL support; FW DPM Tester auto_dpm_tog=sclk | P1 | PM80.12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
6 | EX-FEAT-108 | GFXCLK DPM |  | PMM | CLK-DPM | GFXCLK DFLL support; FW DPM Tester auto_dpm_tog=sclk | P1 | PM80.12.1 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
7 | EX-FEAT-002 | GFXCLK DFLL support |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
8 | EX-FEAT-009 | FW DPM Tester |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
9 | EX-FEAT-075 | Clock Management and Control |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
10 | EX-FEAT-077 | Voltage Controller |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
11 | EX-FEAT-102 | GFX AVFS |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK13
12 | EX-FEAT-073 | DPM Controller/HUB |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
13 | EX-FEAT-108 | GFXCLK DPM |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
14 | EX-FEAT-090 | GFX IMU Interaction |  | PMM | CLK-DPM | GFXCLK DPM naturedpm | P1 | PM80.12.2 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
15 | EX-FEAT-008 | DRAM Temperature reading |  | PMM | Data-Logging | UMC counters;DRAM Temperature reading; Tmon/Tsense Configurability and Reading | P1 | PM80.12.3 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
16 | EX-FEAT-005 | Tmon/Tsense Configurability and Reading |  | PMM | Data-Logging | UMC counters;DRAM Temperature reading; Tmon/Tsense Configurability and Reading | P1 | PM80.12.3 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
17 | EX-FEAT-042 | DRAM Temperature Controlling using UMC BW Throttling |  | PMM | Data-Logging | UMC counters;DRAM Temperature reading; Tmon/Tsense Configurability and Reading | P1 | PM80.12.3 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
18 | EX-FEAT-072 | FW Telemetry Reading |  | PMM | Data-Logging | UMC counters;DRAM Temperature reading; Tmon/Tsense Configurability and Reading | P1 | PM80.12.3 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
19 | EX-FEAT-004 | Power Configurability |  | PMM | Throttling | Power Configurability | P2 | PM80.12.4 | Tserver | PPT_limit | 1 | 1 | Delta | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
20 | EX-FEAT-088 | PPT control |  | PMM | Throttling | Power Configurability | P1 | PM80.12.4 | Tserver | PPT_limit | 1 | 1 | Delta | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
21 | EX-FEAT-010 | FW Logger |  | PMM | Data-Logging | agmlog | P1 | PM80.12.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
22 | EX-FEAT-068 | DMA |  | PMM | Data-Logging | agmlog | P1 | PM80.12.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
23 | EX-FEAT-003 | Data Controller |  | PMM | Data-Logging | agmlog | P1 | PM80.12.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
24 | EX-FEAT-072 | FW Telemetry Reading |  | PMM | Data-Logging | agmlog | P1 | PM80.12.5 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
25 | EX-FEAT-009 | FW DPM Tester |  | PMM | CLK-DPM | FCLK sweep | P1 | PM80.12.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
26 | EX-FEAT-011 | FCLK DPM |  | PMM | CLK-DPM | FCLK sweep | P1 | PM80.12.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
27 | EX-FEAT-011 | FCLK DPM |  | PMM | CLK-DPM | FCLK DPM naturedpm | P1 | PM80.12.7 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK7
28 | EX-FEAT-009 | FW DPM Tester |  | PMM | CLK-DPM | FCLK DPM naturedpm | P1 | PM80.12.7 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
29 | EX-FEAT-075 | Clock Management and Control |  | PMM | CLK-DPM | FCLK DPM naturedpm | P1 | PM80.12.7 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
30 | EX-FEAT-009 | FW DPM Tester |  | PMM | P-state | UCLK force dpm | P1 | PM23.1 | Tserver |  | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
31 | EX-FEAT-077 | Voltage Controller |  | PMM | P-state | UCLK force dpm | P1 | PM23.1 | Tserver |  | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
32 | EX-FEAT-009 | FW DPM Tester |  | PMM | P-state | UCLK DPM sweep dpm | P1 | PM80.12.1 | TNG | autodpmtog=mclk | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
33 | EX-FEAT-012 | UCLK DPM |  | PMM | P-state | UCLK DPM sweep dpm | P1 | PM80.12.1 | TNG | autodpmtog=mclk | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
34 | EX-FEAT-077 | Voltage Controller |  | PMM | P-state | UCLK DPM sweep dpm | P1 | PM80.12.1 | TNG | autodpmtog=mclk | 1 | 1 | New | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
35 | EX-FEAT-012 | UCLK DPM |  | PMM | CLK-DPM | UCLK/MCLK DPM naturedpm | P1 | PM80.12.9 | TNG | nature=mclk | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
36 | EX-FEAT-073 | DPM Controller/HUB |  | PMM | CLK-DPM | UCLK/MCLK DPM naturedpm | P1 | PM80.12.9 | TNG | nature=mclk | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
37 | EX-FEAT-100 | VDDCI DVS |  | PMM | CLK-DPM | UCLK/MCLK DPM naturedpm | P1 | PM80.12.9 | TNG | nature=mclk | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
38 | EX-FEAT-075 | Clock Management and Control |  | PMM | CLK-DPM | UCLK/MCLK DPM naturedpm | P1 | PM80.12.9 | TNG | nature=mclk | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
39 | EX-FEAT-009 | FW DPM Tester |  | PMM | CLK-DPM | UCLK/MCLK DPM naturedpm | P1 | PM80.12.9 | TNG | nature=mclk | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
40 | EX-FEAT-098 | SOC-AVFS on non-GFX Clocks(SOCCLK,MMCLK,DCN,VCN,UCLK) |  | PMM | CLK-DPM | UCLK/MCLK DPM naturedpm | P1 | PM80.12.9 | TNG | nature=mclk | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK13
41 | EX-FEAT-014 | SOCCLK DPM |  | PMM | CLK-DPM | SOCCLK force dpm | P1 | PM20.1 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
42 | EX-FEAT-077 | Voltage Controller |  | PMM | CLK-DPM | SOCCLK force dpm | P1 | PM20.1 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
43 | EX-FEAT-014 | SOCCLK DPM |  | PMM | CLK-DPM | SOCCLK sweep dpm | P1 | PM80.12.1 | TNG | autodpmtog=socclk | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
44 | EX-FEAT-077 | Voltage Controller |  | PMM | CLK-DPM | SOCCLK sweep dpm | P1 | PM80.12.1 | TNG | autodpmtog=socclk | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
45 | EX-FEAT-014 | SOCCLK DPM |  | PMM | CLK-DPM | SOCCLK nature dpm | P1 | PM80.13 | Tserver | nature=socclk | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
46 | EX-FEAT-073 | DPM Controller/HUB |  | PMM | CLK-DPM | SOCCLK nature dpm | P1 | PM80.13 | Tserver | nature=socclk | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
47 | EX-FEAT-075 | Clock Management and Control |  | PMM | CLK-DPM | SOCCLK nature dpm | P1 | PM80.13 | Tserver | nature=socclk | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
48 | EX-FEAT-017 | GPO support |  | PMM | IMU | GPO support | P2 | PM80.12 | Tserver | pmfeature=gpo | 1 | 1 | Delta | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | 0
49 | EX-FEAT-022 | MM CLK DPM |  | PMM | CLK-DPM | MM CLK DPM:force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
50 | EX-FEAT-077 | Voltage Controller |  | PMM | CLK-DPM | MM CLK DPM:force | P1 | PM25.2-4 | Tserver |  | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
51 | EX-FEAT-022 | MM CLK DPM |  | PMM | CLK-DPM | MM CLK DPM:nature | P1 | PM80.12.6 | TNG |  | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
52 | EX-FEAT-073 | DPM Controller/HUB |  | PMM | CLK-DPM | MM CLK DPM:nature | P1 | PM80.12.6 | TNG |  | 1 | 1 | New | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
53 | EX-FEAT-024 | Fan Controller |  | PMM | FAN | Fan Controller | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 0 | 0 |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
54 | EX-FEAT-067 | GPIO Handler |  | PMM | FAN | Fan Controller | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 1 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK6
55 | EX-FEAT-051 | GPIO to turn off Fan |  | PMM | FAN | Fan Controller | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 1 | 0.3 | 0.3 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK12
56 | EX-FEAT-053 | Zero Fan control |  | PMM | FAN | Fan Controller | P1 | PM14.11 | TNG |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
57 | EX-FEAT-024 | Fan Controller |  | PMM | FAN | Fan Controller | P1 | PM14.1 | TNG |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
58 | EX-FEAT-029 | BACO Support |  | PMM | D-State | BACO Support | P1 | PM31.05 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
59 | EX-FEAT-030 | BAMACO |  | PMM | D-State | BAMACO | P1 | PM31.06 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
60 | EX-FEAT-034 | VCN Off |  | PMM | PG | VCN Off | P1 | PM80.805 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
61 | EX-FEAT-041 | SOC ULV |  | PMM | D-State | SOC ULV | P1 | PM80.808 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
62 | EX-FEAT-047 | DF C-state |  | PMM | D-State | SOC ULV | P1 | PM80.808 | TNG |  | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
63 | EX-FEAT-063 | Out Of Band Monitoring and Management |  | PMM | OOB | SMBUS Out-of-Band Management | P1 | PM13.16 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
64 | EX-FEAT-074 | Feature Enablement Arbiter |  | PMM | PPLIB | Feature Enablement Arbiter | P1 | ./agt -ppmode=1 | Tserver |  | 1 | 1 | Legacy | 1 | 0.3 | 0.3 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
65 | EX-FEAT-076 | MP1 <-> IMU Message Interface |  | PMM | MP1-IMU | MP1 <-> IMU Message Interface | P1 | PM80.12.1 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
66 | EX-FEAT-078 | Message Hub |  | PMM | SMN-IF | Message Hub | P1 | PM80.5 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK2
67 | EX-FEAT-079 | I2C Arbiter |  | PMM | I2C | I2C | P1 | PM80.993 | TNG |  | 1 | 1 | Legacy | 1 | 0.5 | 0.5 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK8
68 | EX-FEAT-083 | Mode 1 reset |  | PMM | reset | Driver reset | P1 | Pm36.1 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 | [5 empty] | 0
69 | EX-FEAT-089 | Temperature tracking and Control/Thermal Throttling |  | PMM | Throttling | Temperature tracking and Control/Thermal Throttling | P1 | PM80.12.8 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK9
70 | EX-FEAT-101 | MEMIO/MVDD DVS |  | PMM | CLK-DPM | GCD SOC AVFS | P1 | PM80.12.10 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK12
71 | EX-FEAT-062 | PSM log |  | PMM | PSM | PSM | P1 | pm80.12.11 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK6
72 | EX-FEAT-090 | GFX IMU Interaction |  | PMM | GFXOFF | GFXOFF | P1 | pm80.12.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
73 | EX-FEAT-122 | GFXOFF |  | PMM | GFXOFF | GFXOFF | P1 | pm80.12.12 | TNG |  | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK11
74 | EX-FEAT-055 | GFX in OFF State at Boot |  | PMM | GFX power up | GFX power up | P1 | pm74.3 | Tserver |  | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK1
75 | EX-FEAT-109 | Acoustics-CoilWhine |  | PMM | Acoustics | Acoustics | P1 | Acoustics=sweep/force | Tserver |  | 1 | 1 | New | 1 | 0.7 | 0.7 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK20
76 | EX-FEAT-110 | SCPM |  | PMM | Acoustics | SCPM | P1 | scpm-security | Tserver |  | 1 | 1 | New | 1 | 0.7 | 0.7 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK4
77 | EX-FEAT-120 | RAS support |  | PMM | RAS | RAS | P1 | PMxx.xx.2 | Tserver |  | 1 | 1 | Legacy | 1 | 0.7 | 0.7 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | 0
78 | EX-FEAT-020 | DCN DPM |  | PMM | CLK-DPM | DCN DPM | P2 | PMxx.xx.6 | Tserver |  | 1 | 1 | Legacy | 1 | 0.7 | 0.7 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
79 | EX-FEAT-039 | Dynamic RM |  | PMM | Dynamic RM | Dynamic RM | P2 | PMxx.xx.8 | Tserver |  | 1 | 1 | Legacy | 1 | 0.7 | 0.7 | N-1 | 1 | 1 |  | 1 |  |  | 1 |  | 0 |  |  |  |  | 0 |  | 0
80 | EX-FEAT-115 | PPTable |  | PMM | PPTable | PPTable | P2 | PMxx.xx.9 | Tserver |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK20
81 | EX-FEAT-130 | PPVMIN, SMS status check, RTAVFS |  | PMM | PPVMIN, Dynamic RM, RTAVFS, Smart Shift enablement status check | PPVMIN, Dynamic RM, RTAVFS, Smart Shift enablement status check | P1 | PMxx.xx.12 | TNG |  | 1 | 1 | Legacy | 1 | 0.7 | 0.7 | N-1 | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK11
82 | EX-FEAT-057 | PPVmin |  | PMM | PPVmin,TDVmin | PPVmin,TDVmin | P3 | PMxx.xx.13 | TNG |  | 0 | 0 | Legacy |  | 0 | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK13
83 | EX-FEAT-058 | TDVmin |  | PMM | PPVmin,TDVmin | PPVmin,TDVmin | P3 | PMxx.xx.13 | TNG |  | 0 | 0 | Legacy |  | 0 | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK13