## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | 12 | Navi4x configuration changes | Dennis | GFX |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
1 | 12.001 | Separate color blend opt bits out of CB_COLORn_INFO | Steven/David | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.5 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
2 | 12.001999999999999 | Change SPI_VS_OUT_CONFIG and SPI_PS_IN_CONTROL from context to persistent state regs | Xiaojing | SIO |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
3 | 12.002999999999998 | Separate PS_ITER_SAMPLE out of PA_SC_MODE_CNTL_1 | Steven/David | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.5 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
4 | 12.003999999999998 | Separate SAMPLE_RATE out of DB_COUNT_CONTROL | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
5 | 12.005999999999997 | GE_CNTL and VGT_LS_HS_CONFIG changes | Yu Xuan | GEO |  |  | P1 | ge1.0, ge1.1 | TServer |  | 1 | 1 | New | 1 |  | 0.8 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
6 | 12.006999999999996 | PA_SC_AA_CONFIG changes | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | Delta | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
7 | 12.007999999999996 | PA_SC_CONSERVATIVE_RASTERIZATION_CNTL changes | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | Delta | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
8 | 12.008999999999995 | Eliminate PA_SU_SC_MODE_CNTL.KEEP_TOGETHER_ENABLE | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
9 | 12.009999999999994 | Separate AUTO_RESET_CNTL from PA_SC_LINE_STIPPLE | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
10 | 12.010999999999994 | Implicit viewport scissoring | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
11 | 12.011999999999993 | Simplify workaround for DEGGIGXX0-4644 | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | Delta | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Feature dropped | 0 |  |  |  |  | 1 |  | WK5
12 | 12.012999999999993 | Separate event enable bits out of SPI_CONFIG_CNTL | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
13 | 12.013999999999992 | Split DB_RENDER_OVERRIDE | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
14 | 12.014999999999992 | DB_STENCILREFMASK refactor | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | Delta | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
15 | 12.015999999999991 | Per target control for CB BIG_PAGE/L2_BYPASS | Steven/David | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.5 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
16 | 12.01699999999999 | MSAA shader write support for D/S images | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Covered by 12.164 hybrid_depth_comp | 0 |  |  |  |  | 1 |  | WK5
17 | 12.01899999999999 | Broadcast stores | Frank/Jeff Wheeler | TEX |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
18 | 12.019999999999989 | out of order per-wave vmem returns | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 6 | New | 1 | 6 | 1 | Gopher | 6 | 6 | 6 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
19 | 12.026999999999985 | Configuration agnostic memory scope and policy control (dup of 12.041) | Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
20 | 12.029999999999983 | Add support for image atomics fp32 add (makes fp32 add orthogonal). Make fp behaviour among lds/cmm/df identical | Botao | SH |  |  | P1 | gfx.inst_perf/buffer_atomic_cond_sub_u32 gfx.inst_perf/buffer_atomic_pk_add_bf16 gfx.inst_perf/buffer_atomic_pk_add_f16 gfx.inst_perf/buffer_atomic_sub_clamp_u32 gfx.inst_perf/ds_cond_sub_u32 gfx.inst_perf/ds_pk_add_bf16 gfx.inst_perf/ds_pk_add_f16 gfx.inst_perf/ds_sub_clamp_u32 gfx.inst_perf/global_atomic_cond_sub_u32 gfx.inst_perf/global_atomic_pk_add_bf16 gfx.inst_perf/global_atomic_pk_add_f16 gfx.inst_perf/global_atomic_sub_clamp_u32 gfx.image_op/image_atomic_add_flt gfx.image_op/image_atomic_min_flt gfx.image_op/image_atomic_max_flt gfx.image_op/image_atomic_pk_add_f16 gfx.image_op/image_atomic_pk_add_bf16.1-17 | TNG |  | 1 | 17 | New | 1 | 17 | 1 | C-Model | 17 | 17 | 17 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
21 | 12.030999999999983 | Support greater than 16k x 16k x 8k textures (64k x 64k x 16k, inc. 16 mip levels to support 64k). Reduce/simplify swizzle modes. | Steven/David | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
22 | 12.032999999999982 | Unclamped image load/store support | Frank/Jeff Wheeler | TEX |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
23 | 12.033999999999981 | Move PRT++ atomic ops out of TCP tags | Frank | TEX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not an implemented feature in Navi4x | 0 |  |  |  |  | 1 |  | WK10
24 | 12.03599999999998 | Double Ray Tracing Intersect Engine | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
25 | 12.037 | RT instance node transform | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 0.2 | 0.2 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
26 | 12.039999999999978 | 64B RT node | Frank | TEX |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
27 | 12.041 | New GL2 policies (same/child of 12.027) | Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
28 | 12.041999999999977 | Unify GLC->EA request interface | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
29 | 12.043999999999976 | GLC guarantee of same address order for any op or scope (dep. On 12.042) | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
30 | 12.045999999999975 | GLC Cascading Read-Mod-Write Atomic Ops (includes retaining gfx11 atomic ops) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
31 | 12.047999999999973 | GLC Full CL sized write support | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
32 | 12.048999999999973 | GLC Up to 256B Write Support to EA | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
33 | 12.050999999999972 | cache last_use policy (child of 12.041/12.027) | Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
34 | 12.05299999999997 | Distributed compression architecture in CMM and client impacts (w/ physical meta-data) | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
35 | 12.05499999999997 | Split workgroup barrier | Botao | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
36 | 12.055999999999969 | Shader Instruction Data Prefetch (viola item) | Botao | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
37 | 12.057 | Shader software data dependency control | Botao | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
38 | 12.058999999999967 | Shader SALU Float support (in M1/M2/gfx11.5) | Botao | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
39 | 12.059999999999967 | VGPR DMA for Function Calls (uniform mask only) | Botao | SH |  |  | P1 | gfx.inst_perf/global_load_block gfx.inst_perf/global_store_block gfx.inst_perf/scratch_load_block gfx.inst_perf/scratch_store_block.1-4 | TNG |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
40 | 12.061999999999966 | Shader Debugger Enablement | Botao | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
41 | 12.062999999999965 | Shader Illegal Instruction Detection | Botao | SH |  |  | P2 |  | TNG |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
42 | 12.063999999999965 | Support PERMUTE/BPERMUTE for wave64 | Botao | SH |  |  | P2 |  | TNG |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
43 | 12.064999999999964 | Shader VALU Improvements | Shuhui | SH |  |  | P1 |  | TNG |  | 1 | 1 | Delta | 1 | 0.3 | 0.3 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
44 | 12.065999999999963 | Shader Scalar Improvements | Botao | SH |  |  | P2 |  | TNG |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
45 | 12.066999999999963 | Fix SQG GRBM design | Botao | SH |  |  | P1 |  | TNG |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
46 | 12.067999999999962 | SQC Latency reduction (inherit approach from mi300) | Botao | SH |  |  | P1 |  | TServer |  | 1 | 1 | Legacy | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
47 | 12.068999999999962 | WGP-takeover mode | Botao | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
48 | 12.07099999999996 | Shader Instruction Store convert to Cache (likely in M2/gfx11.5) | Botao | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
49 | 12.07299999999996 | Shader signed memory offsets | Botao | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
50 | 12.077999999999957 | Move SQG outside of SPI | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Hardware feature change, no software visibility. | 0 |  |  |  |  | 1 |  | WK5
51 | 12.078999999999956 | Dynamic VGPR allocation | Shuhui | SH |  |  | P1 | navi48.gfx.dynvgpr | TNG |  | 1 | 1 | New | 1 | 0.9 | 0.9 | C-Model | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7782 | 0 |  |  |  |  | 0 |  | WK5
52 | 12.083999999999953 | Prep for Navi + MIx00 shader merge | Botao | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
53 | 12.092 | Documentation - UTCL* MAS | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not a feature, the MAS to be delivered by the DE team | 0 |  |  |  |  | 1
54 | 12.096 | UTCL1: check page_size using the stored frag_size | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived by UTCL1 design | 0 |  |  |  |  | 1
55 | 12.098 | Remove unused client shootdown interface | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
56 | 12.104 | GPUVM PTE bits | Steven | UTCL2 |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived from gfx coverage by IPSE | 0 |  |  |  |  | 1 |  | WK5
57 | 12.111 | Deprecate metadata probe and client shootdown in UTCL0 | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
58 | 12.112 | GCR single cycle UTC request interface | Steven | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
59 | 12.113 | RLC dont disable CGCG while thread trace is active | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this | 0 |  |  |  |  | 1 |  | WK10
60 | 12.114 | CP ucode use dispatch index for TTMP init | Meiru | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
61 | 12.115 | Single Pass Wave64 Trans Issue (in M2) | Botao | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
62 | 12.118 | PH Memory Queues | Yu Xuan | GEO |  |  | P1 | ge2.0, ge2.1, std1.6 | TServer |  | 1 | 3 | New | 1 |  | 0.8 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
63 | 12.119 | Harvesting enabled by default | Xiaojing | GC |  |  | P1 |  | TNG |  | 1 | 0 | New | 1 |  | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 1 |  | WK5
64 | 12.12 | WGP&RB GRBM Index Remapping (possible gfx11.5) | Xiaojing | CTL |  |  | P1 |  | TServer |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
65 | 12.124 | CSC Group Launch guarantee | Xiaojing | SIO |  |  | P2 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
66 | 12.125 | GFX Pipe Group Launch Guarantee | Xiaojing | SIO |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
67 | 12.128 | Packet Hardening for Microsoft Telemetry | Pierce | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 0.5 | 0.5 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
68 | 12.13 | add TCP out of order response support | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
69 | 12.132 | CP/RLC/SDMA 40-bit Register Addressing to GRBM<>RSMU | Daniel G | CTL |  |  | P1 |  | TNG |  | 1 | 2 | New | 1 | 1 | 0.5 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
70 | 12.133 | Removal of Clear State Context 0 and reclamation for rendering | Daniel G | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
71 | 12.134 | MES Handling Doorbell Misses | Daniel G | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
72 | 12.139 | Simplify software debugger register change process | Xiaojing | SIO |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
73 | 12.142 | Double shader DOT Int4 and Int8 rates | Shuhui | SH |  |  | P1 |  | TNG |  | 1 | 1 | Delta | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
74 | 12.143 | Remove SA Affinity for Pixel Shaders | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Driver team will verify this | 0 |  |  |  |  | 1
75 | 12.146 | RS64 L0 Instr Cache | Yu Xuan | CTL |  |  | P1 | std1.1, gci30.4 | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
76 | 12.148 | RS64 L0 Data Cache | Yu Xuan | CTL |  |  | P1 | std1.1, gci30.4 | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
77 | 12.15 | RS64 Bit Manip Instructions | Yu Xuan | CTL |  |  | P1 | gci3.12 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
78 | 12.152 | RS64 Dynamic TMR Loading | Steven | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
79 | 12.157 | Shader pseudo-scalar trans ops (M2 item) | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
80 | 12.159 | Shader reduce VGPR writes (M2 item, evaluate for gaming) | Shuhui | SH |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
81 | 12.16 | Shader double wave64 VINTERP rate (por gfx11.5, evaluate gaming) | Shuhui | SH |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
82 | 12.162 | Shader Performance Profiler Enablement | Shuhui | SH |  |  | P1 |  | TServer |  | 1 | 1 | Delta | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
83 | 12.163 | Architected SGPR Values | Xiaojing | SIO |  |  | P2 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
84 | 12.164 | Hybrid Depth Compression | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
85 | 12.165 | HiZ/S in SC | Steven/David | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.5 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
86 | 12.167 | CB codec removal/simplifications | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
87 | 12.168 | VRS fragment compression | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Descoped, can drop | 0 |  |  |  |  | 1 |  | WK5
88 | 12.174 | RS64 64bit Stream Input | Yu Xuan | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1 |  | WK5
89 | 12.175 | RS64 Atomic ISA Ext | Yu Xuan | CTL |  |  | P1 | gci30.3 | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
90 | 12.184 | GLx bus widths and configuration | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
91 | 12.185 | CH 256B read/write support | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
92 | 12.186 | Add SP support for float8 (fp8/bf8) dot products (ieee and/or non-ieee) | Shuhui | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
93 | 12.188 | Make shader round-robin arb in workgroup usable by driver | Shuhui | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
94 | 12.191 | Capture shader memviol source to speed up bringup debug | Shuhui | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
95 | 12.192 | UTCL2 UTCL1 Dummy INV interface removal | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
96 | 12.193 | Additional SAx client to UTCL1 (from 12. | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
97 | 12.197 | Ping-Pong walking for dispatches | Xiaojing | SIO |  |  | P2 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
98 | 12.201 | Compute Grid Programmable Walk Order (cs_grid_walk_order). If not doing morton'ish (ex. 2x2) then improving launch rate for existing typewriter (ex 4x1) is P1) | Xiaojing | SIO |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
99 | 12.202 | Compute Thread Walk Order (cs_thread_walk_order) | Xiaojing | SIO |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
100 | 12.206 | DC->SPI wire reduction |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indirect | 0 |  |  |  |  | 1 |  | WK5
101 | 12.208 | wave64 FMAF32 power reduction (M2 item) -> large area | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
102 | 12.209 | Add Structured Sparsity Support | Meiru | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 0.1 | 0.1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
103 | 12.21 | Fully connect capability to use high and normal MALL reuse hint (child of 12.027/12.041) | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
104 | 12.211 | UTCL1_identity_mode (SED Crest) | Steven | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | For chiplet SED Crest, not applicable for NV4m | 0 |  |  |  |  | 1 |  | WK5
105 | 12.213 | deprecate HPG | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Deprecated, not visible to diags | 0 |  |  |  |  | 1
106 | 12.214 | reduce GE_DIST to GE_SE wire count | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | We expect indirect coverage for this feature from many Graphics workloads including Geometry shader. There is no need to plan for direct/dedicated test case for this one. | 0 |  |  |  |  | 1 |  | WK5
107 | 12.216 | All debug bus buffers to 4K size | Daniel G | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1 |  | WK5
108 | 12.219 | ge_se in sed. Sub item under basic configuration | Xiaojing | GEO |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
109 | 12.22 | register cleanup | Xiaojing | GEO |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
110 | 12.221 | Add support to the SDMA to dequeue similar to the way the CP does | Yu Xuan | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1 |  | WK5
111 | 12.223 | Update PA/SC support for 1 to 9SE and updated pix distribution algorithm | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
112 | 12.224 | Drop the FSR support from SC PBB implementation | Steven/David | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
113 | 12.225 | DB design simplificaitons while updating for hybrid depth compression | David/Steven | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
114 | 12.233 | add DRAM logging support for RLC | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE team will cover this, with RLC FW team support | 0 |  |  |  |  | 1 |  | WK10
115 | 12.235 | Add RLC SRM as an RLC_CH client | Pierce | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
116 | 12.236 | change RLC LX7 config used for power management | Pierce | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
117 | 12.239 | increase adaptive stretch response of GDFLL | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indirect covered by regular clock stretch, not directly covered by diag | 0 |  |  |  |  | 1 |  | WK10
118 | 12.247 | Register remap to match M1 | Xiaojing | GEO |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
119 | 12.253 | GFX12 IMU - Remove CPAXI and send doorbells directly to CP/RLC/SDMA | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1 |  | WK5
120 | 12.255 | GFX12 IMU - Modify doorbell interface from Syshub to IMU | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1 |  | WK5
121 | 12.263 | GFX12 IMU - Add Resets and idle sidebands | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1 |  | WK5
122 | 12.266 | GFX12 Firewall update for 40 bit address | David | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
123 | 12.27 | Work Graph Scheduler | David | CTL |  |  | P1 |  | TServer |  | 1 | 1 | New | 0 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
124 | 12.276 | Remove the data duplication for MLOPS | Meiru | SH |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 | 0.2 | 0.2 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
125 | 12.277 | Add Conditional-subtract memory atomic for locks | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
126 | 12.278 | DCC sector size to increase to 128B | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 | Will be covered by any DCC tests | 0 |  |  |  |  | 0 |  | WK5
127 | 12.28 | DCC auto-CT detection | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
128 | 12.281 | Sector-separated DCC compressed data layout | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
129 | 12.282 | rename GE BIA containers | Xiaojing | GEO |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
130 | 12.284 | Data return for clamped PRT is "0" only (no longer needs to be programable) | Frank/Jeff Wheeler | TEX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
131 | 12.285 | Remove BIG_PAGE control for UTC probing | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
132 | 12.286 | Remove passthru_en/esgs_ring_itemsize/old gs fastlaunch | Xiaojing | GEO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
133 | 12.287 | VRS removal in DCC | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
134 | 12.291 | Remove F32 from CPG and CPC; No BC support in PM4 parsers |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
135 | 12.292 | move offchip lds manager to GE | Yu Xuan | GEO |  |  | P1 | ge3.0, std4.34 | TServer |  | 1 | 2 | New | 1 |  | 0.8 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
136 | 12.294 | Improve SPI work limiting controls (spi_work_limit_ctrl) | Xiaojing | SIO |  |  | P1 |  | TServer |  | 1 | 2 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
137 | 12.299 | [Navi4x] Move RTAVFS/DLDO/DFLL initialization to after CP is running workloads | David | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 | Indirect coverage with front door loading | 0 |  |  |  |  | 0 |  | WK10
138 | 12.3 | [Navi4x] SDMA ucode caching | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1 |  | WK10
139 | 12.301 | [Navi4x] CP ucode firmware execution speed-up via cache priming | Daniel G | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | 0.9 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
140 | 12.302 | [Navi4x] Remove SDMA load/run commands or disallow DRAM access allowed for load/run commands |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
141 | 12.308 | RS64 Debug Enablement | Daniel G | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1 |  | WK5
142 | 12.31 | SED client to 256B reads | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
143 | 12.311 | Shader VALU min/max IEEE compliant | Shuhui | SH |  |  | P1 | navi48.gfx.ieee_min_max | TNG |  | 1 | 1 | New | 1 | 0.9 | 0.9 | C-Model | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7987 | 0 |  |  |  |  | 0 |  | WK5
144 | 12.312 | Convert PAL implementation of streamout to sw solution enables GDS removal | Xiaojing | SIO |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
145 | 12.318 | SED<>AID and AID<>AID interfaces must support arbitrary clk deviation, so protocols like valid-only need to be converted. | David/Steven | GC |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Invisible to diags, workload cross the original die interface will cover | 0 |  |  |  |  | 1 |  | WK5
146 | 12.319 | GCRD->GCR response interface to credit/debit | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
147 | 12.32 | GCRD_SE SAX client | Steven/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
148 | 12.321 | Limit wires SED<->AID for PMM Ips | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
149 | 12.322 | GFX12 UTLC2 - Add idle sidebands | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived by design/FET lead | 0 |  |  |  |  | 1 |  | WK10
150 | 12.328 | GFX12 SDMA - Add sidebands to control Idle request | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1 |  | WK5
151 | 12.329 | remove GCR dummy UTCL2 invalidation interface | Steven | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
152 | 12.332 | GFX12 EA - Add idle sidebands | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1 |  | WK10
153 | 12.333 | Swap PRIM_CONFIG register to SA_UNIT_DISABLE register | David | GC |  |  | P2 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
154 | 12.334 | GTS support in GFX12 | David | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
155 | 12.336 | Remove harvesting connectivity/RTL mux in SP | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
156 | 12.339 | GFX12 IH Gasket update for chiplet design | Sid | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
157 | 12.342 | GFX12 IMU - Add FIFO for blocked RSMU writes and keep read outstanding | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1 |  | WK5
158 | 12.343 | SPM sample sync across AID and GFX to DF | Dennis | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
159 | 12.344 | Faulting illegal ops to PCIE | Steven/JJ/Anthony | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
160 | 12.349 | Perfmon: GFX - Convert all counter modules to SPM-only mode | Yu Xuan | GC |  |  | P2 | std1.6 with pv_proxy library | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
161 | 12.356 | Perfmon: GFX - GFX SPM sampling window to be driven by REFCLK | Yu Xuan | GC |  |  | P1 | rlc1.0 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK5
162 | 12.357 | Perfmon: GFX - SQ counters to support shader type filters per individual counter | Dennis | GC |  |  | P1 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
163 | 12.358 | Perfmon: GFX - Custom data injection from CP into SPM with delta counters | Yu Xuan | GC |  |  | P2 | rlc1.0, rlc1.1 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 0 |  |  |  |  | 0 |  | WK10
164 | 12.36 | WMMA wave level matrix load Instruction | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
165 | 12.361 | Perfmon: GFX - VMID Specific Profiling/Debugging | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
166 | 12.366 | NV4x: Perfmon: Review and refinement of available perf counter events for GC and DF | Dennis | GC |  |  | TBD |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | GFX IPSE will cover the Perfmon related features | 0 |  |  |  |  | 1 |  | WK5
167 | 12.37 | Fix VOPD dual V_MOV | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
168 | 12.373 | Modification of GS throttle (due to 12.118 ph_memory_queues) | Xiaojing | GEO |  |  | P1 |  | TServer |  | 1 | 4 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
169 | 12.374 | MEM_PWR_CTRL Bus increase to support FGCG | Pierce | GC |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
170 | 12.382 | [Strix] pbb_tile_order_rev -- from BRP:11.5.017 | Steven/David | PP |  |  | P2 |  |  |  | 1 | 0 | Legacy | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Driver team will verify this | 0 |  |  |  |  | 1
171 | 12.387 | Block Initiatives |  | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not a feature | 0 |  |  |  |  | 1
172 | 12.389 | GFX EDC Controller using XVmin/Mafdd |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
173 | 12.392 | NV4x: GFX Cac Events selection enhancement |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
174 | 12.393 | GFX PCC latency optimization |  | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
175 | 12.396 | Airtight FIFO Design Robustness | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | The change is a quality initiative, and transparent to software. | 0 |  |  |  |  | 1 |  | WK5
176 | 12.397 | Benchmark Stimulus Replay at Block | Xiaojing | GFX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1 |  | WK10
177 | 12.398 | Adoption of RDL2RTL | Xiaojing | GFX |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1 |  | WK10
178 | 12.399 | Remove Coverage into Render Targets | Steven/David | PP |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Design confirmed feature is fully dropped | 0 |  |  |  |  | 1 |  | WK5
179 | 12.4 | SRAM Bit/byte write enable | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pure H/W change which impacts the SRAM access. This would be covered implicitly by running various 3D/Compute workload. There is no need to develop a target test case for this feature. | 0 |  |  |  |  | 1 |  | WK5
180 | 12.401 | Improving MBFF ratio (Octa/Hexa Flops) | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not applicable to our scope and waived | 0 |  |  |  |  | 1 |  | WK10
181 | 12.402 | Repeater Clock Gating (Clock Gating Efficiency focus) | Pierce | GFX |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
182 | 12.403 | MGCG partitioning (Goal is to reduce gating residency of MGCG domains. Power saved is function of reduction in MGCG domain clock residency, and physical partitioning of domain (size of domain, clones, ICG placement, pre MGCG power). | Pierce | GFX |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
183 | 12.406 | With GPO enabled, perfmon clock and flops connected to it are currently not gated. Proposal is to improve clock gating of “event” flops and counters used in performance monitor logic | Pierce | GFX |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
184 | 12.41 | User Data Scatter Engine (RS64) | Pierce | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removed, DEGFX12-10852 | 0 |  |  |  |  | 1 |  | WK5
185 | 12.411 | Replace SDMA F32 with RS64 | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1 |  | WK10
186 | 12.412 | Enable GPA in UTCL0 of SAx GL1C | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 | WGS dependent | 0 |  |  |  |  | 0 |  | WK5
187 | 12.413 | Switch GFX to Memgen-based SRAM FGCG | Pierce | GC |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
188 | 12.414 | Add an L1 TLB into the SDMA front-end | Steven | UTCL2 |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | OSS diag will provide coverage | 0 |  |  |  |  | 1 |  | WK5
189 | 12.417 | GFX12 IMU - Add light sleep and deep sleep to SRAMs | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not POR for NV48/44 | 0 |  |  |  |  | 1 |  | WK5
190 | 12.418 | GFX12 IMU - Add deep sleep support and sideband for IMUCLK | David/Steven | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not POR for NV48/44 | 0 |  |  |  |  | 1 |  | WK5
191 | 12.42 | Increase max scratch allocation | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
192 | 12.421 | TOC updates for RLC FW | David | CTL |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 | Indrect coverage with front door loading | 0 |  |  |  |  | 0 |  | WK5
193 | 12.422 | Navi4c (chiplet) GFXIP STA Targets | Xiaojing | GFX |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | The feature is not applicable to Navi44/48. Please remove this from your feature list. | 0 |  |  |  |  | 1 |  | WK5
194 | 12.425 | GE WD_QOS.DRAW_STALL behavior | Xiaojing | GEO |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Feature removal, no software visibility. | 0 |  |  |  |  | 1 |  | WK10
195 | 12.429 | HP64 child reuse | Frank | TEX |  |  | TBD |  | Tserver |  | 1 | 1 | New | 1 | 0.4 | 0.4 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7
196 | 12.43 | Ray Tracing Tri Pair optimization | Frank/Jeff Wheeler | TEX |  |  | TBD |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK1
197 | 12.438 | Remove Soft Lock feature | Xiaojing | SIO |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a removal, and no direct coverage is required. Makhan/Wanshou to check with Arch and waive from PostSi coverage. | 0 |  |  |  |  | 1 |  | WK10
198 | 12.439 | Improve register based invalidation | Steven/Glenn | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
199 | 12.44 | Make SE CAC Counters accessible over Debug Bus |  | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1
200 | 12.441 | reduce VGPRs for LS and ES stages | Xiaojing | SIO |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Feature removal inside hardware, no software visibility. | 0 |  |  |  |  | 1 |  | WK10
201 | 12.442 | EA and GL2CC move from GRBM to GRBMH | Steven/Glenn | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IPSE confirmed chiplet only | 0 |  |  |  |  | 1 |  | WK10
202 | 12.444 | Expand V# const_stride from 14 to 17 bit width | Frank/Jeff Wheeler | TEX |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
203 | 12.445 | Improve Thread Trace ExecPopCount bandwidth | Shuhui | SH |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
204 | 12.446 | Load_reserved/store_conditional support in SE$ | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 | WGS related | 0 |  |  |  |  | 0 |  | WK10
205 | 12.447 | Load_reserved/store_conditional support in DF | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 | WGS related | 0 |  |  |  |  | 0 |  | WK10
206 | 12.448 | Change flags encoded in barycentrics to simplify detection of procedural nodes | Frank/Jeff Wheeler | TEX |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
207 | 12.449 | Remove culling with skip_triangles in TA | Frank/Jeff Wheeler | TEX |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
208 | 12.45 | Add AtomicAdd packed math for F16 | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
209 | 12.451 | Extend compression control support in Texture | Frank/Jeff Wheeler | TEX |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
210 | 12.452 | Breaking SE reuse in Navi48 | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | No direct coverage required | 0 |  |  |  |  | 1 |  | WK10
211 | 12.453 | Add HS and GS Stages to event collection for PS_DONE and PS_PARTIAL_FLUSH | Xiaojing | SIO |  |  | P2 |  | TServer |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
212 | 12.454 | Proper Handling of the Force Decompression and Comp Key Read Command on compression-bypassed resources | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
213 | 12.455 | Decrease CS max grid size support to X,Y,Z = 32b,16b,16b | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
214 | 12.457 | Decrompress BLTs via SDMA | Yu Xuan | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 |  | 0 |  |  |  |  | 1 |  | WK10
215 | 12.458 | Descope VRS Compression feature | Steven/David | PP |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
216 | 12.459 | Remove support for Shared VGPRs and Subvector Execution | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1
217 | 12.46 | BVH Footprint Improvement | Frank/Jeff Wheeler | TEX |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
218 | 12.461 | RT support for OBB and Instance Node Intersection | Frank/Jeff Wheeler | TEX |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
219 | 12.462 | Descope Verification of 16xaa for VRS Coarse Rates (1x2, 2x2, 2x1) | Steven/David | PP |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Removal feature, not visible to diags | 0 |  |  |  |  | 1
220 | 12.463 | GFXCLK Deep Sleep trigger based on XVMIN | David/Steven | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | PPA team will enable this, IPSE team will verify | 0 |  |  |  |  | 1 |  | WK10
221 | 12.464 | SP Throttling and the first DIDT droop | Shuhui | SH |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags | 0 |  |  |  |  | 1 |  | WK10
222 | 12.465 | SP src operand invalidated by td/lds return | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
223 | 12.466 | Distributed DIDT controller | Pierce | CTL |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
224 | 12.467 | GRBM/H SYNC registers | Daniel G | CTL |  |  | P1 |  | TNG |  | 1 | 2 | New | 1 |  | 0 | C-Model | 2 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
225 | 12.468 | RS64: Adding performance features for both Navi4x and MI400 | Daniel G | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Risc-V features, will be tested by IPSE team | 0 |  |  |  |  | 1 |  | WK10
226 | 12.469 | F8 1.4.3 IEEE mode behavior change (match with NV) | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 | 0.1 | 0.1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
227 | 12.47 | RS64: No support for OOO IO read and write memory transactions | Steven | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Emulator | 1 | 0 |  |  |  |  | 0 | Will use MHUB team's ATHUB RAW check and Single VC for GFX IO test's CPWD variation as coverage | 0 |  |  |  |  | 0 |  | WK5
228 | 12.471 | Save and Restore of perfcounter and ttrace enable for GFXOFF/SRIOV | Xiaojing | SIO |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
229 | 12.473 | GL2 shared across all SEs for Navi44/48 | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 | Indirect coverage | 0 |  |  |  |  | 0 |  | WK5
230 | 12.474 | 2x MLOPs performance | Shuhui | SH |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 | 0.1 | 0.1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
231 | 12.475 | IO traffic can potentially block DRAM traffic | Glenn/Javad | CMM |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Confirmed ownership has been passed to SDMA team for perf verfication | 0 |  |  |  |  | 1 |  | WK5
232 | 12.476 | Descope 8xaa for VRS coarse rates (1x2, 2x2, 2x1) | Steven/David | PP |  |  | P3 |  | TNG |  | 1 | 1 | New | 0.5 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK14
233 | 12.477 | Hook up AVFS debug bus to debug bus chains in 4 gc_2gl2c_1_tiles | Daniel G | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Not visible to diags, will be tested by IPSE team | 0 |  |  |  |  | 1 |  | WK14
234 | 12.479 | Add Ordered-Add memory atomic for faster SW Streamout (global_atomic_ordered_add_b64) | Glenn/Javad/JJ/Anthony | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
235 | 12.48 | Move GFX PSMs to faster clock for faster DIDT controller response | Dennis | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived. PMM Diags, Tools team, and PPA team should cover this. | 0 |  |  |  |  | 1
236 | 12.483 | Processor controllable performance counters for CP Bottleneck profiling | Daniel G | CTL |  |  | P3 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK14
237 | 12.484 | decoding of op ATOMIC_UMAX_8_NO_RTN from EA to SDP is not expected | Glenn/Steven/Frank/Jeff W | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 1 |  | 0 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
238 | 12.485 | Navi4 GFXIMU Interrupt Capability | David | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this | 0 |  |  |  |  | 1 |  | WK14
239 | 12.486 | Allow GFX doorbells through IMU doorbell fence | Pierce | CTL |  |  | P1 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | IMU team will cover this, in diag this is an indirect coverage through GFXOFF | 0 |  |  |  |  | 1 |  | WK5
240 | 12.487 | Increase DB Z cache size for performance | Steven/David | PP |  |  | P3 |  | TNG |  | 1 | 1 | New | 0.5 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK14
241 | 12.488 | Reduce PBB maximum batch size from 1024 to 512 and constrain the minimum bin size in the PBB to 128 pixels | David/Steven | PP |  |  | P3 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK14
242 | 12.489 | Deprioritize NOT_EOP=1 mode | Xiaojing | GEO |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | This is a pre-silicon initiative thus does not apply to PostSi. We can waive this one from PostSi coverage. Makhan/Wanshou to align with design team accordingly. | 0 |  |  |  |  | 1 |  | WK14
243 | 12.49 | GFXCLK has risk to achieve 3.46GHz due to AR change | Dennis | PD |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Waived. PMM Diags and PPA team should cover this. | 0 |  |  |  |  | 1
244 | 12.493 | Add new jump table for SET_SH_REG and SET_SH_REG_PAIRS when packet count=1 and state is clean | Dennis | CTL |  |  | P3 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Indirect coverage with updated/correct CP FW | 0 |  |  |  |  | 1 |  | WK14
245 | 12.494 | [Navi4m] GRBM Queue to optimize CP processor performance | Daniel G | CTL |  |  | P3 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK14
246 | 12.495 | [RS64] Add Load-IO Custom instruction w/16 CSRs | Daniel G | CTL |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Risc-V feature, will be tested by IPSE team | 0 |  |  |  |  | 1 |  | WK10
247 | 12.497 | load_reserved store_conditional unitID aliasing requires a change in GFX client unitID values | Glenn/Javad | CMM |  |  | P1 |  | TNG |  | 1 | 1 | New | 0 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 | WGS related | 0 |  |  |  |  | 0 |  | WK5
248 | 12.498 | Increase in DB FIFOs for Write-Only Performance | Steven/David | PP |  |  | P1 |  | TNG |  | 1 | 1 | New | 0.5 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5
249 | 12.499 | CB/DB compress to clear/single before sending to GLx | Glenn/Javad | CMM |  |  | P2 |  | TNG |  | 1 | 1 | New | 0.8 |  | 0 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK10
250 | 12.5 | 2ch_cant_saturate_pcie_rdBW | Glenn/Javad | CMM |  |  | P2 |  |  |  | 1 | 0 | New | 1 |  | 1 |  | 0 | 0 |  |  |  |  | 1 | Confirmed ownership has been passed to SDMA team for perf verfication | 0 |  |  |  |  | 1 |  | WK10