## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | NV4x-MTAG-0006 | DF4.0 MemClear |  | DCQ |  | Full FB fill - HDP, CPDMA | P2 | umc1.1,2.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+1wk
1 | UMCRTG-IP10-24 | [GDDR6] Supported DRAM density |  | DCQ |  | Full FB fill - CPDMA/SDMA | P1 | umc1.4/5 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | Emulator | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+1wk
2 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Full FB fill - Compute Shader | P1 | umc1.3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
3 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Write Only | P1 | umc1.820,822.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+3wk
4 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Read Only | P1 | umc1.821,823.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+3wk
5 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Compute Shader Read/Compare | P1 | umc1.825 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
6 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | Memory Cell Pattern | P1 | umc375.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
7 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | Memory Cell Pattern using SDMA | P1 | umc381.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
8 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | HDP version | P1 | umc3.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
9 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CP-DMA version | P1 | umc5.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
10 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CP-DMA/MCB version | P1 | umc6.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
11 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CB version | P1 | umc7.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
12 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | CB/MCB version | P1 | umc8.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
13 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | DRMDMA version | P1 | umc24.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
14 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | DRMDMA/MCB version | P1 | umc25.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
15 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | HDP version | P1 | umc9.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
16 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CP-DMA version | P1 | umc10.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
17 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CP-DMA/MCB version | P1 | umc11.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
18 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CB version | P1 | umc12.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
19 | UMCRTG-IP10-32 | [GDDR6] Masked/Partial Writes |  | ARB |  | CB/MCB version | P1 | umc13.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+2wk
20 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit | P1 | umc369.2,3.1-8,5.1-8,6.1-8,8.1-8,9.1-8,11.1-8,12.1-8 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 7 | 7 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
21 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Randmask | P1 | umc370.2,3.1-8,5.1-8,6.1-8,8.1-8,9.1-8,11.1-8,12.1-8 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 6 | 6 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
22 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Randbit | P1 | umc371.2,3.1-8,5.1-8,6.1-8,8.1-8,9.1-8,11.1-8,12.1-8 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 6 | 6 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
23 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit with Nominal DC SSO | P1 | umc376.6-15 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
24 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit 128-bit SSO | P1 | umc382.1-90 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 90 | Legacy | 1 | 90 | 1 | N-1 | 90 | 90 | 90 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
25 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit with Mask @16bpp | P1 | umc378.1-60 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 60 | Legacy | 1 | 60 | 1 | N-1 | 60 | 60 | 60 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
26 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle Walkbit with Mask @32bpp | P1 | umc379.1-124 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 124 | Legacy | 1 | 124 | 1 | N-1 | 124 | 124 | 124 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
27 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | CP-DMA version | P1 | umc372 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
28 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | SDMA version | P1 | umc380 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
29 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle with PRBS pattern | P1 | umc383.1-4,10-19.1-14 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 14 | Legacy | 1 | 14 | 1 | N-1 | 14 | 14 | 14 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
30 | NAVI40-IPNAVI4x-22 | DPM (Dynamic Power Management) on UCLK |  | SPAZ |  | UMC301 - Moving Blt Colorbar | P1 | umc301.2,3.1-13,5-7.1-13,9.1-13,11-13.1-13,21.1-13,22.1-13,24.1-13,25.1-13 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Delta | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
31 | UMCRTG-IP10-35 | [GDDR6] DPM State support for UCLK |  | SPAZ |  | UMC302 - Moving Blt Walkbit | P2 | umc302.2,3.1-38,5.1-38,6.1-38,7.1-38,9.1-38,11.1-38,12.1-38,13.1-38,21.1-38,22.1-38,24.1-38,25.1-38,101.1-38,102.1-38,103.1-38,104.1-38,105.1-38,501.1-38,502.1-38,503.1-38,504.1-38,505.1-38,511.1-38,512.1-38,513.1-38,514.1-38,515.1-38,551.1-38,552.1-38,553.1-38,554.1-38,555.1-38,561.1-38,562.1-38,563.1-38,564.1-38,565.1-38 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+3wk
32 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC303 – Moving Blt Walkpat | P1 | umc303.2,3.1-23,5.1-23,6.1-23,7.1-23,9.1-23,11.1-23,12.1-23,13.1-23,21.1-23,22.1-23,24.1-23,25.1-23,101.1-23,102.1-23,103.1-23,104.1-23,105.1-23,301.1-23,302.1-23,303.1-23,304.1-23,305.1-23 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
33 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC304 – Moving Blt Maskpat | P1 | umc304.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
34 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC305 – Moving Blt Randbit | P1 | umc305.2,3.1-53,5.1-53,6.1-53,7.1-53,9.1-53,11.1-53,12.1-53,13.1-53,21.1-53,22.1-53,24.1-53,25.1-53,101.1-53,102.1-53,103.1-53,104.1-53,105.1-53,201.1-53,202.1-53,203.1-53,204.1-53,205.1-53,301.1-53,302.1-53,303.1-53,304.1-53,305.1-53,401.1-53,402.1-53,403.1-53,404.1-53,405.1-53,501.1-53,502.1-53,503.1-53,504.1-53,505.1-53,511.1-53,512.1-53,513.1-53,514.1-53,515.1-53,551.1-53,552.1-53,553.1-53,554.1-53,555.1-53,561.1-53,562.1-53,563.1-53,564.1-53,565.1-53 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
35 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC306 – Moving Blt Randmask | P1 | umc306.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
36 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC307 - Horizontal Blt Colorbar | P1 | umc307.2,3.1-13,5.1-13,6.1-13,7.1-13,9.1-13,11.1-13,12.1-13,13.1-13,21.1-13,22.1-13,24.1-13,25.1-13 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
37 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC308 - Horizontal Blt Walkbit | P1 | umc308.2,3.1-38,5.1-38,6.1-38,7.1-38,9.1-38,11.1-38,12.1-38,13.1-38,21.1-38,22.1-38,24.1-38,25.1-38,101.1-38,102.1-38,103.1-38,104.1-38,105.1-38,501.1-38,502.1-38,503.1-38,504.1-38,505.1-38,511.1-38,512.1-38,513.1-38,514.1-38,515.1-38,551.1-38,552.1-38,553.1-38,554.1-38,555.1-38,561.1-38,562.1-38,563.1-38,564.1-38,565.1-38 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
38 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC309 - Horizontal Blt Walkpat | P1 | umc309.2,3.1-23,5.1-23,6.1-23,7.1-23,9.1-23,11.1-23,12.1-23,13.1-23,21.1-23,22.1-23,24.1-23,25.1-23,101.1-23,102.1-23,103.1-23,104.1-23,105.1-23,301.1-23,302.1-23,303.1-23,304.1-23,305.1-23 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
39 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC310 - Horizontal Blt Maskpat | P1 | umc310.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
40 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC311 - Horizontal Blt Randbit | P1 | umc311.2,3.1-53,5.1-53,6.1-53,7.1-53,9.1-53,11.1-53,12.1-53,13.1-53,21.1-53,22.1-53,24.1-53,25.1-53,101.1-53,102.1-53,103.1-53,104.1-53,105.1-53,201.1-53,202.1-53,203.1-53,204.1-53,205.1-53,301.1-53,302.1-53,303.1-53,304.1-53,305.1-53,401.1-53,402.1-53,403.1-53,404.1-53,405.1-53,501.1-53,502.1-53,503.1-53,504.1-53,505.1-53,511.1-53,512.1-53,513.1-53,514.1-53,515.1-53,551.1-53,552.1-53,553.1-53,554.1-53,555.1-53,561.1-53,562.1-53,563.1-53,564.1-53,565.1-53 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
41 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC312 - Horizontal Blt Randmask | P1 | umc312.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
42 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC313 - Diagonal Blt Colorbar | P1 | umc313.2,3.1-13,5.1-13,6.1-13,7.1-13,9.1-13,11.1-13,12.1-13,13.1-13,21.1-13,22.1-13,24.1-13,25.1-13 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
43 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC314 - Diagonal Blt Walkbit | P1 | umc314.2,3.1-38,5.1-38,6.1-38,7.1-38,9.1-38,11.1-38,12.1-38,13.1-38,21.1-38,22.1-38,24.1-38,25.1-38,101.1-38,102.1-38,103.1-38,104.1-38,105.1-38,501.1-38,502.1-38,503.1-38,504.1-38,505.1-38,511.1-38,512.1-38,513.1-38,514.1-38,515.1-38,551.1-38,552.1-38,553.1-38,554.1-38,555.1-38,561.1-38,562.1-38,563.1-38,564.1-38,565.1-38 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
44 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC315 - Diagonal Blt Walkpat | P1 | umc315.2,3.1-23,5.1-23,6.1-23,7.1-23,9.1-23,11.1-23,12.1-23,13.1-23,21.1-23,22.1-23,24.1-23,25.1-23,101.1-23,102.1-23,103.1-23,104.1-23,105.1-23,301.1-23,302.1-23,303.1-23,304.1-23,305.1-23 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
45 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC316 - Diagonal Blt Maskpat | P1 | umc316.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
46 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC317 - Diagonal Blt Randbit | P1 | umc317.2,3.1-53,5.1-53,6.1-53,7.1-53,9.1-53,11.1-53,12.1-53,13.1-53,21.1-53,22.1-53,24.1-53,25.1-53,101.1-53,102.1-53,103.1-53,104.1-53,105.1-53,201.1-53,202.1-53,203.1-53,204.1-53,205.1-53,301.1-53,302.1-53,303.1-53,304.1-53,305.1-53,401.1-53,402.1-53,403.1-53,404.1-53,405.1-53,501.1-53,502.1-53,503.1-53,504.1-53,505.1-53,511.1-53,512.1-53,513.1-53,514.1-53,515.1-53,551.1-53,552.1-53,553.1-53,554.1-53,555.1-53,561.1-53,562.1-53,563.1-53,564.1-53,565.1-53 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
47 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC318 - Diagonal Blt Randmask | P1 | umc318.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
48 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC319 - Random Blt Colorbar | P1 | umc319.2,3.1-13,5.1-13,6.1-13,7.1-13,9.1-13,11.1-13,12.1-13,13.1-13,21.1-13,22.1-13,24.1-13,25.1-13 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
49 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC320 - Random Blt Walkbit | P1 | umc320.2,3.1-38,5.1-38,6.1-38,7.1-38,9.1-38,11.1-38,12.1-38,13.1-38,21.1-38,22.1-38,24.1-38,25.1-38,101.1-38,102.1-38,103.1-38,104.1-38,105.1-38,501.1-38,502.1-38,503.1-38,504.1-38,505.1-38,511.1-38,512.1-38,513.1-38,514.1-38,515.1-38,551.1-38,552.1-38,553.1-38,554.1-38,555.1-38,561.1-38,562.1-38,563.1-38,564.1-38,565.1-38 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
50 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC320 - Random Blt WalkPat | P1 | umc321.2,3.1-23,5.1-23,6.1-23,7.1-23,9.1-23,11.1-23,12.1-23,13.1-23,21.1-23,22.1-23,24.1-23,25.1-23,101.1-23,102.1-23,103.1-23,104.1-23,105.1-23,301.1-23,302.1-23,303.1-23,304.1-23,305.1-23 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | Emulator | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
51 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC322 - Random Blt Maskpat | P1 | umc322.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
52 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC323 - Random Blt Randbit | P1 | umc323.2,3.1-53,5.1-53,6.1-53,7.1-53,9.1-53,11.1-53,12.1-53,13.1-53,21.1-53,22.1-53,24.1-53,25.1-53,101.1-53,102.1-53,103.1-53,104.1-53,105.1-53,201.1-53,202.1-53,203.1-53,204.1-53,205.1-53,301.1-53,302.1-53,303.1-53,304.1-53,305.1-53,401.1-53,402.1-53,403.1-53,404.1-53,405.1-53,501.1-53,502.1-53,503.1-53,504.1-53,505.1-53,511.1-53,512.1-53,513.1-53,514.1-53,515.1-53,551.1-53,552.1-53,553.1-53,554.1-53,555.1-53,561.1-53,562.1-53,563.1-53,564.1-53,565.1-53 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
53 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC324 - Random Blt Randmask | P1 | umc324.2,3.1-12,5.1-12,6.1-12,8.1-12,9.1-12,11.1-12,12.1-12,101.1-12,201.1-12,301.1-12,401.1-12 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 12 | Legacy | 1 | 12 | 1 | N-1 | 12 | 12 | 12 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
54 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC210 - Vertical Blt Colorbar | P1 | umc210.2,3.1-13,5.1-13,6.1-13,7.1-13,9.1-13,11.1-13,12.1-13,13.1-13,21.1-13,22.1-13,24.1-13,25.1-13 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 13 | Legacy | 1 | 13 | 1 | N-1 | 13 | 13 | 13 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
55 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC211 - Vertical Blt Walkbit | P1 | umc211.2,3.1-38,5.1-38,6.1-38,7.1-38,9.1-38,11.1-38,12.1-38,13.1-38,21.1-38,22.1-38,24.1-38,25.1-38,101.1-38,102.1-38,103.1-38,104.1-38,105.1-38,501.1-38,502.1-38,503.1-38,504.1-38,505.1-38,511.1-38,512.1-38,513.1-38,514.1-38,515.1-38,551.1-38,552.1-38,553.1-38,554.1-38,555.1-38,561.1-38,562.1-38,563.1-38,564.1-38,565.1-38 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 38 | Legacy | 1 | 38 | 1 | N-1 | 38 | 38 | 38 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
56 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC212 - Vertical Blt Walkpat | P1 | umc212.2,3.1-23,5.1-23,6.1-23,7.1-23,9.1-23,11.1-23,12.1-23,13.1-23,21.1-23,22.1-23,24.1-23,25.1-23,101.1-23,102.1-23,103.1-23,104.1-23,105.1-23,301.1-23,302.1-23,303.1-23,304.1-23,305.1-23 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 23 | Legacy | 1 | 23 | 1 | N-1 | 23 | 23 | 23 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
57 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC213 - Vertical Blt Maskpat | P1 | umc213.2,3.1-8,5.1-8,6.1-8,8.1-8,9.1-8,11.1-8,12.1-8 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
58 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC214 - Vertical Blt Randbit | P1 | umc214.2,3.1-53,5.1-53,6.1-53,7.1-53,9.1-53,11.1-53,12.1-53,13.1-53,21.1-53,22.1-53,24.1-53,25.1-53,101.1-53,102.1-53,103.1-53,104.1-53,105.1-53,201.1-53,202.1-53,203.1-53,204.1-53,205.1-53,301.1-53,302.1-53,303.1-53,304.1-53,305.1-53,401.1-53,402.1-53,403.1-53,404.1-53,405.1-53,501.1-53,502.1-53,503.1-53,504.1-53,505.1-53,511.1-53,512.1-53,513.1-53,514.1-53,515.1-53,551.1-53,552.1-53,553.1-53,554.1-53,555.1-53,561.1-53,562.1-53,563.1-53,564.1-53,565.1-53 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 53 | Legacy | 1 | 53 | 1 | N-1 | 53 | 53 | 53 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
59 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC215 - Vertical Blt Randmask | P1 | umc215.2,3.1-8,5.1-8,6.1-8,8.1-8,9.1-8,11.1-8,12.1-8 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
60 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC216 - Vertical Blt SSOmask | P1 | umc216.2,3.1-8,5.1-8,6.1-8,8.1-8,9.1-8,11.1-8,12.1-8 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
61 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Power Virus Test | P1 | umc56.153,154.1-7,155.1-7,156.1-7,157.1-7,158.1-7,159.1-7 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 7 | Delta | 1 | 7 | 1 | N-1 | 7 | 7 | 7 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
62 | UMCRTG-IP10-30 | Clock Gating |  | SPAZ |  | MACO SR | P1 | umc49.1 | Tserver | -d=1 -v=error -cf=stutter.cf -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 | using umc1.1 test and -nogc -nobios due to BAMACO core off, and adding VCN power off command in advance | AB+8wk | DIAG-13378 having issue and fix
63 | UMCRTG-IP10-39 | PG (Power Gating) |  | SPAZ |  | Static Screen Stutter Mode | P2 | umc1.50 | Tserver | -d=1 -v=error -cf=stutter.cf -log | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 | -D702, BRP025 IFWI, -ppmode=1(agt 3.1.9.0), D701 BRP042diag IFWI | AB+8wk
64 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | REC |  | monitor edc counter | P1 | event_handler_3 | Tserver | -chkedc=all -edcthresh=1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
65 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | WAW – write after write | P1 | umc681.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  | 1 | 0 | [6 empty] | 0 |  | AB+4wk
66 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | RAW – read after write | P1 | umc681.2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
67 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | VC-based Priority Adjustment | P1 | umc683.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 |  |  |  | 1 | 0 | [6 empty] | 0 | display should be connected w/o "-disable_libdce" | AB+4wk
68 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | ARB |  | Bypass Priority Escalation Mode | P1 | umc684.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
69 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | SLT Functional | P1 | umc401.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
70 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Board Functional | P1 | umc413.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
71 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Board Stress | P1 | umc404.1-3,11-13.1-6 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 6 | Legacy | 1 | 6 | 1 | N-1 | 6 | 6 | 6 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
72 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Board Extra | P1 | umc405.1-5,11-15.1-10 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 10 | Legacy | 1 | 10 | 1 | N-1 | 10 | 10 | 10 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
73 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Memfa test | P1 | umc600.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Legacy | 1 |  | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+4wk
74 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Memfa test | P1 | umc601.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Legacy | 1 |  | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+4wk
75 | UMCRTG-IP10-21 | Bank Grouping |  | FEI |  | BW test | P1 | umc70.1,2.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 2 | new | 1 |  | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+6wk
76 | NAVI40-SOCPRS-312 | SOC and DF team support for each single MCD (or PHY) configuration. |  | PMC |  | general event monitor | P1 | event_handler_5 | Tserver | -mcpmcevents | 1 | 1 | Delta | 1 | 1 | 1 | Emulator | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+2wk
77 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | MCA |  | UmcGeccErrorInjectionTest | P1 | umc751.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Delta | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
78 | UMCRTG-IP10-15 | DRAM Error Injection |  | MCA |  | UmcGeccErrorInjectionTest | P1 | umc751.2,3.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+7wk
79 | UMCRTG-IP10-12 | UER is Fatal |  | MCA |  | UmcGeccErrorInjectionTest-IH | P1 | umc752.5 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 1 | Legacy | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+7wk
80 | UMCRTG-IP10-17 | Patrol Scrubber |  | MCA |  | Patrol Scrubber | P1 | umc753.1,2.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+7wk
81 | UMCRTG-IP10-18 | Redirect scrubber |  | MCA |  | Redirect Scrubber | P1 | umc753.3,4.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Delta | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+6wk
82 | UMCRTG-UMC130-15 | Parity check on MP sram |  | MCA |  | LM32 SRAM Parity | P2 | umc764.1,2.1-2 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc -memfa_mem=1 | 1 | 2 | Legacy | 1 | 2 | 1 | N-1 | 2 | 2 | 2 |  |  |  | 1 | [6 empty] | 0 |  | AB+8wk
83 | Intenal_Debug | Internal debug purpose |  | Debug |  | FB Dump Test | P3 | umc510.1-4,6-9.1-8 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 8 | Legacy | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
84 | Intenal_Debug | Internal debug purpose |  | Debug |  | Channel mapping verification | P3 | umc553.1 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 1 | Legacy | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
85 | Intenal_Debug | Internal debug purpose |  | Debug |  | Tacl debug | P3 | umc506.1,2.1-3,3.1-3 | Tserver | -d=1 -v=error -no_toollib -load_ucode=tcore -pm4rb=system -pm4ib=system -pm4rbsize=0x20000 -tc_TCorePreferSysmemInternally -log -mall_config_mode=gncm_noalloc | 1 | 3 | Legacy | 1 | 3 | 1 | Emulator | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
86 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | power_virus_combo_composite | P1 | umc.power_virus_combo_composite.1-8 | TNG |  | 1 | 8 | new | 1 | 8 | 1 | N-1 | 8 | 8 | 8 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
87 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | stress_blt_composite | P1 | umc.stress_blt_composite.1-9 | TNG |  | 1 | 9 | new | 1 | 9 | 1 | N-1 | 9 | 9 | 9 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
88 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Full FB fill - Compute Shader | P1 | umc.full_fb_test/fill | TNG |  | 1 | 1 | new | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
89 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Write Only | P1 | umc.full_fb_rw_only/write_only.1-3 | TNG |  | 1 | 3 | new | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+3wk
90 | UMCRTG-IP10-26 | [GDDR6] Supported transfer rate |  | DCQ |  | Compute Shader Read Only | P1 | umc.full_fb_rw_only/read_only.1-3 | TNG |  | 1 | 3 | new | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+3wk
91 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | DCQ |  | Compute Shader Read/Compare | P1 | umc.full_fb_rw_only/read_check.1-3 | TNG |  | 1 | 3 | new | 1 | 3 | 1 | N-1 | 3 | 3 | 3 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
92 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC303 – Moving Blt Walkpat | P1 | umc.blt_composite/classic | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
93 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | UMC320 - Random Blt WalkPat | P1 | umc.blt_composite/random | TNG |  | 1 | 1 | new | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
94 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | BEQ |  | Rect Toggle with PRBS pattern | P1 | umc.rect_toggle_composite | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
95 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | REC |  | monitor edc counter | P1 | umc.checkedc | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
96 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | REC |  | inject edc error | P1 | umc.umc.edc_error_injection | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+4wk
97 | UMCRTG-IP10-30 | Clock Gating |  | SPAZ |  | MACO SR | P1 | umc.umcch_pg_test | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+8wk
98 | UMCRTG-IP10-39 | PG (Power Gating) |  | SPAZ |  | Static Screen Stutter Mode | P2 | umc.full_fb_test/stutter | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+8wk
99 | UMCRTG-UMC130-13 | PHB (Page Hit Burst) |  | BEQ |  | row_hammer_test | P1 | umc.row_hammer_test | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
100 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.dram_stress_march01 | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
101 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.dram_stress_knaizuk_hartman_test | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
102 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.dram_stress_mod3_test | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
103 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | dram_stress_test | P1 | umc.dram_stress_xmarch_test | TNG |  | 1 | 1 | new | 1 | 1 | 1 | N-1 | 1 | [5 empty] | 0 | [6 empty] | 0 |  | AB+4wk
104 | UMCRTG-IP10-4 | Poor Man's GECC Support |  | MCA |  | gecc_error_injection_irritator | P1 | umc.gecc_error_injection | TNG |  | 1 | 1 | new | 1 |  | 0 | N-1 | 1 | [12 empty] | 0 |  | AB+4wk
105 | NAVI40-NAVI4_SYSPRS-109 | Capability and Performance of FB DRAM |  | FEI |  | Memfa test | P1 | umc.memfa_test | TNG |  | 1 | 1 | new | 1 |  | 0 | N-1 | [6 empty] | 0 | [6 empty] | 0 |  | AB+4wk
106 | Intenal_Debug | Internal debug purpose |  | Debug |  | FB Dump Test | P3 | umc.fb_dump.1-4 | TNG |  | 1 | 4 | new | 1 | 4 | 1 | N-1 | 4 | 4 | 4 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk
107 | Intenal_Debug | Internal debug purpose |  | Debug |  | Channel mapping verification | P3 | umc.channel_mapping | TNG |  | 1 | 1 | new | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 | [6 empty] | 0 |  | AB+5wk