## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | STRIX1-SMU-002 | [CLK] Clock Debug Features | Jane | CLK | CLK Debug feature | Tick Counter/Clock Measurement | P2 | PM002.900 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-1
1 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | GFX CLK deepSleep | GFXCLK DS | P2 | PM010.800 | FEATURE_DS_GFXCLK_BIT | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 | Covered by GFX CGCG | wk-2
2 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | SOCCLK DS | P2 | PM010.032 | FEATURE_DS_SOCCLK_BIT, disable_deepsleep_sideband needs to be fixed | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
3 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | LCLK DS | P2 | PM010.033 | FEATURE_DS_LCLK_BIT | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
4 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | SHUBCLK DS | P2 | PM010.039 | FEATURE_DS_SHUBCLK_BIT, disable_deepsleep_sideband needs to be fixed | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
5 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | FCLK DS | P2 | PM010.038 | FEATURE_DS_FCLK_BIT, need to check RSMU counter config | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
6 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | SMNCLK DS | P2 | PM010.036 | FEATURE_DS_SMNCLK_BIT | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
7 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | MP1CLK DS | P2 | PM010.035 | FEATURE_DS_MP1CLK_BIT | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
8 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | VCN DS | P2 | PM010.042 | FEATURE_DS_VCN_BIT | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
9 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | UMCCLK DS | P2 | PM010.045 | -pm_deepsleep_clock=PM_DFS_UMCCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 | VDDOFF covers | wk-2
10 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | ISPCLK DS | P2 | PM010.045 | -pm_deepsleep_clock=PM_DFS_ISPCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
11 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | HSPCLK DS | P2 | PM010.045 | -pm_deepsleep_clock=PM_DFS_HSPCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
12 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | IPUCLK DS | P2 | PM010.045 | -pm_deepsleep_clock=PM_DFS_IPUCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
13 | STRIX1-SMU-003 | [CLK] Deep Sleep | Jane | CLK | SOC CLK DeepSleep | VPECLK DS | P2 | PM010.045 | -pm_deepsleep_clock=PM_DFS_VPECLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-2
14 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: LCLK DFS Sweep Test: Divide by 8 to 128 | P2 | PM002.002 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
15 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: VCLK DFS Sweep Test: Divide by 8 to 128 | P2 | PM002.003 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
16 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: DCLK DFS Sweep Test: Divide by 8 to 128 | P2 | PM002.004 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
17 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: SOCCLK Sweep Test: Divide by 8 to 128 | P2 | PM002.009 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
18 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: DISPCLK Sweep Test: Divide by 8 to 128 | P2 | PM002.025 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
19 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: HSPCLK Sweep Test: Divide by 8 to 128 | P2 | PM002.028 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
20 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: FCLK Sweep Test: Divide by 8 to 128 | P2 | PM015.001 |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Covered by DF-PState | wk-3
21 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: SHUBCLK Sweep Test: Divide by 8 to 128 | P2 | PM002.104 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
22 | STRIX1-SMU-004 | [CLK] DFS | Jane | CLK | DFS sweep | DFS DID Sweep: DPP Sweep Test: Divide by 8 to 128 | P2 | PM002.113 |  | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-3
23 | STRIX1-SMU-005 | [CLK] Dynamic REFCLK Gating | Jane | CLK | DYN refclk gating | Dynamic ReFCLK gating test | P2 | PM002.300 | -pm_clock_domain=PM_DFS_SOCCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | wk-4
24 | STRIX1-SMU-006 | [CLK] FCState | Jane | CLK | CLK FCState | CLKC FCState INST0 | P2 | PM015.001 | -pm_clock_domain=PM_DFS_FCLK | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | [8 empty] | 0 |  |  |  |  | 0 | Not enabled yet. DPM Hasn't been enabled after initializing! | wk-1
25 | STRIX1-SMU-006 | [CLK] FCState | Jane | CLK | CLK FCState | CLKC FCState INST1 | P2 | PM060.005 | -pm_clock_domain=PM_DFS_ACLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | DF-CState covers | wk-1
26 | STRIX1-SMU-007 | [CLK] Fuses | Jane | FUSE | Fuse Check | FUSES check | P2 | PM001.200 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | DIAG-17862
27 | STRIX1-SMU-009 | [CLK] Spread Spectrum | Jane | CLK | CLK SS | Test for SystemPLL_CLKC5 INST0 Spread Spectrum | P2 | PM060.105 | -pm_clock_domain=PM_DFS_DISPCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | [error][-PM-] [device=1] [PID:7f01ca1bd640] Not support this pll type[1] in is_spread_spectrum_enable. [debug][-PM-] [device=1] [PID:7f01ca1bd640] refclk is 48.000000, real_count is 132, timer_threshold is 480. [debug][-PM-] [device=1] [PID:7f01ca1bd640] current clk is PM_DFS_DCLK, and its rate is 13.200000. [debug][-PM-] [device=1] [PID:7f01ca1bd640] refclk is 48.000000, real_count is 132, timer_threshold is 480. [debug][-PM-] [device=1] [PID:7f01ca1bd640] current clk rate is 13.200000. [error][-PM-] [device=1] [PID:7f01ca1bd640] Not support this PLL type:[1] in get_per_vco_config. [debug][-PM-] [device=1] [PID:7f01ca1bd640] Spread Spectrum enable [error][-PM-] [device=1] [PID:7f01ca1bd640] Not support this pll type[1] in enable spread_spectrum [error][-PM-] [device=1] [PID:7f01ca1bd640] clk pll is not changed in ssc, and its orignal rate is 13.200000, min rate in ssc is 13.200000 [error][-PM-] [device=1] [PID:7f01ca1bd640] Not support this PLL type:[1] in get_per_vco_config. [debug][-PM-] [device=1] [PID:7f01ca1bd640] Spread Spectrum disable [error][-PM-] [device=1] [PID:7f01ca1bd640] Not support this pll type[1] in disable spread_spectrum | wk-2
28 | STRIX1-SMU-009 | [CLK] Spread Spectrum | Jane | CLK | CLK SS | Test for SystemPLL_CLKC1_0 Spread Spectrum | P2 | PM060.105 | -pm_clock_domain=PM_DFS_DISPCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
29 | STRIX1-SMU-009 | [CLK] Spread Spectrum | Jane | CLK | CLK SS | Test for SystemPLL_CLKC1_1 Spread Spectrum | P2 | PM060.105 | -pm_clock_domain=PM_DFS_DPPCLK | 1 | 1 | Legacy | 1 | 0.8 | 0.8 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
30 | STRIX1-SMU-011 | [FUSE] Fuse Distribution | Jane | FUSE | Fuse Distribution | PLL/DFS Fuse distribution | P2 | PM001.200 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | DIAG-17862 | wk-3
31 | STRIX1-SMU-014 | [MP1] CRU | Jane | MP1 | SMU MSG Check | Basic smu message check test | P2 | PM080.010 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0
32 | STRIX1-SMU-015 | [MP1] MMHUB IF | Jane | MP1 | SMU MMHUB IF | Transfer agm table by MMHUB data path | P2 | PM082.006 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0
33 | STRIX1-SMU-016 | [MP1] SMN IF | Jane | MP1 | SMU SMN IF | Test GPU address access by SMNIF | P2 | PM082.001 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0
34 | STRIX1-SMU-016 | [MP1] SMN IF | Jane | MP1 | SMU SMN IF | Test MP0 address access by SMNIF | P2 | PM082.002 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0
35 | STRIX1-SMU-017 | [MP1] SRAM | Jane | MP1 | SMU SRAM | System boot OS can verify this feature | P2 | BOOT cover |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-3
36 | STRIX1-SMU-020 | [MP1] SYSTEMHUB IF | Jane | MP1 | SMU SYSHUB IF | Transfer agm table by SYSHUB data path | P2 | PM082.005 | Panmi | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-6
37 | STRIX1-SMU-021 | [MP1] Tensilica | Jane | MP1 | SMU sanity Check | Covered in CRU | P2 | PM080.010 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-4
38 | STRIX1-SMU-023 | [RSMU] AXI and Register Interface | Jane | RSMU | RSMU AXI path | Covered in Timestamp counter | P2 | Timestamp cover |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-3
39 | STRIX1-SMU-025 | [RSMU] Clock Gating Control Registers | Jane | RSMU | RSMU CG | Clock Gating Control Registers | P2 | PM051.010 | -pm_rsmu_inst=gc | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-5
40 | STRIX1-SMU-026 | [RSMU] DPM Signal | Jane | RSMU | RSMU DPM Signal | DPM Signal | P2 | PM051.007 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | there might be some issues with RSMU lib, use HDT to manually test
41 | STRIX1-SMU-028 | [RSMU] Interrupt | Jane | RSMU | RSMU INTR | Interrupt | P2 | PM051.008 | -pm_rsmu_inst=gc | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-4
42 | STRIX1-SMU-030 | [RSMU] Residency Counter | Jane | RSMU | Residency Counter | Coverd by deepsleep | P2 | DeepSleep cover |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-1
43 | STRIX1-SMU-032 | [RSMU] Timestamp Counter | Jane | RSMU | Timestamp | Timestamp counter | P2 | PM051.004 | -pm_rsmu_inst=dmu | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Use lsdma instance, with db32, RSMU_T_RATE 0.1 | wk-3
44 | STRIX1-SMU-033 | [SMUIO] Display Timer | Jane | SMUIO | One-shot mode | Display timer: One-shot mode | P2 | PM001.005 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0
45 | STRIX1-SMU-033 | [SMUIO] Display Timer | Jane | SMUIO | Periodic mode | Display timer: Periodic mode | P2 | PM001.006 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0
46 | STRIX1-SMU-038 | [SMUIO] SVI3 | Jane | SMUIO | SVI3 | VID Sweep - PM_VDDCR_VDD & Telemetry | P2 | PM033.004 | -pm_volt_start=0.75 -pm_volt_end=1.15 -pm_volt_step=0.01 -pm_volt_threshold=0.02 | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-1
47 | STRIX1-SMU-038 | [SMUIO] SVI3 | Jane | SMUIO | SVI3 | VID Sweep - PM_VDDCR_SOC & Telemetry | P2 | PM033.005 | -pm_volt_start=0.90 -pm_volt_end=1.2 -pm_volt_step=0.01 -pm_volt_threshold=0.03 | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-1
48 | STRIX1-SMU-038 | [SMUIO] SVI3 | Jane | SMUIO | SVI3 | Invalid Slave check | P2 | PM033.021 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-1
49 | STRIX1-SMU-038 | [SMUIO] SVI3 | Jane | SMUIO | SVI3 | VID Change wDelay check | P2 | PM033.022 |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-1
50 | STRIX1-SMU-038 | [SMUIO] SVI3 | Jane | SMUIO | SVI3 | PSI Change | P2 | PM033.023 | Panmi | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-1
51 | STRIX1-SMU-038 | [SMUIO] SVI3 | Jane | SMUIO | SVI3 | Clock Gating | P2 | VID Sweep | -pm_svi3_cg_en=1 | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Pass with PM33.4 | wk-1
52 | STRIX1-SMU-041 | [THM] PROCHOT | Jane | THM | THM | Thermal throttling | P2 | PM012.021 | Wenzhao | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Can see Core freq drop to 600MHz | wk-1
53 | STRIX1-SMU-042 | [THM] Temperature Collection and Calculation Using TCON and TMON/RDI Macro | Jane | THM | THM | Temperature collection and calculation using TCON and TMON/RDI macro | P2 | PM013.024 | -pm_thermal_debug=false | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-1
54 | STRIX1-SMU-043 | [THM] Temperature Report Through SMBUS Interface (THM) | Jane | THM | THM | Temperature report through SMBUS interface | P2 | PM013.022 | SMUBS case covers | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-6
55 | STRIX1-SMU-045 | [THM] THM Interrupt to IH | Jane | THM | THM | Covered by Prochot | P2 | Prochot cover |  | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0
56 | STRIX1-SMU-047 | [MSMU] Register access | Jane | MSMU | MSMU | Sanity Register Access | P2 | PM100.001 | -pm_msmu_instance=<0,1> -pm_msmu_cg_save_restore | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
57 | STRIX1-SMU-047 | [MSMU] Register access | Jane | MSMU | MSMU | Instruction RAM and Data RAM | P2 | PM100.002 | -pm_msmu_instance=<0,1> -pm_msmu_cg_save_restore | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
58 | STRIX1-SMU-047 | [MSMU] Register access | Jane | MSMU | MSMU | FSM Read/Write Instruction | P2 | PM100.003 | -pm_msmu_instance=<0,1> -pm_msmu_cg_save_restore | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
59 | STRIX1-SMU-047 | [MSMU] Register access | Jane | MSMU | MSMU | FSM Test/Jump Instruction | P2 | PM100.004 | -pm_msmu_instance=<0,1> -pm_msmu_cg_save_restore | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
60 | STRIX1-SMU-047 | [MSMU] Register access | Jane | MSMU | MSMU | FSM Poll Instruction | P2 | PM100.005 | -pm_msmu_instance=<0,1> -pm_msmu_cg_save_restore | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
61 | STRIX1-SMU-047 | [MSMU] Register access | Jane | MSMU | MSMU | IRAM and DRAM Deep Sleep | P2 | PM100.006 | -pm_msmu_instance=<0,1> -pm_msmu_cg_save_restore | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
62 | STRIX1-SMU-047 | [MSMU] Register access | Jane | MSMU | MSMU | Clock Gating | P2 | PM100.002 | -pm_msmu_instance=<0,1> -pm_msmu_cg_save_restore -pm_msmu_cg_en=1 | 1 | 1 | Legacy | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-2
63 | STRIX1-SMU-049 | CLDO | Jane | CLDO | L3 DFLL |  | P1 | PM033.011 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 |  | wk-3
64 | STRIX1-SMU-051 | VPE On/Off | Jane | RSMU | VPE |  | P1 | PM041.961 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Manually test pass | wk-3
65 | STRIX1-SMU-051 | VPE On/Off | Jane | RSMU | VPE |  | P1 | PM041.962 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | PPSMC_MSG_PowerDownVpe cannot power down VPE. Can manually powerup/down by PGFSM_CONTROL regs. | wk-3
66 | STRIX1-SMU-052 | Power gate/ungate DPIA | Jane | RSMU |  |  | P1 | PM041.963 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | SMU hang. Manually set PGFSM will make RSMU hang. |  | DIAG-18236, DIAG-18447
67 | STRIX1-SMU-052 | Power gate/ungate DPIA | Jane | RSMU | Power Gate |  | P1 | PM041.964 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | SMU hang. Manually set PGFSM will make RSMU hang. | wk-3 | DIAG-18236, DIAG-18447
68 | STRIX1-SMU-053 | Power gate/ungate LSDMA | Jane | RSMU | Power Gate |  | P1 | PM041.965 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Manually test pass | wk-3
69 | STRIX1-SMU-053 | Power gate/ungate LSDMA | Jane | RSMU | Power Gate |  | P1 | PM041.966 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | RSMU_PGFSM regs stay at 0x0 after sending PPSMC_MSG_DisableLSdma. Can manually powerup/down by PGFSM_CONTROL regs. | wk-3
70 | STRIX1-SMU-055 | DFX power gating | Jane | RSMU |  |  | P1 | PM041.967 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Manually test pass. Write 0x1006 to CONTROL reg to check.
71 | STRIX1-SMU-055 | DFX power gating | Jane | RSMU | Power Gate |  | P1 | PM041.968 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Manually test pass. Write 0x1006 to CONTROL reg to check. | wk-3
72 | STRIX1-SMU-056 | Power gate/ungate VCN | Jane | RSMU |  |  | P1 | PM041.969 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Manually test pass
73 | STRIX1-SMU-056 | Power gate/ungate VCN | Jane | RSMU | Power Gate |  | P1 | PM041.970 |  | 1 | 1 | New | 1 | 0.6 | 0.6 | N-1 | 1 | [7 empty] | 0 |  |  |  |  | 0 | Manually test pass | wk-3

## Sheet3
Test Case ID | Duplicates
BOOT cover | Good
DeepSleep cover | Good
PM001.005 | Good
PM001.006 | Good
PM001.200 | Good
PM001.200 | Duplicate
PM002.002 | Good
PM002.003 | Good
PM002.004 | Good
PM002.009 | Good
PM002.025 | Good
PM002.028 | Good
PM002.104 | Good
PM002.113 | Good
PM002.300 | Good
PM002.900 | Good
PM010.032 | Good
PM010.033 | Good
PM010.035 | Good
PM010.036 | Good
PM010.038 | Good
PM010.039 | Good
PM010.042 | Good
PM010.045 | Good
PM010.045 | Duplicate
PM010.045 | Duplicate
PM010.045 | Duplicate
PM010.045 | Duplicate
PM010.800 | Good
PM012.021 | Good
PM013.022 | Good
PM013.024 | Good
PM015.001 | Good
PM015.001 | Duplicate
PM033.004 | Good
PM033.005 | Good
PM033.011 | Good
PM033.021 | Good
PM033.022 | Good
PM033.023 | Good
PM041.961 | Good
PM041.962 | Good
PM041.963 | Good
PM041.964 | Good
PM041.965 | Good
PM041.966 | Good
PM041.967 | Good
PM041.968 | Good
PM041.969 | Good
PM041.970 | Good
PM051.004 | Good
PM051.007 | Good
PM051.008 | Good
PM051.010 | Good
PM060.005 | Good
PM060.105 | Good
PM060.105 | Duplicate
PM060.105 | Duplicate
PM080.010 | Good
PM080.010 | Duplicate
PM082.001 | Good
PM082.002 | Good
PM082.005 | Good
PM082.006 | Good
PM100.001 | Good
PM100.002 | Good
PM100.002 | Duplicate
PM100.003 | Good
PM100.004 | Good
PM100.005 | Good
PM100.006 | Good
Prochot cover | Good
Timestamp cover | Good
VID Sweep | Good