## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID) | Remainder Variations | input variations | org test case id | test_list_id
0 | KRK1-USB4-001 | SB Register Access | Harikrishnan P | USB4 |  | SB Register Access test | P1 | USB4-LL-01 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-LL-01 | 1
1 | KRK1-USB4-002 | Sideband Transactions | Harikrishnan P | USB4 |  | Sideband transaction Tests : LT, AT and RT | P1 | USB4-LL-02 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 5 | 6 | USB4-LL-02 | 2
2 | KRK1-USB4-003 | RS-FEC Activation and Deactivation | Harikrishnan P | USB4 |  | RS-FEC Activation and Deactivation test | P2 | USB4-LL-16 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-LL-16 | 3
3 | KRK1-USB4-004 | Entry to Sleep | Harikrishnan P | USB4 |  | Entry to Sleep test | P2 | USB4-LL-21 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-LL-21 | 4
4 | KRK1-USB4-005 | Behavior in Sleep State | Harikrishnan P | USB4 |  | Behavior in Sleep State test | P2 | USB4-LL-22 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-LL-22 | 5
5 | KRK1-USB4-006 | Wake Events | Harikrishnan P | USB4 |  | Wake Events test | P2 | USB4-LL-23 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-LL-23 | 6
6 | KRK1-USB4-007 | Exit from Sleep | Harikrishnan P | USB4 |  | Exit from Sleep test | P2 | USB4-LL-24 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-LL-24 | 7
7 | KRK1-USB4-008 | Router Configuration Space | Harikrishnan P | USB4 |  | Router Configuration Space test | P1 | USB4-CS-01 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-CS-01 | 8
8 | KRK1-USB4-009 | Adapter Configuration Space | Harikrishnan P | USB4 |  | Adapter Configuration Space test | P1 | USB4-CS-06 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-CS-06 | 9
9 | KRK1-USB4-010 | Path Configuration Space | Harikrishnan P | USB4 |  | Path Configuration Space test | P1 | USB4-CS-14 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-CS-14 | 10
10 | KRK1-USB4-011 | USB4 Host interface test | Harikrishnan P | USB4 |  | Test USB4 HI Programming interface | P2 | USB4-TS-02 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-TS-02 | 11
11 | KRK1-USB4-012 | Type-C Flip Test | Harikrishnan P | USB |  | Type C flip test on USB4 type C ports and USB3.2 Gen2 type C port | P2 | USB4-TS-05 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-TS-05 | 12
12 | KRK1-USB4-013 | USB4 Enumeration and Tunneling performance | Harikrishnan P | USB4 |  | Test USB4 dock enumeration, USB3 tunneling, PCIe tunneling and DP tunneling | P2 | USB4-ENH-01 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-ENH-01 | 13
13 | KRK1-USB4-014 | USB4 Gen3 and Gen2 - Single lane and dual lane operation | Harikrishnan P | USB4 |  | Test USB4 Gen 3 and Gen 2 in single lane and dual lane mode | P2 | USB4-ENH-02 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-ENH-02 | 14
14 | KRK1-USB4-015 | USB4 Alt Modes for Thunderbolt and Display | Harikrishnan P | USB4 |  | USB4 Alt Modes for Thunderbolt and Display with TBT3 devices (hubs and storages) and type C display respectively | P2 | USB4-ENH-03 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-ENH-03 | 15
15 | KRK1-USB4-016 | USB4 PHY tests | Harikrishnan P | USB4 |  | Test USB4 ports with USB4 docks, TBT3 hubs, USB3.2 Gen 1 hub, USB3.2 Gen2 hub | P2 | USB4-ENH-04 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-ENH-04 | 16
16 | KRK1-USB4-017 | USB4 Host to Host tunneling | Harikrishnan P | USB4 |  | USB4 host to host tunneling test | P2 | USB4-ENH-05 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB4-ENH-05 | 17
17 | KRK1-USB-001 | XHCI Register interface | Harikrishnan P | USB |  | Test the XHCI register space for every host controller | P3 | USB-01 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 1 | 2 | USB-01 | 18
18 | KRK1-USB-002 | USB1.1 Low speed device enumeration | Harikrishnan P | USB |  | USB low speed detection and enumeration test | P3 | USB-02 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-02 | 19
19 | KRK1-USB-003 | USB1.1 Full speed device enumeration | Harikrishnan P | USB |  | FS Device-Attach-Detach -Reset | P3 | USB-03 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-03 | 20
20 | KRK1-USB-004 | USB1.1 Full speed bulk stress | Harikrishnan P | USB |  | FS Bulk Stress testing | P3 | USB-04 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-04 | 21
21 | KRK1-USB-005 | USB1.1 Full speed interrupt stress | Harikrishnan P | USB |  | FS Interrupt Stress testing | P3 | USB-05 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-05 | 22
22 | KRK1-USB-006 | USB1.1 Full speed isoch stress | Harikrishnan P | USB |  | FS Isoch Stress testing | P3 | USB-06 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-06 | 23
23 | KRK1-USB-007 | USB2.0 High speed device enumeration | Harikrishnan P | USB |  | HS Device-Attach-Detach-Reset | P3 | USB-07 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-07 | 24
24 | KRK1-USB-008 | USB2.0 High speed bulk stress | Harikrishnan P | USB |  | HS Bulk Stress testing | P3 | USB-08 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-08 | 25
25 | KRK1-USB-009 | USB2.0 High speed interrupt stress | Harikrishnan P | USB |  | HS Interrupt Stress testing | P3 | USB-09 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-09 | 26
26 | KRK1-USB-010 | USB2.0 High speed isoch stress | Harikrishnan P | USB |  | HS Isoch Stress testing | P3 | USB-10 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-10 | 27
27 | KRK1-USB-011 | USB3.2 Gen 1 (Superspeed) device enumeration | Harikrishnan P | USB |  | SS Device-Attach-Detach-Reset Test | P3 | USB-11 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 11 | 12 | USB-11 | 28
28 | KRK1-USB-012 | USB3.2 Gen 1 (Superspeed) Bulk stress | Harikrishnan P | USB |  | SS Bulk Stress testing | P3 | USB-12 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 11 | 12 | USB-12 | 29
29 | KRK1-USB-013 | USB3.2 Gen 1 (Superspeed) Interrupt stress | Harikrishnan P | USB |  | SS Interrupt Stress testing | P3 | USB-13 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 11 | 12 | USB-13 | 30
30 | KRK1-USB-014 | USB3.2 Gen 1 (Superspeed) Isoch stress | Harikrishnan P | USB |  | SS Isoch Stress testing | P3 | USB-14 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 11 | 12 | USB-14 | 31
31 | KRK1-USB-015 | USB3.2 Gen 2 (Superspeed plus) Bulk stress | Harikrishnan P | USB |  | SSP Bulk Stress testing | P3 | USB-15 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 7 | 8 | USB-15 | 32
32 | KRK1-USB-016 | USB3.2 Gen 2 (Superspeed plus) Interrupt stress | Harikrishnan P | USB |  | SSP Interrupt Stress testing | P3 | USB-16 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 7 | 8 | USB-16 | 33
33 | KRK1-USB-017 | USB3.2 Gen 2 (Superspeed plus) Isoch stress | Harikrishnan P | USB |  | SSP Isoch Stress testing | P3 | USB-17 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 7 | 8 | USB-17 | 34
34 | KRK1-USB-020 | Support Larger Service Interval | Harikrishnan P | USB |  | XHCI SS / HS / FS Interrupt IN /OUT and ISOCH IN/OUT | P3 | USB-20 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 11 | 12 | USB-20 | 35
35 | KRK1-USB-022 | Concurrent Transfer Robustness : High speed bulk devices | Harikrishnan P | USB |  | HS transfer of BULK IN & OUT | P3 | USB-22 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 15 | 16 | USB-22 | 36
36 | KRK1-USB-023 | Concurrent Transfer Robustness : Superspeed bulk devices | Harikrishnan P | USB |  | SS transfer of BULK IN & OUT | P3 | USB-23 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 11 | 12 | USB-23 | 37
37 | KRK1-USB-024 | Concurrent Transfer Robustness : Superspeed plus bulk devices | Harikrishnan P | USB |  | SSP transfer of BULK IN & OUT | P3 | USB-24 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 7 | 8 | USB-24 | 38
38 | KRK1-USB-025 | Concurrent Transfer Robustness : High speed/Superspeed/Superspeed Plus) | Harikrishnan P | USB |  | HS/SS/SSP transfer of BULK IN & OUT | P3 | USB-25 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 7 | 8 | USB-25 | 39
39 | KRK1-USB-026 | PMM : USB D3 cold entry/exit | Harikrishnan P | USB |  | D3 Cold Entry /Exit Sequence | P3 | USB-26 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 23 | 24 | USB-26 | 40
40 | KRK1-USB-027 | PMM : USB wake on device resume in S0i3 & S4 | Harikrishnan P | USB |  | Wake on Device Resume in S3/S4 | P3 | USB-27 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 | N-1 | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 23 | 24 | USB-27 | 41
41 | KRK1-USB-028 | PMM : USB wake on connect & disconnect in S0i3 & S4 | Harikrishnan P | USB |  | Wake on Device Connect and Disconnect in S0i3 | P3 | USB-28 | Other |  | 1 | 1 | Legacy | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 1 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 11 | 12 | USB-28 | 42