## Sheet1
| Feature Task ID | Feature Name / Description | Owner | Sub-IP Block | Sub-Block Test Name | Test Name / Description | Priority | Test Case ID | Framework | Parameters | Effort | Total Variations | Category | % TP Done | # Written | % Code Done | P/S Env. | # of Planned Pre-Si Test Cases | Total Run | Pass | Waived | Fail | Skip | % Pass Rate | Errors or Pre-Silicon Comments / Notes | Total Run.1 | Pass.1 | Waived.1 | Fail.1 | Skip.1 | % Pass Rate.1 | Errors or Execution Comments / Notes | ETA | Issue or Bug Tracking Reference (e.g. JIRA Ticket ID)
0 | 12 | Navi4x configuration changes | Dennis | GFX |  | with pv_proxy library | P1 | std1.6 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 | ./tserverlite -d=1 -cf=tserver-soclfb-frontdoor.cf -test=std1.6 -texture_shader_tile_copy=0 -maxframes=1 -pv_proxy -counter=TA_PERF_SEL_TA_BUSY,CB_PERF_SEL_DRAWN_PIXEL -countertemp=counterfile | WK5 | CTANV48-6011
1 | 12.001 | Separate color blend opt bits out of CB_COLORn_INFO | Steven/David | PP |  |  | P1 | ppi201.2 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK4 | CTANV48-6010
2 | 12.002 | Change SPI_VS_OUT_CONFIG and SPI_PS_IN_CONTROL from context to persistent state regs | Xiaojing/Yu Xuan | SIO |  |  | P1 | spi20.0,spi20.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-6009
3 | 12.003 | Separate PS_ITER_SAMPLE out of PA_SC_MODE_CNTL_1 | Steven/David | PP |  |  | P1 | std4.34 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5 | CTANV48-6008
4 | 12.004 | Separate SAMPLE_RATE out of DB_COUNT_CONTROL | Faez/David | PP |  |  | P1 | PPI39,PPI100.65 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK3 | CTANV48-6007
5 | 12.006 | GE_CNTL and VGT_LS_HS_CONFIG changes | Yu Xuan | GEO |  |  | P1 | ge1.0,ge1.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | ./tserverlite -test=ge1.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; ./tserverlite -test=ge1.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-6006
6 | 12.007 | PA_SC_AA_CONFIG changes | Faez/David/Steven | PP |  |  | P1 | PPI101.5 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK3 | CTANV48-6005
7 | 12.008 | PA_SC_CONSERVATIVE_RASTERIZATION_CNTL changes | Faez/David/Steven | PP |  |  | P1 | PPI100.141 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK3 | CTANV48-6004
8 | 12.009 | Eliminate PA_SU_SC_MODE_CNTL.KEEP_TOGETHER_ENABLE | Faez/David/Steven | PP |  | /=-tglEnableSCBinning/=0 | P1 | STD1.6 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK3 | CTANV48-6003
9 | 12.01 | Separate AUTO_RESET_CNTL from PA_SC_LINE_STIPPLE | Faez/David | PP |  |  | P1 | sc45.1 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK3 | CTANV48-6002
10 | 12.011 | Implicit viewport scissoring | Faez/David | PP |  |  | P1 | sc42.2,sc42.3,sc26.9,sc26.10,sc26.11,sc26.12,sc26.13 | TServer |  | 1 | 7 | New | 1 | 7 | 1 | C-Model | 6 | 2 | 2 |  |  |  | 0.33333 |  | 7 | 7 |  |  |  | 1 |  | WK4 | CTANV48-6001
11 | 12.013 | Separate event enable bits out of SPI_CONFIG_CNTL | Xiaojing | SIO |  |  | P2 | gfx.ge_reg,gfx.sr_stat | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK7 | CTANV48-6000
12 | 12.014 | Split DB_RENDER_OVERRIDE | Faez/David | PP |  |  | P1 | ppi407.0-1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5999
13 | 12.015 | DB_STENCILREFMASK refactor | Faez/David | PP |  |  | P1 | db2.1,db3.1 | TServer |  | 1 | 2 | Delta | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5998
14 | 12.016 | Per target control for CB BIG_PAGE/L2_BYPASS | Steven/David | PP |  |  | P1 | ppi41.2-3,ppi41.22-23,ppi41.42-43,ppi41.52-53 | TServer |  | 1 | 8 | New | 1 | 8 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 8 | 8 |  |  |  | 1 |  | WK5 | CTANV48-5997
15 | 12.019 | Broadcast stores | Faez/Frank | TEX |  |  | P1 | txi91.0-1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 1 |  | 1 |  | 0.5 | logged into jira. Will check on silicon. | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5995
16 | 12.02 | out of order per-wave vmem returns | Frank | TEX |  |  | P1 | txi90.0-5 | TServer |  | 1 | 6 | New | 1 | 6 | 1 | Gopher | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1 |  | WK3 | CTANV48-5994
17 | 12.03 | Add support for image atomics fp32 add (makes fp32 add orthogonal). Make fp behaviour among lds/cmm/df identical | Botao | SH |  |  | P1 | gfx.inst_perf/atomic_denorm,gfx.inst_perf/buffer_atomic_cond_sub_u32,gfx.inst_perf/buffer_atomic_pk_add_bf16,gfx.inst_perf/buffer_atomic_pk_add_f16,gfx.inst_perf/buffer_atomic_sub_clamp_u32,gfx.inst_perf/ds_cond_sub_u32,gfx.inst_perf/ds_pk_add_bf16,gfx.inst_perf/ds_pk_add_f16,gfx.inst_perf/ds_sub_clamp_u32,gfx.inst_perf/global_atomic_cond_sub_u32,gfx.inst_perf/global_atomic_pk_add_bf16,gfx.inst_perf/global_atomic_pk_add_f16,gfx.inst_perf/global_atomic_sub_clamp_u32,gfx.image_op/image_atomic_add_flt,gfx.image_op/image_atomic_min_flt,gfx.image_op/image_atomic_max_flt,gfx.image_op/image_atomic_pk_add_f16,gfx.image_op/image_atomic_pk_add_bf16 | TNG |  | 1 | 18 | New | 1 | 18 | 1 | C-Model | 18 | 18 | 18 |  |  |  | 1 | gfx_inst/atomic_denorm can only run in GopherPlus env. Verify if single variation pass on gopher+ good enough | 18 | 18 |  |  |  | 1 |  | WK5 | CTANV48-5992
18 | 12.031 | Support greater than 16k x 16k x 8k textures (64k x 64k x 16k, inc. 16 mip levels to support 64k). Reduce/simplify swizzle modes. | Steven/David | PP |  |  | P1 | ppi302.3,ppi302.5 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK3 | CTANV48-5991
19 | 12.033 | Unclamped image load/store support | Frank | TEX |  |  | P2 | txi92.0-1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 0 | 0 |  |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK9 | CTANV48-5990
20 | 12.036 | Double Ray Tracing Intersect Engine | Frank | TEX |  |  | P1 | rt1.320 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK2 | CTANV48-5989
21 | 12.037 | RT instance node transform | Frank | TEX |  |  | P1 | rt1.330 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK3 | CTANV48-5988
22 | 12.04 | 64B RT node | Frank | TEX |  |  | P1 | rt1.302 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK2 | CTANV48-5987
23 | 12.041 | New GL2 policies (same/child of 12.027) | Glenn/Javad | CMM |  |  | P1 | gfx.cmm_sa_policy_monolithic_gfx12.1-23 | TNG |  | 1 | 23 | New | 1 | 23 | 1 | Gopher | 18 | 18 | 18 |  |  |  | 1 |  | 23 | 23 |  |  |  | 1 |  | WK4 | CTANV48-5986
24 | 12.042 | Unify GLC->EA request interface | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 | gfx.cmm_cp_access_order_monolithic.1-21,gfx.cmm_sa_access_order_monolithic.1-21 | TNG | -c +/diag/gpu/vml2/global/mode=On -c +/diag/gpu/vml2/context/0/mode=On | 1 | 42 | New | 1 | 42 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 42 | 42 |  |  |  | 1 |  | WK5 | CTANV48-5985
25 | 12.044 | GLC guarantee of same address order for any op or scope (dep. On 12.042) | Glenn/Javad/JJ/Anthony | CMM |  |  | P1 | gfx.cmm_sa_gl2_same_address_monolithic.1-8,gfx.cmm_sa_gl2_same_cacheline_monolithic.1-8 | TNG | -c +/diag/gpu/vml2/global/mode=On -c +/diag/gpu/vml2/context/0/mode=On | 1 | 16 | New | 1 | 16 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 16 | 16 |  |  |  | 1 |  | WK5 | CTANV48-5984
26 | 12.048 | GLC Full CL sized write support | Glenn/Javad | CMM |  |  | P2 | gfx.cmm_db_gl2_access_size_monolithic_gfx12/write | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK7 | CTANV48-5982
27 | 12.049 | GLC Up to 256B Write Support to EA | Glenn/Javad | CMM |  |  | P1 | gfx.cmm_cp_gcea_access_size_monolithic/write,gfx.cmm_sa_gcea_access_size_monolithic/write | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK2 | CTANV48-5981
28 | 12.051 | cache last_use policy (child of 12.041/12.027) | Javad | CMM |  |  | P2 | gfx.cmm_cache_last_use_policy_monolithic | TNG |  | 1 | 6 | New | 1 | 6 | 1 | C-Model | 0 | 0 |  |  |  |  | 1 |  | 6 | 6 |  |  |  | 1 |  | WK8 | CTANV48-5980
29 | 12.053 | Distributed compression architecture in CMM and client impacts (w/ physical meta-data) | Glenn/Javad | CMM |  |  | P1 | glxi60.1-4 | TServer | -vm | 1 | 4 | New | 1 | 4 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK5 | CTANV48-5979
30 | 12.055 | Split workgroup barrier | Botao | SH |  |  | P1 | gci1301.0 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5978
31 | 12.056 | Shader Instruction Data Prefetch (viola item) | Botao | SH |  |  | P1 | gci1304.0 | TServer | -pv_proxy=true -counter=SQC_PERF_SEL_ICACHE_PREFETCH_REQ_CACHELINES,SQC_PERF_SEL_ICACHE_PREFETCH_MISSES -countertemp=counterfile | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5977
32 | 12.057 | Shader software data dependency control | Botao | SH |  |  | P2 | gfx.inst_perf/sched_mode_dep_mode1,gfx.inst_perf/sched_mode_dep_mode2 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK8 | CTANV48-5976
33 | 12.059 | Shader SALU Float support (in M1/M2/gfx11.5) | Botao | SH |  |  | P1 | gfx.inst_perf/s_add_f32,gfx.inst_perf/s_sub_f32,gfx.inst_perf/s_min_num_f32,gfx.inst_perf/s_max_num_f32,gfx.inst_perf/s_minimum_f32,gfx.inst_perf/s_maximum_f32,gfx.inst_perf/s_mul_f32,gfx.inst_perf/s_fmaak_f32,gfx.inst_perf/s_fmamk_f32,gfx.inst_perf/s_fmac_f32,gfx.inst_perf/s_ceil_f32,gfx.inst_perf/s_floor_f32,gfx.inst_perf/s_trunc_f32,gfx.inst_perf/s_rndne_f32,gfx.inst_perf/s_add_f16,gfx.inst_perf/s_sub_f16,gfx.inst_perf/s_min_num_f16,gfx.inst_perf/s_max_num_f16,gfx.inst_perf/s_minimum_f16,gfx.inst_perf/s_maximum_f16,gfx.inst_perf/s_mul_f16,gfx.inst_perf/s_fmac_f16,gfx.inst_perf/s_ceil_f16,gfx.inst_perf/s_floor_f16,gfx.inst_perf/s_trunc_f16,gfx.inst_perf/s_rndne_f16,gfx.inst_perf/s_cmp_lt_f32,gfx.inst_perf/s_cmp_eq_f32,gfx.inst_perf/s_cmp_le_f32,gfx.inst_perf/s_cmp_gt_f32,gfx.inst_perf/s_cmp_lg_f32,gfx.inst_perf/s_cmp_ge_f32,gfx.inst_perf/s_cmp_o_f32,gfx.inst_perf/s_cmp_u_f32,gfx.inst_perf/s_cmp_nge_f32,gfx.inst_perf/s_cmp_nlg_f32,gfx.inst_perf/s_cmp_ngt_f32,gfx.inst_perf/s_cmp_nle_f32,gfx.inst_perf/s_cmp_neq_f32,gfx.inst_perf/s_cmp_nlt_f32,gfx.inst_perf/s_cmp_lt_f16,gfx.inst_perf/s_cmp_eq_f16,gfx.inst_perf/s_cmp_le_f16,gfx.inst_perf/s_cmp_gt_f16,gfx.inst_perf/s_cmp_lg_f16,gfx.inst_perf/s_cmp_ge_f16,gfx.inst_perf/s_cmp_o_f16,gfx.inst_perf/s_cmp_u_f16,gfx.inst_perf/s_cmp_nge_f16,gfx.inst_perf/s_cmp_nlg_f16,gfx.inst_perf/s_cmp_ngt_f16,gfx.inst_perf/s_cmp_nle_f16,gfx.inst_perf/s_cmp_neq_f16,gfx.inst_perf/s_cmp_nlt_f16,gfx.inst_perf/s_cvt_f32_i32,gfx.inst_perf/s_cvt_f32_u32,gfx.inst_perf/s_cvt_i32_f32,gfx.inst_perf/s_cvt_u32_f32,gfx.inst_perf/s_cvt_f16_f32,gfx.inst_perf/s_cvt_pk_rtz_f16_f32,gfx.inst_perf/s_cvt_f32_f16,gfx.inst_perf/s_cvt_hi_f32_f16 | TNG |  | 1 | 62 | New | 1 | 62 | 1 | C-Model | 62 | 62 | 62 |  |  |  | 1 |  | 62 | 62 |  |  |  | 1 |  | WK5 | CTANV48-5975
34 | 12.06 | VGPR DMA for Function Calls (uniform mask only) | Botao | SH |  |  | P1 | gfx.inst_perf/global_load_block,gfx.inst_perf/global_store_block,gfx.inst_perf/scratch_load_block,gfx.inst_perf/scratch_store_block | TNG |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK5 | CTANV48-5974
35 | 12.062 | Shader Debugger Enablement | Botao | SH |  |  | P1 | gci1305.0,gci1305.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5973
36 | 12.063 | Shader Illegal Instruction Detection | Botao | SH |  |  | P2 | gci1305.2 | TServer |  | 1 | 1 | Delta | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK8 | CTANV48-5972
37 | 12.064 | Support PERMUTE/BPERMUTE for wave64 | Botao | SH |  |  | P2 | gfx.inst_perf/ds_permute_b32_w64,gfx.inst_perf/ds_bpermute_b32_w64 | TNG |  | 1 | 2 | Delta | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK8 | CTANV48-5971
38 | 12.065 | Shader VALU Improvements | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_permlanex16_var_b32,gfx.inst_perf/v_permlane16_var_b32 | TNG |  | 1 | 2 | Delta | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8400 | 2 | 2 |  |  |  | 1 |  | WK2 | CTANV48-5970
39 | 12.066 | Shader Scalar Improvements | Botao | SH |  |  | P2 | gfx.inst_perf/s_sleep_var,gfx.inst_perf/s_sleep,gfx.inst_perf/s_add_nc_u64,gfx.inst_perf/s_sub_nc_u64,gfx.inst_perf/s_mul_u64,gfx.inst_perf/s_mul_i32 | TNG |  | 1 | 6 | Delta | 1 | 6 | 1 | C-Model | 6 | 6 | 6 |  |  |  | 1 |  | 6 | 6 |  |  |  | 1 |  | WK8 | CTANV48-5969
40 | 12.067 | Fix SQG GRBM design | Botao | SH |  |  | P1 | gci1303.0 | TServer | -tt_enable=true -tt_config=tt.ini | 1 | 1 | Delta | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | Indirect coverage: Can be covered by any test with thread trace enabled | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5968
41 | 12.069 | WGP-takeover mode | Botao | SH |  |  | P1 | gci1303.0,gci1303.1,gci1303.2 | TServer |  | 1 | 3 | New | 1 | 3 | 1 | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | WK5 | CTANV48-5966
42 | 12.073 | Shader signed memory offsets | Botao | SH |  |  | P2 | gfx.inst_perf/vglobal_signed_offset | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK8 | CTANV48-5964
43 | 12.079 | Dynamic VGPR allocation | Shuhui | SH |  |  | P1 | gci1302.0,gci1302.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK1 | CTANV48-5962
44 | 12.084 | Prep for Navi + MIx00 shader merge | Botao | SH |  |  | P2 | gfx.inst_perf/v_add_f64,gfx.inst_perf/v_mul_f64,gfx.inst_perf/v_lshlrev_b64 | TNG |  | 1 | 3 | New | 1 | 3 | 1 | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 3 | 3 |  |  |  | 1 |  | WK8 | CTANV48-5961
45 | 12.112 | GCR single cycle UTC request interface | Steven | CMM |  |  | P2 | glxi82.1-6 | TServer |  | 1 | 6 | New | 1 | 6 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 6 | 6 |  |  |  | 1 |  | WK8 | CTANV48-5959
46 | 12.115 | Single Pass Wave64 Trans Issue (in M2) | Botao | SH |  |  | P1 | gfx.inst_perf/v_exp_f32_w64,gfx.inst_perf/v_log_f32_w64,gfx.inst_perf/v_rcp_f32_w64,gfx.inst_perf/v_rsq_f32_w64,gfx.inst_perf/v_sqrt_f32_w64,gfx.inst_perf/v_sin_f32_w64,gfx.inst_perf/v_cos_f32_w64,gfx.inst_perf/v_exp_f16_w64,gfx.inst_perf/v_log_f16_w64,gfx.inst_perf/v_rcp_f16_w64,gfx.inst_perf/v_rsq_f16_w64,gfx.inst_perf/v_sqrt_f16_w64,gfx.inst_perf/v_sin_f16_w64,gfx.inst_perf/v_cos_f16_w64 | TNG |  | 1 | 14 | New | 1 | 14 | 1 | C-Model | 14 | 14 | 14 |  |  |  | 1 |  | 14 | 14 |  |  |  | 1 |  | WK5 | CTANV48-5956
47 | 12.118 | PH Memory Queues | Yu Xuan | GEO |  |  | P1 | ge2.0,ge2.1,std1.6 | TServer |  | 1 | 3 | New | 1 | 3 | 1 | Gopher | 3 | 3 | 3 |  |  |  | 1 | ./tserverlite -test=ge2.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; ./tserverlite -test=ge2.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 3 | 3 |  |  |  | 1 |  | WK5 | CTANV48-5955
48 | 12.12 | WGP&RB GRBM Index Remapping (possible gfx11.5) | Xiaojing | CTL |  |  | P1 | gci1300.0,gci1300.1,gci1300.2,gci1300.3 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK5 | CTANV48-5953
49 | 12.124 | CSC Group Launch guarantee | Xiaojing/Yu Xuan | SIO |  |  | P2 | spi124.0,spi124.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK7 | CTANV48-5952
50 | 12.125 | GFX Pipe Group Launch Guarantee | Xiaojing/Yu Xuan | SIO |  |  | P2 | spi125 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 | Issues in gfx_pm4_packets | 1 | 1 |  |  |  | 1 |  | WK6 | CTANV48-5951
51 | 12.128 | Packet Hardening for Microsoft Telemetry | Pierce | CTL |  |  | P1 | navi48.gfx.packet_injector | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5950
52 | 12.13 | add TCP out of order response support | Steven | CMM |  | glxi85.1 + std test + glxi85.2 | P1 | glxi85.1,glxi85.2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5949
53 | 12.132 | CP/RLC/SDMA 40-bit Register Addressing to GRBM<>RSMU | Daniel G | CTL |  |  | P1 | cpi400,cpi404 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK2 | CTANV48-5948
54 | 12.133 | Removal of Clear State Context 0 and reclamation for rendering | Daniel G | CTL |  |  | P1 | cpi410.0 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5947
55 | 12.134 | MES Handling Doorbell Misses | Daniel G | CTL |  |  | P1 | placeholder_r.1 | TServer |  | 1 | 1 | New | 1 | 0.4 | 0.4 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK5 | CTANV48-5946
56 | 12.139 | Simplify software debugger register change process | Xiaojing/Yu Xuan | SIO |  |  | P1 | spi1390,spi1391 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5945
57 | 12.142 | Double shader DOT Int4 and Int8 rates | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_dot4_i32_iu8,gfx.inst_perf/v_dot4_u32_u8,gfx.inst_perf/v_dot8_i32_iu4,gfx.inst_perf/v_dot8_u32_u4,gfx.inst_perf/v_wmma_i32_16x16x16_iu4,gfx.inst_perf/v_wmma_i32_16x16x32_iu4,gfx.inst_perf/v_wmma_i32_16x16x16_iu8 | TNG |  | 1 | 7 | Delta | 1 | 7 | 1 | Gopher | 7 | 7 | 7 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7782 | 7 | 7 |  |  |  | 1 |  | WK1 | CTANV48-5944
58 | 12.146 | RS64 L0 Instr Cache | Yu Xuan | CTL |  |  | P1 | std1.1,gci30.3 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 1 |  | 1 |  | 0.5 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5942
59 | 12.148 | RS64 L0 Data Cache | Yu Xuan | CTL |  |  | P1 | std1.1,gci30.3 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 1 |  | 1 |  | 0.5 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5941
60 | 12.15 | RS64 Bit Manip Instructions | Yu Xuan | CTL |  |  | P1 | gci3.12 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=gci3.12 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5940
61 | 12.157 | Shader pseudo-scalar trans ops (M2 item) | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_s_.1-10 | TNG |  | 1 | 10 | New | 1 | 10 | 1 | C-Model | 10 | 10 | 10 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8507 | 10 | 10 |  |  |  | 1 |  | WK8 | CTANV48-5938
62 | 12.159 | Shader reduce VGPR writes (M2 item, evaluate for gaming) | Shuhui | SH |  |  | P1 | shci2038.0-3,shci2038.104 | TServer |  | 1 | 5 | New | 1 | 5 | 1 | Gopher | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK1 | CTANV48-5937
63 | 12.16 | Shader double wave64 VINTERP rate (por gfx11.5, evaluate gaming) | Shuhui | SH |  |  | P2 | shci2041 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK6 | CTANV48-5936
64 | 12.162 | Shader Performance Profiler Enablement | Shuhui | SH |  |  | P1 | std1.1,std3.1,std4.1,rt1.300,rt1.320,gci1304,gci1305,gci1308,shci2033,shci2036,gssi212.10,std1.1,std3.1,std4.1 | TServer | "-tt_enable=1 -tt_config=exclude_nondetail_wavestart_ext=1,exclude_nondetail_alloc=1,wavestart_mode=wg_id,tracese=0,wavetype=127,ctrlmode=on,stall_all_simds=1 -thread_trace_config=exclude_nondetail_wavestart_ext=1,exclude_nondetail_alloc=1,wavestart_mode=wg_id,tracese=0,wavetype=127,ctrlmode=on,stall_all_simds=1" | 1 | 14 | Delta | 1 | 14 | 1 | Gopher | 14 | 14 | 11 |  | 3 |  | 0.78571 | https://ontrack-internal.amd.com/browse/DIAG-19897 Thread trace related can only be verified in gopher and using thread trace viewer. There are a few perf counters that are not tested but the test is avaliable. SQ_PERF_SEL_INSTS_LOCK SQ_PERF_SEL_INST_CYCLES_VALU_WMMA SQ_PERF_SEL_INSTS_VEC32_VALU_WMMA SQ_PERF_SEL_INSTS_WMMA_LOAD SQ_PERF_SEL_INSTS_TEX_BLOCK_LOAD SQ_PERF_SEL_INSTS_TEX_BLOCK_STORE | 14 | 14 |  |  |  | 1 |  | WK5 | CTANV48-5935
65 | 12.163 | Architected SGPR Values | Xiaojing/Yu Xuan | SIO |  |  | P2 | sh1630,sh1631 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 1 |  | 1 |  | 0.5 | may need write in TNG | 2 | 2 |  |  |  | 1 |  | WK6 | CTANV48-5934
66 | 12.164 | Hybrid Depth Compression | Faez/David | PP |  |  | P1 | PPI406.1-8,PPI406.11-18,PPI406.21-28,PPI406.31-38,PPI406.41-48,db1.1-14 | TServer |  | 1 | 54 | New | 1 | 54 | 1 | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 54 | 54 |  |  |  | 1 |  | WK2 | CTANV48-5933
67 | 12.165 | HiZ/S in SC | Steven/David | PP |  |  | P1 | std5.9 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | run with -tZTileBuffer=0 and 1 | 1 | 1 |  |  |  | 1 |  | WK2 | CTANV48-5932
68 | 12.167 | CB codec removal/simplifications | Faez/David/Steven | PP |  |  | P1 | sh1630,sh1631 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5931
69 | 12.184 | GLx bus widths and configuration | Glenn/Javad | CMM |  |  | P1 | gfx.cmm_sa_gl2_bus_width_monolithic.1-2,gfx.cmm_cb_gl2_bus_width_monolithic.1-2,gfx.cmm_db_gl2_bus_width_monolithic.1-2,gfx.cmm_pa_gl2_bus_width_monolithic.1-2,gfx.cmm_cp_ch_bus_width_monolithic.1-2,gfx.cmm_sdma_ch_bus_width_monolithic.1-2 | TNG |  | 1 | 12 | New | 1 | 12 | 1 | Gopher | 8 | 8 | 8 |  |  |  | 1 |  | 12 | 12 |  |  |  | 1 |  | WK2 | CTANV48-5928
70 | 12.185 | CH 256B read/write support | Glenn/Javad | CMM |  |  | P1 | gfx.cmm_cp_ch_access_size_monolithic_gfx12.1-2,gfx.cmm_sdma_access_size_monolithic.1-2 | TNG |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK3 | CTANV48-5927
71 | 12.186 | Add SP support for float8 (fp8/bf8) dot products (ieee and/or non-ieee) | Shuhui | SH |  |  | P1 | gfx.inst_perf/v_wmma.1-5,gfx.inst_perf/v_cvt.1-5,gfx.inst_perf/v_dot4_f32.1-5 | TNG |  | 1 | 15 | New | 1 | 15 | 1 | C-Model | 15 | 15 | 15 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8491 | 15 | 15 |  |  |  | 1 |  | WK3 | CTANV48-5926
72 | 12.188 | Make shader round-robin arb in workgroup usable by driver | Shuhui | SH |  |  | P1 | gci1306.0-2,gssi212.11 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 3 | 3 | 3 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK4 | CTANV48-5925
73 | 12.191 | Capture shader memviol source to speed up bringup debug | Shuhui | SH |  |  | P1 | gci1305.0,gci1305.3,gci1305.4,gci1305.5,gci1305.6 | TServer | For gci1305.3 only, "-vm -tc_ulVidmemFragmentSize=0" | 1 | 5 | New | 1 | 5 | 1 | C-Model | 5 | 5 | 5 |  |  |  | 1 |  | 5 | 5 |  |  |  | 1 |  | WK5 | CTANV48-5924
74 | 12.193 | Additional SAx client to UTCL1 (from 12. | Steven/JJ/Anthony | CMM |  |  | P1 | gfx.cmm_sax_utcl1_monolithic/utcl0_disable | TNG | -c +/diag/gpu/vml2/global/mode=On -c +/diag/gpu/vml2/context/0/mode=On -c | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5923
75 | 12.197 | Ping-Pong walking for dispatches | Xiaojing/Yu Xuan | SIO |  |  | P2 | spi197 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK8 | CTANV48-5922
76 | 12.201 | Compute Grid Programmable Walk Order (cs_grid_walk_order). If not doing morton ex. 2x2 then improving launch rate for existing typewriter (ex 4x1) is P1) | Xiaojing/Yu Xuan | SIO |  |  | P1 | spi2010,spi2011 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5921
77 | 12.202 | Compute Thread Walk Order (cs_thread_walk_order) | Xiaojing/Yu Xuan | SIO |  |  | P1 | spi2020,spi2021 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | Issues in gfx_pm4_packets | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5920
78 | 12.208 | wave64 FMAF32 power reduction (M2 item) -> large area | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_sad_u8,v_sad_hi_u8,v_sad_u16,gfx.inst_perf/v_swap_b16,v_swaprel_b32,gfx.inst_perf/v_perm_b32,v_permlane64_b32,gfx.inst_perf/v_sat_pk_u8_i16,gfx.inst_perf/v_max3_u32,v_max3_i16,v_max3_u16,v_maxmin_u32,v_maxmin_i32,gfx.inst_perf/v_sub_co_ci_u32,gfx.inst_perf/v_med3_i32,v_med3_u32,v_med3_i16,v_med3_u16,gfx.inst_perf/v_min3_i16,v_min3_u16,gfx.inst_perf/v_qsad_pk_u16_u8,gfx.inst_perf/v_mqsad_pk_u16_u8,gfx.inst_perf/v_mad_u16,v_mad_i16,v_mad_i64_i32,gfx.inst_perf/v_msad_u8,gfx.inst_perf/v_lerp_u8,gfx.inst_perf/v_and_or_b32,gfx.inst_perf/v_cndmask_b16,gfx.inst_perf/v_dual_cndmask_b32,v_dual_add_nc_u32,v_dual_lshlrev_b32,v_dual_and_b32,v_dual_fmac_f32,v_dual_fmaak_f32,v_dual_fmamk_f32,v_dual_mul_f32,v_dual_add_f32,v_dual_sub_f32,v_dual_subrev_f32,v_dual_dot2acc_f32_bf16,gfx.inst_perf/v_frexp_exp_i32_f32,v_frexp_mant_f32,v_frexp_mant_f16,v_frexp_exp_i16_f16,gfx.inst_perf/v_alignbit_b32,v_alignbyte_b32,gfx.inst_perf/v_interp_p10_f16_f32,v_interp_p2_f16_f32,v_interp_p10_rtz_f16_f32,v_interp_p2_rtz_f16_f32,gfx.inst_perf/v_ldexp_f16,gfx.inst_perf/v_div_fixup_f32,v_div_fmas_f32,v_div_scale_f32,v_div_fixup_f16,gfx.inst_perf/v_fract_f16,gfx.inst_perf/v_add_lshl_u32,gfx.inst_perf/v_mul_hi_i32_i24,v_mul_hi_u32_u24,gfx.inst_perf/v_bfrev_b32,gfx.inst_perf/v_cvt_off_f32_i4,gfx.inst_perf/v_clz_i32_u32,gfx.inst_perf/v_ctz_i32_b32,gfx.inst_perf/v_cls_i32 | TNG |  | 1 | 65 | New | 1 | 65 | 1 | C-Model | 64 | 64 | 64 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8760 | 65 | 65 |  |  |  | 1 |  | WK8 | CTANV48-5918
79 | 12.209 | Add Structured Sparsity Support | Claire/Meiru | SH |  | .0 for wave32, .1 for wave64 | P1 | gci0.950-960,gci1.950-960 | TServer |  | 1 | 22 | New | 1 | 22 | 1 | C-Model | 22 | 2 | 2 |  |  |  | 0.090909 |  | 19 | 19 |  |  |  | 0.86364 |  | WK3 | CTANV48-5917
80 | 12.21 | Fully connect capability to use high and normal MALL reuse hint (child of 12.027/12.041) | Steven | CMM |  |  | P1 | gci669.1-12 | TServer |  | 1 | 12 | New | 1 | 12 | 1 | Gopher | 1 | 0 |  |  |  |  | 0 |  | 12 | 12 |  |  |  | 1 |  | WK4 | CTANV48-5916
81 | 12.219 | ge_se in sed. Sub item under basic configuration | Xiaojing | GEO |  |  | P1 | gfx.red_triangle_draw_monolithic.2,gfx.red_triangle_draw_monolithic.3 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 | package/tng_executor - --class gpu -x gfx.red_triangle_draw_monolithic.3 -c +/diag/gpu/interruptsEnabled=false -c +/diag/gpu/gfx/mes/enable=false -c +/diag/gpu/gfx/mes/useKIQ=false -c +/diag/gpu/firmware/CPC/load=No -c +/diag/gpu/firmware/CPG/load=No -c +/diag/gpu/VBIOS/disabled=true -c +/log/root/level=Info | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5913
82 | 12.22 | register cleanup | Xiaojing | GEO |  |  | P1 | gfx.ge_reg | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 | package/tng_executor --class gpu -x gfx.ge_reg -c +/diag/gpu/interruptsEnabled=false -c +/diag/gpu/gfx/mes/enable=false -c +/diag/gpu/gfx/mes/useKIQ=false -c +/diag/gpu/firmware/CPC/load=No -c +/diag/gpu/firmware/CPG/load=No -c +/diag/gpu/VBIOS/disabled=true -c +/log/root/level=Info | 1 | 1 |  |  |  | 1 |  | WK4
83 | 12.223 | Update PA/SC support for 1 to 9SE and updated pix distribution algorithm | David/Steven | PP |  |  | P1 | STD1.6,GCI30.3 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5911
84 | 12.225 | DB design simplificaitons while updating for hybrid depth compression | Faez/David/Steven | PP |  |  | P1 | sh1630,sh1631 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5910
85 | 12.247 | Register remap to match M1 | Xiaojing | GEO |  |  | P1 | food_store,mountain_range,navi48.gfx.ge.register_access | TNG |  | 1 | 3 | New | 1 | 3 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 | package/tng_executor --class gpu gfx.stress3d.1.6 -c +/diag/gpu/interruptsEnabled=false -c +/diag/gpu/gfx/mes/enable=false -c +/diag/gpu/gfx/mes/useKIQ=false -c +/diag/gpu/firmware/CPC/load=No -c +/diag/gpu/firmware/CPG/load=No -c +/diag/gpu/VBIOS/disabled=true -c +/log/root/level=Info package/tng_executor --class gpu gfx.stress3d.2.6 -c +/diag/gpu/interruptsEnabled=false -c +/diag/gpu/gfx/mes/enable=false -c +/diag/gpu/gfx/mes/useKIQ=false -c +/diag/gpu/firmware/CPC/load=No -c +/diag/gpu/firmware/CPG/load=No -c +/diag/gpu/VBIOS/disabled=true -c +/log/root/level=Info | 3 | 3 |  |  |  | 1 |  | WK4 | CTANV48-5905
86 | 12.266 | GFX12 Firewall update for 40 bit address | David | CTL |  | rlci9.1 :: rlc_firewall_40bit_address,rlci10.1 :: cp_firewall_40bit_address | P1 | rlci9.1,rlci10.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5904
87 | 12.27 | Work Graph Scheduler | David | CTL |  | rlci10.1 :: cp_firewall_40bit_address wgs.6 :: wgs_dispatch_sanity_pm4_01 wgs.8 :: wgs_dispatch_two_pipes_pm4_01 wgs.1 :: wgs_ace_cwsr_pm4_01 wgs.100 :: wgs_dispatch_sanity_tacl_01 wgs.12 :: wgs_gl1_ret_xnack_pm4_01 gci30.3 ::linpack_wgs wgs_interrrupt_tacl gci22.11 :: shader_memory_copy | P1 | wgs.6,wgs.8,wgs.1,wgs.100,wgs.12,gci30.3,wgs_interrrupt_tacl,gci22.11 | TServer |  | 1 | 8 | New | 1 | 8 | 1 | Gopher | 6 | 6 | 6 |  |  |  | 1 | wgs.6 :: wgs_dispatch_sanity_pm4_01 pass wgs.8 :: wgs_dispatch_two_pipes_pm4_01 pass wgs.1 :: wgs_ace_cwsr_pm4_01 not run wgs.100 :: wgs_dispatch_sanity_tacl_01 pass wgs.12 :: wgs_gl1_ret_xnack_pm4_01 pass gci30.3 ::linpack_wgs not run wgs_interrrupt_tacl pass gci22.11 :: shader_memory_copy pass | 8 | 7 | 1 |  |  | 1 |  | WK5 | CTANV48-5903
88 | 12.276 | Remove the data duplication for MLOPS | Claire/Meiru | SH |  |  | P1 | gci820.0-19 | TServer |  | 1 | 20 | New | 1 | 20 | 1 | C-Model | 14 | 0 |  |  |  |  | 0 |  | 18 | 18 |  |  |  | 0.9 |  | WK5 | CTANV48-5902
89 | 12.277 | Add Conditional-subtract memory atomic for locks | Shuhui | SH |  |  | P2 | gfx.inst_perf/flat_atomic_cond_sub_u32_global,gfx.inst_perf/flat_atomic_sub_clamp_u32_global,gfx.inst_perf/ds_cond_sub_rtn_u32,gfx.inst_perf/ds_sub_clamp_rtn_u32,gci1307.0-3 | TNG |  | 1 | 8 | New | 1 | 8 | 1 | C-Model | 8 | 8 | 8 |  |  |  | 1 | Partially covered by 12.030 and in tserver gci1307 test. https://ontrack-internal.amd.com/browse/TNG-8541 | 8 | 8 |  |  |  | 1 |  | WK8 | CTANV48-5901
90 | 12.278 | DCC sector size to increase to 128B | Glenn/Javad | CMM |  |  | P1 | glxi60.7 | TServer | -vm | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | Will be covered by any DCC tests | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5900
91 | 12.28 | DCC auto-CT detection | Glenn/Javad | CMM |  |  | P1 | glxi60.5 | TServer | -vm | 1 | 1 | New | 1 | 1 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5899
92 | 12.281 | Sector-separated DCC compressed data layout | Glenn/Javad | CMM |  |  | P1 | glxi60.6 | TServer | -vm | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5898
93 | 12.282 | rename GE BIA containers | Xiaojing | GEO |  |  | P1 | gfx.ge_reg | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 | package/tng_executor --class gpu -x gfx.ge_reg -c +/diag/gpu/interruptsEnabled=false -c +/diag/gpu/gfx/mes/enable=false -c +/diag/gpu/gfx/mes/useKIQ=false -c +/diag/gpu/firmware/CPC/load=No -c +/diag/gpu/firmware/CPG/load=No -c +/diag/gpu/VBIOS/disabled=true -c +/log/root/level=Info | 1 | 1 |  |  |  | 1 |  | WK3
94 | 12.292 | move offchip lds manager to GE | Yu Xuan | GEO |  |  | P1 | ge3.0,std4.34 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | ./tserverlite -test=ge3.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5894
95 | 12.294 | Improve SPI work limiting controls (spi_work_limit_ctrl) | Xiaojing/Yu Xuan | SIO |  |  | P1 | spi2940,spi2941 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5893
96 | 12.301 | [Navi4x] CP ucode firmware execution speed-up via cache priming | Daniel G | CTL |  |  | P2 | placeholder_s.1 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7 | CTANV48-5892
97 | 12.31 | SED client to 256B reads | Glenn/Javad | CMM |  |  | P1 | gfx.cmm_db_gl2_access_size_monolithic_gfx12/read,gfx.cmm_pa_gl2_access_size_monolithic_gfx12/read | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK2 | CTANV48-5890
98 | 12.311 | Shader VALU min/max IEEE compliant | Shuhui | SH |  |  | P1 | gfx.ieee_min_max | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-7987 | 1 | 1 |  |  |  | 1 |  | WK1 | CTANV48-5889
99 | 12.319 | GCRD->GCR response interface to credit/debit | Steven | CMM |  |  | P1 | gfx.cmm_sa_gl2_gcr_monolithic | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5886
100 | 12.32 | GCRD_SE SAX client | Steven/JJ/Anthony | CMM |  |  | P1 | gfx.cmm_sax_utcl0_invalidation_monolithic/utcl0_enable | TNG | -c +/diag/gpu/vml2/global/mode=On -c +/diag/gpu/vml2/context/0/mode=On -c | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK6 | CTANV48-5885
101 | 12.333 | Swap PRIM_CONFIG register to SA_UNIT_DISABLE register | David | GC |  |  | P2 | STD1.6,GCI30.3,STD1.6,GCI30.3 | TNG |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK6 | CTANV48-5883
102 | 12.334 | GTS support in GFX12 | David | CTL |  |  | P1 | placeholder_t.1-2 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK4 | CTANV48-5882
103 | 12.339 | GFX12 IH Gasket update for chiplet design | Sid | CTL |  |  | P1 | GCI28.3 | TServer | ./tserverlite -cf=tserver-soclfb-frontdoor.cf -test=gci28.3 -d=1 | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5881
104 | 12.343 | SPM sample sync across AID and GFX to DF | Yu Xuan | CTL |  | with tgre spm & sqtt | P1 | std1.6 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5879
105 | 12.344 | Faulting illegal ops to PCIE | Steven | CMM |  |  | P1 | glxi86.1-2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK6 | CTANV48-5878
106 | 12.349 | Perfmon: GFX - Convert all counter modules to SPM-only mode | Yu Xuan | GC |  | std1.6 with tgre spm, cp test with spm | P2 | std1.6,gfxmsa12.3 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 1 |  |  | 1 |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK8 | CTANV48-5877
107 | 12.356 | Perfmon: GFX - GFX SPM sampling window to be driven by REFCLK | Yu Xuan | GC |  |  | P1 | rlc1.0 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | ./tserverlite -test=rlc1.0 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5876
108 | 12.357 | Perfmon: GFX - SQ counters to support shader type filters per individual counter | Dennis | GC |  | with legacy pv_proxy | P1 | std4.6,gci1310.1,std4.6,gci1310.1 | TServer | "-pv_proxy=true -no_regtomem=1 -countertemp=counterfile -counter=SQ_PERF_SEL_INSTS_VEC32_TEX_PS,SQ_PERF_SEL_INSTS_VEC32_TEX_GS,SQ_PERF_SEL_INSTS_VEC32_TEX_HS,SQ_PERF_SEL_INSTS_SMEM_PS,SQ_PERF_SEL_INSTS_SMEM_GS,SQ_PERF_SEL_INSTS_SMEM_HS" "-pv_proxy=true -no_regtomem=1 -countertemp=counterfile -counter=SQ_PERF_SEL_INSTS_VEC32_VALU_PS,SQ_PERF_SEL_INSTS_VEC32_VALU_GS,SQ_PERF_SEL_INSTS_VEC32_VALU_HS,SQ_PERF_SEL_INSTS_SALU_PS,SQ_PERF_SEL_INSTS_SALU_GS,SQ_PERF_SEL_INSTS_SALU_HS" "-pv_proxy=true -no_regtomem=1 -countertemp=counterfile -counter=SQG_PERF_SEL_WAVES_PS_VEC32,SQG_PERF_SEL_WAVES_GS_VEC32,SQG_PERF_SEL_WAVES_HS_VEC32,SQG_PERF_SEL_ITEMS_PS,SQG_PERF_SEL_ITEMS_GS,SQG_PERF_SEL_ITEMS_HS" "-pv_proxy=true -no_regtomem=1 -countertemp=counterfile -counter=SQG_PERF_SEL_ITEMS_CS,SQG_PERF_SEL_WAVES_CS_VEC32,SQ_PERF_SEL_INSTS_SALU_CS,SQ_PERF_SEL_INSTS_SMEM_CS,SQ_PERF_SEL_INSTS_VEC32_TEX_CS,SQ_PERF_SEL_INSTS_VEC32_VALU_CS" | 4 | 4 | New | 1 | 4 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK5 | CTANV48-5875
109 | 12.358 | Perfmon: GFX - Custom data injection from CP into SPM with delta counters | Yu Xuan | GC |  |  | P2 | rlc1.0,rlc1.1 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 1 | 1 |  |  |  | 0.5 | ./tserverlite -test=rlc1.1 -skip_consoleblank_check -pcispoof=00ad:7540 -pm4lib_disableCheckBlockBusy=1 -d=1 -nobios -no_toollib -disable_libdce -load_ucode=tcore -tcorelog -tc_Rs64CompEn=1 -tc_Rs64CompProduction=1 -tc_Rs64GfxEn=1 -tc_Rs64GfxProduction=1 -tc_LoadMesUCode=1 -tc_MicrocodeLoadEnable=1 -bEnableIslandPowerGating=1 -tglUsingPairsPacket=0 -mall_bypass_frwk -df_ecc_bypass_frwk -disable_libtmz -disable_displaymanager=1 -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -tCBClearMethod=forcefill -tZBClearMethod=forcefill -tSBClearMethod=fill -tc_SkipHDPCacheFlush -skiptextbuffering -skip_iommu_check -tDumpColor -skip_consoleblank_check -texture_shader_tile_copy=0 -dumpframes=all -tstamptimeout=7200 -tglPresent=0 -v=debug -autocrcprimary=false -tc_DisableCpCmpRings=0 -pm4lib_Present=0 -tDumpImage=1 -crcmode=none; | 2 | 2 |  |  |  | 1 | Test only passes on first run after fresh reboot. | WK8 | CTANV48-5874
110 | 12.36 | WMMA wave level matrix load Instruction | Shuhui | SH |  |  | P2 | gfx.inst_perf/global_load_tr.1-2 | TNG |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8759 | 2 | 2 |  |  |  | 1 |  | WK6 | CTANV48-5873
111 | 12.361 | Perfmon: GFX - VMID Specific Profiling/Debugging | Shuhui | SH |  |  | P2 | shci2039.4,shci2039.5 | TServer | "-tt_enable=1 -vm -tt_config=tracese=0,stall_all_simds=0,wavestart_mode=wg_id" | 2 | 2 | New | 1 | 2 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 | Requires thread trace viewer | 2 | 2 |  |  |  | 1 |  | WK8 | CTANV48-5872
112 | 12.37 | Fix VOPD dual V_MOV | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_dual_mov_b32 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 | https://ontrack-internal.amd.com/browse/TNG-8273 | 1 | 1 |  |  |  | 1 |  | WK6 | CTANV48-5870
113 | 12.373 | Modification of GS throttle (due to 12.118 ph_memory_queues) | Xiaojing/Yu Xuan | GEO |  |  | P1 | std1.6,std2.6,std3.6,std4.6 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK4 | CTANV48-5869
114 | 12.412 | Enable GPA in UTCL0 of SAx GL1C | David/Steven | CMM |  | cs16.0 | P1 | wgs_gpa3_disable_dispatch_pm4_01.1-2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 | WGS dependent | 2 | 2 |  |  |  | 1 |  | WK5 | CTANV48-5861
115 | 12.42 | Increase max scratch allocation | Xiaojing/Botao | SIO |  |  | P2 | gci1311 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 | ./tserverlite -cf=tserver-soclfb-frontdoor.cf -disable_libdce -skiptextbuffering -log -load_ucode=toollib -gpu_copyengine=tcore -tc_DefaultCopyUtil=HostCopy -df_ecc_bypass_frwk -ta_bypass_frwk -disable_mc_event -df_bypass_smc_check -mc_skip_dfcstate_function -test=gci1300.0 -log -d=1 -pcispoof=0x746f:0x7540 -tcorelog | 1 | 1 |  |  |  | 1 |  | WK7 | CTANV48-5860
116 | 12.43 | Ray Tracing Tri Pair optimization | Faez | TEX |  |  | P1 | rt1.400-401 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK4
117 | 12.439 | Improve register based invalidation | Steven/Glenn | CTL |  |  | P2 | utci16.1 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK8 | CTANV48-5856
118 | 12.444 | Expand V# const_stride from 14 to 17 bit width | Frank | TEX |  |  | P2 | txi93.0-3 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK8 | CTANV48-5853
119 | 12.445 | Improve Thread Trace ExecPopCount bandwidth | Shuhui | SH |  |  | P2 | shci2039.0-3 | TServer | "-tt_enable=1 -vm -tt_config=traceSe=0" | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 | Requires thread trace viewer | 4 | 4 |  |  |  | 1 |  | WK8 | CTANV48-5852
120 | 12.448 | Change flags encoded in barycentrics to simplify detection of procedural nodes | Faez | TEX |  |  | P2 | rt33.0 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK8 | CTANV48-5850
121 | 12.449 | Remove culling with skip_triangles in TA | Faez | TEX |  |  | P1 | rt33.1-2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK6 | CTANV48-5849
122 | 12.45 | Add AtomicAdd packed math for F16 | Shuhui | SH |  |  | P2 | gci1307.4-7 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 | Tested on gopher+ Partially addresses by 12.030 | 4 | 4 |  |  |  | 1 |  | WK7 | CTANV48-5848
123 | 12.451 | Extend compression control support in Texture | Frank | TEX |  |  | P1 | txi93.4-7 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | Gopher | 2 | 2 | 2 |  |  |  | 1 | tested on GopherLite | 1 | 1 |  |  |  | 0.25 |  | WK6 | CTANV48-5847
124 | 12.453 | Add HS and GS Stages to event collection for PS_DONE and PS_PARTIAL_FLUSH | Xiaojing/Yu Xuan | SIO |  |  | P2 | spi453 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK6 | CTANV48-5846
125 | 12.454 | Proper Handling of the Force Decompression and Comp Key Read Command on compression-bypassed resources | Glenn/Javad | CMM |  |  | P2 | glxi61.1-2 | TServer | -vm | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 2 | 2 |  |  |  | 1 |  | 2 | 2 |  |  |  | 1 |  | WK8 | CTANV48-5845
126 | 12.455 | Decrease CS max grid size support to X,Y,Z = 32b,16b,16b | Xiaojing | SIO |  |  | P2 | gfx.linpack.30.2 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 | --class gpu gfx.linpack.30.2 -c +/diag/gpu/interruptsEnabled=false -c +/diag/gpu/gfx/mes/enable=false -c +/diag/gpu/gfx/mes/useKIQ=false -c +/diag/gpu/firmware/CPC/load=No -c +/diag/gpu/firmware/CPG/load=No -c +/diag/gpu/VBIOS/disabled=true -c +/log/root/level=Info | 1 | 1 |  |  |  | 1 |  | WK6 | CTANV48-5844
127 | 12.46 | BVH Footprint Improvement | Frank | TEX |  |  | P2 | rt1200.1-8 | TServer |  | 1 | 8 | New | 1 | 8 | 1 | Gopher | 4 | 4 | 4 |  |  |  | 1 |  | 2 | 2 |  |  |  | 0.25 |  | WK7 | CTANV48-5843
128 | 12.461 | RT support for OBB and Instance Node Intersection | Frank | TEX |  |  | P2 | rt1200.100-203,rt1200.11-14 | TServer |  | 1 | 108 | New | 1 | 108 | 1 | Gopher | 20 | 20 | 20 |  |  |  | 1 |  | 108 | 108 |  |  |  | 1 |  | WK8 | CTANV48-5842
129 | 12.465 | SP src operand invalidated by td/lds return | Shuhui | SH |  |  | P2 | gci1310 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | Gopher | 1 | 1 | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  | 1 |  | WK6 | CTANV48-5839
130 | 12.467 | GRBM/H SYNC registers | Daniel G | CTL |  |  | P1 | cpi415.1-2 | TServer |  | 1 | 2 | New | 1 | 2 | 1 | C-Model | 2 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK3 | CTANV48-5837
131 | 12.469 | F8 1.4.3 IEEE mode behavior change (match with NV) | Shuhui | SH |  |  | P2 | gci1309.0-3 | TServer |  | 1 | 4 | New | 1 | 4 | 1 | C-Model | 4 | 4 | 4 |  |  |  | 1 |  | 4 | 4 |  |  |  | 1 |  | WK7 | CTANV48-5835
132 | 12.47 | RS64: No support for OOO IO read and write memory transactions | Steven | CMM |  |  | P1 | gfx.cmm_sa_access_order_monolithic | TNG |  | 1 | 1 | New | 1 | 1 | 1 | Emulator | 1 | 0 |  |  |  |  | 0 | Will use MHUB team's ATHUB RAW check and Single VC for GFX IO test's CPWD variation as coverage | 1 | 1 |  |  |  | 1 |  | WK5 | CTANV48-5834
133 | 12.471 | Save and Restore of perfcounter and ttrace enable for GFXOFF/SRIOV | Xiaojing | SIO |  |  | P2 | gfx.sr_stat | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 | package/tng_executor --class gpu gfx.srstatus.1/0 -c +/diag/gpu/interruptsEnabled=false -c +/diag/gpu/gfx/mes/enable=false -c +/diag/gpu/gfx/mes/useKIQ=false -c +/diag/gpu/firmware/CPC/load=No -c +/diag/gpu/firmware/CPG/load=No -c +/diag/gpu/VBIOS/disabled=true -c +/diag/gpu/firmwareLoading/SDMA/load=Backdoor -c +/log/root/level=Info -c +/diag/gpu/gfx/sq/tt/enabled=true | 0 |  |  |  |  | 0 | PMM test will deliver gfxoff by AB+8wks (dependency) | WK8 | CTANV48-5833
134 | 12.474 | 2x MLOPs performance | Shuhui | SH |  |  | P2 | gfx.inst_perf/v_wmma_f32_16x16x.1-5,gfx.inst_perf/v_wmma_i32_16x16x32_iu4,gci39.1-5 | TNG |  | 1 | 11 | New | 1 | 11 | 1 | Gopher | 11 | 11 | 11 |  |  |  | 1 | Partially covered by 12.209. Checked cycles by using thread trace WMMA8/WMMA16 tokens | 11 | 11 |  |  |  | 1 |  | WK6 | CTANV48-5831
135 | 12.479 | Add Ordered-Add memory atomic for faster SW Streamout (global_atomic_ordered_add_b64) | Glenn/Javad/JJ/Anthony | CMM |  |  | P2 | gfx.cmm_sa_gl2_atomic_ordered_add_monolithic_gfx12 | TNG |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK8 | CTANV48-5828
136 | 12.484 | decoding of op ATOMIC_UMAX_8_NO_RTN from EA to SDP is not expected | Steven/Frank | CMM |  |  | P1 | txi83 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 |  | WK7 | CTANV48-5825
137 | 12.488 | Reduce PBB maximum batch size from 1024 to 512 and constrain the minimum bin size in the PBB to 128 pixels | David/Steven | PP |  |  | P3 | STD1.6 | TServer |  | 1 | 1 | New | 1 | 1 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 1 | 1 |  |  |  | 1 |  | WK8 | CTANV48-5821
138 | 12.499 | CB/DB compress to clear/single before sending to GLx | Glenn/Javad | CMM |  |  | P2 | gfx.cmm_cb_dcc_clear_monolithic_gfx12.1-2 | TNG | -c +/diag/gpu/vml2/global/mode=On -c +/diag/gpu/vml2/context/0/mode=On -c | 1 | 2 | New | 1 | 2 | 1 | C-Model | 1 | 0 |  |  |  |  | 0 |  | 2 | 2 |  |  |  | 1 |  | WK8 | CTANV48-5814